## Waterfall_Auto
Step | Amount | Running Position | Section
Baseline Budget | 225642537.3057 | 225642537.3057 | Total
Approved Changes | 17602368.96 | 243244906.2657 | Approved
Pending Approval | 43429.56 | 243288335.8257 | Pending
Forecast / Trends | 22058158.7002 | 265346494.5259 | Trend
Projected Final Position | 265346494.5259 | 265346494.5259 | Total

## Waterfall_Client_Auto
Phase 1 Change Waterfall – Client Format
Board-ready staging of budget movement: baseline → approved changes → pending approval → forecast trends → projected final position.
Baseline budget |  | Approved changes |  | Pending approval |  | Forecast / trends |  | Projected position |  | Reporting cutoff
225642537.3057 |  | 17602368.96 |  | 43429.56 |  | 22058158.7002 |  | 265346494.5259 |  | 46141
# | Step | Section | Change Ref | Description | Amount (ML) | Running Position | Chart Label | Base | Increase | Decrease | Total | Column1 | Column2 | Label | Value
1 | Original Budget | Total | Baseline | Baseline budget | 225642537.3057 | 225642537.3057 | Original Budget |  |  |  | 225642537.3057 |  |  | Baseline Budget | 225642537.3057
2 | Approved: PDN-B9RD-B0015 | Approved | PDN-B9RD-B0015 | Budget increase request due to price increase (Commitment is higher than allocated budget). | 10626000 | 236268537.3057 | Approved: PDN-B9RD-B0015 | 225642537.3057 | 10626000 |  |  |  |  | Approved Changes | 17602368.96
3 | Approved: PDN-B9RD-B0003 | Approved | PDN-B9RD-B0003 | Additional scope to PPE Agreement under Scope of Services and Contract Price (K124) | 915573.89 | 237184111.1957 | Approved: PDN-B9RD-B0003 | 236268537.3057 | 915573.89
4 | Approved: B9RD-PDN-PPET0001 | Approved | B9RD-PDN-PPET0001 | Variation in FS costing from Lycopodium to execution costing received by the Vendor, PSI | 3260795.07 | 240444906.2657 | Approved: B9RD-PDN-PPET0001 | 237184111.1957 | 3260795.07
5 | Approved: B9DW-PDN-SMEG0001 | Approved | B9DW-PDN-SMEG0001 | Additional Circuit Breaker, Isolator & Line Alteration | 2800000 | 243244906.2657 |  | 0 |  | 0 | 2800000 | 2800000
6 | Balance after Approved | Total | Subtotal | Baseline plus approved changes | 243244906.2657 | 243244906.2657 | Balance after Approved |  |  |  | 243244906.2657 |  |  | Pending Approval | 43429.56
7 | Pending: B9RD-PDN-ABB0001 | Pending approval | B9RD-PDN-ABB0001 | Early Mining Volume Discount | -1864562.984 | 241380343.2817 | Pending: B9RD-PDN-ABB0001 | 241380343.2817 |  | 1864562.984 |  |  |  | Forecast / Trends | 22058158.7002
8 | Pending: B9RD-PDN-ABB0002 | Pending approval | B9RD-PDN-ABB0002 | Addition of DeapSea Controller in the 11 kV AIS switchgear | 129440.9 | 241509784.1817 | Pending: B9RD-PDN-ABB0002 | 241380343.2817 | 129440.9
9 | Pending: B9RD-PDN-ABB0003 | Pending approval | B9RD-PDN-ABB0003 | Fire Detection Design Specification fire alarm central unit - brand ADVANCED. | 123900.7 | 241633684.8817 | Pending: B9RD-PDN-ABB0003 | 241509784.1817 | 123900.7
10 | Pending: B9RD-PDN-ABB0004 | Pending approval | B9RD-PDN-ABB0004 | Additional 11kV Current Transformers (Bushing Mounted) | 54891.4 | 241688576.2817 | Pending: B9RD-PDN-ABB0004 | 241633684.8817 | 54891.4
11 | Pending: B9RD-PDN-ABB0008 | Pending approval | B9RD-PDN-ABB0008 | New Site conditions / New seismic requirements | 52798.72 | 241741375.0017 | Pending: B9RD-PDN-ABB0008 | 241688576.2817 | 52798.72
12 | Pending: B9RD-PDN-ABB0005 | Pending approval | B9RD-PDN-ABB0005 | Additional 3 x RMUs to be designed and delivered | 658284.3 | 242399659.3017 | Pending: B9RD-PDN-ABB0005 | 241741375.0017 | 658284.3
13 | Pending: B9RD-PDN-ABB0006 | Pending approval | B9RD-PDN-ABB0006 | Aux transformer removal | -203626 | 242196033.3017 | Pending: B9RD-PDN-ABB0006 | 242196033.3017 |  | 203626
14 | Pending: B9RD-PDN-ABB0009 | Pending approval | B9RD-PDN-ABB0009 | Fluor Fire Detection and Suppression Design Criteria | 31568.8 | 242227602.1017 | Pending: B9RD-PDN-ABB0009 | 242196033.3017 | 31568.8
15 | Pending: B9RD-PDN-ABB0010 | Pending approval | B9RD-PDN-ABB0010 | Additional COMM panels | 0 | 242227602.1017 | Pending: B9RD-PDN-ABB0010 | 242227602.1017 | 0
16 | Pending: B9RD-PDN-ABB0012 | Pending approval | B9RD-PDN-ABB0012 | Table of contents / Client Instruction requirement | 253500 | 242481102.1017 | Pending: B9RD-PDN-ABB0012 | 242227602.1017 | 253500
17 | Pending: B9RD-PDN-ABB0013 | Pending approval | B9RD-PDN-ABB0013 | Table of contents / Synchronous Condensers | 253500 | 242734602.1017 | Pending: B9RD-PDN-ABB0013 | 242481102.1017 | 253500
18 | Pending: B9RD-PDN-ABB0014 | Pending approval | B9RD-PDN-ABB0014 | Changes in existing kiosks and addition of one kiosk / design change as per revised SLD | 212683.6 | 242947285.7017 | Pending: B9RD-PDN-ABB0014 | 242734602.1017 | 212683.6
19 | Pending: B9RD-PDN-ABB0015 | Pending approval | B9RD-PDN-ABB0015 | Switches at MV switchgear | 0 | 242947285.7017 | Pending: B9RD-PDN-ABB0015 | 242947285.7017 | 0
20 | Pending: B9RD-PDN-ABB0016 | Pending approval | B9RD-PDN-ABB0016 | Changes in MV switchgear | 0 | 242947285.7017 | Pending: B9RD-PDN-ABB0016 | 242947285.7017 | 0
21 | Pending: B9RD-PDN-ABB0007 | Pending approval | B9RD-PDN-ABB0007 | Volume discount | -1539742.006 | 241407543.6957 | Pending: B9RD-PDN-ABB0007 | 241407543.6957 |  | 1539742.006
22 | Pending: B9RD-PDN-PPET0002 | Pending approval | B9RD-PDN-PPET0002 | Shifting of budget from E101 to E113. Costing not allocated in FS for the E103 Bulk Fuel tanks | 1435518.74 | 242843062.4357 | Pending: B9RD-PDN-PPET0002 | 241407543.6957 | 1435518.74
23 | Pending: 6105AK124-0000-BREQ-0002_Rev 2_02.02.2026 | Pending approval | 6105AK124-0000-BREQ-0002_Rev 2_02.02.2026 | Additional Scope | 445273.39 | 243288335.8257 | Pending: 6105AK124-0000-BREQ-0 | 242843062.4357 | 445273.39
24 | Balance incl. Pending | Total | Subtotal | Position after approved and pending changes | 243288335.8257 | 243288335.8257 | Balance incl. Pending |  |  |  | 243288335.8257 |  |  | Projected Final Position | 265346494.5259
25 | Trend: PPET-PTN-000001 | Forecast / trend | PPET-PTN-000001 | WBS 5600-Water Services Fluor addition of scope request. Scope gap from transition of FS EPCM to Fluor | 100000 | 243388335.8257 | Trend: PPET-PTN-000001 | 243288335.8257 | 100000
26 | Trend: Trend to be raised [K138-1] | Forecast / trend | Trend to be raised | Additional scope | 20960529.81 | 264348865.6357 | Trend: Trend to be raised [K13 | 243388335.8257 | 20960529.81
27 | Trend: Trend to be raised [K138-2] | Forecast / trend | Trend to be raised | Additional BOP / final forecast exposure | 997628.8902 | 265346494.5259 | Trend: Trend to be raised [K13 | 264348865.6357 | 997628.8902
28 | Projected Final Position | Total | Total | Baseline plus approved, pending and trend items | 265346494.5259 | 265346494.5259 | Projected Final Position |  |  |  | 265346494.5259

## View_1_Approved_This_Month
ChangeID | Programme | Package | Vendor | Description | Status | DateApproved | CostMostLikely | ForecastCategory | Owner | LastReviewed | IncludedInForecast | Notes
PDN-B9RD-B0015 | EP | E102 | ABB | Budget increase request due to price increase (Commitment is higher than allocated budget). | Approved | 46141 | 10626000 | Approved | EP Package Manager | 46141 | TRUE | Approved to date / latest Master PDN update
PDN-B9RD-B0003 | EP | K124A | PPE Tech | Additional scope to PPE Agreement under Scope of Services and Contract Price (K124) | Approved |  | 915573.89 | Approved | EP Package Manager | 46141 | TRUE | Approved to date / latest Master PDN update
B9RD-PDN-PPET0001 | EP | K137 | PSI | Variation in FS costing from Lycopodium to execution costing received by the Vendor, PSI | Approved |  | 3260795.07 | Approved | EP Package Manager | 46141 | TRUE | Approved to date / latest Master PDN update
Status | Submitted | K125 | Siemens | Additional Circuit Breaker, Isolator & Line Alteration | Approved |  | 2800000 | Approved | EP Package Manager | 46141 | TRUE | Approved to date / latest Master PDN update
Row Labels | Count of ChangeID | Sum of CostMostLikely | Sum of ScheduleImpactDays
| 16 | -401843.83 | 0
46141 | 1 | 10626000 | 0
Grand Total | 17 | 10224156.17 | 0

## View_2_Approved_To_Date
Metric | Value
Approved Count | 4
Approved Value | 17602368.96
Reporting Cutoff | 46141
Notes | PDN-B9RD-B0015 moved from pending/submitted to approved based on latest master list.

## View_3_Forecast_Components
Section | ChangeID | Package | Vendor | Description | Status | Amount | IncludedInForecast
Approved | PDN-B9RD-B0015 | E102 | ABB | Budget increase request due to price increase (Commitment is higher than allocated budget). | Approved | 10626000 | TRUE
Approved | PDN-B9RD-B0003 | K124A | PPE Tech | Additional scope to PPE Agreement under Scope of Services and Contract Price (K124) | Approved | 915573.89 | TRUE
|  |  | Count | CostLow (Sum) | CostMostLikely (Sum) | CostHigh (Sum) | ScheduleImpactDays (Sum)
Scope |  |  | 8 | 1174341.9 | 1174341.9 | 1174341.9 | 0
Scope | Pending |  | 8 | 1174341.9 | 1174341.9 | 1174341.9 | 0
Scope | Pending | true | 8 | 1174341.9 | 1174341.9 | 1174341.9 | 0
Commercial |  |  | 4 | 8657213.75 | 8657213.75 | 8657213.75 | 0
Commercial | Approved |  | 1 | 10626000 | 10626000 | 10626000 | 0
Commercial | Approved | true | 1 | 10626000 | 10626000 | 10626000 | 0
Commercial | Pending |  | 3 | -1968786.25 | -1968786.25 | -1968786.25 | 0
Commercial | Pending | true | 3 | -1968786.25 | -1968786.25 | -1968786.25 | 0
Technical |  |  | 5 | 392600.52 | 392600.52 | 392600.52 | 0
Technical | Pending |  | 5 | 392600.52 | 392600.52 | 392600.52 | 0
Technical | Pending | true | 5 | 392600.52 | 392600.52 | 392600.52 | 0
Pending | B9RD-PDN-ABB0013 | E102 | ABB | Table of contents / Synchronous Condensers | Submitted | 253500 | TRUE
Pending | B9RD-PDN-ABB0014 | E511B | ABB | Changes in existing kiosks and addition of one kiosk / design change as per revised SLD | Submitted | 212683.6 | TRUE
Pending | B9RD-PDN-ABB0015 | E511B | ABB | Switches at MV switchgear | Submitted | 0 | TRUE
Pending | B9RD-PDN-ABB0016 | E511B | ABB | Changes in MV switchgear | Submitted | 0 | TRUE
Pending | B9RD-PDN-ABB0007 | E102 | ABB | Volume discount | Submitted | -1539742.006 | TRUE
Pending | B9RD-PDN-PPET0002 | E113 | Fuelco | Shifting of budget from E101 to E113. Costing not allocated in FS for the E103 Bulk Fuel tanks | Submitted | 1435518.74 | TRUE
Pending | 6105AK124-0000-BREQ-0002_Rev 2_02.02.2026 | K124A | PPE Tech | Additional Scope | Submitted | 445273.39 | TRUE
Contingent | PPET-PTN-000001 | K124A | PPE Tech | WBS 5600-Water Services Fluor addition of scope request. Scope gap from transition of FS EPCM to Fluor | Trend | 100000 | FALSE
Contingent | Trend to be raised [K138-1] | K138 | PSI | Additional scope | Trend | 20960529.81 | FALSE
Contingent | Trend to be raised [K138-2] | K138 | BOP | Additional BOP / final forecast exposure | Trend | 997628.8902 | FALSE

## Waterfall_Client_Format
Phase 1 Change Waterfall – Client Format | [15 empty] | Step | Base | Increase | Decrease | Total
[16 empty] | Baseline Budget | 0 | 0 | 0 | 225642537.3057
Board-ready staging of budget movement: baseline → approved changes → pending approval → forecast trends → projected final position. | [15 empty] | Approved Changes | 225642537.3057 | 17602368.96 | 0 | 0
[16 empty] | Pending Approval | 243244906.2657 | 43429.56 | 0 | 0
Baseline budget |  | Approved changes |  | Pending approval |  | Forecast / trends |  | Projected position |  | Reporting cutoff | [5 empty] | Forecast / Trends | 243288335.8257 | 22058158.7002 | 0 | 0
225642537.3057 |  | 17602368.96 |  | 43429.56 |  | 22058158.7002 |  | 265346494.5259 |  | 46141 | [5 empty] | Projected Final Position | 0 | 0 | 0 | 265346494.5259
# | Step | Section | Change Ref | Description | Amount (ML) | Running Position | Chart Label | Base | Increase | Decrease | Total | Column1 | Column2 | Label | Value
1 | Original Budget | Total | Baseline | Baseline budget | 225642537.3057 | 225642537.3057 | Original Budget |  |  |  | 225642537.3057 |  |  | Baseline Budget | 225642537.3057
2 | Approved: PDN-B9RD-B0015 | Approved | PDN-B9RD-B0015 | Budget increase request due to price increase (Commitment is higher than allocated budget). | 10626000 | 236268537.3057 | Approved: PDN-B9RD-B0015 | 225642537.3057 | 10626000 |  |  |  |  | Approved Changes | 17602368.96
3 | Approved: PDN-B9RD-B0003 | Approved | PDN-B9RD-B0003 | Additional scope to PPE Agreement under Scope of Services and Contract Price (K124) | 915573.89 | 237184111.1957 | Approved: PDN-B9RD-B0003 | 236268537.3057 | 915573.89
4 | Approved: B9RD-PDN-PPET0001 | Approved | B9RD-PDN-PPET0001 | Variation in FS costing from Lycopodium to execution costing received by the Vendor, PSI | 3260795.07 | 240444906.2657 | Approved: B9RD-PDN-PPET0001 | 237184111.1957 | 3260795.07
5 | Approved: B9DW-PDN-SMEG0001 | Approved | B9DW-PDN-SMEG0001 | Additional Circuit Breaker, Isolator & Line Alteration | 2800000 | 243244906.2657 | Approved: B9DW-PDN-SMEG0001 | 240444906.2657 | 2800000
6 | Balance after Approved | Total | Subtotal | Baseline plus approved changes | 243244906.2657 | 243244906.2657 | Balance after Approved |  |  |  | 243244906.2657 |  |  | Pending Approval | 43429.56
7 | Pending: B9RD-PDN-ABB0001 | Pending approval | B9RD-PDN-ABB0001 | Early Mining Volume Discount | -1864562.984 | 241380343.2817 | Pending: B9RD-PDN-ABB0001 | 241380343.2817 |  | 1864562.984 |  |  |  | Forecast / Trends | 22058158.7002
8 | Pending: B9RD-PDN-ABB0002 | Pending approval | B9RD-PDN-ABB0002 | Addition of DeapSea Controller in the 11 kV AIS switchgear | 129440.9 | 241509784.1817 | Pending: B9RD-PDN-ABB0002 | 241380343.2817 | 129440.9
9 | Pending: B9RD-PDN-ABB0003 | Pending approval | B9RD-PDN-ABB0003 | Fire Detection Design Specification fire alarm central unit - brand ADVANCED. | 123900.7 | 241633684.8817 | Pending: B9RD-PDN-ABB0003 | 241509784.1817 | 123900.7
10 | Pending: B9RD-PDN-ABB0004 | Pending approval | B9RD-PDN-ABB0004 | Additional 11kV Current Transformers (Bushing Mounted) | 54891.4 | 241688576.2817 | Pending: B9RD-PDN-ABB0004 | 241633684.8817 | 54891.4
11 | Pending: B9RD-PDN-ABB0008 | Pending approval | B9RD-PDN-ABB0008 | New Site conditions / New seismic requirements | 52798.72 | 241741375.0017 | Pending: B9RD-PDN-ABB0008 | 241688576.2817 | 52798.72
12 | Pending: B9RD-PDN-ABB0005 | Pending approval | B9RD-PDN-ABB0005 | Additional 3 x RMUs to be designed and delivered | 658284.3 | 242399659.3017 | Pending: B9RD-PDN-ABB0005 | 241741375.0017 | 658284.3
13 | Pending: B9RD-PDN-ABB0006 | Pending approval | B9RD-PDN-ABB0006 | Aux transformer removal | -203626 | 242196033.3017 | Pending: B9RD-PDN-ABB0006 | 242196033.3017 |  | 203626
14 | Pending: B9RD-PDN-ABB0009 | Pending approval | B9RD-PDN-ABB0009 | Fluor Fire Detection and Suppression Design Criteria | 31568.8 | 242227602.1017 | Pending: B9RD-PDN-ABB0009 | 242196033.3017 | 31568.8
15 | Pending: B9RD-PDN-ABB0010 | Pending approval | B9RD-PDN-ABB0010 | Additional COMM panels | 0 | 242227602.1017 | Pending: B9RD-PDN-ABB0010 | 242227602.1017 | 0
16 | Pending: B9RD-PDN-ABB0012 | Pending approval | B9RD-PDN-ABB0012 | Table of contents / Client Instruction requirement | 253500 | 242481102.1017 | Pending: B9RD-PDN-ABB0012 | 242227602.1017 | 253500
17 | Pending: B9RD-PDN-ABB0013 | Pending approval | B9RD-PDN-ABB0013 | Table of contents / Synchronous Condensers | 253500 | 242734602.1017 | Pending: B9RD-PDN-ABB0013 | 242481102.1017 | 253500
18 | Pending: B9RD-PDN-ABB0014 | Pending approval | B9RD-PDN-ABB0014 | Changes in existing kiosks and addition of one kiosk / design change as per revised SLD | 212683.6 | 242947285.7017 | Pending: B9RD-PDN-ABB0014 | 242734602.1017 | 212683.6
19 | Pending: B9RD-PDN-ABB0015 | Pending approval | B9RD-PDN-ABB0015 | Switches at MV switchgear | 0 | 242947285.7017 | Pending: B9RD-PDN-ABB0015 | 242947285.7017 | 0
20 | Pending: B9RD-PDN-ABB0016 | Pending approval | B9RD-PDN-ABB0016 | Changes in MV switchgear | 0 | 242947285.7017 | Pending: B9RD-PDN-ABB0016 | 242947285.7017 | 0
21 | Pending: B9RD-PDN-ABB0007 | Pending approval | B9RD-PDN-ABB0007 | Volume discount | -1539742.006 | 241407543.6957 | Pending: B9RD-PDN-ABB0007 | 241407543.6957 |  | 1539742.006
22 | Pending: B9RD-PDN-PPET0002 | Pending approval | B9RD-PDN-PPET0002 | Shifting of budget from E101 to E113. Costing not allocated in FS for the E103 Bulk Fuel tanks | 1435518.74 | 242843062.4357 | Pending: B9RD-PDN-PPET0002 | 241407543.6957 | 1435518.74
23 | Pending: 6105AK124-0000-BREQ-0002_Rev 2_02.02.2026 | Pending approval | 6105AK124-0000-BREQ-0002_Rev 2_02.02.2026 | Additional Scope | 445273.39 | 243288335.8257 | Pending: 6105AK124-0000-BREQ-0 | 242843062.4357 | 445273.39
24 | Balance incl. Pending | Total | Subtotal | Position after approved and pending changes | 243288335.8257 | 243288335.8257 | Balance incl. Pending |  |  |  | 243288335.8257 |  |  | Projected Final Position | 265346494.5259
25 | Trend: PPET-PTN-000001 | Forecast / trend | PPET-PTN-000001 | WBS 5600-Water Services Fluor addition of scope request. Scope gap from transition of FS EPCM to Fluor | 100000 | 243388335.8257 | Trend: PPET-PTN-000001 | 243288335.8257 | 100000
26 | Trend: Trend to be raised [K138-1] | Forecast / trend | Trend to be raised | Additional scope | 20960529.81 | 264348865.6357 | Trend: Trend to be raised [K13 | 243388335.8257 | 20960529.81
27 | Trend: Trend to be raised [K138-2] | Forecast / trend | Trend to be raised | Additional BOP / final forecast exposure | 997628.8902 | 265346494.5259 | Trend: Trend to be raised [K13 | 264348865.6357 | 997628.8902
28 | Projected Final Position | Total | Total | Baseline plus approved, pending and trend items | 265346494.5259 | 265346494.5259 | Projected Final Position |  |  |  | 265346494.5259

## Dashboard_Executive
All Packages combined
Approved Change (ML) |  | Pending Included (ML) | Trend Exposure (ML) | Total Exposure (ML) |  | Status | Value
17602368.96 |  | 43429.56 | 22058158.7002 | 39703957.2202 |  | Approved | 17602368.96
[6 empty] | Pending | 43429.56
[6 empty] | Trend | 22058158.7002
Critical Path Count |  | % of Baseline | % of Contingency | Contingency Remaining
0 |  | 17.6%
Total Logged Changes |  | Approved Count | Submitted Count | Trend Count | Included in Forecast
24 |  | 4 | 17 | 3 | 21
Dashboard updated to reflect the latest Master PDN List as at 29 April 2026.
Status | Count of ChangeID
Approved | 4
Submitted | 17
Trend | 3
Total Active | 24
Row Labels | Count of ChangeID
PDN | 17
Grand Total | 17
Scope | 14
Schedule | 0
Other / Blank | 0
Grand Total | 24

## Dashboard_EP_CM
Programme | Count | Exposure | Included Forecast Count
EP | 24 | 39703957.2202 | 21
CM | 0 | 0 | 0
| Approved | Submitted | Grand Total
Row Labels |  |  | Grand Total
EP | 10626000 | -401843.83 | 10224156.17
Grand Total | 10626000 | -401843.83 | 10224156.17
IncludedInForecast | true
Row Labels | Sum of CostMostLikely
EP | 10224156.17
Grand Total | 10224156.17

## Dashboard_Vendors
Vendor | Count | Exposure | Included Count | Notes
ABB | 16 | 8788637.43 | 16
| Approved | Submitted | Grand Total
Row Labels |  |  | Grand Total
Fuelco | 0 | 1435518.74 | 1435518.74
ABB | 10626000 | -1837362.57 | 8788637.43
Grand Total | 10626000 | -401843.83 | 10224156.17
Grand Total | 24 | 39703957.2202 | 21
IncludedInForecast | true
Row Labels | Sum of CostMostLikely
Fuelco | 1435518.74
ABB | 8788637.43
Grand Total | 10224156.17

## tbl_ChangeRegister
ChangeID | Programme | Package | Vendor | SourceDocumentType | SourceDocumentRef | Description | Origin | ChangeType | Status | DateIdentified | DateSubmitted | DateApproved | CostLow | CostMostLikely | CostHigh | IncludedInForecast | ForecastCategory | ScheduleImpactDays | CriticalPathImpact | MilestoneAffected | GateImpact | LinkedRiskID | Owner | LastReviewed | AgeDays | ActiveFlag
PDN-B9RD-B0015 | EP | E102 | ABB | PDN | PDN-B9RD-B0015 | Budget increase request due to price increase (Commitment is higher than allocated budget). | Vendor | Commercial | Approved | 46100 | 46100 | 46141 | 10626000 | 10626000 | 10626000 | TRUE | Approved | 0 | FALSE |  |  | RSK-E102-001 | EP Package Manager | 46141 | 53 | 1
B9RD-PDN-ABB0001 | EP | E511B | ABB | PDN | B9RD-PDN-ABB0001 | Early Mining Volume Discount | Vendor | Commercial | Submitted | 46105 | 46105 |  | -1864562.984 | -1864562.984 | -1864562.984 | TRUE | Pending | 0 | FALSE |  |  | RSK-E511B-001 | EP Package Manager | 46141 | 36 | 1
B9RD-PDN-ABB0002 | EP | E511B | ABB | PDN | B9RD-PDN-ABB0002 | Addition of DeapSea Controller in the 11 kV AIS switchgear | Vendor | Technical | Submitted | 46107 | 46107 |  | 129440.9 | 129440.9 | 129440.9 | TRUE | Pending | 0 | FALSE |  |  | RSK-E511B-002 | EP Package Manager | 46141 | 34 | 1
B9RD-PDN-ABB0003 | EP | E511B | ABB | PDN | B9RD-PDN-ABB0003 | Fire Detection Design Specification fire alarm central unit - brand ADVANCED. | Vendor | Technical | Submitted | 46105 | 46105 |  | 123900.7 | 123900.7 | 123900.7 | TRUE | Pending | 0 | FALSE |  |  | RSK-E511B-003 | EP Package Manager | 46141 | 36 | 1
B9RD-PDN-ABB0004 | EP | E511B | ABB | PDN | B9RD-PDN-ABB0004 | Additional 11kV Current Transformers (Bushing Mounted) | Vendor | Technical | Submitted | 46105 | 46105 |  | 54891.4 | 54891.4 | 54891.4 | TRUE | Pending | 0 | FALSE |  |  | RSK-E511B-004 | EP Package Manager | 46141 | 36 | 1
B9RD-PDN-ABB0008 | EP | E102 | ABB | PDN | B9RD-PDN-ABB0008 | New Site conditions / New seismic requirements | Vendor | Technical | Submitted | 46141 | 46141 |  | 52798.72 | 52798.72 | 52798.72 | TRUE | Pending | 0 | FALSE |  |  | RSK-E102-002 | EP Package Manager | 46141 | 0 | 1
B9RD-PDN-ABB0005 | EP | E102 | ABB | PDN | B9RD-PDN-ABB0005 | Additional 3 x RMUs to be designed and delivered | Vendor | Scope | Submitted | 46105 | 46105 |  | 658284.3 | 658284.3 | 658284.3 | TRUE | Pending | 0 | FALSE |  |  | RSK-E102-003 | EP Package Manager | 46141 | 36 | 1
B9RD-PDN-ABB0006 | EP | E511B | ABB | PDN | B9RD-PDN-ABB0006 | Aux transformer removal | Vendor | Scope | Submitted | 46107 | 46107 |  | -203626 | -203626 | -203626 | TRUE | Pending | 0 | FALSE |  |  | RSK-E511B-005 | EP Package Manager | 46141 | 34 | 1
B9RD-PDN-ABB0009 | EP | E511B | ABB | PDN | B9RD-PDN-ABB0009 | Fluor Fire Detection and Suppression Design Criteria | Vendor | Technical | Submitted | 46107 | 46107 |  | 31568.8 | 31568.8 | 31568.8 | TRUE | Pending | 0 | FALSE |  |  | RSK-E511B-006 | EP Package Manager | 46141 | 34 | 1
B9RD-PDN-ABB0010 | EP | E511B | ABB | PDN | B9RD-PDN-ABB0010 | Additional COMM panels | Vendor | Scope | Submitted | 46141 | 46141 |  | 0 | 0 | 0 | TRUE | Pending | 0 | FALSE |  |  | RSK-E511B-007 | EP Package Manager | 46141 | 0 | 1
B9RD-PDN-ABB0012 | EP | E511B | ABB | PDN | B9RD-PDN-ABB0012 | Table of contents / Client Instruction requirement | Vendor | Scope | Submitted | 46135 | 46135 |  | 253500 | 253500 | 253500 | TRUE | Pending | 0 | FALSE |  |  | RSK-E511B-008 | EP Package Manager | 46141 | 6 | 1
B9RD-PDN-ABB0013 | EP | E102 | ABB | PDN | B9RD-PDN-ABB0013 | Table of contents / Synchronous Condensers | Vendor | Scope | Submitted | 46141 | 46141 |  | 253500 | 253500 | 253500 | TRUE | Pending | 0 | FALSE |  |  | RSK-E102-004 | EP Package Manager | 46141 | 0 | 1
B9RD-PDN-ABB0014 | EP | E511B | ABB | PDN | B9RD-PDN-ABB0014 | Changes in existing kiosks and addition of one kiosk / design change as per revised SLD | Vendor | Scope | Submitted | 46141 | 46141 |  | 212683.6 | 212683.6 | 212683.6 | TRUE | Pending | 0 | FALSE |  |  | RSK-E511B-009 | EP Package Manager | 46141 | 0 | 1
B9RD-PDN-ABB0015 | EP | E511B | ABB | PDN | B9RD-PDN-ABB0015 | Switches at MV switchgear | Vendor | Scope | Submitted | 46105 | 46105 |  | 0 | 0 | 0 | TRUE | Pending | 0 | FALSE |  |  | RSK-E511B-010 | EP Package Manager | 46141 | 36 | 1
B9RD-PDN-ABB0016 | EP | E511B | ABB | PDN | B9RD-PDN-ABB0016 | Changes in MV switchgear | Vendor | Scope | Submitted | 46141 | 46141 |  | 0 | 0 | 0 | TRUE | Pending | 0 | FALSE |  |  | RSK-E511B-011 | EP Package Manager | 46141 | 0 | 1
B9RD-PDN-ABB0007 | EP | E102 | ABB | PDN | B9RD-PDN-ABB0007 | Volume discount | Vendor | Commercial | Submitted | 46135 | 46135 |  | -1539742.006 | -1539742.006 | -1539742.006 | TRUE | Pending | 0 | FALSE |  |  | RSK-E102-005 | EP Package Manager | 46141 | 6 | 1
B9RD-PDN-PPET0002 | EP | E113 | Fuelco | PDN | B9RD-PDN-PPET0002 | Shifting of budget from E101 to E113. Costing not allocated in FS for the E103 Bulk Fuel tanks | Client | Commercial | Submitted | 46141 | 46141 |  | 1435518.74 | 1435518.74 | 1435518.74 | TRUE | Pending | 0 | FALSE |  |  | RSK-E113-001 | EP Package Manager | 46141 | 0 | 1
PDN-B9RD-B0003 | EP | K124A | PPE Tech | PDN | PDN-B9RD-B0003 | Additional scope to PPE Agreement under Scope of Services and Contract Price (K124) | Client | Scope | Approved |  |  |  | 915573.89 | 915573.89 | 915573.89 | TRUE | Approved | 0 | FALSE |  |  | RSK-K124A-001 | EP Package Manager | 46141 |  | 1
6105AK124-0000-BREQ-0002_Rev 2_02.02.2026 | EP | K124A | PPE Tech | BREQ | 6105AK124-0000-BREQ-0002_Rev 2_02.02.2026 | Additional Scope | Client | Scope | Submitted |  |  |  | 445273.39 | 445273.39 | 445273.39 | TRUE | Pending | 0 | FALSE |  |  | RSK-K124A-002 | EP Package Manager | 46141 |  | 1
PPET-PTN-000001 | EP | K124A | PPE Tech | PTN | PPET-PTN-000001 | WBS 5600-Water Services Fluor addition of scope request. Scope gap from transition of FS EPCM to Fluor | Client | Scope | Trend |  |  |  | 100000 | 100000 | 100000 | FALSE | Contingent | 0 | FALSE |  |  | RSK-K124A-003 | EP Package Manager | 46141 |  | 1
Trend to be raised [K138-1] | EP | K138 | PSI | Trend | Trend to be raised | Additional scope | Vendor | Scope | Trend |  |  |  | 20960529.81 | 20960529.81 | 20960529.81 | FALSE | Contingent | 0 | FALSE |  |  | RSK-K138-001 | EP Package Manager | 46141 |  | 1
B9RD-PDN-PPET0001 | EP | K137 | PSI | PDN | B9RD-PDN-PPET0001 | Variation in FS costing from Lycopodium to execution costing received by the Vendor, PSI | Vendor | Commercial | Approved |  |  |  | 3260795.07 | 3260795.07 | 3260795.07 | TRUE | Approved | 0 | FALSE |  |  | RSK-K137-001 | EP Package Manager | 46141 |  | 1
B9DW-PDN-SMEG0001 | EP | K125 | Siemens | PDN | B9DW-PDN-SMEG0001 | Additional Circuit Breaker, Isolator & Line Alteration | Vendor | Scope | Approved |  |  |  | 2800000 | 2800000 | 2800000 | TRUE | Approved | 0 | FALSE |  |  | RSK-K125-001 | EP Package Manager | 46141 |  | 1
Trend to be raised [K138-2] | EP | K138 | BOP | Trend | Trend to be raised | Additional BOP / final forecast exposure | Client | Scope | Trend |  |  |  | 997628.8902 | 997628.8902 | 997628.8902 | FALSE | Contingent | 0 | FALSE |  |  | RSK-K138-002 | EP Package Manager | 46141 |  | 1

## tbl_RiskRegister
RiskID | LinkedChangeID | RiskCategory | Probability | ImpactValue | MitigationStatus | EscalationLevel | LastReviewed
RSK-E102-001 | PDN-B9RD-B0015 | Commercial | High | 10626000 | Open | Commercial | 46118
RSK-E511B-001 | B9RD-PDN-ABB0001 | Commercial | High | -1864562.984 | Open | Commercial | 46118
RSK-E511B-002 | B9RD-PDN-ABB0002 | Technical | Medium | 129440.9 | Open | Package | 46118
RSK-E511B-003 | B9RD-PDN-ABB0003 | Technical | Medium | 123900.7 | Open | Package | 46118
RSK-E511B-004 | B9RD-PDN-ABB0004 | Technical | Medium | 54891.4 | Open | Package | 46118
RSK-E102-002 | B9RD-PDN-ABB0008 | Technical | Medium | 52798.72 | Open | Package | 46118
RSK-E102-003 | B9RD-PDN-ABB0005 | Scope | Medium | 658284.3 | Open | Package | 46118
RSK-E511B-005 | B9RD-PDN-ABB0006 | Scope | Medium | -203626 | Open | Package | 46118
RSK-E511B-006 | B9RD-PDN-ABB0009 | Technical | Medium | 31568.8 | Open | Package | 46118
RSK-E113-001 | B9RD-PDN-PPET0002 | Commercial | High | 1435518.74 | Open | Commercial | 46118
RSK-K124A-001 | PDN-B9RD-B0003 | Scope | Low | 915573.89 | Closed | Package | 46118
RSK-K124A-002 | 6105AK124-0000-BREQ-0002_Rev 2_02.02.2026 | Scope | Medium | 445273.39 | Open | Package | 46118
RSK-K124A-003 | PPET-PTN-000001 | Scope | Medium | 100000 | Open | Package | 46118
RSK-K138-001 | Trend to be raised [K138-1] | Scope | High | 20960529.81 | Open | Commercial | 46118
RSK-K137-001 | B9RD-PDN-PPET0001 | Commercial | Low | 3260795.07 | Closed | Commercial | 46118
RSK-K125-001 | B9DW-PDN-SMEG0001 | Scope | Low | 2800000 | Closed | Commercial | 46118
RSK-K138-002 | Trend to be raised [K138-2] | Scope | Medium | 997628.8902 | Open | Package | 46118

## tbl_ScheduleImpact
ChangeID | ActivityID | FloatBefore | FloatAfter | CPImpactFlag | RecoveryAction | LastReviewed
PDN-B9RD-B0015 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0001 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0002 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0003 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0004 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0008 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0005 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0006 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0009 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0010 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0012 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0013 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0014 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0015 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0016 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-ABB0007 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141
B9RD-PDN-PPET0002 | TBC-PLN | 30 | 30 | FALSE | No schedule impact currently logged | 46141

## ForecastIntegration
BaselineValue | 225642537.3057
ContingencyValue | 0
ReportingCutoffDate | 46141
Calculated Outputs
ApprovedTotal_ML | 17602368.96
PendingTotal_ML_Included | 43429.56
TrendTotal_ML | 22058158.7002
TotalExposure_ML | 39703957.2202
CriticalPathCount | 0
%OfBaseline_Exposure | 0.17596
%OfContingency_Exposure
ContingencyRemaining
TotalActiveChanges | 24
ApprovedCount | 4
SubmittedCount | 17
TrendCount | 3
RFICount | 0
ROCCount | 0
PCNCount | 0
TechnicalSubmissionCount | 0

## tbl_Snapshot_Log
SnapshotDate | ApprovedTotal_ML | PendingTotal_ML_Included | TrendTotal_ML | TotalExposure_ML | CriticalPathCount | Notes
46073 | 17602368.96 | 43429.56 | 22058158.7002 | 39703957.2202 | 0 | Auto snapshot for demo

## Lists
Packages
UniqueIdentifier | PackageDescription | VendorName | DocType | Vendors | Programme | Status | Origin | ChangeType | GateImpact | ForecastCategory | TRUE_FALSE
K124 | RDMC-Phase 1, E, C & I EPM | PPE Tech | RFI | TBC | EP | Trend | Engineering | Scope | Gate 0 | Approved | TRUE
K124 | RDMC-EW & Phase 1, C&M | PPE Tech | ROC | ABB | CM | Submitted | Procurement | Technical | Gate 1 | Pending | FALSE
K125 | 220kV Transmission Substations | Siemens | PCN | Crestchic |  | Approved | Construction | Commercial | Gate 2 | Contingent
E102 | Synchronous Condensors | ABB | COR | Orient Energy Systems |  | Rejected | Vendor | Schedule | Gate 3 | Excluded
E516B | E-Houses and Transformers | ABB | VO | PPE Tech |  |  | Client | Regulatory | Gate 4
K137 | 220kV & 33kV Overhead Lines | PSI | ECR | PSI |  |  | Interface |  | Gate 5
E123 | 11kV 20MW Resistive Load Bank | Crestchic | Claim | Siemens |  |  | NCR |  | Commissioning
E101 | 36MVA High Speed Diesel Generator Plant | Orient Energy Systems | Instruction |  |  |  | Regulatory |  | None
K108 | Battery Energy Storage Systems | TBC
K110 | Solar PV | TBC
E5188 | PCS Hardware | TBC
E103 | Power Factor Correction Filter Banks | TBC

## Sheet3
Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
5 – Very Likely | M | H | H | VH | VH
4 – Likely | M | M | H | H | VH
3 – Possible | L | M | M | H | H
2 – Unlikely | L | L | M | M | H
1 – Rare | L | L | L | M | M

## Update_Assumptions
Update Notes | Value | Source sheet / logic | Comment
Source workbook | Master PDN List_29.4.2026.xlsx | Uploaded file | Used to update PDNs through 29 April 2026.
Reporting cutoff | 46141 | File name and update date | Used in dashboard and waterfall.
Baseline budget | 225642537.3057 | Existing fixed workbook | Left unchanged.
PDN-B9RD-B0015 status | Approved | ABB sheet / latest master status | Moved from pending/submitted to approved.
B9DW-PDN-SMEG0001 value | 2800000 | Aconex Export total impact | Master month-end sheet showed two USD 1.4m cost splits; total kept at USD 2.8m.
ABB0014 value | 212683.6 | PDN Month end rpt update | Calculated from EUR 162,703 × 1.1 + CHF 25,931 × 1.3.
ABB0007 value | -1539742.006 | PDN Month end rpt update / ABB rate | Calculated from EUR -1,399,765.46 × 1.1.
Trends retained | 22058158.7002 | Existing fixed workbook | Master list is a PDN list; existing forecast/trend items were retained.
Approved total | 17602368.96 | Updated register | Sum of approved rows.
Pending total | 43429.56 | Updated register | Net value of pending/submitted rows included in forecast.
Trend exposure | 22058158.7002 | Updated register | Contingent / trend rows retained.
Total exposure | 39703957.2202 | Approved + pending + trend | Dashboard total exposure.
Projected final position | 265346494.5259 | Baseline + total exposure | Waterfall final position.