## Tracker (hidden)
Area/ WBS No. | Discipline | RDMC Document Number | Sum of % Complete
6200 |  |  | 0%
6240 |  |  | 0%
6243 |  |  | 0%
6250 |  |  | 0%
6260 |  |  | 0%
6262 |  |  | 0%
6263 |  |  | 0%
6264 |  |  | 0%
6280 |  |  | 0%
6286 |  |  | 0%
6292 |  |  | 0%
0000 |  |  | 0%
0100 |  |  | 0%
Grand Total |  |  | 0%

## Docs not in Use (hidden)
Project Number | Package Number | Area/ WBS No. | Discipline | Document Type | Sequential Number | Revision | RDMC Document Number | PPE Doc Number | Sht. # of # | Area / Facility | Major Description | Broad Type | Full Title | Rev A Transmittal Date | Rev 0 Transmittal Date | Aconex Doc Status | Aconex Review Status | % Complete | Doc Owner | Comments | Due Date | Main Group | Sub Group | BH | Drawing Pack
6105A | K124 | 0000 | B | REQ | 0001 | A | 6105AK124-0000-BREQ-0001 | Q24050972-09-0000-B-REQ-0001 |  | General | Change Order Request | General | General - Change Order Request - General |  |  | No status | No status |  | MK | COR'S |  | N/A | N/A | N/A | N/A
6105A | K124 | 0000 | G | PRC | 0001 | A | 6105AK124-0000-GPRC-0001 | Q24050972-09-0000-G-PRC-0001 |  | General | PPE Commissioning SharePoint Document Transmittal Procedure | General | General - PPE Commissioning SharePoint Document Transmittal Procedure - General |  |  | No status | No status |  | CP |  |  | N/A | N/A | N/A | N/A
6105A | K124 | 0000 | G | PRC | 0002 | A | 6105AK124-0000-GPRC-0002 | Q24050972-09-0000-G-PRC-0002 |  | General | Internal Document Review Procedure | General | General - Internal Document Review Procedure - General |  |  | No status | No status |  | CP |  |  | N/A | N/A | N/A | N/A
6105A | K124 | 0000 | G | PRC | 0003 | A | 6105AK124-0000-GPRC-0003 | Q24050972-10-0000-G-PRC-0003 |  | General | PPE Vendor SharePoint Procedure | General | General - PPE Vendor SharePoint Procedure - General |  |  | No status | No status |  | CP |  |  | N/A | N/A | N/A | N/A
6105A | K124 | 0000 | G | PRC | 0004 | A | 6105AK124-0000-GPRC-0004 | Q24050972-01-0000-G-PRC-0004 |  | General | PPE Formal App Review Procedure | General | General - PPE Formal App Review Procedure - General |  |  | No status | No status |  | CP |  |  | N/A | N/A | N/A | N/A

## CDDL
Project Number | Package Number | Area/ WBS No. | Discipline | Document Type | Sequential Number | Revision | RDMC Document Number | PPE Doc Number | Sht. # of # | Area / Facility | Major Description | Broad Type | Full Title | Rev A Transmittal Date | Rev 0 Transmittal Date | Aconex Doc Status | Aconex Review Status | % Complete | Doc Owner | Comments | Due Date | Main Group | Sub Group | BH | Drawing Pack | Activity ID | Schedule Status
6105A | K124 | 6200 | E | BOM | 0001 | A | 6105AK124-6200-EBOM-0001 | Q24050972-07-6200-E-BOM-0001 |  | On-Site Power Supply and Transmission | Neutral Earthing Compensator Resistor (33kV NECr) | Bill of Material | On-Site Power Supply and Transmission - Neutral Earthing Compensator Resistor (33kV NECr) - Bill of Material |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Neutral Earthing Compensator Resistor (33kV NECr) | Bill of Material |  |  |  | Pending
6105A | K124 | 6200 | E | BOM | 0002 | A | 6105AK124-6200-EBOM-0002 | Q24050972-07-6200-E-BOM-0002 |  | On-Site Power Supply and Transmission | Neutral Earthing Reactor (11kV NER) | Bill of Material | On-Site Power Supply and Transmission - Neutral Earthing Reactor (11kV NER) - Bill of Material |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Neutral Earthing Reactor (11kV NER) | Bill of Material |  |  |  | Pending
6105A | K124 | 6200 | E | BOM | 0003 | A | 6105AK124-6200-EBOM-0003 | Q24050972-07-6200-E-BOM-0003 |  | On-Site Power Supply and Transmission | Power Transformers - 33/11kV - 25MVA | Bill of Material | On-Site Power Supply and Transmission - Power Transformers - 33/11kV - 25MVA - Bill of Material |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Power Transformers | Bill of Material |  |  |  | Pending
6105A | K124 | 6263 | E | BOM | 0001 | A | 6105AK124-6263-EBOM-0001 | Q24050972-07-6263-E-BOM-0001 |  | 36 MVA Power Station 1 | High Speed Diesel Generators | Bill of Material | 36 MVA Power Station 1 - High Speed Diesel Generators - Bill of Material |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | High Speed Diesel Generators | Bill of Material |  |  |  | Pending
6105A | K124 | 6262 | E | BOM | 0001 | A | 6105AK124-6262-EBOM-0001 | Q24050972-11-6262-E-BOM-0001 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | 33/11kV Substation | Yard Plant & Equipment - Bill of Material | Emergency Power Substation 1 and Control Room 1 - 33/11kV Substation - Yard Plant & Equipment - Bill of Material - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | 33/11kV Substation | Bill of Material |  |  |  | Pending
6105A | K124 | 6200 | B | BOS | 0001 | A | 6105AK124-6200-BBOS-0001 | Q24050972-07-6200-B-BOS-0001 |  | On-Site Power Supply and Transmission | PPE EP & CM Contractual Schedule | Basis of Schedule | On-Site Power Supply and Transmission - PPE EP & CM Contractual Schedule - Basis of Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | FO |  | TENDER | PPE EP & CM Contractual Schedule | Basis of Schedule |  |  |  | Pending
6105A | K124 | 0100 | G | CHR | 0001 | A | 6105AK124-0100-GCHR-0001 | Q24050972-01-0100-G-CHR-0001 |  | Project Site Wide | Phase 1 Construction Management Organogram | General | Project Site Wide - Phase 1 Construction Management Organogram - General |  |  | RES - Reserved Placeholder | Pending | 0% | JM |  | 2026-05-15 | Organogram | General |  |  |  | Pending
6105A | K124 | 6290 | E | DBD | 0001 | 0 | 6105AK124-6290-EDBD-0001 | Q24050972-11-6290-E-DBD-0001 |  | Renewable Energy | 150MW Solar PV Plant | Basis of Design | Renewable Energy - 150MW Solar PV Plant - Basis of Design | 2026-03-12 | 2026-05-15 | IFU - Issued for Use | Pending | 66.67% | NL |  |  | 150MW Solar PV Plant | Basis of Design |  |  |  | Pending
6105A | K124 | 6290 | E | DBD | 0002 | 0 | 6105AK124-6290-EDBD-0002 | Q24050972-11-6290-E-DBD-0002 |  | Renewable Energy | 50MW BESS System | Basis of Design | Renewable Energy - 50MW BESS System - Basis of Design | 2026-03-13 | 2026-05-15 | IFU - Issued for Use | Pending | 66.67% | NL |  |  | 50MW BESS System | Basis of Design |  |  |  | Pending
6105A | K124 | 0000 | G | DDR | 0001 | A | 6105AK124-0000-GDDR-0001 | Q24050972-08-0000-G-DDR-0001 |  | General | PPE Contractor Document and Data List (CDDL) | CDDL | PPE Contractor Document and Data List (CDDL) |  |  | IFI - Issued for Information | Reviewed | 0% | RV |  |  | CDDL | General |  |  |  | Pending
6105A | K124 | 6200 | E | DST | 0001 | A | 6105AK124-6200-EDST-0001 | Q24050972-03-6200-E-DST-0001 |  | On-Site Power Supply and Transmission | Primary Electrical Reticulation Network - Solar PV Switchyard, Boreholes and Camp | Datasheet | On-Site Power Supply and Transmission - Primary Electrical Reticulation Network - Solar PV Switchyard, Boreholes and Camp - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | MM |  | TENDER | Primary Electrical Reticulation Network | Solar PV Switchyard, Boreholes and Camp |  |  |  | Pending
6105A | K124 | 6200 | E | DST | 0016 | A | 6105AK124-6200-EDST-0016 | Q24050972-07-6200-E-DST-0016 | Sht 1 of 1 | On-Site Power Supply and Transmission | Main Consumer Sub | Layout | On-Site Power Supply and Transmission - Main Consumer Sub - Layout - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Main Consumer Sub | Layout |  |  |  | Pending
6105A | K124 | 6243 | E | DST | 0002 | 0 | 6105AK124-6243-EDST-0002 | Q24050972-06-6243-E-DST-0002 |  | 220/33 kV Plant Main Substation | On-Site Power Supply & Transmission MV 33kV Main Consumer Plant Switchgear | Datasheet | 220/33 kV Plant Main Substation - On-Site Power Supply & Transmission MV 33kV Main Consumer Plant Switchgear - Datasheet | 2025-10-27 | 2026-03-12 | IFU - Issued for Use | Rejected - Revise & Resubmit | 66.67% | JC |  |  | On-Site Power Supply & Transmission | 33kV Main Consumer Plant Switchgear |  |  |  | Pending
6105A | K124 | 6243 | E | DST | 0003 | 0 | 6105AK124-6243-EDST-0003 | Q24050972-06-6243-E-DST-0003 |  | 220/33 kV Plant Main Substation | On-Site Power Supply & Distribution - 33kV Indoor Switchgear | Datasheet | 220/33 kV Plant Main Substation - On-Site Power Supply & Distribution - 33kV Indoor Switchgear - Datasheet | 2025-10-29 | 2026-05-11 | IFU - Issued for Use | Rejected - Revise & Resubmit | 66.67% | JC |  |  | On-Site Power Supply & Distribution | 33kV Indoor Switchgear |  |  |  | Pending
6105A | K124 | 6243 | E | DST | 0004 | A | 6105AK124-6243-EDST-0004 | Q24050972-06-6243-E-DST-0004 |  | 220/33 kV Plant Main Substation | 33kV Distribution Switch Rooms - 4 x Battery Tripping Units (110V DC) | Datasheet | 220/33 kV Plant Main Substation - 33kV Distribution Switch Rooms - 4 x Battery Tripping Units (110V DC) - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | Battery Tripping Units | Datasheet |  |  |  | Pending
6105A | K124 | 6243 | E | DST | 0005 | A | 6105AK124-6243-EDST-0005 | Q24050972-06-6243-E-DST-0005 |  | 220/33 kV Plant Main Substation | Specification for 300mm², 33kV, Single-Core, Unarmored Aluminium Cable | Datasheet | 220/33 kV Plant Main Substation - Specification for 300mm², 33kV, Single-Core, Unarmored Aluminium Cable - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | Specification for 300mm² | 33kV, Single-Core, Unarmored Aluminium Cable |  |  |  | Pending
6105A | K124 | 6250 | E | DST | 0001 | A | 6105AK124-6250-EDST-0001 | Q24050972-07-6250-E-DST-0001 |  | Power Conditioning Equipment | Synchronous Condenser and Excitation System | Datasheet | Power Conditioning Equipment - Synchronous Condenser and Excitation System - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | ET |  | TENDER | Synchronous Condenser | Datasheet |  |  |  | Pending
6105A | K124 | 6260 | E | DST | 0008 | 2 | 6105AK124-6260-EDST-0008 | Q24050972-04-6260-E-DST-0008 |  | Emergency Power Generation (Main Plant) | Neutral Earthing Compensator Resistor (33kV NECr) | Datasheet | Emergency Power Generation (Main Plant) - Neutral Earthing Compensator Resistor (33kV NECr) - Datasheet | 2025-10-24 | 2026-05-20 | IFU - Issued for Use | Pending | 66.67% | IS |  |  | Neutral Earthing Compensator Resistor (33kV NECr) | Datasheet |  |  |  | Pending
6105A | K124 | 6260 | E | DST | 0016 | A | 6105AK124-6260-EDST-0016 | Q24050972-07-6260-E-DST-0016 |  | Emergency Power Generation (Main Plant) | 630kVA Mini-substation (11/0.4kV) | Datasheet | Emergency Power Generation (Main Plant) - 630kVA Mini-substation (11/0.4kV) - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Substation | Datasheet |  |  |  | Pending
6105A | K124 | 6262 | E | DST | 0004 | A | 6105AK124-6262-EDST-0004 | Q24050972-08-6262-E-DST-0004 | Sht 1 of 1 | Emergency Power Generation | 11kVA MV E-house type 1B | Internal Views | Emergency Power Generation - 11kVA MV E-house type 1B - Internal Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | 11kVA MV E-house type 1B | MV Control Room |  |  |  | Pending
6105A | K124 | 6262 | E | DST | 0001 | A | 6105AK124-6262-EDST-0001 | Q24050972-07-6262-E-DST-0001 |  | Emergency Power Substation 1 and Control Room 1 | Auxiliary 400V AC Panel | Datasheet | Emergency Power Substation 1 and Control Room 1 - Auxiliary 400V AC Panel - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Auxiliary 400V AC Panel | Datasheet |  |  |  | Pending
6105A | K124 | 6262 | E | DST | 0002 | 0 | 6105AK124-6262-EDST-0002 | Q24050972-07-6262-E-DST-0002 |  | Emergency Power Substation 1 and Control Room 1 | Auxiliary 230V AC Battery Back-up Supply | Datasheet | Emergency Power Substation 1 and Control Room 1 - Auxiliary 230V AC Battery Back-up Supply - Datasheet | 2025-10-26 | 2025-11-07 | IFD - Issued for Design | Approved | 100% | IS | Approved |  | Auxiliary 230V AC Battery Back-up Supply | Datasheet |  |  |  | Pending
6105A | K124 | 6262 | E | DST | 0003 | 1 | 6105AK124-6262-EDST-0003 | Q24050972-07-6262-E-DST-0003 |  | Emergency Power Substation 1 and Control Room 1 | 11kV MV Switchgear | Datasheet | Emergency Power Substation 1 and Control Room 1 - 11kV MV Switchgear - Datasheet | 2025-10-22 | 2025-12-03 | IFU - Issued for Use | Approved | 100% | IS | Approved |  | 11kV MV Switchgear | Datasheet |  |  |  | Pending
6105A | K124 | 6263 | E | DST | 0002 | A | 6105AK124-6263-EDST-0002 | Q24050972-07-6263-E-DST-0002 |  | 36 MVA Power Station 1 | 20 MW 11kV Load Banks | Datasheet | 36 MVA Power Station 1 - 20 MW 11kV Load Banks - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 20 MW 11kV Load banks | Datasheet |  |  |  | Pending
6105A | K124 | 6263 | E | DST | 0003 | 0 | 6105AK124-6263-EDST-0003 | Q24050972-07-6263-E-DST-0003 |  | 36 MVA Power Station 1 | High Speed Diesel Generators | Datasheet | 36 MVA Power Station 1 - High Speed Diesel Generators - Datasheet | 2025-10-26 | 2025-11-18 | IFD - Issued for Design | Pending | 66.67% | IS |  |  | High Speed Diesel Generators | Datasheet |  |  |  | Pending
6105A | K124 | 6263 | E | DST | 0004 | 0 | 6105AK124-6263-EDST-0004 | Q24050972-07-6263-E-DST-0004 |  | 36 MVA Power Station 1 | Neutral Earthing Resistor (11kV NER) | Datasheet | 36 MVA Power Station 1 - Neutral Earthing Resistor (11kV NER) - Datasheet | 2025-10-26 | 2025-11-07 | IFD - Issued for Design | Approved | 100% | IS | Approved |  | Neutral Earthing Resistor (11kV NER) | Datasheet |  |  |  | Pending
6105A | K124 | 6263 | E | DST | 0005 | A | 6105AK124-6263-EDST-0005 | Q24050972-07-6263-E-DST-0005 |  | 36 MVA Power Station 1 | 11kV RMU for Load Banks | Datasheet | 36 MVA Power Station 1 - 11kV RMU for Load Banks - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 11kV RMU for Load Banks | Datasheet |  |  |  | Pending
6105A | K124 | 6264 | E | DST | 0001 | A | 6105AK124-6264-EDST-0001 | Q24050972-08-6264-E-DST-0001 |  | Bulk Diesel Storage 1 | Bulk Fuel Tanks | Datasheet | Bulk Diesel Storage 1 - Bulk Fuel Tanks - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Bulk Fuel Tanks | Datasheet |  |  |  | Pending
6105A | K124 | 6286 | E | DST | 0001 | 0 | 6105AK124-6286-EDST-0001 | Q24050972-06-6286-E-DST-0001 |  | Primary Crushing | On-Site Power Supply & Transmission_ MV 33kV Mining Sub MV Switchgear | Datasheet | Primary Crushing - On-Site Power Supply & Transmission_ MV 33kV Mining Sub MV Switchgear - Datasheet | 2025-10-22 | 2025-11-07 | IFD - Issued for Design | Approved | 100% | JC | Approved |  | On-Site Power Supply & Transmission | MV 33kV Mining Sub MV Switchgear |  |  |  | Pending
6105A | K124 | 6286 | E | DST | 0002 | A | 6105AK124-6286-EDST-0002 | Q24050972-07-6286-E-DST-0002 |  | Primary Crushing | 11kV Substation | Datasheet | Primary Crushing - 11kV Substation - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 11kV Substation | Datasheet |  |  |  | Pending
6105A | K124 | 6286 | E | DST | 0003 | A | 6105AK124-6286-EDST-0003 | Q24050972-07-6286-E-DST-0003 |  | Primary Crushing | Auxiliary 400Vac Distribution Board | Datasheet | Primary Crushing - Auxiliary 400Vac Distribution Board - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Auxiliary 400Vac Distribution Board | Datasheet |  |  |  | Pending
6105A | K124 | 6286 | E | DST | 0004 | 0 | 6105AK124-6286-EDST-0004 | Q24050972-07-6286-E-DST-0004 |  | Primary Crushing | 11kV Switchgear | Datasheet | Primary Crushing - 11kV Switchgear - Datasheet | 2025-11-19 | 2025-11-30 | IFD - Issued for Design | Pending | 66.67% | IS |  | TENDER | 11KV Switchgear | Datasheet |  |  |  | Pending
6105A | K124 | 6292 | E | DST | 0001 | A | 6105AK124-6292-EDST-0001 | Q24050972-07-6292-E-DST-0001 |  | 11/33 kV Solar PV Substation 1 and Control Room 1 | 33kV Indoor Switchgear | Datasheet | 11/33 kV Solar PV Substation 1 and Control Room 1 - 33kV Indoor Switchgear - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kV Indoor Switchgear | Datasheet |  |  |  | Pending
6105A | K124 | 6292 | E | DST | 0002 | A | 6105AK124-6292-EDST-0002 | Q24050972-07-6292-E-DST-0002 |  | 11/33 kV Solar PV Substation 1 and Control Room 1 | 3x Battery Tripping Units 9110V DC | Datasheet | 11/33 kV Solar PV Substation 1 and Control Room 1 - 3x Battery Tripping Units 9110V DC - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 3x Battery Tripping Units 9110V DC | Datasheet |  |  |  | Pending
6105A | K124 | 6292 | E | DST | 0003 | A | 6105AK124-6292-EDST-0003 | Q24050972-07-6292-E-DST-0003 |  | 11/33 kV Solar PV Substation 1 and Control Room 1 | MV 33kV Solar Plant Sub StationSwitchgear | Datasheet | 11/33 kV Solar PV Substation 1 and Control Room 1 - MV 33kV Solar Plant Sub StationSwitchgear - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | MV 33kV Solar Plant | Sub Station Switchgear |  |  |  | Pending
6105A | K124 | 6292 | E | DST | 0004 | A | 6105AK124-6292-EDST-0004 | Q24050972-08-6292-E-DST-0004 |  | 11/33 kV Solar PV Substation 1 and Control Room 1 | Primary Electrical Reticulation Network - Main Consumer Plant Reticulation | Datasheet | 11/33 kV Solar PV Substation 1 and Control Room 1 - Primary Electrical Reticulation Network - Main Consumer Plant Reticulation - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | Primary Electrical Reticulation Network | Main Consumer Plant Reticulation |  |  |  | Pending
6105A | K124 | 0100 | E | DST | 0002 | A | 6105AK124-0100-EDST-0002 | Q24050972-07-0100-E-DST-0002 |  | Project Site Wide | Pressurisation Fan - MV Switch Rooms | Datasheet | Project Site Wide - Pressurisation Fan - MV Switch Rooms - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Pressurisation Fan | MV Switch Rooms |  |  |  | Pending
6105A | K124 | 0100 | E | DST | 0003 | A | 6105AK124-0100-EDST-0003 | Q24050972-07-0100-E-DST-0003 |  | Project Site Wide | Extraction Fan - MV Control Room | Datasheet | Project Site Wide - Extraction Fan - MV Control Room - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Extraction Fan | MV Control Room |  |  |  | Pending
6105A | K124 | 6260 | E | DST | 0017 | A | 6105AK124-6260-EDST-0017 | Q24050972-07-6260-E-DST-0017 | Sht 1 of 1 | Emergency Power Generation (Main Plant) | Bulk Fuel Storage 1 | Datasheet | Emergency Power Generation (Main Plant) - Bulk Fuel Storage 1 - Datasheet - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Bulk Fuel Storage 1 | Datasheet |  |  |  | Pending
6105A | K124 | 0100 | H | DST | 0001 | A | 6105AK124-0100-HDST-0001 | Q24050972-09-0100-H-DST-0001 |  | Project Site Wide | Critical Lift | Datasheet | Project Site Wide - Critical Lift - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Critical Lift | Datasheet |  |  |  | Pending
6105A | K124 | 0100 | H | DST | 0002 | A | 6105AK124-0100-HDST-0002 | Q24050972-09-0100-H-DST-0002 |  | Project Site Wide | Personnel Lift | Datasheet | Project Site Wide - Personnel Lift - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Personnel Lift | Datasheet |  |  |  | Pending
6105A | K124 | 6260 | E | DST | 0019 | A | 6105AK124-6260-EDST-0019 | Q24050972-10-6260-E-DST-0019 | Sht 1 of 2 | Emergency Power Generation (Main Plant) | Syncon | Power Transformer - 33kV - NER | Emergency Power Generation (Main Plant) - Syncon - Power Transformer - 33kV - NER - Sht 1 of 2 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Power Transformer - 33kV - NER | Datasheet |  |  |  | Pending
6105A | K124 | 6262 | E | DST | 0005 | A | 6105AK124-6262-EDST-0005 | Q24050972-07-6262-E-DST-0005 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | MV Switchgear | 11kV MV Switchgear | Emergency Power Substation 1 and Control Room 1 - MV Switchgear - 11kV MV Switchgear - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | MV Switchgear | 11kV MV Switchgear |  |  |  | Pending
6105A | K124 | 0100 | E | DST | 0004 | 0 | 6105AK124-0100-EDST-0004 | Q24050972-10-0100-E-DST-0004 |  | Project Site Wide | Neutral Earthing Resistor | 11kV Neutral Earthing Resistor (11kV NER) | Project Site Wide - Neutral Earthing Resistor - 11kV Neutral Earthing Resistor (11kV NER) | 2025-11-03 | 2025-12-04 | IFU - Issued for Use | Approved | 100% | IS | Approved |  | Neutral Earthing Resistor | 11kV Neutral Earthing Resistor (11kV NER) |  |  |  | Pending
6105A | K124 | 0100 | E | DST | 0005 | 0 | 6105AK124-0100-EDST-0005 | Q24050972-10-0100-E-DST-0005 | Sht 1 of 1 | Project Site Wide | Power Transformer | 25MVA 33/11kV Dyn1 | Project Site Wide - Power Transformer - 25MVA 33/11kV Dyn1 - Sht 1 of 1 | 2025-11-03 | 2025-11-19 | IFU - Issued for Use | Pending | 66.67% | IS |  |  | Power Transformer | 25MVA 33/11kV Dyn11 |  |  |  | Pending
6105A | K124 | 6262 | E | DST | 0006 | A | 6105AK124-6262-EDST-0006 | Q24050972-11-6262-E-DST-0006 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | Mini-substation | 1MVA, Mini-substation, 11/0.69kV - Datasheet | Emergency Power Substation 1 and Control Room 1 - Mini-substation - 1MVA, Mini-substation, 11/0.69kV - Datasheet - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Mini-substation | Datasheet |  |  |  | Pending
6105A | K124 | 6262 | E | DST | 0008 | A | 6105AK124-6262-EDST-0008 | Q24050972-11-6262-E-DST-0008 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | Mini-substation | 1MVA Mini-substation, 11/0.4kV - Datasheet | Emergency Power Substation 1 and Control Room 1 - Mini-substation - 1MVA Mini-substation, 11/0.4kV - Datasheet - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Mini-substation | 1600kVA, Mini-substation, 11/0.4kV |  |  |  | Pending
6105A | K124 | 6292 | E | DST | 0005 | A | 6105AK124-6292-EDST-0005 | Q24050972-08-6292-E-DST-0005 |  | 11/33 kV Solar PV Substation 1 and Control Room 1 | On-Site Power Supply & Transmission | MV 33kV Solar PV Data Sheet | 11/33 kV Solar PV Substation 1 and Control Room 1 - On-Site Power Supply & Transmission - MV 33kV Solar PV Data Sheet |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | 2026-05-15 | On-Site Power Supply & Transmission | MV 33kV Solar PV |  |  |  | Pending
6105A | K124 | 0100 | E | DST | 0007 | A | 6105AK124-0100-EDST-0007 | Q24050972-11-0100-E-DST-0007 | Sht 1 of 1 | Project Site Wide | Battery Tripping Units (BTU) | Sub-Station BTU (110Vdc) | Project Site Wide - Battery Tripping Units (BTU) - Sub-Station BTU (110Vdc) - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Sub-Station BTU (110Vdc) | Battery Tripping Units (BTU) |  |  |  | Pending
6105A | K124 | 6262 | E | DST | 0009 | A | 6105AK124-6262-EDST-0009 | 6262E-DST-0009A-6105AK124-6262-EDST-0009 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | Neutral Earthing Resistor | 690V NER (300A) | Emergency Power Substation 1 and Control Room 1 - Neutral Earthing Resistor - 690V NER (300A) - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Neutral Earthing Resistor | 690V NER (300A) |  |  |  | Pending
6105A | K124 | 6286 | E | DST | 0006 | A | 6105AK124-6286-EDST-0006 | Q24050972-07-6286-E-DST-0006 | Sht 1 of 1 | Primary Crushing | Auxiliary Supply | 250kVA, Mini-substation, 11/0.4kV - Datasheet | Primary Crushing - Auxiliary Supply - 250kVA, Mini-substation, 11/0.4kV - Datasheet - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 33.33% | IS |  | 2026-05-15 | Auxiliary Supply | 250kVA, Mini-substation, 11/0.4kV |  |  |  | Pending
6105A | K124 | 0100 | E | DST | 0008 | A | 6105AK124-0100-EDST-0008 | Q24050972-12-0100-E-DST-0008 | Sht 1 of 1 | Project Site Wide | Auxiliary Supply | 250kVA Mini-substation, 33/0.4kV - Datasheet | Project Site Wide - Auxiliary Supply - 250kVA Mini-substation, 33/0.4kV - Datasheet - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Auxiliary Supply | 400kVA, Mini-substation |  |  |  | Pending
6105A | K124 | 0100 | E | DST | 0009 | 0 | 6105AK124-0100-EDST-0009 | Q24050972-12-0100-E-DST-0009 | Sht 1 of 1 | Project Site Wide | Insulation Monitoring & High Impedance Earthing | IM-Flex - 690Vac - General Arrangement | Project Site Wide - Insulation Monitoring & High Impedance Earthing - IM-Flex - 690Vac - General Arrangement - Sht 1 of 1 | 2025-12-15 | 2026-01-21 | IFC - Issued for Construction | Approved | 100% | IS | Approved |  | Insulation Monitoring | General Arrangement |  |  |  | Pending
6105A | K124 | 0100 | E | DST | 0010 | 0 | 6105AK124-0100-EDST-0010 | Q24050972-12-0100-E-DST-0010 | Sht 1 of 2 | Project Site Wide | Insulation Monitoring & High Impedance Earthing | IM-Flex - 690Vac - Circuit Diagram | Project Site Wide - Insulation Monitoring & High Impedance Earthing - IM-Flex - 690Vac - Circuit Diagram - Sht 1 of 2 | 2025-12-15 | 2026-01-21 | IFC - Issued for Construction | Approved | 100% | IS | Approved |  | Insulation Monitoring | Circuit Diagram |  |  |  | Pending
6105A | K124 | 0100 | E | DST | 0011 | 0 | 6105AK124-0100-EDST-0011 | Q24050972-12-0100-E-DST-0011 | Sht 2 of 2 | Project Site Wide | Insulation Monitoring & High Impedance Earthing | IM-Flex - 690Vac - Circuit Diagram | Project Site Wide - Insulation Monitoring & High Impedance Earthing - IM-Flex - 690Vac - Circuit Diagram - Sht 2 of 2 | 2025-12-15 | 2026-05-20 | IFC - Issued for Construction | Rejected - Revise & Resubmit | 66.67% | IS |  |  | Insulation Monitoring | Circuit Diagram |  |  |  | Pending
6105A | K124 | 6262 | E | DST | 0010 | A | 6105AK124-6262-EDST-0010 | Q24050972-12-6262-E-DST-0010 |  | Emergency Power Substation 1 and Control Room 1 | High Impedance Earthing | Datasheet | Emergency Power Substation 1 and Control Room 1 - High Impedance Earthing - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Earthing | Datasheet |  |  |  | Pending
6105A | K124 | 6282 | E | DST | 0001 | A | 6105AK124-6282-EDST-0001 | Q24050972-01-6282-E-DST-0001 | Sht 1 of 1 | Potable Water Treatment Plant | Pole Mounted Transformer | 500kVA, 33/0.69kV | Potable Water Treatment Plant - Pole Mounted Transformer - 500kVA, 33/0.69kV |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Mini-substation | Datasheet |  |  |  | Pending
6105A | K124 | 6286 | E | DTL | 0001 | A | 6105AK124-6286-EDTL-0001 | Q24050972-07-6286-E-DTL-0001 | Sht 3 of 3 | Primary Crushing | Auxiliary 400V AC Panel 2 | Details | Primary Crushing - Auxiliary 400V AC Panel 2 - Details - Sht 3 of 3 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Auxiliary 400V AC Panel 2 | Details |  |  |  | Pending
6105A | K124 | 6286 | E | DTL | 0002 | A | 6105AK124-6286-EDTL-0002 | Q24050972-07-6286-E-DTL-0002 | Sht 2 of 3 | Primary Crushing | Auxiliary 400V AC Panel 2 | Details | Primary Crushing - Auxiliary 400V AC Panel 2 - Details - Sht 2 of 3 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Auxiliary 400V AC Panel 2 | Details |  |  |  | Pending
6105A | K124 | 6260 | E | DTL | 0001 | A | 6105AK124-6260-EDTL-0001 | Q24050972-09-6260-E-DTL-0001 | Sht.4 of 4 | Emergency Power Generation (Main Plant) | Mv Cable Isolator Panel | Details | Emergency Power Generation (Main Plant) - Mv Cable Isolator Panel - Details - Sht.4 of 4 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Mv Cable Isolator Panel | Details |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0001 | A | 6105AK124-0100-HFRM-0001 | Q24050972-09-0100-H-FRM-0001 |  | Project Site Wide | Daily Safety Task Instruction DSTI | Form | Project Site Wide - Daily Safety Task Instruction DSTI - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Daily Safety Task Instruction DSTI | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0002 | A | 6105AK124-0100-HFRM-0002 | Q24050972-09-0100-H-FRM-0002 |  | Project Site Wide | SHE Risk Assessment Blank | Form | Project Site Wide - SHE Risk Assessment Blank - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SHE Risk Assessment Blank | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0003 | A | 6105AK124-0100-HFRM-0003 | Q24050972-09-0100-H-FRM-0003 |  | Project Site Wide | Noise SHE Risk Assessment | Form | Project Site Wide - Noise SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Noise SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0004 | A | 6105AK124-0100-HFRM-0004 | Q24050972-09-0100-H-FRM-0004 |  | Project Site Wide | Risk Assessment for First Aid Provision | Form | Project Site Wide - Risk Assessment for First Aid Provision - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Risk Assessment for First Aid Provision | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0005 | A | 6105AK124-0100-HFRM-0005 | Q24050972-09-0100-H-FRM-0005 |  | Project Site Wide | Work in Extreme Hot Conditions SHE Risk Assessment | Form | Project Site Wide - Work in Extreme Hot Conditions SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Work in Extreme Hot Conditions SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0006 | A | 6105AK124-0100-HFRM-0006 | Q24050972-09-0100-H-FRM-0006 |  | Project Site Wide | Personal Protective Equipment SHE Risk Assessment | Form | Project Site Wide - Personal Protective Equipment SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Personal Protective Equipment SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0007 | A | 6105AK124-0100-HFRM-0007 | Q24050972-09-0100-H-FRM-0007 |  | Project Site Wide | Display Screen Equipment DSE SHE Risk Assessment | Form | Project Site Wide - Display Screen Equipment DSE SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Display Screen Equipment DSE SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0008 | A | 6105AK124-0100-HFRM-0008 | Q24050972-09-0100-H-FRM-0008 |  | Project Site Wide | Hand Tools SHE Risk Assessment | Form | Project Site Wide - Hand Tools SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Hand Tools SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0009 | A | 6105AK124-0100-HFRM-0009 | Q24050972-09-0100-H-FRM-0009 |  | Project Site Wide | Legionnaires Disease SHE Risk Assessment | Form | Project Site Wide - Legionnaires Disease SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Legionnaires Disease SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0010 | A | 6105AK124-0100-HFRM-0010 | Q24050972-09-0100-H-FRM-0010 |  | Project Site Wide | Working at Height SHE Risk Assessment | Form | Project Site Wide - Working at Height SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Working at Height SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0011 | A | 6105AK124-0100-HFRM-0011 | Q24050972-09-0100-H-FRM-0011 |  | Project Site Wide | Driving SHE Risk Assessment | Form | Project Site Wide - Driving SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Driving SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0012 | A | 6105AK124-0100-HFRM-0012 | Q24050972-09-0100-H-FRM-0012 |  | Project Site Wide | Access on Working Scaffolds SHE Risk Assessment | Form | Project Site Wide - Access on Working Scaffolds SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Access on Working Scaffolds SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0013 | A | 6105AK124-0100-HFRM-0013 | Q24050972-09-0100-H-FRM-0013 |  | Project Site Wide | Mobile Scaffold Towers SHE Risk Assessment | Form | Project Site Wide - Mobile Scaffold Towers SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Mobile Scaffold Towers SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0014 | A | 6105AK124-0100-HFRM-0014 | Q24050972-09-0100-H-FRM-0014 |  | Project Site Wide | Confined Space Entry SHE Risk Assessment | Form | Project Site Wide - Confined Space Entry SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Confined Space Entry SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0015 | A | 6105AK124-0100-HFRM-0015 | Q24050972-09-0100-H-FRM-0015 |  | Project Site Wide | Fire SHE Risk Assessment | Form | Project Site Wide - Fire SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Fire SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0016 | A | 6105AK124-0100-HFRM-0016 | Q24050972-09-0100-H-FRM-0016 |  | Project Site Wide | Excavations SHE Risk Assessment | Form | Project Site Wide - Excavations SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Excavations SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0017 | A | 6105AK124-0100-HFRM-0017 | Q24050972-09-0100-H-FRM-0017 |  | Project Site Wide | Lone Working Risk Assessment | Form | Project Site Wide - Lone Working Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Lone Working Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0018 | A | 6105AK124-0100-HFRM-0018 | Q24050972-09-0100-H-FRM-0018 |  | Project Site Wide | Travel Abroad SHE Risk Assessment | Form | Project Site Wide - Travel Abroad SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Travel Abroad SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0019 | A | 6105AK124-0100-HFRM-0019 | Q24050972-09-0100-H-FRM-0019 |  | Project Site Wide | Working Over Water SHE Risk Assessment | Form | Project Site Wide - Working Over Water SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Working Over Water SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0020 | A | 6105AK124-0100-HFRM-0020 | Q24050972-09-0100-H-FRM-0020 |  | Project Site Wide | Roadworks SHE Risk Assessment | Form | Project Site Wide - Roadworks SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Roadworks SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0021 | A | 6105AK124-0100-HFRM-0021 | Q24050972-09-0100-H-FRM-0021 |  | Project Site Wide | Electrical Tools SHE Risk-Assessment (2) | Form | Project Site Wide - Electrical Tools SHE Risk-Assessment (2) - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Electrical Tools SHE-Risk-Assessment (2) | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0022 | A | 6105AK124-0100-HFRM-0022 | Q24050972-09-0100-H-FRM-0022 |  | Project Site Wide | Electrical Tools SHE Risk Assessment | Form | Project Site Wide - Electrical Tools SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Electrical Tools SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0023 | A | 6105AK124-0100-HFRM-0023 | Q24050972-09-0100-H-FRM-0023 |  | Project Site Wide | Use of Ladders for Work at Height SHE Risk Assessment | Form | Project Site Wide - Use of Ladders for Work at Height SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Use of Ladders for Work at Height SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0024 | A | 6105AK124-0100-HFRM-0024 | Q24050972-09-0100-H-FRM-0024 |  | Project Site Wide | Placing Concrete SHE Risk Assessment | Form | Project Site Wide - Placing Concrete SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Placing Concrete SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0025 | A | 6105AK124-0100-HFRM-0025 | Q24050972-09-0100-H-FRM-0025 |  | Project Site Wide | Brickwork and Blockwork SHE Risk Assessment | Form | Project Site Wide - Brickwork and Blockwork SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Brickwork and Blockwork SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0026 | A | 6105AK124-0100-HFRM-0026 | Q24050972-09-0100-H-FRM-0026 |  | Project Site Wide | Falseworks Risk Assessment | Form | Project Site Wide - Falseworks Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Falseworks Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0027 | A | 6105AK124-0100-HFRM-0027 | Q24050972-09-0100-H-FRM-0027 |  | Project Site Wide | Temporary Electrical Supplies SHE Risk Assessment (2) | Form | Project Site Wide - Temporary Electrical Supplies SHE Risk Assessment (2) - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Temporary Electrical Supplies SHE Risk Assessment (2) | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0028 | A | 6105AK124-0100-HFRM-0028 | Q24050972-09-0100-H-FRM-0028 |  | Project Site Wide | Temporary Electrical Supplies SHE Risk Assessment | Form | Project Site Wide - Temporary Electrical Supplies SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Temporary Electrical Supplies SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0029 | A | 6105AK124-0100-HFRM-0029 | Q24050972-09-0100-H-FRM-0029 |  | Project Site Wide | Buried Services SHE Risk Assessment | Form | Project Site Wide - Buried Services SHE Risk Assessment - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Buried Services SHE Risk Assessment | Form |  |  |  | Pending
6105A | K124 | 0100 | H | FRM | 0030 | A | 6105AK124-0100-HFRM-0030 | Q24050972-09-0100-H-FRM-0030 |  | Project Site Wide | Two-Week-Lookahead | Form | Project Site Wide - Two-Week-Lookahead - Form |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Two-Week-Lookahead | Form |  |  |  | Pending
6105A | K124 | 6260 | E | GAD | 0002 | A | 6105AK124-6260-EGAD-0002 | Q24050972-04-6260-E-GAD-0002 | Sht 1 of 1 | Emergency Power Generation (Main Plant) | MV Switch Board | General Arrangement | Emergency Power Generation (Main Plant) - MV Switch Board - General Arrangement - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | MV Switch Board | General Arrangement |  |  |  | Pending
6105A | K124 | 6260 | E | GAD | 0005 | A | 6105AK124-6260-EGAD-0005 | Q24050972-07-6260-E-GAD-0005 | Sht 1 of 8 | Emergency Power Generation (Main Plant) | Bulk Fuel Storage Facility | General Arrangement | Emergency Power Generation (Main Plant) - Bulk Fuel Storage Facility - General Arrangement - Sht 1 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Bulk Fuel Storage Facility | General Arrangement |  |  |  | Pending
6105A | K124 | 6260 | E | GAD | 0006 | A | 6105AK124-6260-EGAD-0006 | Q24050972-07-6260-E-GAD-0006 | Sht 2 of 8 | Emergency Power Generation (Main Plant) | Pump house - Fuel Polish Isometric Arrangement | General Arrangement | Emergency Power Generation (Main Plant) - Pump house - Fuel Polish Isometric Arrangement - General Arrangement - Sht 2 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Bulk Fuel Storage Facility | General Arrangement |  |  |  | Pending
6105A | K124 | 6260 | E | GAD | 0007 | A | 6105AK124-6260-EGAD-0007 | Q24050972-07-6260-E-GAD-0007 | Sht 3 of 8 | Emergency Power Generation (Main Plant) | Bulk Fuel Storage Facility - Pump House - Fuel Polishing System | General Arrangement | Emergency Power Generation (Main Plant) - Bulk Fuel Storage Facility - Pump House - Fuel Polishing System - General Arrangement - Sht 3 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Bulk Fuel Storage Facility | General Arrangement |  |  |  | Pending
6105A | K124 | 6260 | E | GAD | 0008 | A | 6105AK124-6260-EGAD-0008 | Q24050972-07-6260-E-GAD-0008 | Sht 4 of 8 | Emergency Power Generation (Main Plant) | Bulk Fuel Storage Facility - Pump House - Fuel Transfer | General Arrangement | Emergency Power Generation (Main Plant) - Bulk Fuel Storage Facility - Pump House - Fuel Transfer - General Arrangement - Sht 4 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Bulk Fuel Storage Facility | General Arrangement |  |  |  | Pending
6105A | K124 | 6260 | E | GAD | 0009 | A | 6105AK124-6260-EGAD-0009 | Q24050972-07-6260-E-GAD-0009 | Sht 5 of 8 | Emergency Power Generation (Main Plant) | Bulk Fuel Storage Facility - Pump House - Fuel Transfer | General Arrangement | Emergency Power Generation (Main Plant) - Bulk Fuel Storage Facility - Pump House - Fuel Transfer - General Arrangement - Sht 5 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Bulk Fuel Storage Facility | General Arrangement |  |  |  | Pending
6105A | K124 | 6260 | E | GAD | 0010 | A | 6105AK124-6260-EGAD-0010 | Q24050972-07-6260-E-GAD-0010 | Sht 6 of 8 | Emergency Power Generation (Main Plant) | Pump house - Off-load system Isometric Arrangement | General Arrangement | Emergency Power Generation (Main Plant) - Pump house - Off-load system Isometric Arrangement - General Arrangement - Sht 6 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Bulk Fuel Storage Facility | General Arrangement |  |  |  | Pending
6105A | K124 | 6260 | E | GAD | 0011 | A | 6105AK124-6260-EGAD-0011 | Q24050972-07-6260-E-GAD-0011 | Sht 7 of 8 | Emergency Power Generation (Main Plant) | Bulk Fuel Offloading and Distribution System | General Arrangement | Emergency Power Generation (Main Plant) - Bulk Fuel Offloading and Distribution System - General Arrangement - Sht 7 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Bulk Fuel Storage Facility | General Arrangement |  |  |  | Pending
6105A | K124 | 6260 | E | GAD | 0012 | A | 6105AK124-6260-EGAD-0012 | Q24050972-08-6260-E-GAD-0012 | Sht 8 of 8 | Emergency Power Generation (Main Plant) | Bulk Fuel Storage Facility-Pump House-Off-Load System | General Arrangement | Emergency Power Generation (Main Plant) - Bulk Fuel Storage Facility-Pump House-Off-Load System - General Arrangement - Sht 8 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Bulk Fuel Storage Facility | General Arrangement |  |  |  | Pending
6105A | K124 | 6262 | M | GAD | 0001 | A | 6105AK124-6262-MGAD-0001 | Q24050972-07-6262-M-GAD-0001 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | 11kVA MV E-house type 1A | External Views | Emergency Power Substation 1 and Control Room 1 - 11kVA MV E-house type 1A - External Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | MV E-house | External Views |  |  |  | Pending
6105A | K124 | 6262 | M | GAD | 0003 | A | 6105AK124-6262-MGAD-0003 | Q24050972-07-6262-M-GAD-0003 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | 11kVA MV E-house type 1A | Plan Views | Emergency Power Substation 1 and Control Room 1 - 11kVA MV E-house type 1A - Plan Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | MV E-house | Plan Views |  |  |  | Pending
6105A | K124 | 6262 | M | GAD | 0004 | A | 6105AK124-6262-MGAD-0004 | Q24050972-07-6262-M-GAD-0004 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | 11kVA MV E-house type 1A | Paint Schedule | Emergency Power Substation 1 and Control Room 1 - 11kVA MV E-house type 1A - Paint Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | MV E-house | Paint Schedule |  |  |  | Pending
6105A | K124 | 6262 | M | GAD | 0005 | A | 6105AK124-6262-MGAD-0005 | Q24050972-07-6262-M-GAD-0005 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | 11kVA MV E-house type 1A | Signage Schedule | Emergency Power Substation 1 and Control Room 1 - 11kVA MV E-house type 1A - Signage Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | MV E-house | Signage Schedule |  |  |  | Pending
6105A | K124 | 6262 | M | GAD | 0010 | A | 6105AK124-6262-MGAD-0010 | Q24050972-08-6262-M-GAD-0010 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | 11kVA MV E-house type 1B | Signage Schedule | Emergency Power Substation 1 and Control Room 1 - 11kVA MV E-house type 1B - Signage Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | MV E-house | Signage Schedule |  |  |  | Pending
6105A | K124 | 6262 | M | GAD | 0006 | A | 6105AK124-6262-MGAD-0006 | Q24050972-08-6262-M-GAD-0006 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | 11kVA MV E-house type 1B | External Views | Emergency Power Substation 1 and Control Room 1 - 11kVA MV E-house type 1B - External Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | MV E-house | External Views |  |  |  | Pending
6105A | K124 | 6262 | M | GAD | 0007 | A | 6105AK124-6262-MGAD-0007 | Q24050972-08-6262-M-GAD-0007 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | 11kVA MV E-house type 1B | Internal Views | Emergency Power Substation 1 and Control Room 1 - 11kVA MV E-house type 1B - Internal Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | MV E-house | Internall Views |  |  |  | Pending
6105A | K124 | 6262 | M | GAD | 0008 | A | 6105AK124-6262-MGAD-0008 | Q24050972-08-6262-M-GAD-0008 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | 11kVA MV E-house type 1B | Plan Views | Emergency Power Substation 1 and Control Room 1 - 11kVA MV E-house type 1B - Plan Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | MV E-house | Plan Views |  |  |  | Pending
6105A | K124 | 6262 | M | GAD | 0009 | A | 6105AK124-6262-MGAD-0009 | Q24050972-08-6262-M-GAD-0009 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | 11kVA MV E-house type 1B | Paint Schedule | Emergency Power Substation 1 and Control Room 1 - 11kVA MV E-house type 1B - Paint Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | MV E-house | Paint Schedule |  |  |  | Pending
6105A | K124 | 6286 | E | GAD | 0001 | A | 6105AK124-6286-EGAD-0001 | Q24050972-08-6286-E-GAD-0001 | Sht 1 of 1 | Primary Crushing | Mining Substation | General Arrangement | Primary Crushing - Mining Substation - General Arrangement - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Mining Substation | General Arrangement |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0001 | A | 6105AK124-6286-MGAD-0001 | Q24050972-07-6286-M-GAD-0001 | Sht 1 of 1 | Primary Crushing | 11kVA MV E-house type 1A | External Views | Primary Crushing - 11kVA MV E-house type 1A - External Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | 11kVA MV E-house type 1A | External Views |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0002 | A | 6105AK124-6286-MGAD-0002 | Q24050972-07-6286-M-GAD-0002 | Sht 1 of 1 | Primary Crushing | 11kVA MV E-house type 1A | Internal Views | Primary Crushing - 11kVA MV E-house type 1A - Internal Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | 11kVA MV E-house type 1A | Internall Views |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0003 | A | 6105AK124-6286-MGAD-0003 | Q24050972-07-6286-M-GAD-0003 | Sht 1 of 1 | Primary Crushing | 11kVA MV E-house type 1A | Plan Views | Primary Crushing - 11kVA MV E-house type 1A - Plan Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | 11kVA MV E-house type 1A | Plan Views |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0004 | A | 6105AK124-6286-MGAD-0004 | Q24050972-07-6286-M-GAD-0004 | Sht 1 of 1 | Primary Crushing | 11kVA MV E-house type 1A | Paint Schedule | Primary Crushing - 11kVA MV E-house type 1A - Paint Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | 11kVA MV E-house type 1A | Paint Schedule |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0005 | A | 6105AK124-6286-MGAD-0005 | Q24050972-07-6286-M-GAD-0005 | Sht 1 of 1 | Primary Crushing | 11kVA MV E-house type 1A | Signage Schedule | Primary Crushing - 11kVA MV E-house type 1A - Signage Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | 11kVA MV E-house type 1A | Signage Schedule |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0006 | A | 6105AK124-6286-MGAD-0006 | Q24050972-07-6286-M-GAD-0006 | Sht 1 of 1 | Primary Crushing | 11kVA MV E-house type 1B | External Views | Primary Crushing - 11kVA MV E-house type 1B - External Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | 11kVA MV E-house type 1B | External Views |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0007 | A | 6105AK124-6286-MGAD-0007 | Q24050972-07-6286-M-GAD-0007 | Sht 1 of 1 | Primary Crushing | 11kVA MV E-house type 1B | Internal Views | Primary Crushing - 11kVA MV E-house type 1B - Internal Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | 11kVA MV E-house type 1B | Internall Views |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0008 | A | 6105AK124-6286-MGAD-0008 | Q24050972-07-6286-M-GAD-0008 | Sht 1 of 1 | Primary Crushing | 11kVA MV E-house type 1B | Plan Views | Primary Crushing - 11kVA MV E-house type 1B - Plan Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | 11kVA MV E-house type 1B | Plan Views |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0009 | A | 6105AK124-6286-MGAD-0009 | Q24050972-07-6286-M-GAD-0009 | Sht 1 of 1 | Primary Crushing | 11kVA MV E-house type 1B | Paint Schedule | Primary Crushing - 11kVA MV E-house type 1B - Paint Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | 11kVA MV E-house type 1B | Paint Schedule |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0010 | A | 6105AK124-6286-MGAD-0010 | Q24050972-07-6286-M-GAD-0010 | Sht 1 of 1 | Primary Crushing | 11kVA MV E-house type 1B | Signage Schedule | Primary Crushing - 11kVA MV E-house type 1B - Signage Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | 11kVA MV E-house type 1B | Signage Schedule |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0011 | A | 6105AK124-6286-MGAD-0011 | Q24050972-09-6286-M-GAD-0011 | Sht 1 of 1 | Primary Crushing | 33kVA MV Switchroom | External Views | Primary Crushing - 33kVA MV Switchroom - External Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV Switchroom | External Views |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0012 | A | 6105AK124-6286-MGAD-0012 | Q24050972-09-6286-M-GAD-0012 | Sht 1 of 1 | Primary Crushing | 33kVA MV Switchroom | Internal Views | Primary Crushing - 33kVA MV Switchroom - Internal Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV Switchroom | Internal Views |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0013 | A | 6105AK124-6286-MGAD-0013 | Q24050972-09-6286-M-GAD-0013 | Sht 1 of 1 | Primary Crushing | 33kVA MV Switchroom | Plan Views | Primary Crushing - 33kVA MV Switchroom - Plan Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV Switchroom | Plan Views |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0014 | A | 6105AK124-6286-MGAD-0014 | Q24050972-09-6286-M-GAD-0014 | Sht 1 of 1 | Primary Crushing | 33kVA MV Switchroom | Paint Schedule | Primary Crushing - 33kVA MV Switchroom - Paint Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV Switchroom | Paint Schedule |  |  |  | Pending
6105A | K124 | 6286 | M | GAD | 0015 | A | 6105AK124-6286-MGAD-0015 | Q24050972-09-6286-M-GAD-0015 | Sht 1 of 1 | Primary Crushing | 33kVA MV Switchroom | Signage Schedule | Primary Crushing - 33kVA MV Switchroom - Signage Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV Switchroom | Signage Schedule |  |  |  | Pending
6105A | K124 | 6260 | M | GAD | 0002 | A | 6105AK124-6260-MGAD-0002 | Q24050972-07-6260-M-GAD-0002 | Sht.1 of 8 | Emergency Power Generation (Main Plant) | Pump house - Plant | Isometric Arrangement | Emergency Power Generation (Main Plant) - Pump house - Plant - Isometric Arrangement - Sht.1 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Pump house - Plant | Isometric Arrangement |  |  |  | Pending
6105A | K124 | 6260 | M | GAD | 0003 | A | 6105AK124-6260-MGAD-0003 | Q24050972-07-6260-M-GAD-0003 | Sht.2 of 8 | Emergency Power Generation (Main Plant) | Pump house | Isometric Arrangement | Emergency Power Generation (Main Plant) - Pump house - Isometric Arrangement - Sht.2 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Pump house | Isometric Arrangement |  |  |  | Pending
6105A | K124 | 6260 | M | GAD | 0004 | A | 6105AK124-6260-MGAD-0004 | Q24050972-07-6260-M-GAD-0004 | Sht.3 of 8 | Emergency Power Generation (Main Plant) | Pump house - Fuel Polish | Isometric Arrangement | Emergency Power Generation (Main Plant) - Pump house - Fuel Polish - Isometric Arrangement - Sht.3 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Pump house - Fuel Polish | Isometric Arrangement |  |  |  | Pending
6105A | K124 | 6260 | M | GAD | 0005 | A | 6105AK124-6260-MGAD-0005 | Q24050972-07-6260-M-GAD-0005 | Sht.4 of 8 | Emergency Power Generation (Main Plant) | Pump house - Fuel Polish | General Arrangement | Emergency Power Generation (Main Plant) - Pump house - Fuel Polish - General Arrangement - Sht.4 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Pump house - Fuel Polish | General Arrangement |  |  |  | Pending
6105A | K124 | 6260 | M | GAD | 0006 | A | 6105AK124-6260-MGAD-0006 | Q24050972-07-6260-M-GAD-0006 | Sht.5 of 8 | Emergency Power Generation (Main Plant) | Pump house - Fuel Transfer | Isometric Arrangement | Emergency Power Generation (Main Plant) - Pump house - Fuel Transfer - Isometric Arrangement - Sht.5 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Pump house - Fuel Transfer | Isometric Arrangement |  |  |  | Pending
6105A | K124 | 6260 | M | GAD | 0007 | A | 6105AK124-6260-MGAD-0007 | Q24050972-07-6260-M-GAD-0007 | Sht.6 of 8 | Emergency Power Generation (Main Plant) | Pump house - Fuel Transfer | General Arrangement | Emergency Power Generation (Main Plant) - Pump house - Fuel Transfer - General Arrangement - Sht.6 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Pump house - Fuel Transfer | General Arrangement |  |  |  | Pending
6105A | K124 | 6260 | M | GAD | 0008 | A | 6105AK124-6260-MGAD-0008 | Q24050972-07-6260-M-GAD-0008 | Sht.7 of 8 | Emergency Power Generation (Main Plant) | Pump house - Off-load system | Isometric Arrangement | Emergency Power Generation (Main Plant) - Pump house - Off-load system - Isometric Arrangement - Sht.7 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Pump house - Off-load system | Isometric Arrangement |  |  |  | Pending
6105A | K124 | 6260 | M | GAD | 0009 | A | 6105AK124-6260-MGAD-0009 | Q24050972-07-6260-M-GAD-0009 | Sht.8 of 8 | Emergency Power Generation (Main Plant) | Pump house | General Arrangement | Emergency Power Generation (Main Plant) - Pump house - General Arrangement - Sht.8 of 8 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Pump house | General Arrangement |  |  |  | Pending
6105A | K124 | 6240 | E | GAD | 0001 | A | 6105AK124-6240-EGAD-0001 | Q24050972-09-6240-E-GAD-0001 | Sht 1 of 1 | High Voltage Substations | Main Consumer intake Power Complex | General Arrangement | High Voltage Substations - Main Consumer intake Power Complex - General Arrangement - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Main Consumer intake Power Complex | General Arrangement |  |  |  | Pending
6105A | K124 | 6240 | E | GAD | 0002 | A | 6105AK124-6240-EGAD-0002 | Q24050972-09-6240-E-GAD-0002 | Sht 1 of 1 | High Voltage Substations | Main Consumer intake Power Complex | Earthing Arrangement | High Voltage Substations - Main Consumer intake Power Complex - Earthing Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Main Consumer intake Power Complex | Earthing Arrangement |  |  |  | Pending
6105A | K124 | 6260 | E | GAD | 0013 | A | 6105AK124-6260-EGAD-0013 | Q24050972-09-6260-E-GAD-0013 | Sht 1 of 4 | Emergency Power Generation (Main Plant) | Mv Cable Isolator Panel | General Arrangement | Emergency Power Generation (Main Plant) - Mv Cable Isolator Panel - General Arrangement - Sht 1 of 4 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Mv Cable Isolator Panel | General Arrangement |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0001 | A | 6105AK124-6243-MGAD-0001 | Q24050972-09-6243-M-GAD-0001 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1A | External Views | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1A - External Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1A | External Views |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0002 | A | 6105AK124-6243-MGAD-0002 | Q24050972-09-6243-M-GAD-0002 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1A | Internal Views | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1A - Internal Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1A | Internal Views |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0003 | A | 6105AK124-6243-MGAD-0003 | Q24050972-09-6243-M-GAD-0003 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1A | Plan Views | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1A - Plan Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1A | Plan Views |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0004 | A | 6105AK124-6243-MGAD-0004 | Q24050972-09-6243-M-GAD-0004 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1A | Paint Schedule | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1A - Paint Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1A | Paint Schedule |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0005 | A | 6105AK124-6243-MGAD-0005 | Q24050972-09-6243-M-GAD-0005 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1A | Signage Schedule | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1A - Signage Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1A | Signage Schedule |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0006 | A | 6105AK124-6243-MGAD-0006 | Q24050972-09-6243-M-GAD-0006 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1B | External Views | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1B - External Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1B | External Views |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0007 | A | 6105AK124-6243-MGAD-0007 | Q24050972-09-6243-M-GAD-0007 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1B | Internal Views | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1B - Internal Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1B | Internal Views |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0008 | A | 6105AK124-6243-MGAD-0008 | Q24050972-09-6243-M-GAD-0008 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1B | Plan Views | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1B - Plan Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1B | Plan Views |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0009 | A | 6105AK124-6243-MGAD-0009 | Q24050972-09-6243-M-GAD-0009 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1B | Paint Schedule | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1B - Paint Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1B | Paint Schedule |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0010 | A | 6105AK124-6243-MGAD-0010 | Q24050972-09-6243-M-GAD-0010 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1B | Signage Schedule | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1B - Signage Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1B | Signage Schedule |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0011 | A | 6105AK124-6243-MGAD-0011 | Q24050972-09-6243-M-GAD-0011 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1C | External Views | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1C - External Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1C | External Views |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0012 | A | 6105AK124-6243-MGAD-0012 | Q24050972-09-6243-M-GAD-0012 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1C | Internal Views | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1C - Internal Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1C | Internal Views |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0013 | A | 6105AK124-6243-MGAD-0013 | Q24050972-09-6243-M-GAD-0013 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1C | Plan Views | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1C - Plan Views - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1C | Plan Views |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0014 | A | 6105AK124-6243-MGAD-0014 | Q24050972-09-6243-M-GAD-0014 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1C | Paint Schedule | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1C - Paint Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1C | Paint Schedule |  |  |  | Pending
6105A | K124 | 6243 | M | GAD | 0015 | A | 6105AK124-6243-MGAD-0015 | Q24050972-09-6243-M-GAD-0015 | Sht 1 of 1 | 220/33 kV Plant Main Substation | 33kVA MV E-house type 1C | Signage Schedule | 220/33 kV Plant Main Substation - 33kVA MV E-house type 1C - Signage Schedule - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kVA MV E-house type 1C | Signage Schedule |  |  |  | Pending
6105A | K124 | 6260 | E | GAD | 0014 | A | 6105AK124-6260-EGAD-0014 | Q24050972-09-6260-E-GAD-0014 | Sht 1 of 1 | Emergency Power Generation (Main Plant) | Emergency Power Substation 1 and Control Room 1 | General Arrangement | Emergency Power Generation (Main Plant) - Emergency Power Substation 1 and Control Room 1 - General Arrangement - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Emergency Power Substation 1 and Control Room 1 | General Arrangement |  |  |  | Pending
6105A | K124 | 6210 | E | GAD | 0001 | A | 6105AK124-6210-EGAD-0001 | Q24050972-10-6210-E-GAD-0001 | Sht 1 of 1 | Power Stations | 33kV/220kV Step-up Transformers Cable Trench | Layout | Power Stations - 33kV/220kV Step-up Transformers Cable Trench - Layout - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | 33kV/220kV Step-up Transformers Cable Trench | Layout |  |  |  | Pending
6105A | K124 | 7337 | E | GAD | 0001 | A | 6105AK124-7337-EGAD-0001 | Q24050972-10-7337-E-GAD-0001 | Sht 1 of 1 | Port Qasim PIBT Control Room | Building | General Arrangement | Port Qasim PIBT Control Room - Building - General Arrangement - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | Port Qasim PIBT Control Room | General Arrangement |  |  |  | Pending
6105A | K124 | 0100 | H | GDL | 0001 | A | 6105AK124-0100-HGDL-0001 | Q24050972-07-0100-H-GDL-0001 |  | Project Site Wide | Project Health And Safety Governance Standards “PHASGS” - Management System Units | Guideline | Project Site Wide - Project Health And Safety Governance Standards “PHASGS” - Management System Units - Guideline |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Project Health And Safety Governance Standards “PHASGS” | Management System Units |  |  |  | Pending
6105A | K124 | 0100 | H | GDL | 0002 | A | 6105AK124-0100-HGDL-0002 | Q24050972-07-0100-H-GDL-0002 |  | Project Site Wide | RAMS-Guidance | Guideline | Project Site Wide - RAMS-Guidance - Guideline |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | RAMS-Guidance | Guideline |  |  |  | Pending
6105A | K124 | 0100 | H | GDL | 0003 | A | 6105AK124-0100-HGDL-0003 | Q24050972-07-0100-H-GDL-0003 |  | Project Site Wide | Induction - Presentation | Guideline | Project Site Wide - Induction - Presentation - Guideline |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Induction-Presentation | Guideline |  |  |  | Pending
6105A | K124 | 0100 | H | GDL | 0004 | A | 6105AK124-0100-HGDL-0004 | Q24050972-07-0100-H-GDL-0004 |  | Project Site Wide | Method Statement and Risk Assessment Guidance | Guideline | Project Site Wide - Method Statement and Risk Assessment Guidance - Guideline |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Method Statement and Risk Assessment Guidance | Guideline |  |  |  | Pending
6105A | K124 | 0100 | H | GDL | 0005 | A | 6105AK124-0100-HGDL-0005 | Q24050972-09-0100-H-GDL-0005 |  | Project Site Wide | E&I Supervisor Roles and Responsibilities | Guideline | Project Site Wide - E&I Supervisor Roles and Responsibilities - Guideline |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | E&I Supervisor Roles and Responsibilities | Guideline |  |  |  | Pending
6105A | K124 | 6286 | E | LAY | 0001 | A | 6105AK124-6286-ELAY-0001 | Q24050972-07-6286-E-LAY-0001 | Sht 1 of 3 | Primary Crushing | Auxiliary 400V AC Panel 2 | Layout | Primary Crushing - Auxiliary 400V AC Panel 2 - Layout - Sht 1 of 3 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Auxiliary 400V AC Panel 2 | Layout |  |  |  | Pending
6105A | K124 | 6260 | E | LAY | 0001 | A | 6105AK124-6260-ELAY-0001 | Q24050972-09-6260-E-LAY-0001 | Sht.2 of 4 | Emergency Power Generation (Main Plant) | Mv Cable Isolator Panel | Layout | Emergency Power Generation (Main Plant) - Mv Cable Isolator Panel - Layout - Sht.2 of 4 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Mv Cable Isolator Panel | Panel Layout |  |  |  | Pending
6105A | K124 | 6280 | E | LAY | 0001 | A | 6105AK124-6280-ELAY-0001 | Q24050972-11-6280-E-LAY-0001 | Sht 1 of 5 | Medium Voltage (33 kV) Overhead Powerlines | Mining Supply 33kV & 11kV OHL Routing | Enlarged Layout | Medium Voltage (33 kV) Overhead Powerlines - Mining Supply 33kV & 11kV OHL Routing - Enlarged Layout - Sht 1 of 5 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | 33kV & 11kV OHL Routing | Enlarged Layout |  |  |  | Pending
6105A | K124 | 6280 | E | LAY | 0002 | A | 6105AK124-6280-ELAY-0002 | Q24050972-11-6280-E-LAY-0002 | Sht 2 of 5 | Medium Voltage (33 kV) Overhead Powerlines | Mining Supply 33kV & 11kV OHL Routing | Enlarged Layout | Medium Voltage (33 kV) Overhead Powerlines - Mining Supply 33kV & 11kV OHL Routing - Enlarged Layout - Sht 2 of 5 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | 33kV & 11kV OHL Routing | Enlarged Layout |  |  |  | Pending
6105A | K124 | 6280 | E | LAY | 0003 | A | 6105AK124-6280-ELAY-0003 | Q24050972-11-6280-E-LAY-0003 | Sht 3 of 5 | Medium Voltage (33 kV) Overhead Powerlines | Mining Supply 33kV & 11kV OHL Routing | Enlarged Layout | Medium Voltage (33 kV) Overhead Powerlines - Mining Supply 33kV & 11kV OHL Routing - Enlarged Layout - Sht 3 of 5 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | 33kV & 11kV OHL Routing | Enlarged Layout |  |  |  | Pending
6105A | K124 | 6280 | E | LAY | 0004 | A | 6105AK124-6280-ELAY-0004 | Q24050972-11-6280-E-LAY-0004 | Sht 4 of 5 | Medium Voltage (33 kV) Overhead Powerlines | Mining Supply 33kV & 11kV OHL Routing | Enlarged Layout | Medium Voltage (33 kV) Overhead Powerlines - Mining Supply 33kV & 11kV OHL Routing - Enlarged Layout - Sht 4 of 5 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | 33kV & 11kV OHL Routing | Enlarged Layout |  |  |  | Pending
6105A | K124 | 6280 | E | LAY | 0005 | A | 6105AK124-6280-ELAY-0005 | Q24050972-11-6280-E-LAY-0005 | Sht 5 of 5 | Medium Voltage (33 kV) Overhead Powerlines | Mining Supply 33kV & 11kV OHL Routing | Enlarged Layout | Medium Voltage (33 kV) Overhead Powerlines - Mining Supply 33kV & 11kV OHL Routing - Enlarged Layout - Sht 5 of 5 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | 33kV & 11kV OHL Routing | Enlarged Layout |  |  |  | Pending
6105A | K124 | 6280 | E | LAY | 0006 | A | 6105AK124-6280-ELAY-0006 | Q24050972-11-6280-E-LAY-0006 | Sht 1 of 6 | Medium Voltage (33 kV) Overhead Powerlines | Mining Supply 33kV & 11kV OHL Routing | Layout - Final Years | Medium Voltage (33 kV) Overhead Powerlines - Mining Supply 33kV & 11kV OHL Routing - Layout - Final Years - Sht 1 of 6 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | 33kV & 11kV OHL Routing | Layout - Final Years |  |  |  | Pending
6105A | K124 | 6280 | E | LAY | 0007 | A | 6105AK124-6280-ELAY-0007 | Q24050972-11-6280-E-LAY-0007 | Sht 2 of 6 | Medium Voltage (33 kV) Overhead Powerlines | Mining Supply 33kV & 11kV OHL Routing | Enlarged Layout - Final years | Medium Voltage (33 kV) Overhead Powerlines - Mining Supply 33kV & 11kV OHL Routing - Enlarged Layout - Final years - Sht 2 of 6 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | 33kV & 11kV OHL Routing | Enlarged Layout - Final years |  |  |  | Pending
6105A | K124 | 6280 | E | LAY | 0008 | A | 6105AK124-6280-ELAY-0008 | Q24050972-11-6280-E-LAY-0008 | Sht 3 of 6 | Medium Voltage (33 kV) Overhead Powerlines | Mining Supply 33kV & 11kV OHL Routing | Enlarged Layout - Final years | Medium Voltage (33 kV) Overhead Powerlines - Mining Supply 33kV & 11kV OHL Routing - Enlarged Layout - Final years - Sht 3 of 6 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | 33kV & 11kV OHL Routing | Enlarged Layout - Final years |  |  |  | Pending
6105A | K124 | 6280 | E | LAY | 0009 | A | 6105AK124-6280-ELAY-0009 | Q24050972-11-6280-E-LAY-0009 | Sht 4 of 6 | Medium Voltage (33 kV) Overhead Powerlines | Mining Supply 33kV & 11kV OHL Routing | Enlarged Layout - Final years | Medium Voltage (33 kV) Overhead Powerlines - Mining Supply 33kV & 11kV OHL Routing - Enlarged Layout - Final years - Sht 4 of 6 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | 33kV & 11kV OHL Routing | Enlarged Layout - Final years |  |  |  | Pending
6105A | K124 | 6280 | E | LAY | 0010 | A | 6105AK124-6280-ELAY-0010 | Q24050972-11-6280-E-LAY-0010 | Sht 5 of 6 | Medium Voltage (33 kV) Overhead Powerlines | MINING SUPPLY 33kV & 11kV OHL ROUTING | Enlarged Layout - Final years | Medium Voltage (33 kV) Overhead Powerlines - MINING SUPPLY 33kV & 11kV OHL ROUTING - Enlarged Layout - Final years - Sht 5 of 6 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | 33kV & 11kV OHL Routing | Enlarged Layout - Final years |  |  |  | Pending
6105A | K124 | 6280 | E | LAY | 0011 | A | 6105AK124-6280-ELAY-0011 | Q24050972-11-6280-E-LAY-0011 | Sht 6 of 6 | Medium Voltage (33 kV) Overhead Powerlines | MINING SUPPLY 33kV & 11kV OHL ROUTING | Enlarged Layout - Final years | Medium Voltage (33 kV) Overhead Powerlines - MINING SUPPLY 33kV & 11kV OHL ROUTING - Enlarged Layout - Final years - Sht 6 of 6 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | 33kV & 11kV OHL Routing | Enlarged Layout - Final years |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0001 | A | 6105AK124-0100-HLST-0001 | Q24050972-09-0100-H-LST-0001 |  | Project Site Wide | Checklist Ladder Inspection | CheckList | Project Site Wide - Checklist Ladder Inspection - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Checklist Ladder Inspection | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0002 | A | 6105AK124-0100-HLST-0002 | Q24050972-09-0100-H-LST-0002 |  | Project Site Wide | Checklist Safety Net Inspection | CheckList | Project Site Wide - Checklist Safety Net Inspection - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Checklist Safety Net Inspection | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0003 | A | 6105AK124-0100-HLST-0003 | Q24050972-09-0100-H-LST-0003 |  | Project Site Wide | Checklist Harness and Lanyard Inspection | CheckList | Project Site Wide - Checklist Harness and Lanyard Inspection - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Checklist Harness and Lanyard Inspection | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0004 | A | 6105AK124-0100-HLST-0004 | Q24050972-09-0100-H-LST-0004 |  | Project Site Wide | Checklist Ladder Inspection and Maintenance | CheckList | Project Site Wide - Checklist Ladder Inspection and Maintenance - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Checklist Ladder Inspection and Maintenance | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0005 | A | 6105AK124-0100-HLST-0005 | Q24050972-09-0100-H-LST-0005 |  | Project Site Wide | Checklist Electrical Safety | CheckList | Project Site Wide - Checklist Electrical Safety - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Electrical Safety | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0006 | A | 6105AK124-0100-HLST-0006 | Q24050972-09-0100-H-LST-0006 |  | Project Site Wide | Checklist Scaffolding Inspection | CheckList | Project Site Wide - Checklist Scaffolding Inspection - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Scaffolding Inspection | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0007 | A | 6105AK124-0100-HLST-0007 | Q24050972-09-0100-H-LST-0007 |  | Project Site Wide | Checklist Utility Clearance | CheckList | Project Site Wide - Checklist Utility Clearance - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Utility Clearance | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0008 | A | 6105AK124-0100-HLST-0008 | Q24050972-09-0100-H-LST-0008 |  | Project Site Wide | Checklist Daily Excavation | CheckList | Project Site Wide - Checklist Daily Excavation - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Daily Excavation | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0009 | A | 6105AK124-0100-HLST-0009 | Q24050972-09-0100-H-LST-0009 |  | Project Site Wide | Checklist Crane-Suspended Personnel Platform Approval | CheckList | Project Site Wide - Checklist Crane-Suspended Personnel Platform Approval - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Crane-Suspended Personnel Platform Approval | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0010 | A | 6105AK124-0100-HLST-0010 | Q24050972-09-0100-H-LST-0010 |  | Project Site Wide | Checklist First Aid and AED Inspection | CheckList | Project Site Wide - Checklist First Aid and AED Inspection - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | First Aid and AED Inspection | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0011 | A | 6105AK124-0100-HLST-0011 | Q24050972-09-0100-H-LST-0011 |  | Project Site Wide | Checklist Violence in the Workplace | CheckList | Project Site Wide - Checklist Violence in the Workplace - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Violence in the Workplace | Violence in the Workplace |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0012 | A | 6105AK124-0100-HLST-0012 | Q24050972-09-0100-H-LST-0012 |  | Project Site Wide | Manual Handling Assessment | CheckList | Project Site Wide - Manual Handling Assessment - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Manual Handling Assessment | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0013 | A | 6105AK124-0100-HLST-0013 | Q24050972-09-0100-H-LST-0013 |  | Project Site Wide | Employment Medical Examination Form | CheckList | Project Site Wide - Employment Medical Examination Form - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Employment Medical Examination Form | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0014 | A | 6105AK124-0100-HLST-0014 | Q24050972-09-0100-H-LST-0014 |  | Project Site Wide | PPE Assessment | CheckList | Project Site Wide - PPE Assessment - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | PPE Assessment | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0015 | A | 6105AK124-0100-HLST-0015 | Q24050972-09-0100-H-LST-0015 |  | Project Site Wide | Workstation DSE Assessment Form | CheckList | Project Site Wide - Workstation DSE Assessment Form - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Workstation DSE Assessment Form | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0016 | A | 6105AK124-0100-HLST-0016 | Q24050972-09-0100-H-LST-0016 |  | Project Site Wide | PPE Inspection | CheckList | Project Site Wide - PPE Inspection - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | PPE Inspection | Checlist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0017 | A | 6105AK124-0100-HLST-0017 | Q24050972-09-0100-H-LST-0017 |  | Project Site Wide | Lifting Equipment and Accessories | Register | Project Site Wide - Lifting Equipment and Accessories - Register |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Lifting Equipment and Accessories | Register |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0018 | A | 6105AK124-0100-HLST-0018 | Q24050972-09-0100-H-LST-0018 |  | Project Site Wide | Register Hazardous Materials | Register | Project Site Wide - Register Hazardous Materials - Register |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Hazardous Materials | Register |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0019 | A | 6105AK124-0100-HLST-0019 | Q24050972-09-0100-H-LST-0019 |  | Project Site Wide | Register Plant and Equipment | Register | Project Site Wide - Register Plant and Equipment - Register |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Plant and Equipment | Register |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0020 | A | 6105AK124-0100-HLST-0020 | Q24050972-09-0100-H-LST-0020 |  | Project Site Wide | Register Training First Aider | Register | Project Site Wide - Register Training First Aider - Register |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Training First Aider | Register |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0021 | A | 6105AK124-0100-HLST-0021 | Q24050972-09-0100-H-LST-0021 |  | Project Site Wide | Reporting 24 hr. Initial Incident | CheckList | Project Site Wide - Reporting 24 hr. Initial Incident - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Reporting_24 hr. Initial Incident | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0022 | A | 6105AK124-0100-HLST-0022 | Q24050972-09-0100-H-LST-0022 |  | Project Site Wide | Investigation-Serious OSH Incident | CheckList | Project Site Wide - Investigation-Serious OSH Incident - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Investigation-Serious OSH Incident | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0023 | A | 6105AK124-0100-HLST-0023 | Q24050972-09-0100-H-LST-0023 |  | Project Site Wide | Investigation Serious OSH Incident | CheckList | Project Site Wide - Investigation Serious OSH Incident - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Investigation Serious OSH Incident | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0024 | A | 6105AK124-0100-HLST-0024 | Q24050972-09-0100-H-LST-0024 |  | Project Site Wide | Reporting First Aid Case | CheckList | Project Site Wide - Reporting First Aid Case - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Reporting_ First Aid Case | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0025 | A | 6105AK124-0100-HLST-0025 | Q24050972-07-0100-H-LST-0025 |  | Project Site Wide | Projects Risk | Register | Project Site Wide - Projects Risk - Register |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Projects-Risk | Register |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0026 | A | 6105AK124-0100-HLST-0026 | Q24050972-09-0100-H-LST-0026 |  | Project Site Wide | E&I Supervisor Daily Inspection | CheckList | Project Site Wide - E&I Supervisor Daily Inspection - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | E&I Supervisor Daily Inspection | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | LST | 0027 | A | 6105AK124-0100-HLST-0027 | Q24050972-09-0100-H-LST-0027 |  | Project Site Wide | Safe Behavioral Observation | CheckList | Project Site Wide - Safe Behavioral Observation - CheckList |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Safe Behavioral Observation | Checklist |  |  |  | Pending
6105A | K124 | 0100 | H | MAN | 0001 | A | 6105AK124-0100-HMAN-0001 | Q24050972-07-0100-H-MAN-0001 |  | Project Site Wide | PHASGS | Management Manual | Project Site Wide - PHASGS - Management Manual |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | PHASGS | Management Manual |  |  |  | Pending
6105A | K124 | 6200 | E | PHL | 0001 | A | 6105AK124-6200-EPHL-0001 | Q24050972-10-6200-E-PHL-0001 |  | On-Site Power Supply and Transmission | Energy Management System | Control Philosophy (EMS) | On-Site Power Supply and Transmission - Energy Management System - Control Philosophy (EMS) |  |  | RES - Reserved Placeholder | Pending | 0% | ET |  | 2026-12-05 | Energy Management System | Control Philosophy (EMS) |  |  |  | Pending
6105A | K124 | 0100 | H | PLN | 0001 | A | 6105AK124-0100-HPLN-0001 | Q24050972-09-0100-H-PLN-0001 |  | Project Site Wide | Lift Plan-Low Risk | Plan | Project Site Wide - Lift Plan-Low Risk - Plan |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Lift Plan-Low Risk | Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PLN | 0002 | A | 6105AK124-0100-HPLN-0002 | Q24050972-09-0100-H-PLN-0002 |  | Project Site Wide | Lifting Plan - Medium-Critical Risk | Plan | Project Site Wide - Lifting Plan - Medium-Critical Risk - Plan |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Lifting Plan-Medium-Critical Risk | Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PLN | 0003 | A | 6105AK124-0100-HPLN-0003 | Q24050972-09-0100-H-PLN-0003 |  | Project Site Wide | Critical Lift Plan | Plan | Project Site Wide - Critical Lift Plan - Plan |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Critical Lift Plan | Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PLN | 0004 | A | 6105AK124-0100-HPLN-0004 | Q24050972-09-0100-H-PLN-0004 |  | Project Site Wide | Lifting Operation | Plan | Project Site Wide - Lifting Operation - Plan |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Lifting Operation Plan | Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PLN | 0005 | A | 6105AK124-0100-HPLN-0005 | Q24050972-09-0100-H-PLN-0005 |  | Project Site Wide | Fall Protection | Plan | Project Site Wide - Fall Protection - Plan |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Fall Protection | Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PLN | 0006 | A | 6105AK124-0100-HPLN-0006 | Q24050972-09-0100-H-PLN-0006 |  | Project Site Wide | Personal Emergency Evacuation | Plan | Project Site Wide - Personal Emergency Evacuation - Plan |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Personal Emergency Evacuation | Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PLN | 0007 | A | 6105AK124-0100-HPLN-0007 | Q24050972-09-0100-H-PLN-0007 |  | Project Site Wide | Traffic Management Plan Goods Transportation | Plan | Project Site Wide - Traffic Management Plan Goods Transportation - Plan |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Traffic Management Plan Goods Transportation | Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PLN | 0008 | A | 6105AK124-0100-HPLN-0008 | Q24050972-09-0100-H-PLN-0008 |  | Project Site Wide | Evacuation | Plan | Project Site Wide - Evacuation - Plan |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Evacuation | Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PLN | 0009 | A | 6105AK124-0100-HPLN-0009 | Q24050972-09-0100-H-PLN-0009 |  | Project Site Wide | Security | Plan | Project Site Wide - Security - Plan |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Security | Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PLN | 0010 | A | 6105AK124-0100-HPLN-0010 | Q24050972-09-0100-H-PLN-0010 |  | Project Site Wide | Country Security Briefing | Plan | Project Site Wide - Country Security Briefing - Plan |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Country Security | Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PLN | 0011 | A | 6105AK124-0100-HPLN-0011 | Q24050972-09-0100-H-PLN-0011 |  | Project Site Wide | Heat Stress | Plan | Project Site Wide - Heat Stress - Plan |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Heat_Stress | Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PLN | 0012 | A | 6105AK124-0100-HPLN-0012 | Q24050972-09-0100-H-PLN-0012 |  | Project Site Wide | Fatigue Management | Plan | Project Site Wide - Fatigue Management - Plan |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Fatigue Management | Plan |  |  |  | Pending
6105A | K124 | 0100 | B | PLN | 0001 | A | 6105AK124-0100-BPLN-0001 | Q24050972-01-0100-B-PLN-0001 |  | Project Site Wide | Project Cost Management | Plan | Project Site Wide - Project Cost Management - Plan | 2026-02-27 |  | IFR - Issued for Review | Pending | 33.33% | MC |  |  | Project Cost Management | Plan |  |  |  | Pending
6105A | K124 | 0100 | B | PLN | 0002 | A | 6105AK124-0100-BPLN-0002 | Q24050972-01-0100-B-PLN-0002 |  | Project Site Wide | Material and Logistics Management | Plan | Project Site Wide - Material and Logistics Management - Plan | 2026-02-27 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | MC |  |  | Material and Logistics Management | Plan |  |  |  | Pending
6105A | K124 | 0100 | B | PLN | 0003 | A | 6105AK124-0100-BPLN-0003 | Q24050972-01-0100-B-PLN-0003 |  | Project Site Wide | Project Document Management and Control | Plan | Project Site Wide - Project Document Management and Control - Plan | 2026-02-27 |  | IFR - Issued for Review | Pending | 33.33% | MC |  |  | Project Document Management and Control Plan | Plan |  |  |  | Pending
6105A | K124 | 0100 | G | PLN | 0001 | A | 6105AK124-0100-GPLN-0001 | Q24050972-01-0100-G-PLN-0001 |  | Project Site Wide | Procurement and Contracting Management | Plan | Project Site Wide - Procurement and Contracting Management - Plan | 2026-02-03 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | JM |  |  | Procurement and Contracting Management | Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0001 | A | 6105AK124-0100-HPRC-0001 | Q24050972-09-0100-H-PRC-0001 |  | Project Site Wide | SOP 01.0 - Administration | Procedure | Project Site Wide - SOP 01.0 - Administration - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Administration |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0002 | A | 6105AK124-0100-HPRC-0002 | Q24050972-09-0100-H-PRC-0002 |  | Project Site Wide | SOP 02.0 - Incident Notification, Investigation and Reporting | Procedure | Project Site Wide - SOP 02.0 - Incident Notification, Investigation and Reporting - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Incident Notification, Investigation and Reporting |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0003 | A | 6105AK124-0100-HPRC-0003 | Q24050972-09-0100-H-PRC-0003 |  | Project Site Wide | SOP 03.0 - Occupational Noise | Procedure | Project Site Wide - SOP 03.0 - Occupational Noise - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Occupational Noise |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0004 | A | 6105AK124-0100-HPRC-0004 | Q24050972-09-0100-H-PRC-0004 |  | Project Site Wide | SOP 03.1 - Vibration | Procedure | Project Site Wide - SOP 03.1 - Vibration - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Vibration |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0005 | A | 6105AK124-0100-HPRC-0005 | Q24050972-09-0100-H-PRC-0005 |  | Project Site Wide | SOP 04.0 - First Aid and Medical Emergency Treatment | Procedure | Project Site Wide - SOP 04.0 - First Aid and Medical Emergency Treatment - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | First Aid and Medical Emergency Treatment |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0006 | A | 6105AK124-0100-HPRC-0006 | Q24050972-09-0100-H-PRC-0006 |  | Project Site Wide | SOP 05.0 - Occupational Health Screening and Medical Surveillance | Procedure | Project Site Wide - SOP 05.0 - Occupational Health Screening and Medical Surveillance - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Occupational Health Screening and Medical Surveillance |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0007 | A | 6105AK124-0100-HPRC-0007 | Q24050972-09-0100-H-PRC-0007 |  | Project Site Wide | SOP 06.0 - Performance Monitoring and Reporting | Procedure | Project Site Wide - SOP 06.0 - Performance Monitoring and Reporting - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Performance Monitoring and Reporting |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0008 | A | 6105AK124-0100-HPRC-0008 | Q24050972-09-0100-H-PRC-0008 |  | Project Site Wide | SOP 07.0 - Organization OSH Practitioner Registration and Appointment of Principal Contractor | Procedure | Project Site Wide - SOP 07.0 - Organization OSH Practitioner Registration and Appointment of Principal Contractor - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Organization OSH Practitioner Registration and Appointment of Principal Contractor |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0009 | A | 6105AK124-0100-HPRC-0009 | Q24050972-09-0100-H-PRC-0009 |  | Project Site Wide | SOP 08.0 - General Workplace Amenities | Procedure | Project Site Wide - SOP 08.0 - General Workplace Amenities - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | General Workplace Amenities |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0010 | A | 6105AK124-0100-HPRC-0010 | Q24050972-09-0100-H-PRC-0010 |  | Project Site Wide | SOP 09.0 - Workplace Wellness | Procedure | Project Site Wide - SOP 09.0 - Workplace Wellness - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Workplace Wellness |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0011 | A | 6105AK124-0100-HPRC-0011 | Q24050972-09-0100-H-PRC-0011 |  | Project Site Wide | SOP 09.1- New and Expectant Mothers | Procedure | Project Site Wide - SOP 09.1- New and Expectant Mothers - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | New and Expectant Mothers |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0012 | A | 6105AK124-0100-HPRC-0012 | Q24050972-09-0100-H-PRC-0012 |  | Project Site Wide | SOP 09.2 - Managing Work-Related Stress | Procedure | Project Site Wide - SOP 09.2 - Managing Work-Related Stress - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Managing Work-Related Stress |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0013 | A | 6105AK124-0100-HPRC-0013 | Q24050972-09-0100-H-PRC-0013 |  | Project Site Wide | SOP 09.3 - Drinking Water | Procedure | Project Site Wide - SOP 09.3 - Drinking Water - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Drinking Water |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0014 | A | 6105AK124-0100-HPRC-0014 | Q24050972-09-0100-H-PRC-0014 |  | Project Site Wide | SOP 09.4 - Silica | Procedure | Project Site Wide - SOP 09.4 - Silica - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Silica |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0015 | A | 6105AK124-0100-HPRC-0015 | Q24050972-09-0100-H-PRC-0015 |  | Project Site Wide | SOP 10.0 - Rehabilitation and Return to Work | Procedure | Project Site Wide - SOP 10.0 - Rehabilitation and Return to Work - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Rehabilitation and Return to Work |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0016 | A | 6105AK124-0100-HPRC-0016 | Q24050972-09-0100-H-PRC-0016 |  | Project Site Wide | SOP 11.0 - Safety in the Heat | Procedure | Project Site Wide - SOP 11.0 - Safety in the Heat - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Safety in the Heat |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0017 | A | 6105AK124-0100-HPRC-0017 | Q24050972-09-0100-H-PRC-0017 |  | Project Site Wide | SOP 12.0 - Personal Protective Equipment | Procedure | Project Site Wide - SOP 12.0 - Personal Protective Equipment - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Personal Protective Equipment |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0018 | A | 6105AK124-0100-HPRC-0018 | Q24050972-09-0100-H-PRC-0018 |  | Project Site Wide | SOP 13.0 - Violence in the Workplace | Procedure | Project Site Wide - SOP 13.0 - Violence in the Workplace - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Violence in the Workplace |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0019 | A | 6105AK124-0100-HPRC-0019 | Q24050972-09-0100-H-PRC-0019 |  | Project Site Wide | SOP 14.0 - Manual Handling and Ergonomics | Procedure | Project Site Wide - SOP 14.0 - Manual Handling and Ergonomics - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Manual Handling and Ergonomics |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0020 | A | 6105AK124-0100-HPRC-0020 | Q24050972-09-0100-H-PRC-0020 |  | Project Site Wide | SOP 15.0 - Electrical Safety | Procedure | Project Site Wide - SOP 15.0 - Electrical Safety - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Electrical Safety |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0021 | A | 6105AK124-0100-HPRC-0021 | Q24050972-09-0100-H-PRC-0021 |  | Project Site Wide | SOP 16.0 - OSH Requirements for People with Special Needs | Procedure | Project Site Wide - SOP 16.0 - OSH Requirements for People with Special Needs - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | OSH Requirements for People with Special Needs |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0022 | A | 6105AK124-0100-HPRC-0022 | Q24050972-09-0100-H-PRC-0022 |  | Project Site Wide | SOP 17.0 - Safety Signage and Signals | Procedure | Project Site Wide - SOP 17.0 - Safety Signage and Signals - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Safety Signage and Signals |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0023 | A | 6105AK124-0100-HPRC-0023 | Q24050972-09-0100-H-PRC-0023 |  | Project Site Wide | SOP 18.0 - Employer Supplied Accommodation | Procedure | Project Site Wide - SOP 18.0 - Employer Supplied Accommodation - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Employer Supplied Accommodation |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0024 | A | 6105AK124-0100-HPRC-0024 | Q24050972-09-0100-H-PRC-0024 |  | Project Site Wide | SOP 18.1 - Temporary Employer Supplied Accommodation | Procedure | Project Site Wide - SOP 18.1 - Temporary Employer Supplied Accommodation - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Temporary Employer Supplied Accommodation |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0025 | A | 6105AK124-0100-HPRC-0025 | Q24050972-09-0100-H-PRC-0025 |  | Project Site Wide | SOP 19.0 - Occupational Food Handling and Food Preparation Areas | Procedure | Project Site Wide - SOP 19.0 - Occupational Food Handling and Food Preparation Areas - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Occupational Food Handling and Food Preparation Areas |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0026 | A | 6105AK124-0100-HPRC-0026 | Q24050972-09-0100-H-PRC-0026 |  | Project Site Wide | SOP 20.0 - Safety in Design (Construction) | Procedure | Project Site Wide - SOP 20.0 - Safety in Design (Construction) - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Safety in Design (Construction) |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0027 | A | 6105AK124-0100-HPRC-0027 | Q24050972-09-0100-H-PRC-0027 |  | Project Site Wide | SOP 21.0 - Permit to Work Systems | Procedure | Project Site Wide - SOP 21.0 - Permit to Work Systems - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Permit to Work Systems |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0028 | A | 6105AK124-0100-HPRC-0028 | Q24050972-09-0100-H-PRC-0028 |  | Project Site Wide | SOP 22.0 - Barricading of Hazards | Procedure | Project Site Wide - SOP 22.0 - Barricading of Hazards - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Barricading of Hazards |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0029 | A | 6105AK124-0100-HPRC-0029 | Q24050972-09-0100-H-PRC-0029 |  | Project Site Wide | SOP 23.0 - Working at Heights | Procedure | Project Site Wide - SOP 23.0 - Working at Heights - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Working at Heights |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0030 | A | 6105AK124-0100-HPRC-0030 | Q24050972-09-0100-H-PRC-0030 |  | Project Site Wide | SOP 23.1 - Floor and Wall Openings | Procedure | Project Site Wide - SOP 23.1 - Floor and Wall Openings - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Floor and Wall Openings |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0031 | A | 6105AK124-0100-HPRC-0031 | Q24050972-09-0100-H-PRC-0031 |  | Project Site Wide | SOP 24.0 - Lock Out Tag Out | Procedure | Project Site Wide - SOP 24.0 - Lock Out Tag Out - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Lock Out Tag Out |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0032 | A | 6105AK124-0100-HPRC-0032 | Q24050972-09-0100-H-PRC-0032 |  | Project Site Wide | SOP 25.0 - Driver Fatigue | Procedure | Project Site Wide - SOP 25.0 - Driver Fatigue - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Driver Fatigue |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0033 | A | 6105AK124-0100-HPRC-0033 | Q24050972-09-0100-H-PRC-0033 |  | Project Site Wide | SOP 26.0 - Scaffolding | Procedure | Project Site Wide - SOP 26.0 - Scaffolding - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Scaffolding |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0034 | A | 6105AK124-0100-HPRC-0034 | Q24050972-09-0100-H-PRC-0034 |  | Project Site Wide | SOP 27.0 - Confined Space | Procedure | Project Site Wide - SOP 27.0 - Confined Space - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Confined Space |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0035 | A | 6105AK124-0100-HPRC-0035 | Q24050972-09-0100-H-PRC-0035 |  | Project Site Wide | SOP 28.0 - Hot Work Operations | Procedure | Project Site Wide - SOP 28.0 - Hot Work Operations - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Hot Work Operations |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0036 | A | 6105AK124-0100-HPRC-0036 | Q24050972-09-0100-H-PRC-0036 |  | Project Site Wide | SOP 28.1 - Construction Fire Safety | Procedure | Project Site Wide - SOP 28.1 - Construction Fire Safety - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Construction Fire Safety |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0037 | A | 6105AK124-0100-HPRC-0037 | Q24050972-09-0100-H-PRC-0037 |  | Project Site Wide | SOP 29.0 - Excavation Work | Procedure | Project Site Wide - SOP 29.0 - Excavation Work - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Excavation Work |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0038 | A | 6105AK124-0100-HPRC-0038 | Q24050972-09-0100-H-PRC-0038 |  | Project Site Wide | SOP 30.0 - Lone Working and or in Remote Locations | Procedure | Project Site Wide - SOP 30.0 - Lone Working and or in Remote Locations - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Lone Working and or in Remote Locations |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0039 | A | 6105AK124-0100-HPRC-0039 | Q24050972-09-0100-H-PRC-0039 |  | Project Site Wide | SOP 30.1 - Working in International Locations | Procedure | Project Site Wide - SOP 30.1 - Working in International Locations - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Working in International Locations |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0040 | A | 6105AK124-0100-HPRC-0040 | Q24050972-09-0100-H-PRC-0040 |  | Project Site Wide | SOP 31.0 - Working On-Over or Adjacent to Water | Procedure | Project Site Wide - SOP 31.0 - Working On-Over or Adjacent to Water - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Working On-Over or Adjacent to Water |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0041 | A | 6105AK124-0100-HPRC-0041 | Q24050972-09-0100-H-PRC-0041 |  | Project Site Wide | SOP 32.0 - Hazardous Materials | Procedure | Project Site Wide - SOP 32.0 - Hazardous Materials - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Hazardous Materials |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0042 | A | 6105AK124-0100-HPRC-0042 | Q24050972-09-0100-H-PRC-0042 |  | Project Site Wide | SOP 33.0 - Working On or Adjacent to a Road | Procedure | Project Site Wide - SOP 33.0 - Working On or Adjacent to a Road - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Working On or Adjacent to a Road |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0043 | A | 6105AK124-0100-HPRC-0043 | Q24050972-09-0100-H-PRC-0043 |  | Project Site Wide | SOP 34.0 - Safe Use of Lifting Equipment and Lifting Accessories | Procedure | Project Site Wide - SOP 34.0 - Safe Use of Lifting Equipment and Lifting Accessories - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Safe Use of Lifting Equipment and Lifting Accessories |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0044 | A | 6105AK124-0100-HPRC-0044 | Q24050972-09-0100-H-PRC-0044 |  | Project Site Wide | SOP 34.1 - Personnel Lift Plan | Procedure | Project Site Wide - SOP 34.1 - Personnel Lift Plan - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Personnel Lift Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0045 | A | 6105AK124-0100-HPRC-0045 | Q24050972-09-0100-H-PRC-0045 |  | Project Site Wide | SOP 35.0 - Portable Power Tools | Procedure | Project Site Wide - SOP 35.0 - Portable Power Tools - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Portable Power Tools |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0046 | A | 6105AK124-0100-HPRC-0046 | Q24050972-09-0100-H-PRC-0046 |  | Project Site Wide | SOP 36.0 - Plant and Equipment | Procedure | Project Site Wide - SOP 36.0 - Plant and Equipment - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Plant and Equipment |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0047 | A | 6105AK124-0100-HPRC-0047 | Q24050972-09-0100-H-PRC-0047 |  | Project Site Wide | SOP 37.0 - Ladders | Procedure | Project Site Wide - SOP 37.0 - Ladders - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Ladders |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0048 | A | 6105AK124-0100-HPRC-0048 | Q24050972-09-0100-H-PRC-0048 |  | Project Site Wide | SOP 38.0 - Concrete Placing Equipment | Procedure | Project Site Wide - SOP 38.0 - Concrete Placing Equipment - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Concrete Placing Equipment |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0049 | A | 6105AK124-0100-HPRC-0049 | Q24050972-09-0100-H-PRC-0049 |  | Project Site Wide | SOP 39.0 - Overhead and Underground Services | Procedure | Project Site Wide - SOP 39.0 - Overhead and Underground Services - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Overhead and Underground Services |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0050 | A | 6105AK124-0100-HPRC-0050 | Q24050972-09-0100-H-PRC-0050 |  | Project Site Wide | SOP 40.0 - Falsework | Procedure | Project Site Wide - SOP 40.0 - Falsework - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Falsework |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0051 | A | 6105AK124-0100-HPRC-0051 | Q24050972-09-0100-H-PRC-0051 |  | Project Site Wide | SOP 41.0 - Steel Erection | Procedure | Project Site Wide - SOP 41.0 - Steel Erection - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Steel Erection |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0052 | A | 6105AK124-0100-HPRC-0052 | Q24050972-09-0100-H-PRC-0052 |  | Project Site Wide | SOP 42.0 - Pre-Cast Construction | Procedure | Project Site Wide - SOP 42.0 - Pre-Cast Construction - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Pre-Cast Construction |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0053 | A | 6105AK124-0100-HPRC-0053 | Q24050972-09-0100-H-PRC-0053 |  | Project Site Wide | SOP 43.0 - Temporary Structures | Procedure | Project Site Wide - SOP 43.0 - Temporary Structures - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Temporary Structures |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0054 | A | 6105AK124-0100-HPRC-0054 | Q24050972-09-0100-H-PRC-0054 |  | Project Site Wide | SOP 44.0 - Traffic Management and Logistics | Procedure | Project Site Wide - SOP 44.0 - Traffic Management and Logistics - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Traffic Management and Logistics |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0055 | A | 6105AK124-0100-HPRC-0055 | Q24050972-09-0100-H-PRC-0055 |  | Project Site Wide | SOP 45.0 - Underwater Activities | Procedure | Project Site Wide - SOP 45.0 - Underwater Activities - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Underwater Activities |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0056 | A | 6105AK124-0100-HPRC-0056 | Q24050972-09-0100-H-PRC-0056 |  | Project Site Wide | SOP 46.0 - Underground Construction | Procedure | Project Site Wide - SOP 46.0 - Underground Construction - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Underground Construction |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0057 | A | 6105AK124-0100-HPRC-0057 | Q24050972-09-0100-H-PRC-0057 |  | Project Site Wide | SOP 47.0 - Machine Guarding | Procedure | Project Site Wide - SOP 47.0 - Machine Guarding - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Machine Guarding |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0058 | A | 6105AK124-0100-HPRC-0058 | Q24050972-09-0100-H-PRC-0058 |  | Project Site Wide | SOP 48.0 - Spray Finishing | Procedure | Project Site Wide - SOP 48.0 - Spray Finishing - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Spray Finishing |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0059 | A | 6105AK124-0100-HPRC-0059 | Q24050972-09-0100-H-PRC-0059 |  | Project Site Wide | SOP 49.0 - Compressed Gases and Air | Procedure | Project Site Wide - SOP 49.0 - Compressed Gases and Air - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Compressed Gases and Air |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0060 | A | 6105AK124-0100-HPRC-0060 | Q24050972-09-0100-H-PRC-0060 |  | Project Site Wide | SOP 50.0 - Abrasive Blasting and Associated Protective Coating Work | Procedure | Project Site Wide - SOP 50.0 - Abrasive Blasting and Associated Protective Coating Work - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Abrasive Blasting and Associated Protective Coating Work |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0061 | A | 6105AK124-0100-HPRC-0061 | Q24050972-09-0100-H-PRC-0061 |  | Project Site Wide | SOP 51.0 - Powered Lift Trucks | Procedure | Project Site Wide - SOP 51.0 - Powered Lift Trucks - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Powered Lift Trucks |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0062 | A | 6105AK124-0100-HPRC-0062 | Q24050972-09-0100-H-PRC-0062 |  | Project Site Wide | SOP 52.0 - Local Exhaust Ventilation | Procedure | Project Site Wide - SOP 52.0 - Local Exhaust Ventilation - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Local Exhaust Ventilation |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0063 | A | 6105AK124-0100-HPRC-0063 | Q24050972-09-0100-H-PRC-0063 |  | Project Site Wide | SOP 53.0 - OSH Management During Construction Work | Procedure | Project Site Wide - SOP 53.0 - OSH Management During Construction Work - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | OSH Management During Construction Work |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0064 | A | 6105AK124-0100-HPRC-0064 | Q24050972-09-0100-H-PRC-0064 |  | Project Site Wide | SOP 53.1 - OSH Construction Management Plan | Procedure | Project Site Wide - SOP 53.1 - OSH Construction Management Plan - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | OSH Construction Management Plan |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0065 | A | 6105AK124-0100-HPRC-0065 | Q24050972-09-0100-H-PRC-0065 |  | Project Site Wide | SOP 54.0 - Night Work | Procedure | Project Site Wide - SOP 54.0 - Night Work - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Night Work |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0066 | A | 6105AK124-0100-HPRC-0066 | Q24050972-09-0100-H-PRC-0066 |  | Project Site Wide | SOP 55.0 - Pandemic Preparedness | Procedure | Project Site Wide - SOP 55.0 - Pandemic Preparedness - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP | Pandemic Preparedness |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0067 | A | 6105AK124-0100-HPRC-0067 | Q24050972-09-0100-H-PRC-0067 |  | Project Site Wide | Confined Space Permit to Work | Procedure | Project Site Wide - Confined Space Permit to Work - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Confined Space Permit to Work | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0068 | A | 6105AK124-0100-HPRC-0068 | Q24050972-09-0100-H-PRC-0068 |  | Project Site Wide | Confined Space Permit to Enter | Procedure | Project Site Wide - Confined Space Permit to Enter - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Confined Space Permit to Enter | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0069 | A | 6105AK124-0100-HPRC-0069 | Q24050972-09-0100-H-PRC-0069 |  | Project Site Wide | Hot Work Permit | Procedure | Project Site Wide - Hot Work Permit - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Hot Work Permit | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0070 | A | 6105AK124-0100-HPRC-0070 | Q24050972-09-0100-H-PRC-0070 |  | Project Site Wide | Crane Permit | Procedure | Project Site Wide - Crane Permit - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Crane Permit | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0071 | A | 6105AK124-0100-HPRC-0071 | Q24050972-09-0100-H-PRC-0071 |  | Project Site Wide | Permit to Dig | Procedure | Project Site Wide - Permit to Dig - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Permit to Dig | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0072 | A | 6105AK124-0100-HPRC-0072 | Q24050972-09-0100-H-PRC-0072 |  | Project Site Wide | Dive Permit | Procedure | Project Site Wide - Dive Permit - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Dive Permit | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0073 | A | 6105AK124-0100-HPRC-0073 | Q24050972-09-0100-H-PRC-0073 |  | Project Site Wide | Working Near Overhead Powerlines | Procedure | Project Site Wide - Working Near Overhead Powerlines - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Working Near Overhead Powerlines | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0074 | A | 6105AK124-0100-HPRC-0074 | Q24050972-09-0100-H-PRC-0074 |  | Project Site Wide | Working at Height Permit | Procedure | Project Site Wide - Working at Height Permit - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Working at Height Permit | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0075 | A | 6105AK124-0100-HPRC-0075 | Q24050972-09-0100-H-PRC-0075 |  | Project Site Wide | Excavation Permit | Procedure | Project Site Wide - Excavation Permit - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Excavation Permit | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0076 | A | 6105AK124-0100-HPRC-0076 | Q24050972-09-0100-H-PRC-0076 |  | Project Site Wide | Traffic Management Work Permit | Procedure | Project Site Wide - Traffic Management Work Permit - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Traffic Management Work Permit | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0077 | A | 6105AK124-0100-HPRC-0077 | Q24050972-09-0100-H-PRC-0077 |  | Project Site Wide | SOP-PQQ1-HSE | Procedure | Project Site Wide - SOP-PQQ1-HSE - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | SOP-PQQ1-HSE | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0078 | A | 6105AK124-0100-HPRC-0078 | Q24050972-09-0100-H-PRC-0078 |  | Project Site Wide | PQQ2-Questionaire HSE | Procedure | Project Site Wide - PQQ2-Questionaire HSE - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | PQQ2-Questionaire HSE | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0079 | A | 6105AK124-0100-HPRC-0079 | Q24050972-09-0100-H-PRC-0079 |  | Project Site Wide | PQQ3-Contractor Guidance | Procedure | Project Site Wide - PQQ3-Contractor Guidance - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | PQQ3-Contractor Guidance | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0080 | A | 6105AK124-0100-HPRC-0080 | Q24050972-09-0100-H-PRC-0080 |  | Project Site Wide | HSE PQQ4-Scoring Sheet | Procedure | Project Site Wide - HSE PQQ4-Scoring Sheet - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | HSE PQQ4-Scoring Sheet | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0081 | A | 6105AK124-0100-HPRC-0081 | Q24050972-09-0100-H-PRC-0081 |  | Project Site Wide | PQQ5-Document Flowchart | Procedure | Project Site Wide - PQQ5-Document Flowchart - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | PQQ5-Document Flowchart | Procedure |  |  |  | Pending
6105A | K124 | 0100 | H | PRC | 0082 | A | 6105AK124-0100-HPRC-0082 | Q24050972-09-0100-H-PRC-0082 |  | Project Site Wide | Two Week Lookahead | Procedure | Project Site Wide - Two Week Lookahead - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Two Week Lookahead | Procedure |  |  |  | Pending
6105A | K124 | 6250 | E | REQ | 0001 | A | 6105AK124-6250-EREQ-0001 | Q24050972-07-6250-E-REQ-0001 |  | Power Conditioning Equipment | Synchronous Condenser | Request | Power Conditioning Equipment - Synchronous Condenser - Request |  |  | RES - Reserved Placeholder | Pending | 0% | ET |  | TENDER | Synchronous Condenser | Request |  |  |  | Pending
6105A | K124 | 0000 | G | RFA | 0001 | A | 6105AK124-0000-GRFA-0001 | Q24050972-09-0000-G-RFA-0001 |  | General | Commercial Agreement | Recommendation for Award | General - Commercial Agreement - Recommendation for Award |  |  | RES - Reserved Placeholder | Pending | 0% | JV |  | 2026-05-15 | Commercial Agreement | General |  |  |  | Pending
6105A | K124 | 6262 | E | RFA | 0001 | A | 6105AK124-6262-ERFA-0001 | Q24050972-09-6262-E-RFA-0001 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | High Speed Diesel Generators | Recommendation for Award | Emergency Power Substation 1 and Control Room 1 - High Speed Diesel Generators - Recommendation for Award - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | High-speed Diesel Generation | Recommendation for Award |  |  |  | Pending
6105A | K124 | 6251 | E | RFA | 0001 | A | 6105AK124-6251-ERFA-0001 | Q24050972-10-6251-E-RFA-0001 |  | Load Bank | 11kV load banks , RMU's & Switchrooms | Provision of engineering and Supply of EI Equipment - Recommendation for Award | Load Bank - 11kV load banks , RMU's & Switchrooms - Provision of engineering and Supply of EI Equipment - Recommendation for Award |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | Tender | 11kV load banks , RMU's & Switchrooms | Provision of engineering and Supply of EI Equipment - Recommendation for Award |  |  |  | Pending
6105A | K124 | 6264 | E | RFA | 0001 | A | 6105AK124-6264-ERFA-0001 | Q24050972-11-6264-E-RFA-0001 | Sht. 1 of 1 | Bulk Diesel Storage 1 | Bulk Fuel | Bulk Fuel Storage Facility | Bulk Diesel Storage 1 - Bulk Fuel - Bulk Fuel Storage Facility - Sht. 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Bulk Fuel | Storage Facility |  |  |  | Pending
6105A | K124 | 0100 | H | RPT | 0001 | A | 6105AK124-0100-HRPT-0001 | Q24050972-09-0100-H-RPT-0001 |  | Project Site Wide | Contractors’ Weekly Safety Statistics | Report | Project Site Wide - Contractors’ Weekly Safety Statistics - Report |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Contractors’ Weekly Safety Statistics | Report |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0001 | 0 | 6105AK124-0000-GRPT-0001 | Q24050972-09-0000-G-RPT-0001 |  | General | Monthly Report | Report | General - Monthly Report | 2026-01-28 | 2026-01-28 | IFI - Issued for Information | Pending | 66.67% | MC |  |  | Monthly Report | General |  |  |  | Pending
6105A | K124 | 6241 | E | RPT | 0001 | A | 6105AK124-6241-ERPT-0001 | Q24050972-09-6241-E-RPT-0001 |  | 33/220 kV Solar PV Substation | Solar and BESS Feasibility report Evaluation and comparison | Report | 33/220 kV Solar PV Substation - Solar and BESS Feasibility report Evaluation and comparison - Report |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Solar and BESS Feasibility | Report |  |  |  | Pending
6105A | K124 | 6286 | E | RPT | 0001 | A | 6105AK124-6286-ERPT-0001 | Q24050972-10-6286-E-RPT-0001 |  | Primary Crushing | Early Works Shovels - Load flow and Fault level study | Report | Primary Crushing - Early Works Shovels - Load flow and Fault level study - Report | 2026-05-20 |  | IFR - Issued for Review | Pending | 33.33% | RP |  |  | Load flow and Fault level study | Report |  |  |  | Pending
6105A | K124 | 6286 | E | RPT | 0002 | A | 6105AK124-6286-ERPT-0002 | Q24050972-10-6286-E-RPT-0002 |  | Primary Crushing | Trailing Cable Selection - Voltage drop calculation | Report | Primary Crushing - Trailing Cable Selection - Voltage drop calculation - Report | 2026-05-07 |  | IFR - Issued for Review | Pending | 33.33% | RP |  |  | Trailing Cable Selection | Report |  |  |  | Pending
6105A | K124 | 6243 | E | RPT | 0001 | A | 6105AK124-6243-ERPT-0001 | Q24050972-11-6243-E-RPT-0001 |  | 220/33 kV Plant Main Substation | Fault Level Calculations | Report | 220/33 kV Plant Main Substation - Fault Level Calculations - Report | 2026-05-12 |  | IFR - Issued for Review | Pending | 33.33% | RP |  |  | Fault Level | Calculations |  |  |  | Pending
6105A | K124 | 0100 | H | SCH | 0001 | A | 6105AK124-0100-HSCH-0001 | Q24050972-09-0100-H-SCH-0001 |  | Project Site Wide | Contractor Monthly Health and Safety Monitoring Schedule | Schedule | Project Site Wide - Contractor Monthly Health and Safety Monitoring Schedule - Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Contractor Monthly Health and Safety Monitoring | Schedule |  |  |  | Pending
6105A | K124 | 6260 | E | SEC | 0001 | A | 6105AK124-6260-ESEC-0001 | Q24050972-09-6260-E-SEC-0001 | Sht.3 of 4 | Emergency Power Generation (Main Plant) | Mv Cable Isolator Panel | Section | Emergency Power Generation (Main Plant) - Mv Cable Isolator Panel - Section - Sht.3 of 4 |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | TENDER | Mv Cable Isolator Panel | Section |  |  |  | Pending
6105A | K124 | 6243 | E | SLD | 0001 | A | 6105AK124-6243-ESLD-0001 | Q24050972-07-6243-E-SLD-0001 | Sht 1 of 1 | 220/33 kV Plant Main Substation | Primary Electrical Reticulation Network - Main Consumer Plant Reticulation | Single Line Diagram | 220/33 kV Plant Main Substation - Primary Electrical Reticulation Network - Main Consumer Plant Reticulation - Single Line Diagram - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | Main Consumer Plant Reticulation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6250 | E | SLD | 0001 | A | 6105AK124-6250-ESLD-0001 | Q24050972-07-6250-E-SLD-0001 | Sht 1 of 1 | Power Conditioning Equipment | Primary Electrical Reticulation Network - Synchronous Condensers Preliminary Design | Single Line Diagram | Power Conditioning Equipment - Primary Electrical Reticulation Network - Synchronous Condensers Preliminary Design - Single Line Diagram - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | ET |  | TENDER | Synchronous Condenser | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6260 | E | SLD | 0001 | A | 6105AK124-6260-ESLD-0001 | Q24050972-04-6260-E-SLD-0001 | Sht 1 of 1 | Emergency Power Generation (Main Plant) | 11kV Emergency Power Substation | Single Line Diagram | Emergency Power Generation (Main Plant) - 11kV Emergency Power Substation - Single Line Diagram - Sht 1 of 1 | 2025-10-27 | 2025-11-07 | IFD - Issued for Design | Pending | 66.67% | IS |  |  | 11kV Emergency Power Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6260 | E | SLD | 0002 | A | 6105AK124-6260-ESLD-0002 | Q24050972-06-6260-E-SLD-0002 | Sht 1 of 3 | Emergency Power Generation (Main Plant) | Auxiliary 400V AC Panel | Single Line Diagram | Emergency Power Generation (Main Plant) - Auxiliary 400V AC Panel - Single Line Diagram - Sht 1 of 3 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | TENDER | Auxiliary 400V AC Panel | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6260 | E | SLD | 0003 | A | 6105AK124-6260-ESLD-0003 | Q24050972-06-6260-E-SLD-0003 | Sht 2 of 3 | Emergency Power Generation (Main Plant) | Auxiliary 400V AC Panel | Single Line Diagram | Emergency Power Generation (Main Plant) - Auxiliary 400V AC Panel - Single Line Diagram - Sht 2 of 3 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | TENDER | Auxiliary 400V AC Panel | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6260 | E | SLD | 0004 | A | 6105AK124-6260-ESLD-0004 | Q24050972-06-6260-E-SLD-0004 | Sht 3 of 3 | Emergency Power Generation (Main Plant) | Auxiliary 400V AC Panel | Single Line Diagram | Emergency Power Generation (Main Plant) - Auxiliary 400V AC Panel - Single Line Diagram - Sht 3 of 3 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | TENDER | Auxiliary 400V AC Panel | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6280 | E | SLD | 0001 | A | 6105AK124-6280-ESLD-0001 | Q24050972-06-6280-E-SLD-0001 | Sht 1 of 1 | Medium Voltage (33 kV) Overhead Powerlines | Primary Electrical Reticulation Network - 33kV Open Pit Substation | Single Line Diagram | Medium Voltage (33 kV) Overhead Powerlines - Primary Electrical Reticulation Network - 33kV Open Pit Substation - Single Line Diagram - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | EB |  | TENDER | Primary Electrical Reticulation Network | 33kV Open Pit Substation |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0001 | A | 6105AK124-6286-ESLD-0001 | Q24050972-07-6286-E-SLD-0001 | Sht 1 of 1 | Primary Crushing | Auxiliary 400V AC Panel 2 | Single Line Diagram | Primary Crushing - Auxiliary 400V AC Panel 2 - Single Line Diagram - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Auxiliary 400V AC Panel 2 | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0011 | A | 6105AK124-6200-ESLD-0011 | Q24050972-10-6200-E-SLD-0011 | Sht.1 of 4 | On-Site Power Supply and Transmission | Single Line Diagram Index | Primary Electrical Reticulation Network | On-Site Power Supply and Transmission - Single Line Diagram Index - Primary Electrical Reticulation Network - Sht.1 of 4 |  |  | RES - Reserved Placeholder | Pending | 0% | ET |  | 2026-05-15 | Primary Electrical Reticulation Network | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0012 | A | 6105AK124-6200-ESLD-0012 | Q24050972-10-6200-E-SLD-0012 | Sht. 2 of 4 | On-Site Power Supply and Transmission | Single Line Diagram Legend | Primary Electrical Reticulation Network | On-Site Power Supply and Transmission - Single Line Diagram Legend - Primary Electrical Reticulation Network - Sht. 2 of 4 |  |  | RES - Reserved Placeholder | Pending | 0% | ET |  | 2026-05-15 | Primary Electrical Reticulation Network | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0013 | A | 6105AK124-6200-ESLD-0013 | Q24050972-10-6200-E-SLD-0013 | Sht. 3 of 4 | On-Site Power Supply and Transmission | Single Line Diagram of Primary Network Overall | Primary Electrical Reticulation Network | On-Site Power Supply and Transmission - Single Line Diagram of Primary Network Overall - Primary Electrical Reticulation Network - Sht. 3 of 4 |  |  | RES - Reserved Placeholder | Pending | 0% | ET |  | 2026-05-15 | Primary Electrical Reticulation Network | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0017 | A | 6105AK124-6200-ESLD-0017 | Q24050972-10-6200-E-SLD-0017 | Sht. 4 of 4 | On-Site Power Supply and Transmission | Single Line Diagram of Primary Network Overal | Primary Electrical Reticulation Network | On-Site Power Supply and Transmission - Single Line Diagram of Primary Network Overal - Primary Electrical Reticulation Network - Sht. 4 of 4 |  |  | RES - Reserved Placeholder | Pending | 0% | ET |  | 2026-05-15 | Primary Electrical Reticulation Network | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6262 | E | SLD | 0001 | A | 6105AK124-6262-ESLD-0001 | Q24050972-10-6262-E-SLD-0001 | Sht 1 of 1 | Emergency Power Substation 1 and Control Room 1 | Emergency Power Generation | Auxiliary Supply - Single Line Diagram | Emergency Power Substation 1 and Control Room 1 - Emergency Power Generation - Auxiliary Supply - Single Line Diagram - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Emergency Power Generation | Auxiliary Supply - Single Line Diagram |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0002 | 0 | 6105AK124-6286-ESLD-0002 | Q24050972-07-6286-E-SLD-0002 | Sht. 1 of 1 | Primary Crushing | 11kV Open Pit Mining Substation | Primary Electrical Reticulation Network - Single Line Diagram | Primary Crushing - 11kV Open Pit Mining Substation - Primary Electrical Reticulation Network - Single Line Diagram - Sht. 1 of 1 | 2025-10-27 | 2025-11-07 | IFD - Issued for Design | Pending | 66.67% | RS |  |  | 11kV Open Pit Mining Substation | Primary Electrical Reticulation Network |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0003 | 0 | 6105AK124-6286-ESLD-0003 | Q24050972-07-6286-E-SLD-0003 | Sht. 1 of 1 | Primary Crushing | 33kV Open Pit Mining Substation | Primary Electrical Reticulation Network - Single Line Diagram | Primary Crushing - 33kV Open Pit Mining Substation - Primary Electrical Reticulation Network - Single Line Diagram - Sht. 1 of 1 | 2025-10-27 | 2025-11-07 | IFD - Issued for Design | Pending | 66.67% | RS |  |  | 33kV Open Pit Mining Substation | Primary Electrical Reticulation Network |  |  |  | Pending
6105A | K124 | 6243 | E | SLD | 0002 | A | 6105AK124-6243-ESLD-0002 | Q24050972-07-6243-E-SLD-0002 | Sht 1 of 1 | 220/33 kV Plant Main Substation | Main Consumer Plant Substation | Primary Electrical Reticulation Network - Single Line Diagram | 220/33 kV Plant Main Substation - Main Consumer Plant Substation - Primary Electrical Reticulation Network - Single Line Diagram - Sht 1 of 1 | 2025-10-27 | 2025-11-07 | IFD - Issued for Design | Pending | 66.67% | RS |  |  | Main Consumer Plant Substation | Primary Electrical Reticulation Network |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0004 | A | 6105AK124-6286-ESLD-0004 | Q24050972-10-6286-E-SLD-0004 | Sht. 1 of 1 | Primary Crushing | Auxiliary Power Supply | Single Line Diagram | Primary Crushing - Auxiliary Power Supply - Single Line Diagram - Sht. 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Auxiliary Power Supply | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0001 | A | 6105AK124-6251-ESLD-0001 | Q24050972-10-6251-E-SLD-0001 | Sht.1 of 1 | Load Bank | 4125kVA, 11kV, 3-Phase Resistive and Inductive Loadbank | Primary Electrical Reticulation Network | Load Bank - 4125kVA, 11kV, 3-Phase Resistive and Inductive Loadbank - Primary Electrical Reticulation Network - Sht.1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | 2026-05-15 | Primary Electrical Reticulation Network | 4125kVA, 11kV, 3-Phase Resistive and Inductive Loadbank |  |  |  | Pending
6105A | K124 | 6292 | E | SLD | 0001 | A | 6105AK124-6292-ESLD-0001 | Q24050972-11-6292-E-SLD-0001 |  | 11/33 kV Solar PV Substation 1 and Control Room 1 | Primary Electrical Reticulation Network-Single Line Diagram | MV 33kV Solar PV | 11/33 kV Solar PV Substation 1 and Control Room 1 - Primary Electrical Reticulation Network-Single Line Diagram - MV 33kV Solar PV |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | 2026-05-15 | Primary Electrical Reticulation Network | MV 33kV Solar PV |  |  |  | Pending
6105A | K124 | 6200 | E | SOW | 0001 | A | 6105AK124-6200-ESOW-0001 | Q24050972-07-6200-E-SOW-0001 |  | On-Site Power Supply and Transmission | Power Transformers & NER | Scope of Work | On-Site Power Supply and Transmission - Power Transformers & NER - Scope of Work |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Power Transformers & NER | Scope of Work |  |  |  | Pending
6105A | K124 | 6243 | E | SOW | 0001 | A | 6105AK124-6243-ESOW-0001 | Q24050972-06-6243-E-SOW-0001 |  | 220/33 kV Plant Main Substation | MV 33KV GIS Switchgear and Switch Room | Scope of Work | 220/33 kV Plant Main Substation - MV 33KV GIS Switchgear and Switch Room - Scope of Work |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | Switch Room | Scope of Work |  |  |  | Pending
6105A | K124 | 6250 | E | SOW | 0001 | A | 6105AK124-6250-ESOW-0001 | Q24050972-07-6250-E-SOW-0001 |  | Power Conditioning Equipment | Synchronous Condenser | Scope of Work | Power Conditioning Equipment - Synchronous Condenser - Scope of Work |  |  | RES - Reserved Placeholder | Pending | 0% | ET |  | TENDER | Synchronous Condenser | Scope of Work |  |  |  | Pending
6105A | K124 | 6260 | E | SOW | 0003 | A | 6105AK124-6260-ESOW-0003 | Q24050972-06-6260-E-SOW-0003 |  | Emergency Power Generation (Main Plant) | Power Transformers | Scope of Work | Emergency Power Generation (Main Plant) - Power Transformers - Scope of Work |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Power Transformer | Scope of Work |  |  |  | Pending
6105A | K124 | 6262 | E | SOW | 0001 | A | 6105AK124-6262-ESOW-0001 | Q24050972-07-6262-E-SOW-0001 |  | Emergency Power Substation 1 and Control Room 1 | MV Switchroom & MV Switchgear | Scope of Work | Emergency Power Substation 1 and Control Room 1 - MV Switchroom & MV Switchgear - Scope of Work |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | MV Switchroom & MV Switchgear | Scope of Work |  |  |  | Pending
6105A | K124 | 6263 | E | SOW | 0001 | A | 6105AK124-6263-ESOW-0001 | Q24050972-07-6263-E-SOW-0001 |  | 36 MVA Power Station 1 | 20 MW 11kV Load banks | Scope of Work | 36 MVA Power Station 1 - 20 MW 11kV Load banks - Scope of Work |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 20 MW 11kV Load banks | Scope of Work |  |  |  | Pending
6105A | K124 | 6263 | E | SOW | 0002 | A | 6105AK124-6263-ESOW-0002 | Q24050972-07-6263-E-SOW-0002 |  | 36 MVA Power Station 1 | High Speed Diesel Generators | Scope of Work | 36 MVA Power Station 1 - High Speed Diesel Generators - Scope of Work |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | High Speed Diesel Generators | Scope of Work |  |  |  | Pending
6105A | K124 | 6264 | E | SOW | 0001 | A | 6105AK124-6264-ESOW-0001 | Q24050972-08-6264-E-SOW-0001 |  | Bulk Diesel Storage 1 | Bulk Fuel Tanks | Scope of Work | Bulk Diesel Storage 1 - Bulk Fuel Tanks - Scope of Work |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | TENDER | Bulk Fuel Tanks | Scope of Work |  |  |  | Pending
6105A | K124 | 6292 | E | SOW | 0001 | A | 6105AK124-6292-ESOW-0001 | Q24050972-07-6292-E-SOW-0001 |  | 11/33 kV Solar PV Substation 1 and Control Room 1 | 33kV GIS Switchgear & Switchrooms - Solar Plant | Scope of Work | 11/33 kV Solar PV Substation 1 and Control Room 1 - 33kV GIS Switchgear & Switchrooms - Solar Plant - Scope of Work |  |  | RES - Reserved Placeholder | Pending | 0% | JC |  | TENDER | 33kV GIS Switchgear & Switchrooms | Solar Plant |  |  |  | Pending
6105A | K124 | 0100 | H | STD | 0001 | A | 6105AK124-0100-HSTD-0001 | Q24050972-07-0100-H-STD-0001 |  | Project Site Wide | Project Health And Safety Governance | Standards | Project Site Wide - Project Health And Safety Governance - Standards | 2026-02-27 |  | IFR - Issued for Review | Pending | 33.33% | FV |  |  | Project Health And Safety | Governance Standards |  |  |  | Pending
6105A | K124 | 0100 | E | STD | 0001 | A | 6105AK124-0100-ESTD-0001 | Q24050972-12-0100-E-STD-0001 | Sht 1 of 1 | Project Site Wide | NER | 11kV - ONAN NER Schematic | Project Site Wide - NER - 11kV - ONAN NER Schematic - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | NER | 11kV - ONAN NER Schematic |  |  |  | Pending
6105A | K124 | 0100 | E | STD | 0002 | A | 6105AK124-0100-ESTD-0002 | Q24050972-12-0100-E-STD-0002 | Sht 1 of 1 | Project Site Wide | NER | 690V - ONAN NER Schematic | Project Site Wide - NER - 690V - ONAN NER Schematic - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | NER | 690V - ONAN NER Schematic |  |  |  | Pending
6105A | K124 | 0100 | H | SUM | 0001 | A | 6105AK124-0100-HSUM-0001 | Q24050972-09-0100-H-SUM-0001 |  | Project Site Wide | Abbreviations and Terminology Manual | Summary | Project Site Wide - Abbreviations and Terminology Manual - Summary |  |  | RES - Reserved Placeholder | Pending | 0% | FV |  | 2026-06-15 | Abbreviations and Terminology | Summary |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0002 | A | 6105AK124-0000-ITMP-0002 | Q24050972-10-0000-I-TMP-0002 |  | General | Hook-Up Drawing - Audible Alarm with Lens | Template | General - Hook-Up Drawing - Audible Alarm with Lens - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Audible Alarm with Lens | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0003 | A | 6105AK124-0000-ITMP-0003 | Q24050972-10-0000-I-TMP-0003 |  | General | Hook-Up Drawing - Audible Alarm Typical | Template | General - Hook-Up Drawing - Audible Alarm Typical - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Audible Alarm Typical | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0004 | A | 6105AK124-0000-ITMP-0004 | Q24050972-10-0000-I-TMP-0004 |  | General | Hook-Up Drawing - Drip Cover dor Audible Alarm | Template | General - Hook-Up Drawing - Drip Cover dor Audible Alarm - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Drip Cover dor Audible Alarm | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0005 | A | 6105AK124-0000-ITMP-0005 | Q24050972-10-0000-I-TMP-0005 |  | General | Hook-Up Drawing - Typ On-off Actuated Valve | Template | General - Hook-Up Drawing - Typ On-off Actuated Valve - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Typ On-off Actuated Valve | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0006 | A | 6105AK124-0000-ITMP-0006 | Q24050972-10-0000-I-TMP-0006 |  | General | Hook-Up Drawing -Typ Filter-Regulator Install | Template | General - Hook-Up Drawing -Typ Filter-Regulator Install - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Typ Filter-Regulator Install | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0007 | A | 6105AK124-0000-ITMP-0007 | Q24050972-10-0000-I-TMP-0007 |  | General | Hook-Up Drawing - Solenoid Valve on Pinch Valve | Template | General - Hook-Up Drawing - Solenoid Valve on Pinch Valve - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Solenoid Valve on Pinch Valve | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0008 | A | 6105AK124-0000-ITMP-0008 | Q24050972-10-0000-I-TMP-0008 |  | General | Hook-Up Drawing - Typ Dwg for Drip Covers. | Template | General - Hook-Up Drawing - Typ Dwg for Drip Covers. - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Typ Dwg for Drip Covers. | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0009 | A | 6105AK124-0000-ITMP-0009 | Q24050972-10-0000-I-TMP-0009 |  | General | Hook-Up Drawing - Clam Shell & Radial Gate Prox sw | Template | General - Hook-Up Drawing - Clam Shell & Radial Gate Prox sw - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Clam Shell & Radial Gate Prox sw | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0010 | A | 6105AK124-0000-ITMP-0010 | Q24050972-10-0000-I-TMP-0010 |  | General | Hook-Up Drawing - Cable & Tubing Support Metho | Template | General - Hook-Up Drawing - Cable & Tubing Support Metho - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable & Tubing Support Metho | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0011 | A | 6105AK124-0000-ITMP-0011 | Q24050972-10-0000-I-TMP-0011 |  | General | Hook-Up Drawing - Vibrating Level Switch for Underpan | Template | General - Hook-Up Drawing - Vibrating Level Switch for Underpan - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Vibrating Level Switch for Underpan | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0012 | A | 6105AK124-0000-ITMP-0012 | Q24050972-10-0000-I-TMP-0012 |  | General | Hook-Up Drawing - Modulating Control Valve | Template | General - Hook-Up Drawing - Modulating Control Valve - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Modulating Control Valve | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0013 | A | 6105AK124-0000-ITMP-0013 | Q24050972-10-0000-I-TMP-0013 |  | General | Hook-Up Drawing - Capacitance level switch | Template | General - Hook-Up Drawing - Capacitance level switch - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Capacitance level switch | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0014 | A | 6105AK124-0000-ITMP-0014 | Q24050972-10-0000-I-TMP-0014 |  | General | Hook-Up Drawing - Belt alignment switch | Template | General - Hook-Up Drawing - Belt alignment switch - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Belt alignment switch | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0015 | A | 6105AK124-0000-ITMP-0015 | Q24050972-10-0000-I-TMP-0015 |  | General | Hook-Up Drawing - Belt slip monitor | Template | General - Hook-Up Drawing - Belt slip monitor - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Belt slip monitor | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0016 | A | 6105AK124-0000-ITMP-0016 | Q24050972-10-0000-I-TMP-0016 |  | General | Hook-Up Drawing - Mounting bracket for belt alignment | Template | General - Hook-Up Drawing - Mounting bracket for belt alignment - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Mounting bracket for belt alignment | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0017 | A | 6105AK124-0000-ITMP-0017 | Q24050972-10-0000-I-TMP-0017 |  | General | Hook-Up Drawing - Proximity position switch | Template | General - Hook-Up Drawing - Proximity position switch - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Proximity position switch | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0018 | A | 6105AK124-0000-ITMP-0018 | Q24050972-10-0000-I-TMP-0018 |  | General | Hook-Up Drawing - Flow switch in-line target type | Template | General - Hook-Up Drawing - Flow switch in-line target type - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Flow switch in-line target type | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0019 | A | 6105AK124-0000-ITMP-0019 | Q24050972-10-0000-I-TMP-0019 |  | General | Hook-Up Drawing - Float switch for flood alarms | Template | General - Hook-Up Drawing - Float switch for flood alarms - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Float switch for flood alarms | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0020 | A | 6105AK124-0000-ITMP-0020 | Q24050972-10-0000-I-TMP-0020 |  | General | Hook-Up Drawing - Tilt switches (typ) for vertical mounting | Template | General - Hook-Up Drawing - Tilt switches (typ) for vertical mounting - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Tilt switches (typ) for vertical mounting | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0021 | A | 6105AK124-0000-ITMP-0021 | Q24050972-10-0000-I-TMP-0021 |  | General | Hook-Up Drawing - Float switch for sump control | Template | General - Hook-Up Drawing - Float switch for sump control - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Float switch for sump control | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0022 | A | 6105AK124-0000-ITMP-0022 | Q24050972-10-0000-I-TMP-0022 |  | General | Hook-Up Drawing - Ultrasonic level switchl | Template | General - Hook-Up Drawing - Ultrasonic level switchl - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Ultrasonic level switchl | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0023 | A | 6105AK124-0000-ITMP-0023 | Q24050972-10-0000-I-TMP-0023 |  | General | Hook-Up Drawing - Temperature switch | Template | General - Hook-Up Drawing - Temperature switch - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Temperature switch | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0024 | A | 6105AK124-0000-ITMP-0024 | Q24050972-10-0000-I-TMP-0024 |  | General | Hook-Up Drawing - Vibrating fork level switch | Template | General - Hook-Up Drawing - Vibrating fork level switch - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Vibrating fork level switch | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0025 | A | 6105AK124-0000-ITMP-0025 | Q24050972-10-0000-I-TMP-0025 |  | General | Hook-Up Drawing - Pressure gauge direct mounted | Template | General - Hook-Up Drawing - Pressure gauge direct mounted - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pressure gauge direct mounted | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0026 | A | 6105AK124-0000-ITMP-0026 | Q24050972-10-0000-I-TMP-0026 |  | General | Hook-Up Drawing - Pressure gauge for liquid service | Template | General - Hook-Up Drawing - Pressure gauge for liquid service - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pressure gauge for liquid service | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0027 | A | 6105AK124-0000-ITMP-0027 | Q24050972-10-0000-I-TMP-0027 |  | General | Hook-Up Drawing - Hand Switches _Contact Points | Template | General - Hook-Up Drawing - Hand Switches _Contact Points - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Hand Switches _Contact Points | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0028 | A | 6105AK124-0000-ITMP-0028 | Q24050972-10-0000-I-TMP-0028 |  | General | Hook-Up Drawing - Ultrasonic transducer closed tank | Template | General - Hook-Up Drawing - Ultrasonic transducer closed tank - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Ultrasonic transducer closed tank | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0029 | A | 6105AK124-0000-ITMP-0029 | Q24050972-10-0000-I-TMP-0029 |  | General | Hook-Up Drawing - Pressure switch on pinch valve | Template | General - Hook-Up Drawing - Pressure switch on pinch valve - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pressure switch on pinch valve | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0030 | A | 6105AK124-0000-ITMP-0030 | Q24050972-10-0000-I-TMP-0030 |  | General | Hook-Up Drawing - Ultrasonic transducer open tank | Template | General - Hook-Up Drawing - Ultrasonic transducer open tank - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Ultrasonic transducer open tank | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0031 | A | 6105AK124-0000-ITMP-0031 | Q24050972-10-0000-I-TMP-0031 |  | General | Hook-Up Drawing - Microwave blocked chute detector (typical) | Template | General - Hook-Up Drawing - Microwave blocked chute detector (typical) - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Microwave blocked chute detector (typical) | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0032 | A | 6105AK124-0000-ITMP-0032 | Q24050972-10-0000-I-TMP-0032 |  | General | Hook-Up Drawing - Density sensor. | Template | General - Hook-Up Drawing - Density sensor. - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Density sensor. | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0033 | A | 6105AK124-0000-ITMP-0033 | Q24050972-10-0000-I-TMP-0033 |  | General | Hook-Up Drawing - Electromagnetic flow meter | Template | General - Hook-Up Drawing - Electromagnetic flow meter - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Electromagnetic flow meter | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0034 | A | 6105AK124-0000-ITMP-0034 | Q24050972-10-0000-I-TMP-0034 |  | General | Hook-Up Drawing - Metal detector | Template | General - Hook-Up Drawing - Metal detector - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Metal detector | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0035 | A | 6105AK124-0000-ITMP-0035 | Q24050972-10-0000-I-TMP-0035 |  | General | Hook-Up Drawing - Humidity transmitter | Template | General - Hook-Up Drawing - Humidity transmitter - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Humidity transmitter | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0037 | A | 6105AK124-0000-ITMP-0037 | Q24050972-10-0000-I-TMP-0037 |  | General | Hook-Up Drawing - Capacitance level probe | Template | General - Hook-Up Drawing - Capacitance level probe - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Capacitance level probe | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0038 | A | 6105AK124-0000-ITMP-0038 | Q24050972-10-0000-I-TMP-0038 |  | General | Hook-Up Drawing - Mass meter load cell for bins | Template | General - Hook-Up Drawing - Mass meter load cell for bins - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Mass meter load cell for bins | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0039 | A | 6105AK124-0000-ITMP-0039 | Q24050972-10-0000-I-TMP-0039 |  | General | Hook-Up Drawing - Orifice plate | Template | General - Hook-Up Drawing - Orifice plate - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Orifice plate | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0040 | A | 6105AK124-0000-ITMP-0040 | Q24050972-10-0000-I-TMP-0040 |  | General | Hook-Up Drawing - Single instrument stand. | Template | General - Hook-Up Drawing - Single instrument stand. - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Single instrument stand. | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0041 | A | 6105AK124-0000-ITMP-0041 | Q24050972-10-0000-I-TMP-0041 |  | General | Hook-Up Drawing - Double instrument stand | Template | General - Hook-Up Drawing - Double instrument stand - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Double instrument stand | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0042 | A | 6105AK124-0000-ITMP-0042 | Q24050972-10-0000-I-TMP-0042 |  | General | Hook-Up Drawing - Laser transmitter mounted vertically | Template | General - Hook-Up Drawing - Laser transmitter mounted vertically - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Laser transmitter mounted vertically | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0043 | A | 6105AK124-0000-ITMP-0043 | Q24050972-10-0000-I-TMP-0043 |  | General | Hook-Up Drawing - Thermocouple-RTD with integral transmitter | Template | General - Hook-Up Drawing - Thermocouple-RTD with integral transmitter - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Thermocouple-RTD with integral transmitter | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0044 | A | 6105AK124-0000-ITMP-0044 | Q24050972-10-0000-I-TMP-0044 |  | General | Hook-Up Drawing - Whisker type limit switch | Template | General - Hook-Up Drawing - Whisker type limit switch - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Whisker type limit switch | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0045 | A | 6105AK124-0000-ITMP-0045 | Q24050972-10-0000-I-TMP-0045 |  | General | Hook-Up Drawing - Pressure switch | Template | General - Hook-Up Drawing - Pressure switch - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pressure switch | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0046 | A | 6105AK124-0000-ITMP-0046 | Q24050972-10-0000-I-TMP-0046 |  | General | Hook-Up Drawing - Single solenoid with term box | Template | General - Hook-Up Drawing - Single solenoid with term box - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Single solenoid with term box | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0047 | A | 6105AK124-0000-ITMP-0047 | Q24050972-10-0000-I-TMP-0047 |  | General | Hook-Up Drawing - Nuclear level switch | Template | General - Hook-Up Drawing - Nuclear level switch - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Nuclear level switch | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0048 | A | 6105AK124-0000-ITMP-0048 | Q24050972-10-0000-I-TMP-0048 |  | General | Hook-Up Drawing - Double acting solenoid with term box | Template | General - Hook-Up Drawing - Double acting solenoid with term box - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Double acting solenoid with term box | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0049 | A | 6105AK124-0000-ITMP-0049 | Q24050972-10-0000-I-TMP-0049 |  | General | Hook-Up Drawing - Weightometer | Template | General - Hook-Up Drawing - Weightometer - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Weightometer | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0050 | A | 6105AK124-0000-ITMP-0050 | Q24050972-10-0000-I-TMP-0050 |  | General | Hook-Up Drawing - Typical pratley box installation | Template | General - Hook-Up Drawing - Typical pratley box installation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Typical pratley box installation | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0051 | A | 6105AK124-0000-ITMP-0051 | Q24050972-10-0000-I-TMP-0051 |  | General | Hook-Up Drawing - JB and Instrument labels | Template | General - Hook-Up Drawing - JB and Instrument labels - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | JB and Instrument labels | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0052 | A | 6105AK124-0000-ITMP-0052 | Q24050972-10-0000-I-TMP-0052 |  | General | Hook-Up Drawing - Capacitance level switch for underpan | Template | General - Hook-Up Drawing - Capacitance level switch for underpan - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Capacitance level switch for underpan | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0053 | A | 6105AK124-0000-ITMP-0053 | Q24050972-10-0000-I-TMP-0053 |  | General | Hook-Up Drawing - Pressure transmitter | Template | General - Hook-Up Drawing - Pressure transmitter - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pressure transmitter | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0054 | A | 6105AK124-0000-ITMP-0054 | Q24050972-10-0000-I-TMP-0054 |  | General | Hook-Up Drawing - Thermocouple-RTD with remote transmitter | Template | General - Hook-Up Drawing - Thermocouple-RTD with remote transmitter - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Thermocouple-RTD with remote transmitter | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0055 | A | 6105AK124-0000-ITMP-0055 | Q24050972-10-0000-I-TMP-0055 |  | General | Hook-Up Drawing - Laser transmitter mounted horizontally | Template | General - Hook-Up Drawing - Laser transmitter mounted horizontally - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Laser transmitter mounted horizontally | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0056 | A | 6105AK124-0000-ITMP-0056 | Q24050972-10-0000-I-TMP-0056 |  | General | Hook-Up Drawing - Photo electric switch | Template | General - Hook-Up Drawing - Photo electric switch - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Photo electric switch | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0057 | A | 6105AK124-0000-ITMP-0057 | Q24050972-10-0000-I-TMP-0057 |  | General | Hook-Up Drawing - Hydraulic ram position transmitter | Template | General - Hook-Up Drawing - Hydraulic ram position transmitter - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Hydraulic ram position transmitter | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0058 | A | 6105AK124-0000-ITMP-0058 | Q24050972-10-0000-I-TMP-0058 |  | General | Hook-Up Drawing - Ultrasonic transducer for grizzly dump feed bin | Template | General - Hook-Up Drawing - Ultrasonic transducer for grizzly dump feed bin - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Ultrasonic transducer for grizzly dump feed bin | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0001 | A | 6105AK124-0000-ETMP-0001 | Q24050972-09-0000-E-TMP-0001 |  | General | Hook-Up Drawing - 16A Socket Outlet | Template | General - Hook-Up Drawing - 16A Socket Outlet - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | 16A Socket Outlet | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0002 | A | 6105AK124-0000-ETMP-0002 | Q24050972-09-0000-E-TMP-0002 |  | General | Hook-Up Drawing - 16A Socket Outlet 2 | Template | General - Hook-Up Drawing - 16A Socket Outlet 2 - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | 16A Socket Outlet 2 | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0003 | A | 6105AK124-0000-ETMP-0003 | Q24050972-09-0000-E-TMP-0003 |  | General | Hook-Up Drawing - 63A Welding Socket 1. | Template | General - Hook-Up Drawing - 63A Welding Socket 1. - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | 63A Welding Socket 1. | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0004 | A | 6105AK124-0000-ETMP-0004 | Q24050972-09-0000-E-TMP-0004 |  | General | Hook-Up Drawing - 63A Welding Socket 2 | Template | General - Hook-Up Drawing - 63A Welding Socket 2 - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | 63A Welding Socket 2 | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0005 | A | 6105AK124-0000-ETMP-0005 | Q24050972-09-0000-E-TMP-0005 |  | General | Hook-Up Drawing - Building mounted Floodlight | Template | General - Hook-Up Drawing - Building mounted Floodlight - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Building mounted Floodlight | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0006 | A | 6105AK124-0000-ETMP-0006 | Q24050972-09-0000-E-TMP-0006 |  | General | Hook-Up Drawing - Buried Cable typical Installation | Template | General - Hook-Up Drawing - Buried Cable typical Installation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Buried Cable typical Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0007 | A | 6105AK124-0000-ETMP-0007 | Q24050972-09-0000-E-TMP-0007 |  | General | Hook-Up Drawing - Cable Ladder and Unistrut Installation | Template | General - Hook-Up Drawing - Cable Ladder and Unistrut Installation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable Ladder and Unistrut Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0008 | A | 6105AK124-0000-ETMP-0008 | Q24050972-09-0000-E-TMP-0008 |  | General | Hook-Up Drawing - Cable Rack Bending Detail | Template | General - Hook-Up Drawing - Cable Rack Bending Detail - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable Rack Bending Detail | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0009 | A | 6105AK124-0000-ETMP-0009 | Q24050972-09-0000-E-TMP-0009 |  | General | Hook-Up Drawing - Cable Rack channel iron supports | Template | General - Hook-Up Drawing - Cable Rack channel iron supports - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable Rack channel iron supports | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0010 | A | 6105AK124-0000-ETMP-0010 | Q24050972-09-0000-E-TMP-0010 |  | General | Hook-Up Drawing - Cable Rack Earthing Installation | Template | General - Hook-Up Drawing - Cable Rack Earthing Installation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable Rack Earthing Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0011 | A | 6105AK124-0000-ETMP-0011 | Q24050972-09-0000-E-TMP-0011 |  | General | Hook-Up Drawing - Cable Rack Installation on I Beam 1 | Template | General - Hook-Up Drawing - Cable Rack Installation on I Beam 1 - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable Rack Installation on I Beam 1 | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0012 | A | 6105AK124-0000-ETMP-0012 | Q24050972-09-0000-E-TMP-0012 |  | General | Hook-Up Drawing - Cable Rack Installation on I Beam 2 | Template | General - Hook-Up Drawing - Cable Rack Installation on I Beam 2 - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable Rack Installation on I Beam 2 | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0013 | A | 6105AK124-0000-ETMP-0013 | Q24050972-09-0000-E-TMP-0013 |  | General | Hook-Up Drawing - Cable Rack on cast in Typical | Template | General - Hook-Up Drawing - Cable Rack on cast in Typical - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable Rack on cast in Typical | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0014 | A | 6105AK124-0000-ETMP-0014 | Q24050972-09-0000-E-TMP-0014 |  | General | Hook-Up Drawing - Cable Rack Plinth Supports | Template | General - Hook-Up Drawing - Cable Rack Plinth Supports - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable Rack Plinth Supports | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0015 | A | 6105AK124-0000-ETMP-0015 | Q24050972-09-0000-E-TMP-0015 |  | General | Hook-Up Drawing - Cable Rack Support in ground | Template | General - Hook-Up Drawing - Cable Rack Support in ground - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable Rack Support in ground | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0016 | A | 6105AK124-0000-ETMP-0016 | Q24050972-09-0000-E-TMP-0016 |  | General | Hook-Up Drawing - Cable run on Angle Iron Runner | Template | General - Hook-Up Drawing - Cable run on Angle Iron Runner - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable run on Angle Iron Runner | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0017 | A | 6105AK124-0000-ETMP-0017 | Q24050972-09-0000-E-TMP-0017 |  | General | Hook-Up Drawing - Cable Tagging detail | Template | General - Hook-Up Drawing - Cable Tagging detail - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable Tagging detail | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0018 | A | 6105AK124-0000-ETMP-0018 | Q24050972-09-0000-E-TMP-0018 |  | General | Hook-Up Drawing - Cable typical arrangement on ladder | Template | General - Hook-Up Drawing - Cable typical arrangement on ladder - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable typical arrangement on ladder | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0019 | A | 6105AK124-0000-ETMP-0019 | Q24050972-09-0000-E-TMP-0019 |  | General | Hook-Up Drawing - Conveyor Gantry Light Pole | Template | General - Hook-Up Drawing - Conveyor Gantry Light Pole - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Conveyor Gantry Light Pole | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0020 | A | 6105AK124-0000-ETMP-0020 | Q24050972-09-0000-E-TMP-0020 |  | General | Hook-Up Drawing - Earthing for conveyor foundation | Template | General - Hook-Up Drawing - Earthing for conveyor foundation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Earthing for conveyor foundation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0021 | A | 6105AK124-0000-ETMP-0021 | Q24050972-09-0000-E-TMP-0021 |  | General | Hook-Up Drawing - Earthing for Conveyors | Template | General - Hook-Up Drawing - Earthing for Conveyors - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Earthing for Conveyors | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0022 | A | 6105AK124-0000-ETMP-0022 | Q24050972-09-0000-E-TMP-0022 |  | General | Hook-Up Drawing - Earthing Pipe Rack | Template | General - Hook-Up Drawing - Earthing Pipe Rack - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Earthing Pipe Rack | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0023 | A | 6105AK124-0000-ETMP-0023 | Q24050972-09-0000-E-TMP-0023 |  | General | Hook-Up Drawing - Earthing Terminal from rebar | Template | General - Hook-Up Drawing - Earthing Terminal from rebar - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Earthing Terminal from rebar | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0024 | A | 6105AK124-0000-ETMP-0024 | Q24050972-09-0000-E-TMP-0024 |  | General | Hook-Up Drawing - Electric Motor Cable Hook up | Template | General - Hook-Up Drawing - Electric Motor Cable Hook up - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Electric Motor Cable Hook up | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0025 | A | 6105AK124-0000-ETMP-0025 | Q24050972-09-0000-E-TMP-0025 |  | General | Hook-Up drawing – Emergency Stop Push Button | Template | General - Hook-Up drawing – Emergency Stop Push Button - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Emergency Stop Push Button | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0026 | A | 6105AK124-0000-ETMP-0026 | Q24050972-09-0000-E-TMP-0026 |  | General | Hook-Up Drawing - Emergency Stop Mounted on wall | Template | General - Hook-Up Drawing - Emergency Stop Mounted on wall - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Emergency Stop Mounted on wall | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0027 | A | 6105AK124-0000-ETMP-0027 | Q24050972-09-0000-E-TMP-0027 |  | General | Hook-Up Drawing - Emergency Stop Mounting | Template | General - Hook-Up Drawing - Emergency Stop Mounting - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Emergency Stop Mounting | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0028 | A | 6105AK124-0000-ETMP-0028 | Q24050972-09-0000-E-TMP-0028 |  | General | Hook-Up Drawing - Flourescent Bulk Head Fitting on Building | Template | General - Hook-Up Drawing - Flourescent Bulk Head Fitting on Building - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Flourescent Bulk Head Fitting on Building | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0029 | A | 6105AK124-0000-ETMP-0029 | Q24050972-09-0000-E-TMP-0029 |  | General | Hook-Up Drawing - Flourescent Bulk Head Fitting Pole mount | Template | General - Hook-Up Drawing - Flourescent Bulk Head Fitting Pole mount - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Flourescent Bulk Head Fitting Pole mount | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0030 | A | 6105AK124-0000-ETMP-0030 | Q24050972-09-0000-E-TMP-0030 |  | General | Hook-Up Drawing - Highbay Fitting Plant | Template | General - Hook-Up Drawing - Highbay Fitting Plant - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Highbay Fitting Plant | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0031 | A | 6105AK124-0000-ETMP-0031 | Q24050972-09-0000-E-TMP-0031 |  | General | Hook-Up Drawing - Highbay Fitting Workshop | Template | General - Hook-Up Drawing - Highbay Fitting Workshop - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Highbay Fitting Workshop | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0032 | A | 6105AK124-0000-ETMP-0032 | Q24050972-09-0000-E-TMP-0032 |  | General | Hook-Up Drawing - Highmast Distribution Typical | Template | General - Hook-Up Drawing - Highmast Distribution Typical - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Highbay Roof Purlin Mounting | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0034 | A | 6105AK124-0000-ETMP-0034 | Q24050972-09-0000-E-TMP-0034 |  | General | Hook-Up Drawing - Highmast Light Kiosk Typical | Template | General - Hook-Up Drawing - Highmast Light Kiosk Typical - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Highmast Light Kiosk Typical | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0035 | A | 6105AK124-0000-ETMP-0035 | Q24050972-09-0000-E-TMP-0035 |  | General | Hook-Up Drawing - Highmast Structure and Luminaire Arrangement | Template | General - Hook-Up Drawing - Highmast Structure and Luminaire Arrangement - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Highmast Structure and Luminaire Arrangemen | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0036 | A | 6105AK124-0000-ETMP-0036 | Q24050972-09-0000-E-TMP-0036 |  | General | Hook-Up Drawing - Unistrut attached to I-Beam | Template | General - Hook-Up Drawing - Unistrut attached to I-Beam - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Unistrut attached to I-Beam | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0037 | A | 6105AK124-0000-ETMP-0037 | Q24050972-09-0000-E-TMP-0037 |  | General | Hook-Up Drawing - Electrical Lighting DB Mounting detail 1 | Template | General - Hook-Up Drawing - Electrical Lighting DB Mounting detail 1 - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Lighting DB Mounting detail 1 | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0038 | A | 6105AK124-0000-ETMP-0038 | Q24050972-09-0000-E-TMP-0038 |  | General | Hook-Up Drawing - Electrical Lighting DB Mounting detail 2 | Template | General - Hook-Up Drawing - Electrical Lighting DB Mounting detail 2 - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Lighting DB Mounting detail 2 | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0039 | A | 6105AK124-0000-ETMP-0039 | Q24050972-09-0000-E-TMP-0039 |  | General | Hook-Up Drawing - Electrical Lighting DB Mounting detail 3 over Trench | Template | General - Hook-Up Drawing - Electrical Lighting DB Mounting detail 3 over Trench - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Lighting DB Mounting detail 3 over Trench | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0040 | A | 6105AK124-0000-ETMP-0040 | Q24050972-09-0000-E-TMP-0040 |  | General | Hook-Up Drawing - Electrical Motor Earthing typical | Template | General - Hook-Up Drawing - Electrical Motor Earthing typical - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Motor Earthing typical | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0041 | A | 6105AK124-0000-ETMP-0041 | Q24050972-09-0000-E-TMP-0041 |  | General | Hook-Up Drawing - Electrical Photocell Day- Night Switch Installation | Template | General - Hook-Up Drawing - Electrical Photocell Day- Night Switch Installation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Photocell Day- Night Switch Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0042 | A | 6105AK124-0000-ETMP-0042 | Q24050972-09-0000-E-TMP-0042 |  | General | Hook-Up Drawing - Electrical Pratley CCG Box 3 way installation | Template | General - Hook-Up Drawing - Electrical Pratley CCG Box 3 way installation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pratley CCG Box 3 way installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0043 | A | 6105AK124-0000-ETMP-0043 | Q24050972-09-0000-E-TMP-0043 |  | General | Hook-Up Drawing - Electrical Pratley CCG Box termination | Template | General - Hook-Up Drawing - Electrical Pratley CCG Box termination - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pratley CCG Box termination | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0044 | A | 6105AK124-0000-ETMP-0044 | Q24050972-09-0000-E-TMP-0044 |  | General | Hook-Up Drawing - Electrical Stop Start Station with Canopy | Template | General - Hook-Up Drawing - Electrical Stop Start Station with Canopy - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Stop Start Station with Canopy | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0045 | A | 6105AK124-0000-ETMP-0045 | Q24050972-09-0000-E-TMP-0045 |  | General | Hook-Up Drawing - Electrical Unistrut to side of I-Beam | Template | General - Hook-Up Drawing - Electrical Unistrut to side of I-Beam - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Unistrut to side of I-Beam | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0059 | A | 6105AK124-0000-ITMP-0059 | Q24050972-10-0000-I-TMP-0059 |  | General | Hook-Up Drawing - Instrumentation Lighting DB Mounting detail 1 | Template | General - Hook-Up Drawing - Instrumentation Lighting DB Mounting detail 1 - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Lighting DB Mounting | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0060 | A | 6105AK124-0000-ITMP-0060 | Q24050972-10-0000-I-TMP-0060 |  | General | Hook-Up Drawing - Instrumentation Lighting DB Mounting detail 2 | Template | General - Hook-Up Drawing - Instrumentation Lighting DB Mounting detail 2 - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Lighting DB Mounting | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0061 | A | 6105AK124-0000-ITMP-0061 | Q24050972-10-0000-I-TMP-0061 |  | General | Hook-Up Drawing - Instrumentation Lighting DB Mounting detail 3 over Trench | Template | General - Hook-Up Drawing - Instrumentation Lighting DB Mounting detail 3 over Trench - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Lighting DB Mounting detail 3 over Trench | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0062 | A | 6105AK124-0000-ITMP-0062 | Q24050972-10-0000-I-TMP-0062 |  | General | Hook-Up Drawing - Instrumentation Motor Earthing typical | Template | General - Hook-Up Drawing - Instrumentation Motor Earthing typical - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Motor Earthing typical | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0063 | A | 6105AK124-0000-ITMP-0063 | Q24050972-10-0000-I-TMP-0063 |  | General | Hook-Up Drawing - Instrumentation Photocell Day- Night Switch Installation | Template | General - Hook-Up Drawing - Instrumentation Photocell Day- Night Switch Installation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Photocell Day- Night Switch Installation | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0064 | A | 6105AK124-0000-ITMP-0064 | Q24050972-10-0000-I-TMP-0064 |  | General | Hook-Up Drawing - Instrumentation Pratley CCG Box 3 way installation | Template | General - Hook-Up Drawing - Instrumentation Pratley CCG Box 3 way installation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pratley CCG Box 3 way installation | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0065 | A | 6105AK124-0000-ITMP-0065 | Q24050972-10-0000-I-TMP-0065 |  | General | Hook-Up Drawing - Instrumentation Pratley CCG Box termination | Template | General - Hook-Up Drawing - Instrumentation Pratley CCG Box termination - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pratley CCG Box termination | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0066 | A | 6105AK124-0000-ITMP-0066 | Q24050972-10-0000-I-TMP-0066 |  | General | Hook-Up Drawing - Instrumentation Stop Start Station with Canopy | Template | General - Hook-Up Drawing - Instrumentation Stop Start Station with Canopy - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Stop Start Station with Canopy | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0067 | A | 6105AK124-0000-ITMP-0067 | Q24050972-10-0000-I-TMP-0067 |  | General | Hook-Up Drawing - Instrumentation Unistrut to side of I-Beam | Template | General - Hook-Up Drawing - Instrumentation Unistrut to side of I-Beam - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Unistrut to side of I-Beam | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0046 | A | 6105AK124-0000-ETMP-0046 | Q24050972-09-0000-E-TMP-0046 |  | General | Electrical Check list - Above Ground Cables - Form | Template | General - Electrical Check list - Above Ground Cables - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Above Ground Cables | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0047 | A | 6105AK124-0000-ETMP-0047 | Q24050972-09-0000-E-TMP-0047 |  | General | Electrical Check list - Battery Tripping Unit (BTU) - Form | Template | General - Electrical Check list - Battery Tripping Unit (BTU) - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Battery Tripping Unit (BTU) | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0048 | A | 6105AK124-0000-ETMP-0048 | Q24050972-09-0000-E-TMP-0048 |  | General | Electrical Check list - Cable Ladder Inspection - Form | Template | General - Electrical Check list - Cable Ladder Inspection - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable Ladder Inspection | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0049 | A | 6105AK124-0000-ETMP-0049 | Q24050972-09-0000-E-TMP-0049 |  | General | Electrical Check list - DB Installation - Form | Template | General - Electrical Check list - DB Installation - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | DB Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0050 | A | 6105AK124-0000-ETMP-0050 | Q24050972-09-0000-E-TMP-0050 |  | General | Electrical Check list - Glanding and Termination of Cables - Form | Template | General - Electrical Check list - Glanding and Termination of Cables - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Glanding and Termination of Cables | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0051 | A | 6105AK124-0000-ETMP-0051 | Q24050972-09-0000-E-TMP-0051 |  | General | Electrical Check list - Installation of Safety Earths - Form | Template | General - Electrical Check list - Installation of Safety Earths - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Installation of Safety Earths | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0052 | A | 6105AK124-0000-ETMP-0052 | Q24050972-09-0000-E-TMP-0052 |  | General | Electrical Check list - JB Installation - Form | Template | General - Electrical Check list - JB Installation - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | JB Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0053 | A | 6105AK124-0000-ETMP-0053 | Q24050972-09-0000-E-TMP-0053 |  | General | Electrical Check list - Lighting and Small Power - Form | Template | General - Electrical Check list - Lighting and Small Power - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Lighting and Small Power | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0054 | A | 6105AK124-0000-ETMP-0054 | Q24050972-09-0000-E-TMP-0054 |  | General | Electrical Check list - Manufacture and Installation Cable Rack - Form | Template | General - Electrical Check list - Manufacture and Installation Cable Rack - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Manufacture and Installation Cable Rack | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0055 | A | 6105AK124-0000-ETMP-0055 | Q24050972-09-0000-E-TMP-0055 |  | General | Electrical Check list - MCC Installation - Form | Template | General - Electrical Check list - MCC Installation - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | MCC Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0056 | A | 6105AK124-0000-ETMP-0056 | Q24050972-09-0000-E-TMP-0056 |  | General | Electrical Check list - Motor Installation- Form | Template | General - Electrical Check list - Motor Installation- Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Motor Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0057 | A | 6105AK124-0000-ETMP-0057 | Q24050972-09-0000-E-TMP-0057 |  | General | Electrical Check list - Stand Station Installation - Form | Template | General - Electrical Check list - Stand Station Installation - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Stand Station Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0058 | A | 6105AK124-0000-ETMP-0058 | Q24050972-09-0000-E-TMP-0058 |  | General | Electrical Check list - Test Certificate Equipment Safety Earth - Form | Template | General - Electrical Check list - Test Certificate Equipment Safety Earth - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Test Certificate Equipment Safety Earth | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0059 | A | 6105AK124-0000-ETMP-0059 | Q24050972-09-0000-E-TMP-0059 |  | General | Electrical Check list - Transformer Installation- Form | Template | General - Electrical Check list - Transformer Installation- Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Transformer Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0060 | A | 6105AK124-0000-ETMP-0060 | Q24050972-09-0000-E-TMP-0060 |  | General | Electrical Check list - Trenching and Underground Cable Installation - Form | Template | General - Electrical Check list - Trenching and Underground Cable Installation - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Trenching and Underground Cable Installation | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0068 | A | 6105AK124-0000-ITMP-0068 | Q24050972-10-0000-I-TMP-0068 |  | General | Instrumentation Check list - Above Ground Cables - Form | Template | General - Instrumentation Check list - Above Ground Cables - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Above Ground Cables | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0069 | A | 6105AK124-0000-ITMP-0069 | Q24050972-10-0000-I-TMP-0069 |  | General | Instrumentation Check list - Control Valve Installation - Form | Template | General - Instrumentation Check list - Control Valve Installation - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Battery Tripping Unit (BTU) | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0070 | A | 6105AK124-0000-ITMP-0070 | Q24050972-10-0000-I-TMP-0070 |  | General | Instrumentation Check list - Cable Ladder Inspection - Form | Template | General - Instrumentation Check list - Cable Ladder Inspection - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Cable Ladder Inspection | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0071 | A | 6105AK124-0000-ITMP-0071 | Q24050972-10-0000-I-TMP-0071 |  | General | Instrumentation Check list - DB Installation - Form | Template | General - Instrumentation Check list - DB Installation - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | DB Installation | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0072 | A | 6105AK124-0000-ITMP-0072 | Q24050972-10-0000-I-TMP-0072 |  | General | Instrumentation Check list - Glanding and Termination of Cables - Form | Template | General - Instrumentation Check list - Glanding and Termination of Cables - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Glanding and Termination of Cables | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0073 | A | 6105AK124-0000-ITMP-0073 | Q24050972-10-0000-I-TMP-0073 |  | General | Instrumentation Check list - Field Installed Level Transmitter - Form | Template | General - Instrumentation Check list - Field Installed Level Transmitter - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Installation of Safety Earths | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0074 | A | 6105AK124-0000-ITMP-0074 | Q24050972-10-0000-I-TMP-0074 |  | General | Instrumentation Check list - JB Installation - Form | Template | General - Instrumentation Check list - JB Installation - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | JB Installation | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0075 | A | 6105AK124-0000-ITMP-0075 | Q24050972-10-0000-I-TMP-0075 |  | General | Instrumentation Check list - Field Installed Transmitter - Form | Template | General - Instrumentation Check list - Field Installed Transmitter - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Lighting and Small Power | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0076 | A | 6105AK124-0000-ITMP-0076 | Q24050972-10-0000-I-TMP-0076 |  | General | Instrumentation Check list - Manufacture and Installation Cable Rack - Form | Template | General - Instrumentation Check list - Manufacture and Installation Cable Rack - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Manufacture and Installation Cable Rack | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0077 | A | 6105AK124-0000-ITMP-0077 | Q24050972-10-0000-I-TMP-0077 |  | General | Instrumentation Check list - Flow Transmitter - Form | Template | General - Instrumentation Check list - Flow Transmitter - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | MCC Installation | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0078 | A | 6105AK124-0000-ITMP-0078 | Q24050972-10-0000-I-TMP-0078 |  | General | Instrumentation Check list - Instrument Tubing - Form | Template | General - Instrumentation Check list - Instrument Tubing - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Motor Installation | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0079 | A | 6105AK124-0000-ITMP-0079 | Q24050972-10-0000-I-TMP-0079 |  | General | Instrumentation Check list - Stand Station Installation - Form | Template | General - Instrumentation Check list - Stand Station Installation - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Stand Station Installation | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0080 | A | 6105AK124-0000-ITMP-0080 | Q24050972-10-0000-I-TMP-0080 |  | General | Instrumentation Check list - Pressure Switch Installation - Forms | Template | General - Instrumentation Check list - Pressure Switch Installation - Forms - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Test Certificate Equipment Safety Earth | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0081 | A | 6105AK124-0000-ITMP-0081 | Q24050972-10-0000-I-TMP-0081 |  | General | Instrumentation Checklist - Instrument Installation - Form | Template | General - Instrumentation Checklist - Instrument Installation - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Transformer Installation | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0082 | A | 6105AK124-0000-ITMP-0082 | Q24050972-10-0000-I-TMP-0082 |  | General | Instrumentation Check list - Trenching and Underground Cable Installation - Form | Template | General - Instrumentation Check list - Trenching and Underground Cable Installation - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Trenching and Underground Cable Installation | General |  |  |  | Pending
6105A | K124 | 0000 | F | TMP | 0001 | A | 6105AK124-0000-FTMP-0001 | Q24050972-09-0000-F-TMP-0001 |  | General | Check List - Manhole and Splice for FOC Installation - Form | Template | General - Check List - Manhole and Splice for FOC Installation - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Manhole and Splice for FOC Installation | General |  |  |  | Pending
6105A | K124 | 0000 | G | TMP | 0001 | A | 6105AK124-0000-GTMP-0001 | Q24050972-09-0000-G-TMP-0001 |  | General | Check list - Punch List - Form | Template | General - Check list - Punch List - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Punch List | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0061 | A | 6105AK124-0000-ETMP-0061 | Q24050972-09-0000-E-TMP-0061 |  | General | ITP Motor Cable Installation | Template | General - ITP Motor Cable Installation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | ITP Motor Cable Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0062 | A | 6105AK124-0000-ETMP-0062 | Q24050972-09-0000-E-TMP-0062 |  | General | ITP Transformer Istallation | Template | General - ITP Transformer Istallation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | ITP Transformer Istallation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0063 | A | 6105AK124-0000-ETMP-0063 | Q24050972-09-0000-E-TMP-0063 |  | General | Electrical - ITP Cable Tray | Template | General - Electrical - ITP Cable Tray - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | ITP Cable Tray | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0064 | A | 6105AK124-0000-ETMP-0064 | Q24050972-09-0000-E-TMP-0064 |  | General | Electrical - ITP Distribution Board | Template | General - Electrical - ITP Distribution Board - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | ITP Distribution Board | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0065 | A | 6105AK124-0000-ETMP-0065 | Q24050972-09-0000-E-TMP-0065 |  | General | ITP Earthing Installation | Template | General - ITP Earthing Installation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | ITP Earthing Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0066 | A | 6105AK124-0000-ETMP-0066 | Q24050972-09-0000-E-TMP-0066 |  | General | ITP MCC Installations | Template | General - ITP MCC Installations - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | ITP MCC Installations | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0067 | A | 6105AK124-0000-ETMP-0067 | Q24050972-09-0000-E-TMP-0067 |  | General | ITP Motor Installation | Template | General - ITP Motor Installation - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | ITP Motor Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0068 | A | 6105AK124-0000-ETMP-0068 | Q24050972-09-0000-E-TMP-0068 |  | General | ITP Small Power and Lighting | Template | General - ITP Small Power and Lighting - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | ITP Small Power and Lighting | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0083 | A | 6105AK124-0000-ITMP-0083 | Q24050972-10-0000-I-TMP-0083 |  | General | Instrumentation - ITP Cable Tray | Template | General - Instrumentation - ITP Cable Tray - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | ITP Cable Tray | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0084 | A | 6105AK124-0000-ITMP-0084 | Q24050972-10-0000-I-TMP-0084 |  | General | ITP Density Transmitters | Template | General - ITP Density Transmitters - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Density Transmitters | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0085 | A | 6105AK124-0000-ITMP-0085 | Q24050972-10-0000-I-TMP-0085 |  | General | Instrumentation - ITP Distribution Board | Template | General - Instrumentation - ITP Distribution Board - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Distribution Board | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0086 | A | 6105AK124-0000-ITMP-0086 | Q24050972-10-0000-I-TMP-0086 |  | General | ITP Flow Control Valves | Template | General - ITP Flow Control Valves - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Flow Control Valves | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0087 | A | 6105AK124-0000-ITMP-0087 | Q24050972-10-0000-I-TMP-0087 |  | General | ITP Flow Switches | Template | General - ITP Flow Switches - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Flow Switches | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0088 | A | 6105AK124-0000-ITMP-0088 | Q24050972-10-0000-I-TMP-0088 |  | General | ITP Flow Transmitters | Template | General - ITP Flow Transmitters - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Flow Transmitters | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0089 | A | 6105AK124-0000-ITMP-0089 | Q24050972-10-0000-I-TMP-0089 |  | General | ITP Hand Switches | Template | General - ITP Hand Switches - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Hand Switches | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0090 | A | 6105AK124-0000-ITMP-0090 | Q24050972-10-0000-I-TMP-0090 |  | General | ITP Junction Boxes | Template | General - ITP Junction Boxes - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Junction Boxes | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0091 | A | 6105AK124-0000-ITMP-0091 | Q24050972-10-0000-I-TMP-0091 |  | General | ITP Level Control Valves | Template | General - ITP Level Control Valves - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Level Control Valves | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0092 | A | 6105AK124-0000-ITMP-0092 | Q24050972-10-0000-I-TMP-0092 |  | General | ITP Level Switches | Template | General - ITP Level Switches - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Level Switches | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0093 | A | 6105AK124-0000-ITMP-0093 | Q24050972-10-0000-I-TMP-0093 |  | General | ITP Level Transmitters | Template | General - ITP Level Transmitters - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Level Transmitters | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0094 | A | 6105AK124-0000-ITMP-0094 | Q24050972-10-0000-I-TMP-0094 |  | General | ITP Limit Switches | Template | General - ITP Limit Switches - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Limit Switches | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0095 | A | 6105AK124-0000-ITMP-0095 | Q24050972-10-0000-I-TMP-0095 |  | General | ITP Pneumatic Valves | Template | General - ITP Pneumatic Valves - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pneumatic Valves | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0096 | A | 6105AK124-0000-ITMP-0096 | Q24050972-10-0000-I-TMP-0096 |  | General | ITP Pressure Control Valves | Template | General - ITP Pressure Control Valves - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pressure Control Valves | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0097 | A | 6105AK124-0000-ITMP-0097 | Q24050972-10-0000-I-TMP-0097 |  | General | ITP Pressure Gauge | Template | General - ITP Pressure Gauge - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pressure Gauge | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0098 | A | 6105AK124-0000-ITMP-0098 | Q24050972-10-0000-I-TMP-0098 |  | General | ITP Pressure Transmitters | Template | General - ITP Pressure Transmitters - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Pressure Transmitters | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0099 | A | 6105AK124-0000-ITMP-0099 | Q24050972-10-0000-I-TMP-0099 |  | General | ITP Sample Points | Template | General - ITP Sample Points - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Sample Points | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0100 | A | 6105AK124-0000-ITMP-0100 | Q24050972-10-0000-I-TMP-0100 |  | General | ITP Speed Transmitters | Template | General - ITP Speed Transmitters - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Speed Transmitters | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0101 | A | 6105AK124-0000-ITMP-0101 | Q24050972-10-0000-I-TMP-0101 |  | General | ITP Temperature Transmitters | Template | General - ITP Temperature Transmitters - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Temperature Transmitters | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0102 | A | 6105AK124-0000-ITMP-0102 | Q24050972-10-0000-I-TMP-0102 |  | General | ITP Vibration Transmitters | Template | General - ITP Vibration Transmitters - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Vibration Transmitters | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0103 | A | 6105AK124-0000-ITMP-0103 | Q24050972-10-0000-I-TMP-0103 |  | General | ITP Weightometer | Template | General - ITP Weightometer - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Weightometer | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0069 | A | 6105AK124-0000-ETMP-0069 | Q24050972-10-0000-E-TMP-0069 |  | General | Test Certificate - Insulation Test of Cables - Form | Template | General - Test Certificate - Insulation Test of Cables - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Insulation Test of Cables | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0070 | A | 6105AK124-0000-ETMP-0070 | Q24050972-10-0000-E-TMP-0070 |  | General | Test Certificate - Earth Resistance - Form | Template | General - Test Certificate - Earth Resistance - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Earth Resistance | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0071 | A | 6105AK124-0000-ETMP-0071 | Q24050972-10-0000-E-TMP-0071 |  | General | Test Certificate - Motor Installation- Form | Template | General - Test Certificate - Motor Installation- Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Motor Installation | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0072 | A | 6105AK124-0000-ETMP-0072 | Q24050972-10-0000-E-TMP-0072 |  | General | Test Certificate - Transformer - Form | Template | General - Test Certificate - Transformer - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Transformer | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0104 | A | 6105AK124-0000-ITMP-0104 | Q24050972-10-0000-I-TMP-0104 |  | General | Test Certificate - Instrument Cables - Form | Template | General - Test Certificate - Instrument Cables - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Instrument Cables | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0105 | A | 6105AK124-0000-ITMP-0105 | Q24050972-10-0000-I-TMP-0105 |  | General | Test Certificate - Instrument Loop Test - Form | Template | General - Test Certificate - Instrument Loop Test - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Instrument Loop Test | General |  |  |  | Pending
6105A | K124 | 0000 | I | TMP | 0106 | A | 6105AK124-0000-ITMP-0106 | Q24050972-10-0000-I-TMP-0106 |  | General | Test Certificate - Test Acceptance Instrument Tubing - Form | Template | General - Test Certificate - Test Acceptance Instrument Tubing - Form - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Test Acceptance Instrument Tubing | General |  |  |  | Pending
6105A | K124 | 0000 | E | TMP | 0073 | A | 6105AK124-0000-ETMP-0073 | Q24050972-10-0000-E-TMP-0073 |  | General | Hook-Up Drawing - Highbay Roof Purlin Mountin | Template | General - Hook-Up Drawing - Highbay Roof Purlin Mountin - Template |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-10-30 | Transformer | General |  |  |  | Pending
6105A | K124 | 0100 | B | CON | 0001 | A | 6105AK124-0100-BCON-0001 | Q24050972-01-0100-B-CON-0001 |  | Project Site Wide | Notice of delay - Delay Notification Contractual | General | Project Site Wide - Notice of delay - Delay Notification Contractual - General |  |  | RES - Reserved Placeholder | Pending | 0% | JV |  | 2026-05-15 | Delay Notification Contractual | General |  |  |  | Pending
6105A | K124 | 0100 | B | CON | 0002 | A | 6105AK124-0100-BCON-0002 | Q24050972-01-0100-B-CON-0002 |  | Project Site Wide | Contract Management (EPCM) - Contract Processes and Agreements. | General | Project Site Wide - Contract Management (EPCM) - Contract Processes and Agreements. - General |  |  | RES - Reserved Placeholder | Pending | 0% | JV |  | 2026-05-15 | Contract Processes and Agreements. | General |  |  |  | Pending
6105A | K124 | 0100 | B | CON | 0003 | A | 6105AK124-0100-BCON-0003 | Q24050972-01-0100-B-CON-0003 |  | Project Site Wide | Strategic Coontract Management - Managing Director’s Directive | General | Project Site Wide - Strategic Coontract Management - Managing Director’s Directive - General |  |  | RES - Reserved Placeholder | Pending | 0% | JV |  | 2026-05-15 | Managing Director’s Directive | General |  |  |  | Pending
6105A | K124 | 0100 | B | CON | 0004 | A | 6105AK124-0100-BCON-0004 | Q24050972-01-0100-B-CON-0004 |  | Project Site Wide | Contract Management Processes and Lifecycle | General | Project Site Wide - Contract Management Processes and Lifecycle - General |  |  | RES - Reserved Placeholder | Pending | 0% | JV |  | 2026-05-15 | Dispute Resolution | General |  |  |  | Pending
6105A | K124 | 0100 | B | CON | 0005 | A | 6105AK124-0100-BCON-0005 | Q24050972-01-0100-B-CON-0005 |  | Project Site Wide | Dispute Notice | General | Project Site Wide - Dispute Notice - General |  |  | RES - Reserved Placeholder | Pending | 0% | JV |  | 2026-05-15 | Dispute Notice | General |  |  |  | Pending
6105A | K124 | 0100 | E | LST | 0001 | A | 6105AK124-0100-ELST-0001 | Q24050972-01-0100-E-LST-0001 |  | Project Site Wide | Electrical Equipment | List | Project Site Wide - Electrical Equipment - List |  |  | RES - Reserved Placeholder | Pending | 0% | JM |  | 2026-05-15 | Electrical Equipment | List |  |  |  | Pending
6105A | K124 | 0000 | B | CON | 0001 | A | 6105AK124-0000-BCON-0001 | Q24050972-02-0000-B-CON-0001 |  | General | Notice of Intent to Claim (EOT) - Extension of Time and Cost | Contract | General - Notice of Intent to Claim (EOT) - Extension of Time and Cost - Contract |  |  | RES - Reserved Placeholder | Pending | 0% | JV |  | 2026-05-15 | Notice of Intent to Claim | Extension of Time and Cost |  |  |  | Pending
6105A | K124 | 6262 | E | DST | 0011 | A | 6105AK124-6262-EDST-0011 | Q24050972-12-6262-E-DST-0011 |  | Emergency Power Substation 1 and Control Room 1 | Generator - Main Aux Supply | 1MVA, 400Vac - Datasheet | Emergency Power Substation 1 and Control Room 1 - Generator - Main Aux Supply - 1MVA, 400Vac - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Generator | Datasheet |  |  |  | Pending
6105A | K124 | 6286 | E | DST | 0007 | A | 6105AK124-6286-EDST-0007 | Q24050972-02-6286-E-DST-0007 |  | Primary Crushing | Generator | 250kVA, 400Vac - Datasheet | Primary Crushing - Generator - 250kVA, 400Vac - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Generator | Datasheet |  |  |  | Pending
6105A | K124 | 6241 | E | DST | 0001 | A | 6105AK124-6241-EDST-0001 | Q24050972-02-6241-E-DST-0001 |  | 33/220 kV Solar PV Substation | Generator | 250kVA, 400Vac - Datasheet | 33/220 kV Solar PV Substation - Generator - 250kVA, 400Vac - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Generator | Datasheet |  |  |  | Pending
6105A | K124 | 6242 | E | DST | 0001 | A | 6105AK124-6242-EDST-0001 | Q24050972-02-6242-E-DST-0001 |  | 33/220 kV Power Station Substation | Generator - Wärtsilä | 250kVA 400Vac - Datasheet | 33/220 kV Power Station Substation - Generator - Wärtsilä - 250kVA 400Vac - Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Generator | Datasheet |  |  |  | Pending
6105A | K124 | 0000 | G | PLN | 0001 | A | 6105AK124-0000-GPLN-0001 | Q24050972-02-0000-G-PLN-0001 |  | General | Phase 1 Construction Project Management | Plan | General - Phase 1 Construction Project Management - Plan | 2026-02-27 |  | IFR - Issued for Review | Reviewed With Comments | 33.33% | MC |  |  | Construction Project Management | Datasheet |  |  |  | Pending
6105A | K124 | 6262 | E | DST | 0012 | A | 6105AK124-6262-EDST-0012 | Q24050972-02-6262-E-DST-0012 |  | Emergency Power Substation 1 and Control Room 1 | Generator | 630kVA- Datasheet | Emergency Power Substation 1 and Control Room 1 - Generator - 630kVA- Datasheet |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Generator | Datasheet |  |  |  | Pending
6105A | K124 | 0100 | E | SLD | 0001 | 0 | 6105AK124-0100-ESLD-0001 | Q24050972-02-0100-E-SLD-0001 |  | Project Site Wide | Phase 1 Power Supply and Grid Stabilisation Packages | Overall Conceptual Single Line Diagram | Project Site Wide - Phase 1 Power Supply and Grid Stabilisation Packages - Overall Conceptual Single Line Diagram | 2026-02-26 | 2026-04-08 | IFC - Issued for Construction | Rejected - Revise & Resubmit | 66.67% | TDK |  |  | Power Supply and Grid Stabilisation Packages | Single Line Diagram |  |  |  | Pending
6105A | K124 | 0000 | G | PRC | 0001 | A | 6105AK124-0000-GPRC-0001 | Q24050972-02-0000-G-PRC-0001 |  | General | Project and Package Management | Procedure | General - Project and Package Management - Procedure | 2026-02-27 |  | IFR - Issued for Review | Pending | 33.33% | MC |  |  | Project and Package Management | Procedure |  |  |  | Pending
6105A | K124 | 0100 | E | PLN | 0001 | A | 6105AK124-0100-EPLN-0001 | Q24050972-02-0100-E-PLN-0001 |  | Project Site Wide | RDMC Phase 1 Power Supply and Grid Stabilization Packages – E, C & I Engineering Management | Plan | Project Site Wide - RDMC Phase 1 Power Supply and Grid Stabilization Packages – E, C & I Engineering Management - Plan | 2026-03-03 |  | IFR - Issued for Review | Reviewed With Comments | 33.33% | MM |  |  | Power Supply and Grid Stabilization Packages E,C & I Engineering Management | Plan |  |  |  | Pending
6105A | K124 | 0000 | G | PLN | 0002 | 0 | 6105AK124-0000-GPLN-0002 | Q24050972-02-0000-G-PLN-0002 |  | General | ​Project Site Wide 3D Model Management | Plan | General - ​Project Site Wide 3D Model Management - Plan | 2026-03-10 | 2026-04-24 | IFU - Issued for Use | Pending | 66.67% | JM |  |  | Project Site Wide 3D Model Management | Datasheet |  |  |  | Pending
6105A | K124 | 0000 | G | PRC | 0002 | A | 6105AK124-0000-GPRC-0002 | Q24050972-02-0000-G-PRC-0002 |  | General | Construction Readiness & Interface Management Framework | Procedure | General - Construction Readiness & Interface Management Framework - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-05-15 | Management Framework | Procedure |  |  |  | Pending
6105A | K124 | 0000 | G | PRC | 0003 | A | 6105AK124-0000-GPRC-0003 | Q24050972-02-0000-G-PRC-0003 |  | General | Risk Management Process | Procedure | General - Risk Management Process - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-05-15 | Risk Management Process | Procedure |  |  |  | Pending
6105A | K124 | 0000 | G | PRC | 0004 | A | 6105AK124-0000-GPRC-0004 | Q24050972-02-0000-G-PRC-0004 |  | General | FAT Govemance (EP side) | Procedure | General - FAT Govemance (EP side) - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-05-15 | FAT Govemance (EP side) | Procedure |  |  |  | Pending
6105A | K124 | 0000 | G | PRC | 0005 | A | 6105AK124-0000-GPRC-0005 | Q24050972-02-0000-G-PRC-0005 |  | General | Interface Management | Procedure | General - Interface Management - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-05-15 | Interface Management | Procedure |  |  |  | Pending
6105A | K124 | 0000 | G | PRC | 0006 | A | 6105AK124-0000-GPRC-0006 | Q24050972-02-0000-G-PRC-0006 |  | General | Reporting & Performance KPIs | Procedure | General - Reporting & Performance KPIs - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-05-15 | Reporting & Performance KPIs | Procedure |  |  |  | Pending
6105A | K124 | 0000 | G | PRC | 0007 | A | 6105AK124-0000-GPRC-0007 | Q24050972-02-0000-G-PRC-0007 |  | General | Quality Oversight (ITPs, NCRs) | Procedure | General - Quality Oversight (ITPs, NCRs) - Procedure |  |  | RES - Reserved Placeholder | Pending | 0% | MC |  | 2026-05-15 | Quality Oversight (ITPs, NCRs) | Procedure |  |  |  | Pending
6105A | K124 | 0000 | G | PRC | 0008 | A | 6105AK124-0000-GPRC-0008 | Q24050972-02-0000-G-PRC-0008 |  | General | Project Controls | Procedure | General - Project Controls - Procedure | 2026-02-27 |  | IFR - Issued for Review | Pending | 33.33% | MC |  |  | PPE Phase 1 Project Controls | Procedure |  |  |  | Pending
6105A | K124 | 0000 | G | CHR | 0001 | A | 6105AK124-0000-GCHR-0001 | Q24050972-02-0000-G-CHR-0001 |  | General | Phase 1 - Package Management Organogram | Chart | General - Phase 1 - Package Management Organogram - Chart |  |  | RES - Reserved Placeholder | Pending | 0% | JM |  | 2026-05-15 | Phase 1 - Package Management | Organogram Chart |  |  |  | Pending
6105A | K124 | 0100 | G | MDR | 0001 | 0 | 6105AK124-0100-GMDR-0001 | Q24050972-01-0100-G-MDR-0001 |  | Project Site Wide | Master Deliverables Register | Document Register for Engineering - April 2026 | Project Site Wide - Master Deliverables Register - Document Register for Engineering - April 2026 |  | 2026-04-22 | IFI - Issued for Information | Pending | 0% | VV |  | Monthly | Master Deliverables Register | Document Register for Engineering |  |  |  | Pending
6105A | K124 | 6243 | E | SOW | 0002 | A | 6105AK124-6243-ESOW-0002 | Q24050972-06-6243-E-SOW-0002 |  | 220/33 kV Plant Main Substation | Overall Plant | Scope of Works : Supply, install and Commissiong | 220/33 kV Plant Main Substation - Overall Plant - Scope of Works : Supply, install and Commissiong |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Overall Plant | Scope of Work |  |  |  | Pending
6105A | K124 | 0100 | E | GAD | 0002 | A | 6105AK124-0100-EGAD-0002 | Q24050972-02-0100-E-GAD-0002 | Sht 1 of 1 | Project Site Wide | Switch Room | Typical Earthing Arrangement | Project Site Wide - Switch Room - Typical Earthing Arrangement - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Switch Room | Typical Earthing Arrangement |  |  |  | Pending
6105A | K124 | 0100 | E | GAD | 0003 | A | 6105AK124-0100-EGAD-0003 | Q24050972-02-0100-E-GAD-0003 | Sht 1 of 1 | Project Site Wide | Typical Rebar Earthing | Detail | Project Site Wide - Typical Rebar Earthing - Detail - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Typical Rebar Earthing | Detail |  |  |  | Pending
6105A | K124 | 6241 | E | SOW | 0001 | A | 6105AK124-6241-ESOW-0001 | Q24050972-02-6241-E-SOW-0001 |  | 33/220 kV Solar PV Substation | Overall Plant | Scope of Works : Supply, install and Commissiong | 33/220 kV Solar PV Substation - Overall Plant - Scope of Works : Supply, install and Commissiong |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Overall Plant | Scope of Works : Supply, install and Commissiong |  |  |  | Pending
6105A | K124 | 6286 | E | SOW | 0001 | A | 6105AK124-6286-ESOW-0001 | Q24050972-02-6286-E-SOW-0001 |  | Primary Crushing | Substation | Scope of Works: Construct, Supply, Iinstall and Commissiong | Primary Crushing - Substation - Scope of Works: Construct, Supply, Iinstall and Commissiong |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Overall Plant | Scope of Work |  |  |  | Pending
6105A | K124 | 6200 | E | SOW | 0002 | A | 6105AK124-6200-ESOW-0002 | Q24050972-02-6200-E-SOW-0002 |  | On-Site Power Supply and Transmission | Overhead Lines (33kV and 220kVA) | Scope of Works: Interface (OHL & Switching Yards) | On-Site Power Supply and Transmission - Overhead Lines (33kV and 220kVA) - Scope of Works: Interface (OHL & Switching Yards) |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Overhead Lines (33kV and 220kVA) | Scope of Work |  |  |  | Pending
6105A | K124 | 0100 | E | SOW | 0001 | A | 6105AK124-0100-ESOW-0001 | Q24050972-02-0100-E-SOW-0001 |  | Project Site Wide | Equipment Earthing | Scope of Works: Earthing and Bonding of Equipment | Project Site Wide - Equipment Earthing - Scope of Works: Earthing and Bonding of Equipment | 2026-05-19 |  | IFR - Issued for Review | Pending | 33.33% | IS |  |  | Equipment Earthing | Scope of Works |  |  |  | Pending
6105A | K124 | 0000 | B | PCN | 0001 | A | 6105AK124-0000-BPCN-0001 | Q24050972-02-0000-B-PCN-0001 |  | General | Phase 1 Contractual Response to Call off Agreement 10 | Project Change Notice | General - Phase 1 Contractual Response to Call off Agreement 10 - Project Change Notice |  |  | RES - Reserved Placeholder | Pending | 0% | JM |  | 2026-05-15 | Call off Agreement | Project Change Notice |  |  |  | Pending
6105A | K124 | 0000 | B | PCN | 0002 | A | 6105AK124-0000-BPCN-0002 | Q24050972-02-0000-B-PCN-0002 |  | General | Phase 1 Contractual Response to Call off Agreement 11 | Project Change Notice | General - Phase 1 Contractual Response to Call off Agreement 11 - Project Change Notice |  |  | RES - Reserved Placeholder | Pending | 0% | JM |  | 2026-05-15 | Call off Agreement | Project Change Notice |  |  |  | Pending
6105A | K124 | 0000 | B | PCN | 0003 | A | 6105AK124-0000-BPCN-0003 | Q24050972-02-0000-B-PCN-0003 |  | General | Response to Engineering Change Request: Additional Equipment | Project Change Notice | General - Response to Engineering Change Request: Additional Equipment - Project Change Notice |  |  | RES - Reserved Placeholder | Pending | 0% | JM |  | 2026-05-15 | Response to Engineering Change Request | Project Change Notice |  |  |  | Pending
6105A | K124 | 6286 | E | LAY | 0003 | 0 | 6105AK124-6286-ELAY-0003 | Q24050972-02-6286-E-LAY-0003 |  | Primary Crushing | Open Pit Mining Switchroom | Layout | Primary Crushing - Open Pit Mining Switchroom - Layout | 2026-04-16 | 2026-05-27 | IFC - Issued for Construction | Pending | 66.67% | CLR |  |  | Switchroom | Layout |  |  |  | Pending
6105A | K124 | 0000 | Q | QAD | 0001 | A | 6105AK124-0000-QQAD-0001 | Q24050972-02-0000-Q-QAD-0001 |  | General | EPCM - Responsibilities | Quality Assurance Documents | General - EPCM - Responsibilities - Quality Assurance Documents | 2026-04-28 |  | IFR - Issued for Review | Pending | 33.33% | JM |  | 2026-05-15 | Quality Assurance Responsibilities | Quality Assurance Documents |  |  |  | Pending
6105A | K124 | 6286 | G | BOM | 0001 | A | 6105AK124-6286-GBOM-0001 | Q24050972-02-6286-G-BOM-0001 |  | Primary Crushing | Plant & Equipment | Bill of Material | Primary Crushing - Plant & Equipment - Bill of Material |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Plant & Equipment | Bill of Material |  |  |  | Pending
6105A | K124 | 6286 | E | SCH | 0001 | A | 6105AK124-6286-ESCH-0001 | Q24050972-02-6286-E-SCH-0001 |  | Primary Crushing | Cable | Schedule | Primary Crushing - Cable - Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Cable | Schedule |  |  |  | Pending
6105A | K124 | 0000 | Q | STD | 0001 | 0 | 6105AK124-0000-QSTD-0001 | Q24050972-02-0000-Q-STD-0001 |  | General | PCM - Project Quality Governance - Power Packages | Standard | General - PCM - Project Quality Governance - Power Packages - Standard | 2026-03-09 | 2026-04-24 | IFU - Issued for Use | Pending | 66.67% | JM |  |  | General - EPCM - Project Quality Governance - Power Packages | Standard |  |  |  | Pending
6105A | K124 | 0000 | B | CON | 0002 | A | 6105AK124-0000-BCON-0002 | Q24050972-02-0000-B-CON-0002 |  | General | Change Control Log | Contract | General - Change Control Log - Contract |  |  | RES - Reserved Placeholder | Pending | 0% | JM |  | 2026-05-15 | Change Control Log | Contract |  |  |  | Pending
6105A | K124 | 6286 | E | LAY | 0004 | A | 6105AK124-6286-ELAY-0004 | Q24050972-02-6286-E-LAY-0004 |  | Primary Crushing | Mining Substation | Earthing layout | Primary Crushing - Mining Substation - Earthing layout | 2026-05-25 |  | IFR - Issued for Review | Pending | 33.33% | TDK |  |  | Earth Mat Design | Layout |  |  |  | Pending
6105A | K124 | 6286 | E | LAY | 0005 | A | 6105AK124-6286-ELAY-0005 | Q24050972-02-6286-E-LAY-0005 |  | Primary Crushing | Mining Substation | Overall Lighting Layout | Primary Crushing - Mining Substation - Overall Lighting Layout | 2026-05-25 |  | IFR - Issued for Review | Pending | 33.33% | TDK |  |  | Earthing for lighting | Layout |  |  |  | Pending
6105A | K124 | 6251 | E | LAY | 0001 | A | 6105AK124-6251-ELAY-0001 | Q24050972-02-6251-E-LAY-0001 |  | Load Bank | Wartsila Power Plant 1 | Civil Layout | Load Bank - Wartsila Power Plant 1 - Civil Layout | 2026-04-16 |  | IFR - Issued for Review | Reviewed | 33.33% | CLR |  |  | Wartsila Power Plant 1 | Civil Layout |  |  |  | Pending
6105A | K124 | 6251 | E | SEC | 0001 | A | 6105AK124-6251-ESEC-0001 | Q24050972-10-6251-E-SEC-0001 |  | Load Bank | Wartsila Power Plant 1 | Section views | Load Bank - Wartsila Power Plant 1 - Section views | 2026-04-16 |  | IFR - Issued for Review | Reviewed | 33.33% | CLR |  |  | Wartsila Power Plant 1 | Section views |  |  |  | Pending
6105A | K124 | 6243 | E | GAD | 0001 | A | 6105AK124-6243-EGAD-0001 | Q24050972-02-6243-E-GAD-0001 |  | 220/33 kV Plant Main Substation | Main Consumer Intake Power Complex | Auxiliary Power General Arrangement | 220/33 kV Plant Main Substation - Main Consumer Intake Power Complex - Auxiliary Power General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Auxiliary Power | General Arrangement |  |  |  | Pending
6105A | K124 | 0000 | G | DDR | 0002 | A | 6105AK124-0000-GDDR-0002 | Q24050972-02-0000-G-DDR-0002 |  | General | Initial controlled issue with tracking enhancements and dashboard | Document and Data Register | General - Initial controlled issue with tracking enhancements and dashboard - Document and Data Register |  |  | RES - Reserved Placeholder | Pending | 0% | JM |  | 2026-05-15 | Document and Data Register | Initial controlled issue |  |  |  | Pending
6105A | K124 | 0100 | G | CHR | 0002 | A | 6105AK124-0100-GCHR-0002 | Q24050972-02-0100-G-CHR-0002 |  | Project Site Wide | Change Management Process Flow | General | Project Site Wide - Change Management Process Flow - General |  |  | RES - Reserved Placeholder | Pending | 0% | JM |  | 2026-05-15 | Chart | General |  |  |  | Pending
6105A | K124 | 6243 | C | SPC | 0001 | A | 6105AK124-6243-CSPC-0001 | Q24050972-02-6243-C-SPC-0001 |  | 220/33 kV Plant Main Substation | Bulk Earthworks | Specification | 220/33 kV Plant Main Substation - Bulk Earthworks - Specification |  |  | RES - Reserved Placeholder | Pending | 0% | AS |  | 2026-05-15 | Bulk Earthworks | Specifications |  |  |  | Pending
6105A | K124 | 6243 | C | BOM | 0001 | A | 6105AK124-6243-CBOM-0001 | Q24050972-02-6243-C-BOM-0001 |  | 220/33 kV Plant Main Substation | Bulk Earthworks | Bill of Material | 220/33 kV Plant Main Substation - Bulk Earthworks - Bill of Material |  |  | RES - Reserved Placeholder | Pending | 0% | AS |  | 2026-05-15 | Bulk Earthworks | Bill of Material |  |  |  | Pending
6105A | K124 | 0100 | G | CHR | 0003 | A | 6105AK124-0100-GCHR-0003 | Q24050972-02-0100-G-CHR-0003 |  | Project Site Wide | RDMC Project - Phase 1 EP Org Chart | General | Project Site Wide - RDMC Project - Phase 1 EP Org Chart - General |  |  | RES - Reserved Placeholder | Pending | 0% | JM |  | 2026-05-15 | Organogram | General |  |  |  | Pending
6105A | K124 | 6186 | E | DBD | 0001 | A | 6105AK124-6186-EDBD-0001 | Q24050972-02-6186-E-DBD-0001 |  | Firewater - Tank & Fire Fighting System | Heat Trace Systems utilized on the EW and Ph- 1 Site | Design Basis and Criteria | Firewater - Tank & Fire Fighting System - Heat Trace Systems utilized on the EW and Ph- 1 Site - Design Basis and Criteria | 2026-03-09 |  | IFR - Issued for Review | Reviewed With Comments | 33.33% | VV |  |  | Heat Trace Systems | Design Basis and Criteria |  |  |  | Pending
6105A | K124 | 0000 | G | PRC | 0009 | A | 6105AK124-0000-GPRC-0009 | Q24050972-02-0000-G-PRC-0009 |  | General | Construction Data and As-Built Management | Procedure | General - Construction Data and As-Built Management - Procedure | 2026-03-09 |  | IFR - Issued for Review | Reviewed With Comments | 33.33% | MC |  |  | Construction Data | Procedure |  |  |  | Pending
6105A | K124 | 0000 | G | PLN | 0003 | A | 6105AK124-0000-GPLN-0003 | Q24050972-02-0000-G-PLN-0003 |  | General | Construction Execution | Plan | General - Construction Execution - Plan | 2026-03-09 |  | IFR - Issued for Review | Reviewed With Comments | 33.33% | MC |  |  | Construction Execution | Plan |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0001 | B | 6105AK124-6200-CLAY-0001 | Q24050972-03-6200-C-LAY-0001 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Layout | 2026-04-14 |  | IFR - Issued for Review | Reviewed | 33.33% | CLR |  |  | Main Consumer intake | Layout |  |  |  | Pending
6105A | K124 | 6282 | E | SLD | 0001 | A | 6105AK124-6282-ESLD-0001 | Q24050972-03-6282-E-SLD-0001 |  | Potable Water Treatment Plant | 33kV OHL Routing for Borefields | 33kV OHL Single Line diagram for Boreholes | Potable Water Treatment Plant - 33kV OHL Routing for Borefields - 33kV OHL Single Line diagram for Boreholes |  |  | RES - Reserved Placeholder | Pending | 0% | TDK |  | 2026-07-15 | Routing for Borefields | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SOW | 0003 | A | 6105AK124-6200-ESOW-0003 | Q24050972-03-6200-E-SOW-0003 |  | On-Site Power Supply and Transmission | Plant Wide Substations | Scope of Works : Supply, install and Commissiong | On-Site Power Supply and Transmission - Plant Wide Substations - Scope of Works : Supply, install and Commissiong |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Overall Plant | Scope of Work |  |  |  | Pending
6105A | K124 | 0100 | E | DTL | 0001 | A | 6105AK124-0100-EDTL-0001 | Q24050972-0-0100-E-DTL-0001 |  | Project Site Wide | 20m Flood Light Pole | Concept General Arrangement | Project Site Wide - 20m Flood Light Pole - Concept General Arrangement | 2026-05-25 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | TDK |  |  | Flood Light Pole | Detail |  |  |  | Pending
6105A | K124 | 0100 | E | DTL | 0002 | A | 6105AK124-0100-EDTL-0002 | Q24050972-03-0100-E-DTL-0002 |  | Project Site Wide | 6m Light Pole | Concept General Arrangement | Project Site Wide - 6m Light Pole - Concept General Arrangement | 2026-05-25 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | TDK |  |  | Light Pole | Detail |  |  |  | Pending
6105A | K124 | 0100 | E | DTL | 0003 | A | 6105AK124-0100-EDTL-0003 | Q24050972-03-0100-E-DTL-0003 |  | Project Site Wide | 20m Flood Light Pole | Foundation Concept | Project Site Wide - 20m Flood Light Pole - Foundation Concept | 2026-05-25 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | TDK |  |  | Flood Light Pole | Detail |  |  |  | Pending
6105A | K124 | 6200 | G | BOM | 0001 | A | 6105AK124-6200-GBOM-0001 | Q24050972-03-6200-G-BOM-0001 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Bill of Material : Supply, install and Commissiong | On-Site Power Supply and Transmission - Main Consumer Substation - Bill of Material : Supply, install and Commissiong |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-15 | Overall Plant | Bill of Material |  |  |  | Pending
6105A | K124 | 6242 | C | LAY | 0001 | A | 6105AK124-6242-CLAY-0001 | Q24050972-03-6242-C-LAY-0001 |  | 33/220 kV Power Station Substation | Siemens switchyard | Layout | 33/220 kV Power Station Substation - Siemens switchyard - Layout | 2026-04-16 |  | IFR - Issued for Review | Pending | 0% | CLR |  |  | Siemens switchyard | Layout |  |  |  | Pending
6105A | K124 | 6242 | C | LAY | 0002 | A | 6105AK124-6242-CLAY-0002 | Q24050972-03-6242-C-LAY-0002 | Sht. 1 of 2 | 33/220 kV Power Station Substation | Siemens switchyard | Bulk Eartworks Layout Sht.1 of 2 | 33/220 kV Power Station Substation - Siemens switchyard - Bulk Eartworks Layout Sht.1 of 2 | 2026-04-16 |  | IFR - Issued for Review | Pending | 0% | CLR |  |  | Siemens switchyard | Layout |  |  |  | Pending
6105A | K124 | 6242 | C | LAY | 0003 | A | 6105AK124-6242-CLAY-0003 | Q24050972-03-6242-C-LAY-0003 | Sht. 1 of 1 | 33/220 kV Power Station Substation | Siemens switchyard | Bulk Eartworks Layout sht 1 of 1 | 33/220 kV Power Station Substation - Siemens switchyard - Bulk Eartworks Layout sht 1 of 1 | 2026-04-16 |  | IFR - Issued for Review | Pending | 0% | CLR |  |  | Siemens switchyard | Layout |  |  |  | Pending
6105A | K124 | 6242 | C | SEC | 0001 | A | 6105AK124-6242-CSEC-0001 | Q24050972-03-6242-C-SEC-0001 | Sht. 1 of 1 | 33/220 kV Power Station Substation | Siemens switchyard | Bulk Eartworks Profile Layout sht 1 of 1 | 33/220 kV Power Station Substation - Siemens switchyard - Bulk Eartworks Profile Layout sht 1 of 1 | 2026-04-16 |  | IFR - Issued for Review | Pending | 0% | CLR |  |  | Siemens switchyard | Sections |  |  |  | Pending
6105A | K124 | 6242 | C | SEC | 0002 | A | 6105AK124-6242-CSEC-0002 | Q24050972-03-6242-C-SEC-0002 | Sht. 1 of 5 | 33/220 kV Power Station Substation | Siemens switchyard | Bulk Eartworks Profile Sections Sht 1 of 5 | 33/220 kV Power Station Substation - Siemens switchyard - Bulk Eartworks Profile Sections Sht 1 of 5 | 2026-04-16 |  | IFR - Issued for Review | Pending | 0% | CLR |  |  | Siemens switchyard | Sections |  |  |  | Pending
6105A | K124 | 6242 | C | SEC | 0003 | A | 6105AK124-6242-CSEC-0003 | Q24050972-03-6242-C-SEC-0003 | Sht. 2 of 5 | 33/220 kV Power Station Substation | Siemens switchyard | Bulk Eartworks Profile Sections Sht 2 of 5 | 33/220 kV Power Station Substation - Siemens switchyard - Bulk Eartworks Profile Sections Sht 2 of 5 | 2026-04-16 |  | IFR - Issued for Review | Pending | 0% | CLR |  |  | Siemens switchyard | Sections |  |  |  | Pending
6105A | K124 | 6242 | C | SEC | 0004 | A | 6105AK124-6242-CSEC-0004 | Q24050972-03-6242-C-SEC-0004 | Sht. 3 of 5 | 33/220 kV Power Station Substation | Siemens switchyard | Bulk Eartworks Profile Sections Sht 3 of 5 | 33/220 kV Power Station Substation - Siemens switchyard - Bulk Eartworks Profile Sections Sht 3 of 5 | 2026-04-16 |  | IFR - Issued for Review | Pending | 0% | CLR |  |  | Siemens switchyard | Sections |  |  |  | Pending
6105A | K124 | 6242 | C | SEC | 0005 | A | 6105AK124-6242-CSEC-0005 | Q24050972-03-6242-C-SEC-0005 | Sht. 4 of 5 | 33/220 kV Power Station Substation | Siemens switchyard | Bulk Eartworks Profile Sections Sht 4 of 5 | 33/220 kV Power Station Substation - Siemens switchyard - Bulk Eartworks Profile Sections Sht 4 of 5 | 2026-04-16 |  | IFR - Issued for Review | Pending | 0% | CLR |  |  | Siemens switchyard | Sections |  |  |  | Pending
6105A | K124 | 6242 | C | SEC | 0006 | A | 6105AK124-6242-CSEC-0006 | Q24050972-03-6242-C-SEC-0006 | Sht. 5 of 5 | 33/220 kV Power Station Substation | Siemens switchyard | Bulk Eartworks Profile Sections Sht 5 of 5 | 33/220 kV Power Station Substation - Siemens switchyard - Bulk Eartworks Profile Sections Sht 5 of 5 | 2026-04-16 |  | IFR - Issued for Review | Pending | 0% | CLR |  |  | Siemens switchyard | Sections |  |  |  | Pending
6105A | K124 | 6200 | E | LAY | 0002 | A | 6105AK124-6200-ELAY-0002 | Q24050972-03-6200-E-LAY-0002 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Earthing layout | On-Site Power Supply and Transmission - Main Consumer Substation - Earthing layout |  |  | RES - Reserved Placeholder | Pending | 0% | TDK |  | 2026-06-15 | Earthing for lighting | Layout |  |  |  | Pending
6105A | K124 | 6200 | E | LAY | 0003 | A | 6105AK124-6200-ELAY-0003 | Q24050972-03-6200-E-LAY-0003 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Overall Lighting Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Overall Lighting Layout |  |  | RES - Reserved Placeholder | Pending | 0% | TDK |  | 2026-06-15 | Main Consumer Intake Power Complex | Layout |  |  |  | Pending
6105A | K124 | 0100 | B | CON | 0006 | A | 6105AK124-0100-BCON-0006 | Q24050972-03-0100-B-CON-0006 |  | Project Site Wide | Notice Force Majeure - Siemens | General | Project Site Wide - Notice Force Majeure - Siemens - General |  |  | RES - Reserved Placeholder | Pending | 0% | JV |  | 2026-05-15 | Notice Force Majeure | General |  |  |  | Pending
6105A | K124 | 0100 | B | CON | 0007 | A | 6105AK124-0100-BCON-0007 | Q24050972-03-0100-B-CON-0007 |  | Project Site Wide | Notice Force Majeure - Wärtsilä | General | Project Site Wide - Notice Force Majeure - Wärtsilä - General |  |  | RES - Reserved Placeholder | Pending | 0% | JV |  | 2026-05-15 | Notice Force Majeure | General |  |  |  | Pending
6105A | K124 | 6200 | E | SCH | 0001 | A | 6105AK124-6200-ESCH-0001 | Q24050972-03-6200-E-SCH-0001 | Sht 1 of 1 | On-Site Power Supply and Transmission | Main Consumer Intake Power Complex | Cable Schedule | On-Site Power Supply and Transmission - Main Consumer Intake Power Complex - Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Main Consumer Intake Power Complex | Schedule |  |  |  | Pending
6105A | K124 | 6243 | E | SLD | 0003 | A | 6105AK124-6243-ESLD-0003 | Q24050972-03-6243-E-SLD-0003 |  | 220/33 kV Plant Main Substation | Main Consumer Substation-220kV/33kV Panel K08, K16, K29 Mains Incomers | Single Line Diagram | 220/33 kV Plant Main Substation - Main Consumer Substation-220kV/33kV Panel K08, K16, K29 Mains Incomers - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-15 | Main Consumer Plant Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0023 | A | 6105AK124-6200-ESLD-0023 | Q24050972-03-6200-E-SLD-0023 |  | On-Site Power Supply and Transmission | Main Consumer Sub Panel K15 & K18 and Emergency Gen Switchboard Panel K13 & K17 | Single Line Diagram | On-Site Power Supply and Transmission - Main Consumer Sub Panel K15 & K18 and Emergency Gen Switchboard Panel K13 & K17 - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-15 | Consumer Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0024 | A | 6105AK124-6200-ESLD-0024 | Q24050972-03-6200-E-SLD-0024 |  | On-Site Power Supply and Transmission | Consumer Substation-Panel K10-K22 - Bus Couplers | Single Line Diagram | On-Site Power Supply and Transmission - Consumer Substation-Panel K10-K22 - Bus Couplers - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-15 | Consumer Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0025 | A | 6105AK124-6200-ESLD-0025 | Q24050972-03-6200-E-SLD-0025 |  | On-Site Power Supply and Transmission | Consumer Substation-Panel K01-K04,K06,K09,K12,K14,K19,K21,K23,K27-K30 - Feeders | Single Line Diagram | On-Site Power Supply and Transmission - Consumer Substation-Panel K01-K04,K06,K09,K12,K14,K19,K21,K23,K27-K30 - Feeders - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-15 | Consumer Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0026 | A | 6105AK124-6200-ESLD-0026 | Q24050972-03-6200-E-SLD-0026 |  | On-Site Power Supply and Transmission | Consumer Substation-Panel K17 - Cable Differential | Single Line Diagram | On-Site Power Supply and Transmission - Consumer Substation-Panel K17 - Cable Differential - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-15 | Consumer Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0027 | A | 6105AK124-6200-ESLD-0027 | Q24050972-03-6200-E-SLD-0027 |  | On-Site Power Supply and Transmission | Consumer Substation-Panel K07-K25 - Capacitor Feeders | Single Line Diagram | On-Site Power Supply and Transmission - Consumer Substation-Panel K07-K25 - Capacitor Feeders - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-15 | Consumer Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0005 | A | 6105AK124-6286-ESLD-0005 | Q24050972-03-6286-E-SLD-0005 |  | Primary Crushing | Mining Substation-33kV/11kV Mining Open Pit Panel K02 & K07 and A07 & A11 | Single Line Diagram | Primary Crushing - Mining Substation-33kV/11kV Mining Open Pit Panel K02 & K07 and A07 & A11 - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-15 | Mining Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6260 | E | SLD | 0005 | A | 6105AK124-6260-ESLD-0005 | Q24050972-03-6260-E-SLD-0005 |  | Emergency Power Generation (Main Plant) | Emergency Switchroom Generators-Panel K01-K09 & K21-K29 - Generator Incomers | Single Line Diagram | Emergency Power Generation (Main Plant) - Emergency Switchroom Generators-Panel K01-K09 & K21-K29 - Generator Incomers - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-15 | Emergency Switchroom | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6260 | E | SLD | 0006 | A | 6105AK124-6260-ESLD-0006 | Q24050972-03-6260-E-SLD-0006 |  | Emergency Power Generation (Main Plant) | Emergency Switchroom Bus Coupler-Panel K15 - Bus Coupler | Single Line Diagram | Emergency Power Generation (Main Plant) - Emergency Switchroom Bus Coupler-Panel K15 - Bus Coupler - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-15 | Emergency Switchroom | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6260 | E | SLD | 0007 | A | 6105AK124-6260-ESLD-0007 | Q24050972-03-6260-E-SLD-0007 |  | Emergency Power Generation (Main Plant) | Emergency Switchroom Feeders-Panel K10-K13 & K17-K20 | Single Line Diagram | Emergency Power Generation (Main Plant) - Emergency Switchroom Feeders-Panel K10-K13 & K17-K20 - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-15 | Emergency Switchroom | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0006 | A | 6105AK124-6286-ESLD-0006 | Q24050972-03-6286-E-SLD-0006 |  | Primary Crushing | Mining 11kV Switch Room 1-Panel A02-A16 - Capacitor Feeders | Single Line Diagram | Primary Crushing - Mining 11kV Switch Room 1-Panel A02-A16 - Capacitor Feeders - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-06-15 | Bus Sections | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0007 | A | 6105AK124-6286-ESLD-0007 | Q24050972-03-6286-E-SLD-0007 |  | Primary Crushing | Mining 11kV Switch Room 1-Panel A01, A03-A06 and A12-15 & A17 Feeders | Single Line Diagram | Primary Crushing - Mining 11kV Switch Room 1-Panel A01, A03-A06 and A12-15 & A17 Feeders - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-06-15 | Bus Sections | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0008 | A | 6105AK124-6286-ESLD-0008 | Q24050972-03-6286-E-SLD-0008 |  | Primary Crushing | Mining 11kV Switch Room 1-Panel A09 Bus Section | Single Line Diagram | Primary Crushing - Mining 11kV Switch Room 1-Panel A09 Bus Section - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-06-15 | Bus Sections | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0009 | A | 6105AK124-6286-ESLD-0009 | Q24050972-03-6286-E-SLD-0009 |  | Primary Crushing | Mining 33kV Switch Room 1-Panel K04 Bus Section | Single Line Diagram | Primary Crushing - Mining 33kV Switch Room 1-Panel K04 Bus Section - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-06-15 | Bus Sections | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0010 | A | 6105AK124-6286-ESLD-0010 | Q24050972-03-6286-E-SLD-0010 |  | Primary Crushing | Mining 33kV Switch Room 1-Panel K01 & K08 Feeders | Single Line Diagram | Primary Crushing - Mining 33kV Switch Room 1-Panel K01 & K08 Feeders - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-06-15 | Bus Sections | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0011 | A | 6105AK124-6286-ESLD-0011 | Q24050972-03-6286-E-SLD-0011 |  | Primary Crushing | Mining 33kV Switch Room 1-Panel K03 & K06 Incomer Feeders | Single Line Diagram | Primary Crushing - Mining 33kV Switch Room 1-Panel K03 & K06 Incomer Feeders - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-15 | Bus Sections | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6286 | C | LAY | 0001 | 0 | 6105AK124-6286-CLAY-0001 | Q24050972-03-6286-C-LAY-0001 | Sht.1 of 1 | Primary Crushing | 33/220 kV switchyard | Bulk Eartworks Layout | Primary Crushing - 33/220 kV switchyard - Bulk Eartworks Layout - Sht.1 of 1 | 2026-04-20 | 2026-05-25 | IFC - Issued for Construction | Pending | 66.67% | CLR |  |  | 33/220 kV switchyard | Layout |  |  |  | Pending
6105A | K124 | 6286 | C | SEC | 0001 | 0 | 6105AK124-6286-CSEC-0001 | Q24050972-03-6286-C-SEC-0001 | Sht.1 of 1 | Primary Crushing | 33/220 kV switchyard | Bulk Eartworks Profile Layout | Primary Crushing - 33/220 kV switchyard - Bulk Eartworks Profile Layout - Sht.1 of 1 | 2026-02-25 | 2026-05-25 | IFC - Issued for Construction | Pending | 66.67% | CLR |  |  | Bulk Earth Works | Sections |  |  |  | Pending
6105A | K124 | 6286 | C | SEC | 0002 | 0 | 6105AK124-6286-CSEC-0002 | Q24050972-03-6286-C-SEC-0002 | Sht.1 of 3 | Primary Crushing | 33/220 kV switchyard | Bulk Eartworks Profile Sections | Primary Crushing - 33/220 kV switchyard - Bulk Eartworks Profile Sections - Sht.1 of 3 | 2026-02-25 | 2026-05-27 | IFC - Issued for Construction | Pending | 66.67% | CLR |  |  | Bulk Earth Works | Sections |  |  |  | Pending
6105A | K124 | 6286 | C | SEC | 0003 | 0 | 6105AK124-6286-CSEC-0003 | Q24050972-03-6286-C-SEC-0003 | Sht.2 of 3 | Primary Crushing | 33/220 kV switchyard | Bulk Eartworks Profile Sections | Primary Crushing - 33/220 kV switchyard - Bulk Eartworks Profile Sections - Sht.2 of 3 | 2026-02-25 | 2026-05-25 | IFC - Issued for Construction | Pending | 66.67% | CLR |  |  | Bulk Earth Works | Sections |  |  |  | Pending
6105A | K124 | 6286 | C | SEC | 0004 | 0 | 6105AK124-6286-CSEC-0004 | Q24050972-03-6286-C-SEC-0004 | Sht.3 of 3 | Primary Crushing | 33/220 kV switchyard | Bulk Eartworks Profile Sections | Primary Crushing - 33/220 kV switchyard - Bulk Eartworks Profile Sections - Sht.3 of 3 | 2026-02-25 | 2026-05-25 | IFC - Issued for Construction | Pending | 66.67% | CLR |  |  | Bulk Earth Works | Sections |  |  |  | Pending
6105A | K124 | 0000 | E | LST | 0001 | A | 6105AK124-0000-ELST-0001 | Q24050972-03-0000-E-LST-0001 |  | General | RDMC Phase 1 – Spare Parts Planning Register | List | General - RDMC Phase 1 – Spare Parts Planning Register - List |  |  | RES - Reserved Placeholder | Pending | 0% | JM |  | 2026-05-15 | Spare Parts Planning Register | List |  |  |  | Pending
6105A | K124 | 6200 | E | GAD | 0001 | A | 6105AK124-6200-EGAD-0001 | Q24050972-03-6200-E-GAD-0001 |  | On-Site Power Supply and Transmission | Main Consumer Intake Power Complex | Auxiliary Power General Arrangement | On-Site Power Supply and Transmission - Main Consumer Intake Power Complex - Auxiliary Power General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-15 | Main Consumer Intake Power Complex | General Arrangement Drawing |  |  |  | Pending
6105A | K124 | 6200 | A | STD | 0001 | A | 6105AK124-6200-ASTD-0001 | Q24050972-03-6200-A-STD-0001 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Building Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Building Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station | Building Design |  |  |  | Pending
6105A | K124 | 6200 | A | STD | 0002 | A | 6105AK124-6200-ASTD-0002 | Q24050972-03-6200-A-STD-0002 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Building Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Building Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station | Building Design |  |  |  | Pending
6105A | K124 | 6200 | A | STD | 0003 | A | 6105AK124-6200-ASTD-0003 | Q24050972-03-6200-A-STD-0003 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Building Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Building Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Control Room and Ablution Facilities | Building Design |  |  |  | Pending
6105A | K124 | 6200 | B | PHL | 0001 | A | 6105AK124-6200-BPHL-0001 | Q24050972-03-6200-B-PHL-0001 |  | On-Site Power Supply and Transmission | On-Site Power Supply and Transmission | Control Philosophy | On-Site Power Supply and Transmission - On-Site Power Supply and Transmission - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Concentrator 33 kV Main Consumer | Control Philosophy |  |  |  | Pending
6105A | K124 | 6200 | B | PHL | 0002 | A | 6105AK124-6200-BPHL-0002 | Q24050972-03-6200-B-PHL-0002 |  | On-Site Power Supply and Transmission | On-Site Power Supply and Transmission | Synchronization Philosophy | On-Site Power Supply and Transmission - On-Site Power Supply and Transmission - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Concentrator 33 kV Main Consumer | Synchronization Philosophy |  |  |  | Pending
6105A | K124 | 6200 | B | DBD | 0001 | A | 6105AK124-6200-BDBD-0001 | Q24050972-03-6200-B-DBD-0001 |  | On-Site Power Supply and Transmission | Concentrator 33 kV Main Consumer SS Project Package | Design Criteria / Basis of Design | On-Site Power Supply and Transmission - Concentrator 33 kV Main Consumer SS Project Package - Design Criteria / Basis of Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Concentrator 33 kV Main Consumer | Basis of Design |  |  |  | Pending
6105A | K124 | 6200 | B | STD | 0001 | A | 6105AK124-6200-BSTD-0001 | Q24050972-03-6200-B-STD-0001 |  | On-Site Power Supply and Transmission | Concentrator 33 kV Main Consumer SS Project Package | System Detailed Engineering Design | On-Site Power Supply and Transmission - Concentrator 33 kV Main Consumer SS Project Package - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Concentrator 33 kV Main Consumer | System Detailed Engineering Design |  |  |  | Pending
6105A | K124 | 6200 | B | SPC | 0001 | A | 6105AK124-6200-BSPC-0001 | Q24050972-03-6200-B-SPC-0001 |  | On-Site Power Supply and Transmission | Concentrator 33 kV Main Consumer SS Project Package | Functional Design Specification | On-Site Power Supply and Transmission - Concentrator 33 kV Main Consumer SS Project Package - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Concentrator 33 kV Main Consumer | Functional Design Specification |  |  |  | Pending
6105A | K124 | 6200 | C | CAL | 0001 | A | 6105AK124-6200-CCAL-0001 | Q24050972-03-6200-C-CAL-0001 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | Structure Stress Calculations and Expansion Provisions | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Structure Stress Calculations |  |  |  | Pending
6105A | K124 | 6200 | C | CAL | 0002 | A | 6105AK124-6200-CCAL-0002 | Q24050972-03-6200-C-CAL-0002 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply | Structure Stress Calculations and Expansion Provisions | On-Site Power Supply and Transmission - Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Mining Sub Station | Structure Stress Calculations |  |  |  | Pending
6105A | K124 | 6200 | C | CAL | 0003 | A | 6105AK124-6200-CCAL-0003 | Q24050972-03-6200-C-CAL-0003 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation | Structure Stress Calculations and Expansion Provisions | On-Site Power Supply and Transmission - Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV OHL Income from HV Substation | Structure Stress Calculations |  |  |  | Pending
6105A | K124 | 6200 | C | DID | 0001 | A | 6105AK124-6200-CDID-0001 | Q24050972-03-6200-C-DID-0001 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Ventilation and Air Filtration Systems Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Ventilation and Air Filtration Systems Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Ventilation and Air Filtration Systems |  |  |  | Pending
6105A | K124 | 6200 | C | FND | 0001 | A | 6105AK124-6200-CFND-0001 | Q24050972-03-6200-C-FND-0001 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Civil Foundation Design | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6200 | C | FND | 0002 | A | 6105AK124-6200-CFND-0002 | Q24050972-03-6200-C-FND-0002 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Civil Foundation Design | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6200 | C | FND | 0003 | A | 6105AK124-6200-CFND-0003 | Q24050972-03-6200-C-FND-0003 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | Plinth Design and Layout | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Plinth Design and Layout |  |  |  | Pending
6105A | K124 | 6200 | C | FND | 0004 | A | 6105AK124-6200-CFND-0004 | Q24050972-03-6200-C-FND-0004 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | Civil Foundation Design | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6200 | C | FND | 0005 | A | 6105AK124-6200-CFND-0005 | Q24050972-03-6200-C-FND-0005 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Civil Foundation Design | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6200 | C | FND | 0006 | A | 6105AK124-6200-CFND-0006 | Q24050972-03-6200-C-FND-0006 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply | Civil Foundation Design | On-Site Power Supply and Transmission - Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Mining Sub Station | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6200 | C | FND | 0007 | A | 6105AK124-6200-CFND-0007 | Q24050972-03-6200-C-FND-0007 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation | Civil Foundation Design | On-Site Power Supply and Transmission - Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV OHL Income from HV Substation | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0001 | A | 6105AK124-6200-CGAD-0001 | Q24050972-03-6200-C-GAD-0001 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Buildings and Structures GA | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0002 | A | 6105AK124-6200-CGAD-0002 | Q24050972-03-6200-C-GAD-0002 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Cables, OHL and Fibre Route GA | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Cables, OHL and Fibre Route GA |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0003 | A | 6105AK124-6200-CGAD-0003 | Q24050972-03-6200-C-GAD-0003 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Key Emergency Points and Equipment | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Key Emergency Points and Equipment |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0004 | A | 6105AK124-6200-CGAD-0004 | Q24050972-03-6200-C-GAD-0004 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Terrace Equipment GA | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0005 | A | 6105AK124-6200-CGAD-0005 | Q24050972-03-6200-C-GAD-0005 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Disposal Areas General Arrangement | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Disposal Areas |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0006 | A | 6105AK124-6200-CGAD-0006 | Q24050972-03-6200-C-GAD-0006 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Laydown Areas and Temp Buildings GA | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Laydown Areas and Temp Buildings |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0007 | A | 6105AK124-6200-CGAD-0007 | Q24050972-03-6200-C-GAD-0007 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Stormwater and Effluent System Design | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Stormwater and Effluent System |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0008 | A | 6105AK124-6200-CGAD-0008 | Q24050972-03-6200-C-GAD-0008 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Lighting Design and Layout GA | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Lighting Design and Layout |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0010 | A | 6105AK124-6200-CGAD-0010 | Q24050972-03-6200-C-GAD-0010 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Buildings and Structures GA | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0011 | A | 6105AK124-6200-CGAD-0011 | Q24050972-03-6200-C-GAD-0011 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Terrace Equipment GA | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0012 | A | 6105AK124-6200-CGAD-0012 | Q24050972-03-6200-C-GAD-0012 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Pipe Routing General Arrangement | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Pipe Routing General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | General Arrangement |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0014 | A | 6105AK124-6200-CGAD-0014 | Q24050972-03-6200-C-GAD-0014 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Roads, Pathways, Offloading Areas and Fences GA | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Offloading Areas and Fences |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0015 | A | 6105AK124-6200-CGAD-0015 | Q24050972-03-6200-C-GAD-0015 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Water Reticulation & Sewer System Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Water Reticulation & Sewer System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Water Reticulation & Sewer System |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0016 | A | 6105AK124-6200-CGAD-0016 | Q24050972-03-6200-C-GAD-0016 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Buildings and Structures GA | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0017 | A | 6105AK124-6200-CGAD-0017 | Q24050972-03-6200-C-GAD-0017 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Terrace Equipment GA | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0019 | A | 6105AK124-6200-CGAD-0019 | Q24050972-03-6200-C-GAD-0019 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Stormwater and Effluent System Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Stormwater and Effluent System |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0020 | A | 6105AK124-6200-CGAD-0020 | Q24050972-03-6200-C-GAD-0020 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Roads, Pathways, Offloading Areas and Fences GA | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Offloading Areas and Fences |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0021 | A | 6105AK124-6200-CGAD-0021 | Q24050972-03-6200-C-GAD-0021 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Water Reticulation & Sewer System Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Water Reticulation & Sewer System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Water Reticulation & Sewer System |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0022 | A | 6105AK124-6200-CGAD-0022 | Q24050972-03-6200-C-GAD-0022 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Utilities Connections and Battery Limits GA | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Utilities Connections and Battery Limits GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Utilities Connections and Battery Limits |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0023 | A | 6105AK124-6200-CGAD-0023 | Q24050972-03-6200-C-GAD-0023 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Key Emergency Points and Equipment | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Key Emergency Points and Equipment |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0024 | A | 6105AK124-6200-CGAD-0024 | Q24050972-03-6200-C-GAD-0024 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Laydown Areas and Temp Buildings GA | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Laydown Areas and Temp Buildings |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0025 | A | 6105AK124-6200-CGAD-0025 | Q24050972-03-6200-C-GAD-0025 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Stormwater and Effluent System Design | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Stormwater and Effluent System |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0026 | A | 6105AK124-6200-CGAD-0026 | Q24050972-03-6200-C-GAD-0026 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Buildings and Structures GA | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Buildings and Structures |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0027 | A | 6105AK124-6200-CGAD-0027 | Q24050972-03-6200-C-GAD-0027 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Cables, OHL and Fibre Route GA | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cables, OHL and Fibre Route |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0028 | A | 6105AK124-6200-CGAD-0028 | Q24050972-03-6200-C-GAD-0028 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Terrace Equipment GA | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Terrace Equipment |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0029 | A | 6105AK124-6200-CGAD-0029 | Q24050972-03-6200-C-GAD-0029 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Roads, Pathways, Offloading Areas and Fences GA | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Offloading Areas and Fences |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0030 | A | 6105AK124-6200-CGAD-0030 | Q24050972-03-6200-C-GAD-0030 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Buildings and Structures GA | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Buildings and Structures |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0031 | A | 6105AK124-6200-CGAD-0031 | Q24050972-03-6200-C-GAD-0031 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Cable Gantry General Arrangement | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Cable Gantry General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Sub Station Yard | Cables, OHL and Fibre Route |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0032 | A | 6105AK124-6200-CGAD-0032 | Q24050972-03-6200-C-GAD-0032 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Terrace Equipment GA | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Terrace Equipment |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0033 | A | 6105AK124-6200-CGAD-0033 | Q24050972-03-6200-C-GAD-0033 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | Terrace Equipment GA | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Terrace Equipment |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0034 | A | 6105AK124-6200-CGAD-0034 | Q24050972-03-6200-C-GAD-0034 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | Pipe Routing General Arrangement | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - Pipe Routing General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe Routing General Arrangement |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0035 | A | 6105AK124-6200-CGAD-0035 | Q24050972-03-6200-C-GAD-0035 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Lighting Design and Layout GA | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Lighting Design and Layout |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0037 | A | 6105AK124-6200-CGAD-0037 | Q24050972-03-6200-C-GAD-0037 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | Lighting Design and Layout GA | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Lighting Design and Layout |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0038 | A | 6105AK124-6200-CGAD-0038 | Q24050972-03-6200-C-GAD-0038 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | Cables, OHL and Fibre Route GA | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cables, OHL and Fibre Route |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0039 | A | 6105AK124-6200-CGAD-0039 | Q24050972-03-6200-C-GAD-0039 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Buildings and Structures GA | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Buildings and Structures |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0040 | A | 6105AK124-6200-CGAD-0040 | Q24050972-03-6200-C-GAD-0040 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Cables, OHL and Fibre Route GA | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cables, OHL and Fibre Route |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0041 | A | 6105AK124-6200-CGAD-0041 | Q24050972-03-6200-C-GAD-0041 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Terrace Equipment GA | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Terrace Equipment |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0042 | A | 6105AK124-6200-CGAD-0042 | Q24050972-03-6200-C-GAD-0042 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Laydown Areas and Temp Buildings GA | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Laydown Areas and Temp Buildings |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0043 | A | 6105AK124-6200-CGAD-0043 | Q24050972-03-6200-C-GAD-0043 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Lighting Design and Layout GA | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Lighting Design and Layout |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0044 | A | 6105AK124-6200-CGAD-0044 | Q24050972-03-6200-C-GAD-0044 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Roads, Pathways, Offloading Areas and Fences GA | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Offloading Areas and Fences |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0045 | A | 6105AK124-6200-CGAD-0045 | Q24050972-03-6200-C-GAD-0045 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Buildings and Structures GA | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Sub Station Yard | Buildings and Structures |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0046 | A | 6105AK124-6200-CGAD-0046 | Q24050972-03-6200-C-GAD-0046 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Terrace Equipment GA | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Terrace Equipment |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0047 | A | 6105AK124-6200-CGAD-0047 | Q24050972-03-6200-C-GAD-0047 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Pipe Routing General Arrangement | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Pipe Routing General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe Routing General Arrangement |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0048 | A | 6105AK124-6200-CGAD-0048 | Q24050972-03-6200-C-GAD-0048 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Roads, Pathways, Offloading Areas and Fences GA | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Offloading Areas and Fences |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0049 | A | 6105AK124-6200-CGAD-0049 | Q24050972-03-6200-C-GAD-0049 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Water Reticulation & Sewer System Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Water Reticulation & Sewer System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Water Reticulation & Sewer System |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0050 | A | 6105AK124-6200-CGAD-0050 | Q24050972-03-6200-C-GAD-0050 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Utilities Connections and Battery Limits GA | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Utilities Connections and Battery Limits GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Utilities Connections and Battery Limits |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0051 | A | 6105AK124-6200-CGAD-0051 | Q24050972-03-6200-C-GAD-0051 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Key Emergency Points and Equipment | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Key Emergency Points and Equipment |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0052 | A | 6105AK124-6200-CGAD-0052 | Q24050972-03-6200-C-GAD-0052 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Laydown Areas and Temp Buildings GA | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Laydown Areas and Temp Buildings |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0053 | A | 6105AK124-6200-CGAD-0053 | Q24050972-03-6200-C-GAD-0053 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply | Terrace Equipment GA | On-Site Power Supply and Transmission - Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Sub Station 33kV OHL Supply | Terrace Equipment |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0054 | A | 6105AK124-6200-CGAD-0054 | Q24050972-03-6200-C-GAD-0054 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation | Terrace Equipment GA | On-Site Power Supply and Transmission - Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV OHL Income from HV Substation | Terrace Equipmen |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0055 | A | 6105AK124-6200-CGAD-0055 | Q24050972-03-6200-C-GAD-0055 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Fire Detection and Suppression System | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Fire Detection and Suppression System |  |  |  | Pending
6105A | K124 | 6200 | C | MDL | 0001 | A | 6105AK124-6200-CMDL-0001 | Q24050972-03-6200-C-MDL-0001 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | 3D Designs and Drawings | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | MDL | 0002 | A | 6105AK124-6200-CMDL-0002 | Q24050972-03-6200-C-MDL-0002 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | 3D Designs and Drawings | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | MDL | 0003 | A | 6105AK124-6200-CMDL-0003 | Q24050972-03-6200-C-MDL-0003 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | 3D Designs and Drawings | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | MDL | 0004 | A | 6105AK124-6200-CMDL-0004 | Q24050972-03-6200-C-MDL-0004 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | 3D Designs and Drawings | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | MDL | 0005 | A | 6105AK124-6200-CMDL-0005 | Q24050972-03-6200-C-MDL-0005 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | 3D Designs and Drawings | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | MDL | 0006 | A | 6105AK124-6200-CMDL-0006 | Q24050972-03-6200-C-MDL-0006 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | 3D Designs and Drawings | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | MDL | 0007 | A | 6105AK124-6200-CMDL-0007 | Q24050972-03-6200-C-MDL-0007 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | 3D Designs and Drawings | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | MDL | 0008 | A | 6105AK124-6200-CMDL-0008 | Q24050972-03-6200-C-MDL-0008 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | 3D Designs and Drawings | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | MDL | 0009 | A | 6105AK124-6200-CMDL-0009 | Q24050972-03-6200-C-MDL-0009 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | 3D Designs and Drawings | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | MDL | 0010 | A | 6105AK124-6200-CMDL-0010 | Q24050972-03-6200-C-MDL-0010 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | 3D Designs and Drawings | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | MDL | 0011 | A | 6105AK124-6200-CMDL-0011 | Q24050972-03-6200-C-MDL-0011 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | 3D Designs and Drawings | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | PPL | 0001 | A | 6105AK124-6200-CPPL-0001 | Q24050972-03-6200-C-PPL-0001 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Operational & Maint Access Routes Design | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Operational & Maint Access Routes Design |  |  |  | Pending
6105A | K124 | 6200 | C | PPL | 0002 | A | 6105AK124-6200-CPPL-0002 | Q24050972-03-6200-C-PPL-0002 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Operational & Maint Access Routes Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Operational & Maint Access Routes Design |  |  |  | Pending
6105A | K124 | 6200 | C | PPL | 0003 | A | 6105AK124-6200-CPPL-0003 | Q24050972-03-6200-C-PPL-0003 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Operational & Maint Access Routes Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Operational & Maint Access Routes Design |  |  |  | Pending
6105A | K124 | 6200 | C | PPL | 0004 | A | 6105AK124-6200-CPPL-0004 | Q24050972-03-6200-C-PPL-0004 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Operational & Maint Access Routes Design | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Operational & Maint Access Routes Design |  |  |  | Pending
6105A | K124 | 6200 | C | PPL | 0005 | A | 6105AK124-6200-CPPL-0005 | Q24050972-03-6200-C-PPL-0005 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Operational & Maint Access Routes Design | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Operational & Maint Access Routes Design |  |  |  | Pending
6105A | K124 | 6200 | C | PPL | 0006 | A | 6105AK124-6200-CPPL-0006 | Q24050972-03-6200-C-PPL-0006 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Operational & Maint Access Routes Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Operational & Maint Access Routes Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0011 | A | 6105AK124-6200-CSEC-0011 | Q24050972-03-6200-C-SEC-0011 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Structural Earthing and Bonding Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Structural Earthing and Bonding Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0012 | A | 6105AK124-6200-CSEC-0012 | Q24050972-03-6200-C-SEC-0012 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Structural Earthing and Bonding Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Structural Earthing and Bonding Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0013 | A | 6105AK124-6200-CSEC-0013 | Q24050972-03-6200-C-SEC-0013 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Corrosion Prevention and Protection Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Corrosion Prevention and Protection Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0014 | A | 6105AK124-6200-CSEC-0014 | Q24050972-03-6200-C-SEC-0014 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Corrosion Prevention and Protection Design | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Corrosion Prevention and Protection Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0015 | A | 6105AK124-6200-CSEC-0015 | Q24050972-03-6200-C-SEC-0015 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Structural Earthing and Bonding Design | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Structural Earthing and Bonding Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0016 | A | 6105AK124-6200-CSEC-0016 | Q24050972-03-6200-C-SEC-0016 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | Structural Earthing and Bonding Design | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Structural Earthing and Bonding Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0017 | A | 6105AK124-6200-CSEC-0017 | Q24050972-03-6200-C-SEC-0017 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Corrosion Prevention and Protection Design | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Corrosion Prevention and Protection Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0018 | A | 6105AK124-6200-CSEC-0018 | Q24050972-03-6200-C-SEC-0018 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Structural Earthing and Bonding Design | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Structural Earthing and Bonding Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0019 | A | 6105AK124-6200-CSEC-0019 | Q24050972-03-6200-C-SEC-0019 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Corrosion Prevention and Protection Design | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Corrosion Prevention and Protection Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0020 | A | 6105AK124-6200-CSEC-0020 | Q24050972-03-6200-C-SEC-0020 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Structural Earthing and Bonding Design | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Structural Earthing and Bonding Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0021 | A | 6105AK124-6200-CSEC-0021 | Q24050972-03-6200-C-SEC-0021 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Structural Earthing and Bonding Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Structural Earthing and Bonding Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0022 | A | 6105AK124-6200-CSEC-0022 | Q24050972-03-6200-C-SEC-0022 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Corrosion Prevention and Protection Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Corrosion Prevention and Protection Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0023 | A | 6105AK124-6200-CSEC-0023 | Q24050972-03-6200-C-SEC-0023 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply | Structural Earthing and Bonding Design | On-Site Power Supply and Transmission - Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Mining Sub Station 33kV OHL Supply | Structural Earthing and Bonding Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0024 | A | 6105AK124-6200-CSEC-0024 | Q24050972-03-6200-C-SEC-0024 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation | Structural Earthing and Bonding Design | On-Site Power Supply and Transmission - Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV OHL Income from HV Substation | Structural Earthing and Bonding Design |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0025 | A | 6105AK124-6200-CSEC-0025 | Q24050972-03-6200-C-SEC-0025 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Corrosion Prevention and Protection Design | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Corrosion Prevention and Protection Design |  |  |  | Pending
6105A | K124 | 6200 | C | SHP | 0001 | A | 6105AK124-6200-CSHP-0001 | Q24050972-03-6200-C-SHP-0001 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Equipment Assembly Drawings | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Equipment Assembly Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | SHP | 0002 | A | 6105AK124-6200-CSHP-0002 | Q24050972-03-6200-C-SHP-0002 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | Equipment Assembly Drawings | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Equipment Assembly Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | SHP | 0003 | A | 6105AK124-6200-CSHP-0003 | Q24050972-03-6200-C-SHP-0003 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Equipment Assembly Drawings | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Equipment Assembly Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | SHP | 0004 | A | 6105AK124-6200-CSHP-0004 | Q24050972-03-6200-C-SHP-0004 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply | Equipment Assembly Drawings | On-Site Power Supply and Transmission - Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Mining Sub Station 33kV OHL Supply | Equipment Assembly Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | SHP | 0005 | A | 6105AK124-6200-CSHP-0005 | Q24050972-03-6200-C-SHP-0005 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation | Equipment Assembly Drawings | On-Site Power Supply and Transmission - Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV OHL Income from HV Substation | Equipment Assembly Drawings |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0001 | A | 6105AK124-6200-CSPC-0001 | Q24050972-03-6200-C-SPC-0001 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Civil Design Requirements | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Civil Design Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0002 | A | 6105AK124-6200-CSPC-0002 | Q24050972-03-6200-C-SPC-0002 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Excavation, Trenching and Compacting Design | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Excavation, Trenching and Compacting Design |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0003 | A | 6105AK124-6200-CSPC-0003 | Q24050972-03-6200-C-SPC-0003 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Concrete Construction Material Specifications | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Concrete Construction Material Specifications |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0004 | A | 6105AK124-6200-CSPC-0004 | Q24050972-03-6200-C-SPC-0004 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Civil Design Requirements | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Design Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0005 | A | 6105AK124-6200-CSPC-0005 | Q24050972-03-6200-C-SPC-0005 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Excavation, Trenching and Compacting Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Excavation, Trenching and Compacting Design |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0006 | A | 6105AK124-6200-CSPC-0006 | Q24050972-03-6200-C-SPC-0006 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Concrete Construction Material Specifications | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Concrete Construction Material Specifications |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0007 | A | 6105AK124-6200-CSPC-0007 | Q24050972-03-6200-C-SPC-0007 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Civil Design Requirements | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Design Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0008 | A | 6105AK124-6200-CSPC-0008 | Q24050972-03-6200-C-SPC-0008 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Excavation, Trenching and Compacting Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Excavation, Trenching and Compacting Design |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0009 | A | 6105AK124-6200-CSPC-0009 | Q24050972-03-6200-C-SPC-0009 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Concrete Construction Material Specifications | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Concrete Construction Material Specifications |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0010 | A | 6105AK124-6200-CSPC-0010 | Q24050972-03-6200-C-SPC-0010 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Steel Structures Corrosion Protection Specification | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Steel Structures Corrosion Protection Specification |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0011 | A | 6105AK124-6200-CSPC-0011 | Q24050972-03-6200-C-SPC-0011 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Civil Design Requirements | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Design Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0012 | A | 6105AK124-6200-CSPC-0012 | Q24050972-03-6200-C-SPC-0012 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Excavation, Trenching and Compacting Design | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Excavation, Trenching and Compacting Design |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0013 | A | 6105AK124-6200-CSPC-0013 | Q24050972-03-6200-C-SPC-0013 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Concrete Construction Material Specifications | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Concrete Construction Material Specifications |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0014 | A | 6105AK124-6200-CSPC-0014 | Q24050972-03-6200-C-SPC-0014 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Civil Design Requirements | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Design Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0015 | A | 6105AK124-6200-CSPC-0015 | Q24050972-03-6200-C-SPC-0015 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Concrete Construction Material Specifications | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Material Specifications |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0016 | A | 6105AK124-6200-CSPC-0016 | Q24050972-03-6200-C-SPC-0016 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Steel Structures Corrosion Protection Specification | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Protection Specification |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0017 | A | 6105AK124-6200-CSPC-0017 | Q24050972-03-6200-C-SPC-0017 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Civil Design Requirements | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Design Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0018 | A | 6105AK124-6200-CSPC-0018 | Q24050972-03-6200-C-SPC-0018 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Excavation, Trenching and Compacting Design | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Excavation, Trenching and Compacting Design |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0019 | A | 6105AK124-6200-CSPC-0019 | Q24050972-03-6200-C-SPC-0019 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Concrete Construction Material Specifications | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Material Specifications |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0020 | A | 6105AK124-6200-CSPC-0020 | Q24050972-03-6200-C-SPC-0020 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | Steel Structures Corrosion Protection Specification | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Protection Specification |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0021 | A | 6105AK124-6200-CSPC-0021 | Q24050972-03-6200-C-SPC-0021 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Concrete Construction Material Specifications | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Material Specifications |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0022 | A | 6105AK124-6200-CSPC-0022 | Q24050972-03-6200-C-SPC-0022 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Excavation, Trenching and Compacting Design | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Excavation, Trenching and Compacting Design |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0023 | A | 6105AK124-6200-CSPC-0023 | Q24050972-03-6200-C-SPC-0023 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | Excavation, Trenching and Compacting Design | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Excavation, Trenching and Compacting Design |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0024 | A | 6105AK124-6200-CSPC-0024 | Q24050972-03-6200-C-SPC-0024 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | Concrete Construction Material Specifications | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Material Specifications |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0025 | A | 6105AK124-6200-CSPC-0025 | Q24050972-03-6200-C-SPC-0025 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | Steel Structures Corrosion Protection Specification | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Protection Specification |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0026 | A | 6105AK124-6200-CSPC-0026 | Q24050972-03-6200-C-SPC-0026 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Concrete Construction Material Specifications | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Material Specifications |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0027 | A | 6105AK124-6200-CSPC-0027 | Q24050972-03-6200-C-SPC-0027 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Civil Design Requirements | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Design Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0028 | A | 6105AK124-6200-CSPC-0028 | Q24050972-03-6200-C-SPC-0028 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Excavation, Trenching and Compacting Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Excavation, Trenching and Compacting Design |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0029 | A | 6105AK124-6200-CSPC-0029 | Q24050972-03-6200-C-SPC-0029 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Concrete Construction Material Specifications | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Material Specifications |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0030 | A | 6105AK124-6200-CSPC-0030 | Q24050972-03-6200-C-SPC-0030 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Steel Structures Corrosion Protection Specification | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Protection Specification |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0031 | A | 6105AK124-6200-CSPC-0031 | Q24050972-03-6200-C-SPC-0031 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply | Concrete Construction Material Specifications | On-Site Power Supply and Transmission - Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Mining Sub Station 33kV OHL Supply | Material Specifications |  |  |  | Pending
6105A | K124 | 6200 | C | SPC | 0032 | A | 6105AK124-6200-CSPC-0032 | Q24050972-03-6200-C-SPC-0032 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation | Concrete Construction Material Specifications | On-Site Power Supply and Transmission - Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV OHL Income from HV Substation | Material Specifications |  |  |  | Pending
6105A | K124 | 6200 | C | SPL | 0001 | A | 6105AK124-6200-CSPL-0001 | Q24050972-03-6200-C-SPL-0001 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Pipe Fabrication and Field Installation Inspection | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Pipe Fabrication and Field Installation Inspection |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Installation Inspection |  |  |  | Pending
6105A | K124 | 6200 | C | SPL | 0002 | A | 6105AK124-6200-CSPL-0002 | Q24050972-03-6200-C-SPL-0002 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Pipe Fabrication and Field Installation Inspection | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Pipe Fabrication and Field Installation Inspection |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Installation Inspection |  |  |  | Pending
6105A | K124 | 6200 | C | SSD | 0001 | A | 6105AK124-6200-CSSD-0001 | Q24050972-03-6200-C-SSD-0001 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Steel Support Structures Design | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Steel Support Structures Design |  |  |  | Pending
6105A | K124 | 6200 | C | SSD | 0002 | A | 6105AK124-6200-CSSD-0002 | Q24050972-03-6200-C-SSD-0002 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | Steel Support Structures Design | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Steel Support Structures Design |  |  |  | Pending
6105A | K124 | 6200 | C | SSD | 0003 | A | 6105AK124-6200-CSSD-0003 | Q24050972-03-6200-C-SSD-0003 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | Steel Support Structures Design | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Steel Support Structures Design |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0001 | A | 6105AK124-6200-CSTD-0001 | Q24050972-03-6200-C-STD-0001 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Bund-wall Requirements and Design | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Bund-wall Requirements and Design |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0002 | A | 6105AK124-6200-CSTD-0002 | Q24050972-03-6200-C-STD-0002 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Civil Construction Requirements | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Civil Construction Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0003 | A | 6105AK124-6200-CSTD-0003 | Q24050972-03-6200-C-STD-0003 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Underground Pipe Route and Cable Bedding Design | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Pipe Route and Cable Bedding |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0004 | A | 6105AK124-6200-CSTD-0004 | Q24050972-03-6200-C-STD-0004 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Bund-wall Requirements and Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Bund-wall Requirements and Design |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0005 | A | 6105AK124-6200-CSTD-0005 | Q24050972-03-6200-C-STD-0005 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Civil Construction Requirements | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Construction Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0006 | A | 6105AK124-6200-CSTD-0006 | Q24050972-03-6200-C-STD-0006 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Roofing and Elevated Platforms Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Roofing and Elevated Platforms Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Roofing and Elevated Platforms Design |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0007 | A | 6105AK124-6200-CSTD-0007 | Q24050972-03-6200-C-STD-0007 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Underground Pipe Route and Cable Bedding Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe Route and Cable Bedding |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0008 | A | 6105AK124-6200-CSTD-0008 | Q24050972-03-6200-C-STD-0008 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Bund-wall Requirements and Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Bund-wall Requirements and Design |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0009 | A | 6105AK124-6200-CSTD-0009 | Q24050972-03-6200-C-STD-0009 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Civil Construction Requirements | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Construction Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0010 | A | 6105AK124-6200-CSTD-0010 | Q24050972-03-6200-C-STD-0010 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Roofing and Elevated Platforms Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Roofing and Elevated Platforms Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Roofing and Elevated Platforms Design |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0011 | A | 6105AK124-6200-CSTD-0011 | Q24050972-03-6200-C-STD-0011 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Underground Pipe Route and Cable Bedding Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe Route and Cable Bedding |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0012 | A | 6105AK124-6200-CSTD-0012 | Q24050972-03-6200-C-STD-0012 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Bund-wall Requirements and Design | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Bund-wall Requirements and Design |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0013 | A | 6105AK124-6200-CSTD-0013 | Q24050972-03-6200-C-STD-0013 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Fire Protection System Design (Civil Works) | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Fire Protection System Design |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0014 | A | 6105AK124-6200-CSTD-0014 | Q24050972-03-6200-C-STD-0014 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Civil Construction Requirements | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Construction Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0015 | A | 6105AK124-6200-CSTD-0015 | Q24050972-03-6200-C-STD-0015 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Underground Pipe Route and Cable Bedding Design | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe Route and Cable Bedding |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0016 | A | 6105AK124-6200-CSTD-0016 | Q24050972-03-6200-C-STD-0016 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Underground Pipe Route and Cable Bedding Design | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe Route and Cable Bedding |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0017 | A | 6105AK124-6200-CSTD-0017 | Q24050972-03-6200-C-STD-0017 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Civil Construction Requirements | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Construction Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0018 | A | 6105AK124-6200-CSTD-0018 | Q24050972-03-6200-C-STD-0018 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Underground Pipe Route and Cable Bedding Design | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe Route and Cable Bedding |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0019 | A | 6105AK124-6200-CSTD-0019 | Q24050972-03-6200-C-STD-0019 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | Underground Pipe Route and Cable Bedding Design | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe Route and Cable Bedding |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0020 | A | 6105AK124-6200-CSTD-0020 | Q24050972-03-6200-C-STD-0020 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Civil Construction Requirements | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Construction Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0021 | A | 6105AK124-6200-CSTD-0021 | Q24050972-03-6200-C-STD-0021 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Underground Pipe Route and Cable Bedding Design | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe Route and Cable Bedding |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0022 | A | 6105AK124-6200-CSTD-0022 | Q24050972-03-6200-C-STD-0022 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Civil Construction Requirements | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Construction Requirements |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0023 | A | 6105AK124-6200-CSTD-0023 | Q24050972-03-6200-C-STD-0023 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Roofing and Elevated Platforms Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Roofing and Elevated Platforms Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Roofing and Elevated Platforms Design |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0024 | A | 6105AK124-6200-CSTD-0024 | Q24050972-03-6200-C-STD-0024 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Underground Pipe Route and Cable Bedding Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe Route and Cable Bedding |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0025 | A | 6105AK124-6200-CSTD-0025 | Q24050972-03-6200-C-STD-0025 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Fire Protection System Design (Civil Works) | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Fire Protection System Design |  |  |  | Pending
6105A | K124 | 6200 | C | STD | 0026 | A | 6105AK124-6200-CSTD-0026 | Q24050972-03-6200-C-STD-0026 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Civil Construction Requirements | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Construction Requirements |  |  |  | Pending
6105A | K124 | 6200 | E | CAL | 0004 | A | 6105AK124-6200-ECAL-0004 | Q24050972-03-6200-E-CAL-0004 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Conductor Sag and Tension Plan | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Conductor Sag and Tension Plan |  |  |  | Pending
6105A | K124 | 6200 | E | CAL | 0005 | A | 6105AK124-6200-ECAL-0005 | Q24050972-03-6200-E-CAL-0005 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Cable and Conductor Sizing (incl Volt Drop Calcs) | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable and Conductor Sizing |  |  |  | Pending
6105A | K124 | 6200 | E | CAL | 0006 | A | 6105AK124-6200-ECAL-0006 | Q24050972-03-6200-E-CAL-0006 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Cable and Conductor Sizing (incl Volt Drop Calcs) | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable and Conductor Sizing |  |  |  | Pending
6105A | K124 | 6200 | E | CAL | 0007 | A | 6105AK124-6200-ECAL-0007 | Q24050972-03-6200-E-CAL-0007 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Impedance and Burn-off Calculations | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Impedance and Burn-off Calculations |  |  |  | Pending
6105A | K124 | 6200 | E | CAL | 0008 | A | 6105AK124-6200-ECAL-0008 | Q24050972-03-6200-E-CAL-0008 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Cable and Conductor Sizing (incl Volt Drop Calcs) | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable and Conductor Sizing |  |  |  | Pending
6105A | K124 | 6200 | E | CAL | 0009 | A | 6105AK124-6200-ECAL-0009 | Q24050972-03-6200-E-CAL-0009 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Conductor Sag and Tension Plan | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Conductor Sag and Tension Plan |  |  |  | Pending
6105A | K124 | 6200 | E | CAL | 0010 | A | 6105AK124-6200-ECAL-0010 | Q24050972-03-6200-E-CAL-0010 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Cable and Conductor Sizing (incl Volt Drop Calcs) | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable and Conductor Sizing |  |  |  | Pending
6105A | K124 | 6200 | E | CAL | 0011 | A | 6105AK124-6200-ECAL-0011 | Q24050972-03-6200-E-CAL-0011 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply | Conductor Sag and Tension Plan | On-Site Power Supply and Transmission - Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Mining Sub Station 33kV OHL Supply | Conductor Sag and Tension Plan |  |  |  | Pending
6105A | K124 | 6200 | E | CAL | 0012 | A | 6105AK124-6200-ECAL-0012 | Q24050972-03-6200-E-CAL-0012 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation | Conductor Sag and Tension Plan | On-Site Power Supply and Transmission - Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV OHL Income from HV Substation | Conductor Sag and Tension Plan |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0001 | A | 6105AK124-6200-EDIA-0001 | Q24050972-03-6200-E-DIA-0001 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0002 | A | 6105AK124-6200-EDIA-0002 | Q24050972-03-6200-E-DIA-0002 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Electrical Circuit Diagrams (Schematics) | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Electrical Circuit Diagrams |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0003 | A | 6105AK124-6200-EDIA-0003 | Q24050972-03-6200-E-DIA-0003 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | E/I Termination Schedule | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Termination Schedule |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0004 | A | 6105AK124-6200-EDIA-0004 | Q24050972-03-6200-E-DIA-0004 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0005 | A | 6105AK124-6200-EDIA-0005 | Q24050972-03-6200-E-DIA-0005 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | E/I Termination Schedule | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Termination Schedule |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0006 | A | 6105AK124-6200-EDIA-0006 | Q24050972-03-6200-E-DIA-0006 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0007 | A | 6105AK124-6200-EDIA-0007 | Q24050972-03-6200-E-DIA-0007 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | E/I Termination Schedule | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Termination Schedule |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0008 | A | 6105AK124-6200-EDIA-0008 | Q24050972-03-6200-E-DIA-0008 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Electrical Circuit Diagrams (Schematics) | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Electrical Circuit Diagrams |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0009 | A | 6105AK124-6200-EDIA-0009 | Q24050972-03-6200-E-DIA-0009 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0010 | A | 6105AK124-6200-EDIA-0010 | Q24050972-03-6200-E-DIA-0010 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | E/I Termination Schedule | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Termination Schedule |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0011 | A | 6105AK124-6200-EDIA-0011 | Q24050972-03-6200-E-DIA-0011 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0012 | A | 6105AK124-6200-EDIA-0012 | Q24050972-03-6200-E-DIA-0012 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Electrical Block Diagram | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Electrical Block Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0013 | A | 6105AK124-6200-EDIA-0013 | Q24050972-03-6200-E-DIA-0013 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Electrical Circuit Diagrams (Schematics) | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Electrical Circuit Diagrams |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0014 | A | 6105AK124-6200-EDIA-0014 | Q24050972-03-6200-E-DIA-0014 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | E/I Termination Schedule | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Termination Schedule |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0015 | A | 6105AK124-6200-EDIA-0015 | Q24050972-03-6200-E-DIA-0015 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0016 | A | 6105AK124-6200-EDIA-0016 | Q24050972-03-6200-E-DIA-0016 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Electrical Circuit Diagrams (Schematics) | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Electrical Circuit Diagrams |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0017 | A | 6105AK124-6200-EDIA-0017 | Q24050972-03-6200-E-DIA-0017 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | E/I Termination Schedule | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Termination Schedule |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0018 | A | 6105AK124-6200-EDIA-0018 | Q24050972-03-6200-E-DIA-0018 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable Block Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0019 | A | 6105AK124-6200-EDIA-0019 | Q24050972-03-6200-E-DIA-0019 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Electrical Circuit Diagrams (Schematics) | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Electrical Circuit Diagrams |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0020 | A | 6105AK124-6200-EDIA-0020 | Q24050972-03-6200-E-DIA-0020 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | E/I Termination Schedule | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Termination Schedule |  |  |  | Pending
6105A | K124 | 6200 | E | DST | 0002 | A | 6105AK124-6200-EDST-0002 | Q24050972-07-6200-E-DST-0002 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Equipment Register and Technical Specifications | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | DST | 0003 | A | 6105AK124-6200-EDST-0003 | Q24050972-07-6200-E-DST-0003 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Equipment Register and Technical Specifications | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | DST | 0004 | A | 6105AK124-6200-EDST-0004 | Q24050972-07-6200-E-DST-0004 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Equipment Register and Technical Specifications | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | DST | 0005 | A | 6105AK124-6200-EDST-0005 | Q24050972-07-6200-E-DST-0005 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Equipment Register and Technical Specifications | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | DST | 0006 | A | 6105AK124-6200-EDST-0006 | Q24050972-07-6200-E-DST-0006 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Equipment Register and Technical Specifications | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | DST | 0007 | A | 6105AK124-6200-EDST-0007 | Q24050972-07-6200-E-DST-0007 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Equipment Register and Technical Specifications | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | DST | 0008 | A | 6105AK124-6200-EDST-0008 | Q24050972-07-6200-E-DST-0008 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply | Equipment Register and Technical Specifications | On-Site Power Supply and Transmission - Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Mining Sub Station 33kV OHL Supply | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | DST | 0009 | A | 6105AK124-6200-EDST-0009 | Q24050972-07-6200-E-DST-0009 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation | Equipment Register and Technical Specifications | On-Site Power Supply and Transmission - Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV OHL Income from HV Substation | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | DST | 0010 | A | 6105AK124-6200-EDST-0010 | Q24050972-07-6200-E-DST-0010 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Equipment Register and Technical Specifications | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | EQL | 0001 | A | 6105AK124-6200-EEQL-0001 | Q24050972-07-6200-E-EQL-0001 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Electrical Equipment Load Register | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Electrical Equipment Load Register |  |  |  | Pending
6105A | K124 | 6200 | E | EQL | 0002 | A | 6105AK124-6200-EEQL-0002 | Q24050972-07-6200-E-EQL-0002 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Electrical Equipment Load Register | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Electrical Equipment Load Register |  |  |  | Pending
6105A | K124 | 6200 | E | LAY | 0004 | A | 6105AK124-6200-ELAY-0004 | Q24050972-03-6200-E-LAY-0004 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Control Room Power and Earthing Design | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Control Room Power and Earthing Design |  |  |  | Pending
6105A | K124 | 6200 | E | LAY | 0005 | A | 6105AK124-6200-ELAY-0005 | Q24050972-03-6200-E-LAY-0005 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Control Room Power and Earthing Design | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Control Room Power and Earthing Design |  |  |  | Pending
6105A | K124 | 6200 | E | QRA | 0001 | A | 6105AK124-6200-EQRA-0001 | Q24050972-03-6200-E-QRA-0001 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Lightning Protection Study and Risk Assessment | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Lightning Protection Study and Risk Assessment |  |  |  | Pending
6105A | K124 | 6200 | E | QRA | 0002 | A | 6105AK124-6200-EQRA-0002 | Q24050972-03-6200-E-QRA-0002 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Risk Assessment: Electrical Hazards | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Risk Assessment |  |  |  | Pending
6105A | K124 | 6200 | E | QRA | 0003 | A | 6105AK124-6200-EQRA-0003 | Q24050972-03-6200-E-QRA-0003 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Lightning Protection Study and Risk Assessment | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Lightning Protection Study and Risk Assessment |  |  |  | Pending
6105A | K124 | 6200 | E | QRA | 0004 | A | 6105AK124-6200-EQRA-0004 | Q24050972-03-6200-E-QRA-0004 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Lightning Protection Study and Risk Assessment | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Lightning Protection Study and Risk Assessment |  |  |  | Pending
6105A | K124 | 6200 | E | QRA | 0005 | A | 6105AK124-6200-EQRA-0005 | Q24050972-03-6200-E-QRA-0005 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply | Risk Assessment: Electrical Hazards | On-Site Power Supply and Transmission - Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Mining Sub Station 33kV OHL Supply | Risk Assessment |  |  |  | Pending
6105A | K124 | 6200 | E | QRA | 0006 | A | 6105AK124-6200-EQRA-0006 | Q24050972-03-6200-E-QRA-0006 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation | Risk Assessment: Electrical Hazards | On-Site Power Supply and Transmission - Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV OHL Income from HV Substation | Risk Assessment |  |  |  | Pending
6105A | K124 | 6200 | E | QRA | 0007 | A | 6105AK124-6200-EQRA-0007 | Q24050972-03-6200-E-QRA-0007 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Risk Assessment: Electrical Hazards | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Risk Assessment |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0028 | A | 6105AK124-6200-ESLD-0028 | Q24050972-03-6200-E-SLD-0028 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Electrical Single Line Diagram | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0029 | A | 6105AK124-6200-ESLD-0029 | Q24050972-03-6200-E-SLD-0029 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Electrical Single Line Diagram | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SPC | 0001 | A | 6105AK124-6200-ESPC-0001 | Q24050972-03-6200-E-SPC-0001 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Cable and Conductor Specifications | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable and Conductor Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | SPC | 0002 | A | 6105AK124-6200-ESPC-0002 | Q24050972-03-6200-E-SPC-0002 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Cable and Conductor Specifications | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable and Conductor Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | SPC | 0003 | A | 6105AK124-6200-ESPC-0003 | Q24050972-03-6200-E-SPC-0003 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Lighting and Luminaire Design | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Lighting and Luminaire Design |  |  |  | Pending
6105A | K124 | 6200 | E | SPC | 0004 | A | 6105AK124-6200-ESPC-0004 | Q24050972-03-6200-E-SPC-0004 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Cable Termination Specifications | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable Termination Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | SPC | 0005 | A | 6105AK124-6200-ESPC-0005 | Q24050972-03-6200-E-SPC-0005 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Cable and Conductor Specifications | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable and Conductor Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | SPC | 0006 | A | 6105AK124-6200-ESPC-0006 | Q24050972-03-6200-E-SPC-0006 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Lighting and Luminaire Design | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Lighting and Luminaire Design |  |  |  | Pending
6105A | K124 | 6200 | E | SPC | 0007 | A | 6105AK124-6200-ESPC-0007 | Q24050972-03-6200-E-SPC-0007 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Cable Termination Specifications | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Cable Termination Specifications |  |  |  | Pending
6105A | K124 | 6200 | E | SPC | 0008 | A | 6105AK124-6200-ESPC-0008 | Q24050972-03-6200-E-SPC-0008 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Lighting and Luminaire Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Lighting and Luminaire Design |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0001 | A | 6105AK124-6200-ESTD-0001 | Q24050972-03-6200-E-STD-0001 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Electrical Equipment Installation Requirements | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Installation Requirements |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0002 | A | 6105AK124-6200-ESTD-0002 | Q24050972-03-6200-E-STD-0002 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Hazardous Area Classification | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Hazardous Area Classification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Hazardous Area Classification |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0003 | A | 6105AK124-6200-ESTD-0003 | Q24050972-03-6200-E-STD-0003 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Thermal Management and Fire Prevention Design | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Thermal Management and Fire Prevention Design | Thermal Management and Fire Prevention Design | Thermal Management and Fire Prevention Design |  | Pending
6105A | K124 | 6200 | E | STD | 0004 | A | 6105AK124-6200-ESTD-0004 | Q24050972-03-6200-E-STD-0004 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Thermal Management and Fire Prevention Design | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Thermal Management and Fire Prevention Design |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0005 | A | 6105AK124-6200-ESTD-0005 | Q24050972-03-6200-E-STD-0005 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Electrical Equipment Installation Requirements | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Installation Requirements |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0006 | A | 6105AK124-6200-ESTD-0006 | Q24050972-03-6200-E-STD-0006 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Electrical Design Standards | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Electrical Design Standards |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0007 | A | 6105AK124-6200-ESTD-0007 | Q24050972-03-6200-E-STD-0007 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Thermal Management and Fire Prevention Design | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Thermal Management and Fire Prevention Design |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0008 | A | 6105AK124-6200-ESTD-0008 | Q24050972-03-6200-E-STD-0008 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Earth Map and Bonding Design | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Earth Map and Bonding Design |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0009 | A | 6105AK124-6200-ESTD-0009 | Q24050972-03-6200-E-STD-0009 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Electrical Design Standards | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Electrical Design Standards |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0010 | A | 6105AK124-6200-ESTD-0010 | Q24050972-03-6200-E-STD-0010 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Electrical Equipment Installation Requirements | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Installation Requirements |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0011 | A | 6105AK124-6200-ESTD-0011 | Q24050972-03-6200-E-STD-0011 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Earth Map and Bonding Design | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Earth Map and Bonding Design |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0012 | A | 6105AK124-6200-ESTD-0012 | Q24050972-03-6200-E-STD-0012 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Electrical Design Standards | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Electrical Design Standards |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0013 | A | 6105AK124-6200-ESTD-0013 | Q24050972-03-6200-E-STD-0013 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Earth Map and Bonding Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Earth Map and Bonding Design |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0014 | A | 6105AK124-6200-ESTD-0014 | Q24050972-03-6200-E-STD-0014 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Electrical Design Standards | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Electrical Design Standards |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0015 | A | 6105AK124-6200-ESTD-0015 | Q24050972-03-6200-E-STD-0015 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply | Electrical Equipment Installation Requirements | On-Site Power Supply and Transmission - Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Mining Sub Station 33kV OHL Supply | Installation Requirements |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0016 | A | 6105AK124-6200-ESTD-0016 | Q24050972-03-6200-E-STD-0016 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply | Electrical Design Standards | On-Site Power Supply and Transmission - Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Mining Sub Station 33kV OHL Supply | Electrical Design Standards |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0017 | A | 6105AK124-6200-ESTD-0017 | Q24050972-03-6200-E-STD-0017 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation | Electrical Equipment Installation Requirements | On-Site Power Supply and Transmission - Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV OHL Income from HV Substation | Installation Requirements |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0018 | A | 6105AK124-6200-ESTD-0018 | Q24050972-03-6200-E-STD-0018 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation | Electrical Design Standards | On-Site Power Supply and Transmission - Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV OHL Income from HV Substation | Electrical Design Standards |  |  |  | Pending
6105A | K124 | 6200 | E | STD | 0019 | A | 6105AK124-6200-ESTD-0019 | Q24050972-03-6200-E-STD-0019 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Thermal Management and Fire Prevention Design | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Thermal Management and Fire Prevention Design |  |  |  | Pending
6105A | K124 | 6200 | F | DIA | 0001 | A | 6105AK124-6200-FDIA-0001 | Q24050972-03-6200-F-DIA-0001 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Control Network Architecture Design | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Control Network Architecture Design |  |  |  | Pending
6105A | K124 | 6200 | F | DIA | 0002 | A | 6105AK124-6200-FDIA-0002 | Q24050972-03-6200-F-DIA-0002 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Interface Panel and I/O Schematics | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Interface Panel and I/O Schematics |  |  |  | Pending
6105A | K124 | 6200 | F | DIA | 0003 | A | 6105AK124-6200-FDIA-0003 | Q24050972-03-6200-F-DIA-0003 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Control Network Architecture Design | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Control Network Architecture Design |  |  |  | Pending
6105A | K124 | 6200 | F | DIA | 0004 | A | 6105AK124-6200-FDIA-0004 | Q24050972-03-6200-F-DIA-0004 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Control Network Communication Design | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Control Network Architecture Design |  |  |  | Pending
6105A | K124 | 6200 | F | DIA | 0005 | A | 6105AK124-6200-FDIA-0005 | Q24050972-03-6200-F-DIA-0005 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Emergency Shutdown System Design | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Emergency Shutdown System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Emergency Shutdown System Design |  |  |  | Pending
6105A | K124 | 6200 | F | DBD | 0001 | A | 6105AK124-6200-FDBD-0001 | Q24050972-03-6200-F-DBD-0001 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Control System Configuration | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Control System Configuration |  |  |  | Pending
6105A | K124 | 6200 | F | NAR | 0001 | A | 6105AK124-6200-FNAR-0001 | Q24050972-03-6200-F-NAR-0001 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Control System Control Narrative & Interlock Design | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Control Narrative & Interlock Design |  |  |  | Pending
6105A | K124 | 6200 | F | NAR | 0002 | A | 6105AK124-6200-FNAR-0002 | Q24050972-03-6200-F-NAR-0002 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Emergency Shutdown System Control Narrative | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Emergency Shutdown System |  |  |  | Pending
6105A | K124 | 6200 | I | CAL | 0001 | A | 6105AK124-6200-ICAL-0001 | Q24050972-03-6200-I-CAL-0001 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Instrument Sizing and Specification Sheets | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Instrument Sizing and Specification Sheets |  |  |  | Pending
6105A | K124 | 6200 | I | CAL | 0002 | A | 6105AK124-6200-ICAL-0002 | Q24050972-03-6200-I-CAL-0002 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Hazardous Area Classification Design and Calculations | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Hazardous Area Classification Design and Calculations |  |  |  | Pending
6105A | K124 | 6200 | I | CAL | 0003 | A | 6105AK124-6200-ICAL-0003 | Q24050972-03-6200-I-CAL-0003 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Instrument Sizing and Specification Sheets | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Instrument Sizing and Specification Sheets |  |  |  | Pending
6105A | K124 | 6200 | I | DIA | 0001 | A | 6105AK124-6200-IDIA-0001 | Q24050972-03-6200-I-DIA-0001 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Smoke and Fire Detection System Design | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Smoke and Fire Detection System |  |  |  | Pending
6105A | K124 | 6200 | I | DIA | 0002 | A | 6105AK124-6200-IDIA-0002 | Q24050972-03-6200-I-DIA-0002 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Confined Space Protection System Design | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Confined Space Protection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Confined Space Protection System |  |  |  | Pending
6105A | K124 | 6200 | I | DIA | 0003 | A | 6105AK124-6200-IDIA-0003 | Q24050972-03-6200-I-DIA-0003 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | Closed Circuit Television (CCTV) Design | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - Closed Circuit Television (CCTV) Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Closed Circuit Television (CCTV) Design |  |  |  | Pending
6105A | K124 | 6200 | I | DIA | 0004 | A | 6105AK124-6200-IDIA-0004 | Q24050972-03-6200-I-DIA-0004 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Smoke and Fire Detection System Design | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Smoke and Fire Detection System |  |  |  | Pending
6105A | K124 | 6200 | I | HAC | 0001 | A | 6105AK124-6200-IHAC-0001 | Q24050972-03-6200-I-HAC-0001 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Process Safety Design Review (HAZOP & LOPA) | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Process Safety Design Review |  |  |  | Pending
6105A | K124 | 6200 | I | ITD | 0001 | A | 6105AK124-6200-IITD-0001 | Q24050972-03-6200-I-ITD-0001 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Instrument Wiring Loop Diagrams and Cable Schedule | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6200 | I | LST | 0001 | A | 6105AK124-6200-ILST-0001 | Q24050972-03-6200-I-LST-0001 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Instrumentation Equipment Tag Register | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6200 | I | LST | 0002 | A | 6105AK124-6200-ILST-0002 | Q24050972-03-6200-I-LST-0002 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Equipment Alarm and Trip Level Register | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Alarm and Trip Level Register |  |  |  | Pending
6105A | K124 | 6200 | I | LST | 0003 | A | 6105AK124-6200-ILST-0003 | Q24050972-03-6200-I-LST-0003 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Equipment Alarm and Trip Level Register | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Alarm and Trip Level Register |  |  |  | Pending
6105A | K124 | 6200 | I | LST | 0004 | A | 6105AK124-6200-ILST-0004 | Q24050972-03-6200-I-LST-0004 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Instrumentation Equipment Tag Register | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6200 | I | PID | 0001 | A | 6105AK124-6200-IPID-0001 | Q24050972-03-6200-I-PID-0001 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Pipe & Instrument Diagrams | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe & Instrument Diagrams |  |  |  | Pending
6105A | K124 | 6200 | I | QRA | 0001 | A | 6105AK124-6200-IQRA-0001 | Q24050972-03-6200-I-QRA-0001 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Risk Assessment: Fire and Explosions | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Risk Assessment |  |  |  | Pending
6105A | K124 | 6200 | I | QRA | 0002 | A | 6105AK124-6200-IQRA-0002 | Q24050972-03-6200-I-QRA-0002 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Risk Assessment: Fire and Explosions | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Risk Assessment |  |  |  | Pending
6105A | K124 | 6200 | I | SPC | 0001 | A | 6105AK124-6200-ISPC-0001 | Q24050972-03-6200-I-SPC-0001 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Automated Isolation Valve Specification | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Valve Specification |  |  |  | Pending
6105A | K124 | 6200 | I | SPC | 0002 | A | 6105AK124-6200-ISPC-0002 | Q24050972-03-6200-I-SPC-0002 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Junction Box and Interface Cabinet Design | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Junction Box and Interface Cabinet Design |  |  |  | Pending
6105A | K124 | 6200 | M | CAL | 0001 | A | 6105AK124-6200-MCAL-0001 | Q24050972-03-6200-M-CAL-0001 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Piping Pressure Drop Calculations | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Piping Pressure Drop Calculations |  |  |  | Pending
6105A | K124 | 6200 | M | CAL | 0002 | A | 6105AK124-6200-MCAL-0002 | Q24050972-03-6200-M-CAL-0002 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Piping Pressure Drop Calculations | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Piping Pressure Drop Calculations |  |  |  | Pending
6105A | K124 | 6200 | M | CAL | 0003 | A | 6105AK124-6200-MCAL-0003 | Q24050972-03-6200-M-CAL-0003 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Vessel and Structure Design with Stress Analysis Calcs | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Vessel and Structure Design |  |  |  | Pending
6105A | K124 | 6200 | M | CAL | 0004 | A | 6105AK124-6200-MCAL-0004 | Q24050972-03-6200-M-CAL-0004 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Piping Pressure Drop Calculations | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Piping Pressure Drop Calculations |  |  |  | Pending
6105A | K124 | 6200 | M | CAL | 0005 | A | 6105AK124-6200-MCAL-0005 | Q24050972-03-6200-M-CAL-0005 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply | Vessel and Structure Design with Stress Analysis Calcs | On-Site Power Supply and Transmission - Transfer Bus Gantry for 33kV Mining Sub Station 33kV OHL Supply - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Mining Sub Station 33kV OHL Supply | Vessel and Structure Design |  |  |  | Pending
6105A | K124 | 6200 | M | CAL | 0006 | A | 6105AK124-6200-MCAL-0006 | Q24050972-03-6200-M-CAL-0006 |  | On-Site Power Supply and Transmission | Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation | Vessel and Structure Design with Stress Analysis Calcs | On-Site Power Supply and Transmission - Transfer Bus Gantry Termination for 33kV OHL Income from HV Substation - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV OHL Income from HV Substation | Vessel and Structure Design |  |  |  | Pending
6105A | K124 | 6200 | M | CAL | 0007 | A | 6105AK124-6200-MCAL-0007 | Q24050972-03-6200-M-CAL-0007 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Piping Pressure Drop Calculations | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Piping Pressure Drop Calculations |  |  |  | Pending
6105A | K124 | 6200 | M | DST | 0001 | A | 6105AK124-6200-MDST-0001 | Q24050972-03-6200-M-DST-0001 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Pressure Relief Devices Design and Specification | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pressure Relief Devices Design and Specification |  |  |  | Pending
6105A | K124 | 6200 | M | DST | 0002 | A | 6105AK124-6200-MDST-0002 | Q24050972-03-6200-M-DST-0002 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Pressure Relief Devices Design and Specification | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pressure Relief Devices Design and Specification |  |  |  | Pending
6105A | K124 | 6200 | M | EQL | 0001 | A | 6105AK124-6200-MEQL-0001 | Q24050972-03-6200-M-EQL-0001 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Mechanical Equipment Register with Specifications | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Mechanical Equipment Register with Specifications |  |  |  | Pending
6105A | K124 | 6200 | M | EQL | 0004 | A | 6105AK124-6200-MEQL-0004 | Q24050972-03-6200-M-EQL-0004 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Mechanical Equipment Register with Specifications | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Mechanical Equipment Register with Specifications |  |  |  | Pending
6105A | K124 | 6200 | M | EQL | 0005 | A | 6105AK124-6200-MEQL-0005 | Q24050972-03-6200-M-EQL-0005 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Mechanical Equipment Register with Specifications | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Mechanical Equipment Register with Specifications |  |  |  | Pending
6105A | K124 | 6200 | M | ISO | 0001 | A | 6105AK124-6200-MISO-0001 | Q24050972-03-6200-M-ISO-0001 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Piping Isometric Design and Layouts | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Piping Isometric Design and Layouts |  |  |  | Pending
6105A | K124 | 6200 | M | ISO | 0002 | A | 6105AK124-6200-MISO-0002 | Q24050972-03-6200-M-ISO-0002 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Piping Isometric Design and Layouts | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Piping Isometric Design and Layouts |  |  |  | Pending
6105A | K124 | 6200 | M | ISO | 0003 | A | 6105AK124-6200-MISO-0003 | Q24050972-03-6200-M-ISO-0003 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Piping Isometric Design and Layouts | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Piping Isometric Design and Layouts |  |  |  | Pending
6105A | K124 | 6200 | M | ISO | 0004 | A | 6105AK124-6200-MISO-0004 | Q24050972-03-6200-M-ISO-0004 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Piping Isometric Design and Layouts | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Piping Isometric Design and Layouts |  |  |  | Pending
6105A | K124 | 6200 | M | PRC | 0001 | A | 6105AK124-6200-MPRC-0001 | Q24050972-03-6200-M-PRC-0001 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Rigging Study and Lifting Equipment Design | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Study and Lifting Equipment Design |  |  |  | Pending
6105A | K124 | 6200 | M | PRC | 0002 | A | 6105AK124-6200-MPRC-0002 | Q24050972-03-6200-M-PRC-0002 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Rigging Study and Lifting Equipment Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Study and Lifting Equipment Design |  |  |  | Pending
6105A | K124 | 6200 | M | PRC | 0003 | A | 6105AK124-6200-MPRC-0003 | Q24050972-03-6200-M-PRC-0003 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Fastener Specification and Torque Procedures | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Specification and Torque Procedures |  |  |  | Pending
6105A | K124 | 6200 | M | PRC | 0004 | A | 6105AK124-6200-MPRC-0004 | Q24050972-03-6200-M-PRC-0004 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Fastener Specification and Torque Procedures | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Specification and Torque Procedures |  |  |  | Pending
6105A | K124 | 6200 | M | PRC | 0005 | A | 6105AK124-6200-MPRC-0005 | Q24050972-03-6200-M-PRC-0005 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | Rigging Study and Lifting Equipment Design | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Study and Lifting Equipment Design |  |  |  | Pending
6105A | K124 | 6200 | M | PRC | 0006 | A | 6105AK124-6200-MPRC-0006 | Q24050972-03-6200-M-PRC-0006 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Rigging Study and Lifting Equipment Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Study and Lifting Equipment Design |  |  |  | Pending
6105A | K124 | 6200 | M | PRC | 0007 | A | 6105AK124-6200-MPRC-0007 | Q24050972-03-6200-M-PRC-0007 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Fastener Specification and Torque Procedures | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Specification and Torque Procedures |  |  |  | Pending
6105A | K124 | 6200 | M | PSP | 0001 | A | 6105AK124-6200-MPSP-0001 | Q24050972-03-6200-M-PSP-0001 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Pipe and Cable Support Racks Design | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe and Cable Support Racks Design |  |  |  | Pending
6105A | K124 | 6200 | M | PSP | 0002 | A | 6105AK124-6200-MPSP-0002 | Q24050972-03-6200-M-PSP-0002 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | Pipe and Cable Support Racks Design | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe and Cable Support Racks Design |  |  |  | Pending
6105A | K124 | 6200 | M | PSP | 0003 | A | 6105AK124-6200-MPSP-0003 | Q24050972-03-6200-M-PSP-0003 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Pipe and Cable Support Racks Design | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pipe and Cable Support Racks Design |  |  |  | Pending
6105A | K124 | 6200 | M | QAD | 0001 | A | 6105AK124-6200-MQAD-0001 | Q24050972-03-6200-M-QAD-0001 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Fabrication Inspection QC Pack (Incl. NDT) | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Fabrication Inspection |  |  |  | Pending
6105A | K124 | 6200 | M | QAD | 0002 | A | 6105AK124-6200-MQAD-0002 | Q24050972-03-6200-M-QAD-0002 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | Fabrication Inspection QC Pack (Incl. NDT) | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Fabrication Inspection |  |  |  | Pending
6105A | K124 | 6200 | M | QAD | 0003 | A | 6105AK124-6200-MQAD-0003 | Q24050972-03-6200-M-QAD-0003 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Fabrication Inspection QC Pack (Incl. NDT) | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Fabrication Inspection |  |  |  | Pending
6105A | K124 | 6200 | M | QAD | 0004 | A | 6105AK124-6200-MQAD-0004 | Q24050972-03-6200-M-QAD-0004 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Fabrication Inspection QC Pack (Incl. NDT) | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Fabrication Inspection |  |  |  | Pending
6105A | K124 | 6200 | M | SHP | 0001 | A | 6105AK124-6200-MSHP-0001 | Q24050972-03-6200-M-SHP-0001 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | Equipment Fabrication Drawings | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - Equipment Fabrication Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Fabrication Drawings |  |  |  | Pending
6105A | K124 | 6200 | M | SPC | 0001 | A | 6105AK124-6200-MSPC-0001 | Q24050972-03-6200-M-SPC-0001 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Manual Isolation Valve Design Specification | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Manual Isolation Valve Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Valve Design Specification |  |  |  | Pending
6105A | K124 | 6200 | M | SPC | 0004 | A | 6105AK124-6200-MSPC-0004 | Q24050972-03-6200-M-SPC-0004 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Gasket Schedule and Material Specification | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Gasket Schedule and Material Specification |  |  |  | Pending
6105A | K124 | 6200 | M | SPC | 0005 | A | 6105AK124-6200-MSPC-0005 | Q24050972-03-6200-M-SPC-0005 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Pump Design and Specifications | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Pump Design and Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Pump Design and Specifications |  |  |  | Pending
6105A | K124 | 6200 | M | SPC | 0006 | A | 6105AK124-6200-MSPC-0006 | Q24050972-03-6200-M-SPC-0006 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Lifting and Crawl Beam Design Specification | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Lifting and Crawl Beam Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Lifting and Crawl Beam Design Specification |  |  |  | Pending
6105A | K124 | 6200 | M | SPC | 0007 | A | 6105AK124-6200-MSPC-0007 | Q24050972-03-6200-M-SPC-0007 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Material Selection and Verification Specification | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Material Selection and Verification Specification |  |  |  | Pending
6105A | K124 | 6200 | M | SPC | 0008 | A | 6105AK124-6200-MSPC-0008 | Q24050972-03-6200-M-SPC-0008 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Rotating Equipment Alignment Specifications | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Rotating Equipment Alignment Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Alignment Specifications |  |  |  | Pending
6105A | K124 | 6200 | M | SPC | 0009 | A | 6105AK124-6200-MSPC-0009 | Q24050972-03-6200-M-SPC-0009 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Drive Coupling and Connector Design Specification | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Drive Coupling and Connector Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Drive Coupling and Connector Design Specification |  |  |  | Pending
6105A | K124 | 6200 | M | SPC | 0010 | A | 6105AK124-6200-MSPC-0010 | Q24050972-03-6200-M-SPC-0010 |  | On-Site Power Supply and Transmission | Cable Racks and Trays for Main Consumer Sub Station Yard | Material Selection and Verification Specification | On-Site Power Supply and Transmission - Cable Racks and Trays for Main Consumer Sub Station Yard - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Material Selection and Verification Specification |  |  |  | Pending
6105A | K124 | 6200 | M | SPC | 0011 | A | 6105AK124-6200-MSPC-0011 | Q24050972-03-6200-M-SPC-0011 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Manual Isolation Valve Design Specification | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Manual Isolation Valve Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Manual Isolation Valve Design |  |  |  | Pending
6105A | K124 | 6200 | M | SPC | 0014 | A | 6105AK124-6200-MSPC-0014 | Q24050972-03-6200-M-SPC-0014 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Gasket Schedule and Material Specification | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Gasket Schedule and Material Specification |  |  |  | Pending
6105A | K124 | 6200 | M | SPC | 0015 | A | 6105AK124-6200-MSPC-0015 | Q24050972-03-6200-M-SPC-0015 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Material Selection and Verification Specification | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Material Selection and Verification Specification |  |  |  | Pending
6105A | K124 | 6200 | M | SPC | 0016 | A | 6105AK124-6200-MSPC-0016 | Q24050972-03-6200-M-SPC-0016 |  | On-Site Power Supply and Transmission | Fire Protection and Detection System for Main Consumer Sub Station Yard | Gasket Schedule and Material Specification | On-Site Power Supply and Transmission - Fire Protection and Detection System for Main Consumer Sub Station Yard - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Gasket Schedule and Material Specification |  |  |  | Pending
6105A | K124 | 6200 | M | STD | 0001 | A | 6105AK124-6200-MSTD-0001 | Q24050972-03-6200-M-STD-0001 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Diesel Fuel Handling and Storage Design | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Diesel Fuel Handling and Storage Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Fuel Handling and Storage Design |  |  |  | Pending
6105A | K124 | 6200 | T | RPT | 0001 | A | 6105AK124-6200-TRPT-0001 | Q24050972-03-6200-T-RPT-0001 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Site Surveying & Geotechnical Report | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Site Surveying & Geotechnical Report |  |  |  | Pending
6105A | K124 | 6200 | T | RPT | 0002 | A | 6105AK124-6200-TRPT-0002 | Q24050972-03-6200-T-RPT-0002 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Site Surveying & Geotechnical Report | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Site Surveying & Geotechnical Report |  |  |  | Pending
6105A | K124 | 6200 | T | RPT | 0003 | A | 6105AK124-6200-TRPT-0003 | Q24050972-03-6200-T-RPT-0003 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Site Surveying & Geotechnical Report | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Site Surveying & Geotechnical Report |  |  |  | Pending
6105A | K124 | 6200 | T | RPT | 0004 | A | 6105AK124-6200-TRPT-0004 | Q24050972-03-6200-T-RPT-0004 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Site Surveying & Geotechnical Report | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Site Surveying & Geotechnical Report |  |  |  | Pending
6105A | K124 | 6200 | T | RPT | 0005 | A | 6105AK124-6200-TRPT-0005 | Q24050972-03-6200-T-RPT-0005 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | Site Surveying & Geotechnical Report | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Site Surveying & Geotechnical Report |  |  |  | Pending
6105A | K124 | 6200 | T | RPT | 0006 | A | 6105AK124-6200-TRPT-0006 | Q24050972-03-6200-T-RPT-0006 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Site Surveying & Geotechnical Report | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Site Surveying & Geotechnical Report |  |  |  | Pending
6105A | K124 | 6200 | T | SPC | 0001 | A | 6105AK124-6200-TSPC-0001 | Q24050972-03-6200-T-SPC-0001 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Civil Design and Requirements | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Design and Requirements |  |  |  | Pending
6105A | K124 | 6200 | T | SPC | 0002 | A | 6105AK124-6200-TSPC-0002 | Q24050972-03-6200-T-SPC-0002 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Civil Design and Requirements | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Design and Requirements |  |  |  | Pending
6105A | K124 | 6200 | T | SPC | 0003 | A | 6105AK124-6200-TSPC-0003 | Q24050972-03-6200-T-SPC-0003 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Civil Design and Requirements | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Design and Requirements |  |  |  | Pending
6105A | K124 | 6200 | T | SPC | 0004 | A | 6105AK124-6200-TSPC-0004 | Q24050972-03-6200-T-SPC-0004 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Civil Design and Requirements | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Design and Requirements |  |  |  | Pending
6105A | K124 | 6200 | T | SPC | 0005 | A | 6105AK124-6200-TSPC-0005 | Q24050972-03-6200-T-SPC-0005 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Civil Design and Requirements | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Design and Requirements |  |  |  | Pending
6105A | K124 | 6200 | T | SPC | 0006 | A | 6105AK124-6200-TSPC-0006 | Q24050972-03-6200-T-SPC-0006 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Civil Design and Requirements | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Civil Design and Requirements |  |  |  | Pending
6105A | K124 | 6200 | W | ELE | 0001 | A | 6105AK124-6200-WELE-0001 | Q24050972-03-6200-W-ELE-0001 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Bulk Earth Works Design and Report | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Bulk Earth Works Design and Report |  |  |  | Pending
6105A | K124 | 6200 | W | ELE | 0002 | A | 6105AK124-6200-WELE-0002 | Q24050972-03-6200-W-ELE-0002 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Bulk Earth Works Design and Report | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Bulk Earth Works Design and Report |  |  |  | Pending
6105A | K124 | 6200 | W | ELE | 0003 | A | 6105AK124-6200-WELE-0003 | Q24050972-03-6200-W-ELE-0003 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Bulk Earth Works Design and Report | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Bulk Earth Works Design and Report |  |  |  | Pending
6105A | K124 | 6200 | W | ELE | 0004 | A | 6105AK124-6200-WELE-0004 | Q24050972-03-6200-W-ELE-0004 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Bulk Earth Works Design and Report | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Bulk Earth Works Design and Report |  |  |  | Pending
6105A | K124 | 6200 | W | ELE | 0005 | A | 6105AK124-6200-WELE-0005 | Q24050972-03-6200-W-ELE-0005 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Bulk Earth Works Design and Report | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Bulk Earth Works Design and Report |  |  |  | Pending
6105A | K124 | 6200 | W | ELE | 0006 | A | 6105AK124-6200-WELE-0006 | Q24050972-03-6200-W-ELE-0006 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Bulk Earth Works Design and Report | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Bulk Earth Works Design and Report |  |  |  | Pending
6105A | K124 | 6200 | W | LAY | 0001 | A | 6105AK124-6200-WLAY-0001 | Q24050972-03-6200-W-LAY-0001 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Drainage, Run-off and Impoundment Design | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Drainage, Run-off and Impoundment Design |  |  |  | Pending
6105A | K124 | 6200 | W | LAY | 0002 | A | 6105AK124-6200-WLAY-0002 | Q24050972-03-6200-W-LAY-0002 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Drainage, Run-off and Impoundment Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Drainage, Run-off and Impoundment Design |  |  |  | Pending
6105A | K124 | 6200 | W | LAY | 0003 | A | 6105AK124-6200-WLAY-0003 | Q24050972-03-6200-W-LAY-0003 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Drainage, Run-off and Impoundment Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Drainage, Run-off and Impoundment Design |  |  |  | Pending
6105A | K124 | 6200 | W | LAY | 0004 | A | 6105AK124-6200-WLAY-0004 | Q24050972-03-6200-W-LAY-0004 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Drainage, Run-off and Impoundment Design | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Drainage, Run-off and Impoundment Design |  |  |  | Pending
6105A | K124 | 6200 | W | LAY | 0005 | A | 6105AK124-6200-WLAY-0005 | Q24050972-03-6200-W-LAY-0005 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Drainage, Run-off and Impoundment Design | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Drainage, Run-off and Impoundment Design |  |  |  | Pending
6105A | K124 | 6200 | W | LAY | 0006 | A | 6105AK124-6200-WLAY-0006 | Q24050972-03-6200-W-LAY-0006 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Drainage, Run-off and Impoundment Design | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Drainage, Run-off and Impoundment Design |  |  |  | Pending
6105A | K124 | 6200 | W | TRP | 0001 | A | 6105AK124-6200-WTRP-0001 | Q24050972-03-6200-W-TRP-0001 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Soil Classification and Nomination Deliverables | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Soil Classification and Nomination Deliverables |  |  |  | Pending
6105A | K124 | 6200 | W | TRP | 0002 | A | 6105AK124-6200-WTRP-0002 | Q24050972-03-6200-W-TRP-0002 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Soil Resistivity Testing Report | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer SS | Soil Resistivity Testing Report |  |  |  | Pending
6105A | K124 | 6200 | W | TRP | 0003 | A | 6105AK124-6200-WTRP-0003 | Q24050972-03-6200-W-TRP-0003 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Soil Classification and Nomination Deliverables | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Soil Classification and Nomination Deliverables |  |  |  | Pending
6105A | K124 | 6200 | W | TRP | 0004 | A | 6105AK124-6200-WTRP-0004 | Q24050972-03-6200-W-TRP-0004 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Soil Classification and Nomination Deliverables | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Soil Classification and Nomination Deliverables |  |  |  | Pending
6105A | K124 | 6200 | W | TRP | 0005 | A | 6105AK124-6200-WTRP-0005 | Q24050972-03-6200-W-TRP-0005 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Soil Classification and Nomination Deliverables | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Soil Classification and Nomination Deliverables |  |  |  | Pending
6105A | K124 | 6200 | W | TRP | 0006 | A | 6105AK124-6200-WTRP-0006 | Q24050972-03-6200-W-TRP-0006 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Soil Resistivity Testing Report | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Soil Resistivity Testing Report |  |  |  | Pending
6105A | K124 | 6200 | W | TRP | 0007 | A | 6105AK124-6200-WTRP-0007 | Q24050972-03-6200-W-TRP-0007 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Soil Classification and Nomination Deliverables | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Soil Classification and Nomination Deliverables |  |  |  | Pending
6105A | K124 | 6230 | B | PHL | 0001 | A | 6105AK124-6230-BPHL-0001 | Q24050972-03-6230-B-PHL-0001 |  | High Voltage (220 kV) Transmission Lines | 220 kV & 33kV Overhead Lines Project Package | Control Philosophy | High Voltage (220 kV) Transmission Lines - 220 kV & 33kV Overhead Lines Project Package - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 220 kV & 33kV Overhead Lines | Control Philosophy |  |  |  | Pending
6105A | K124 | 6230 | B | PHL | 0002 | A | 6105AK124-6230-BPHL-0002 | Q24050972-03-6230-B-PHL-0002 |  | High Voltage (220 kV) Transmission Lines | 220 kV & 33kV Overhead Lines Project Package | Synchronization Philosophy | High Voltage (220 kV) Transmission Lines - 220 kV & 33kV Overhead Lines Project Package - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 220 kV & 33kV Overhead Lines | Synchronization Philosophy |  |  |  | Pending
6105A | K124 | 6230 | B | DBD | 0001 | A | 6105AK124-6230-BDBD-0001 | Q24050972-03-6230-B-DBD-0001 |  | High Voltage (220 kV) Transmission Lines | 220 kV & 33kV Overhead Lines Project Package | Design Criteria / Basis of Design | High Voltage (220 kV) Transmission Lines - 220 kV & 33kV Overhead Lines Project Package - Design Criteria / Basis of Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 220 kV & 33kV Overhead Lines | Basis of Design |  |  |  | Pending
6105A | K124 | 6230 | B | SPC | 0001 | A | 6105AK124-6230-BSPC-0001 | Q24050972-03-6230-B-SPC-0001 |  | High Voltage (220 kV) Transmission Lines | 220 kV & 33kV Overhead Lines Project Package | Functional Design Specification | High Voltage (220 kV) Transmission Lines - 220 kV & 33kV Overhead Lines Project Package - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 220 kV & 33kV Overhead Lines | Functional Design Specification |  |  |  | Pending
6105A | K124 | 6230 | B | STD | 0001 | A | 6105AK124-6230-BSTD-0001 | Q24050972-03-6230-B-STD-0001 |  | High Voltage (220 kV) Transmission Lines | 220 kV & 33kV Overhead Lines Project Package | System Detailed Engineering Design | High Voltage (220 kV) Transmission Lines - 220 kV & 33kV Overhead Lines Project Package - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 220 kV & 33kV Overhead Lines | Detailed Engineering Design |  |  |  | Pending
6105A | K124 | 6240 | B | DBD | 0001 | A | 6105AK124-6240-BDBD-0001 | Q24050972-03-6240-B-DBD-0001 |  | High Voltage Substations | 220kV Transmission Substations Project Package | Design Criteria / Basis of Design | High Voltage Substations - 220kV Transmission Substations Project Package - Design Criteria / Basis of Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 220kV Transmission Substations | Basis of Design |  |  |  | Pending
6105A | K124 | 6240 | B | PHL | 0001 | A | 6105AK124-6240-BPHL-0001 | Q24050972-03-6240-B-PHL-0001 |  | High Voltage Substations | 220kV Transmission Substations Project Package | Control Philosophy | High Voltage Substations - 220kV Transmission Substations Project Package - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 220kV Transmission Substations | Control Philosophy |  |  |  | Pending
6105A | K124 | 6240 | B | PHL | 0002 | A | 6105AK124-6240-BPHL-0002 | Q24050972-03-6240-B-PHL-0002 |  | High Voltage Substations | 220kV Transmission Substations Project Package | Synchronisation Philosophy | High Voltage Substations - 220kV Transmission Substations Project Package - Synchronisation Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 220kV Transmission Substations | Synchronisation Philosophy |  |  |  | Pending
6105A | K124 | 6240 | B | SPC | 0001 | A | 6105AK124-6240-BSPC-0001 | Q24050972-03-6240-B-SPC-0001 |  | High Voltage Substations | 220kV Transmission Substations Project Package | Functional Design Specification | High Voltage Substations - 220kV Transmission Substations Project Package - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 220kV Transmission Substations | Functional Design Specification |  |  |  | Pending
6105A | K124 | 6240 | B | STD | 0001 | A | 6105AK124-6240-BSTD-0001 | Q24050972-03-6240-B-STD-0001 |  | High Voltage Substations | 220kV Transmission Substations Project Package | System Detailed Engineering Design | High Voltage Substations - 220kV Transmission Substations Project Package - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 220kV Transmission Substations | Detailed Engineering Design |  |  |  | Pending
6105A | K124 | 6241 | B | STD | 0001 | A | 6105AK124-6241-BSTD-0001 | Q24050972-03-6241-B-STD-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | System Detailed Engineering Design | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Detailed Engineering Design |  |  |  | Pending
6105A | K124 | 6241 | B | SPC | 0001 | A | 6105AK124-6241-BSPC-0001 | Q24050972-03-6241-B-SPC-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Functional Design Specification | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Functional Design Specification |  |  |  | Pending
6105A | K124 | 6241 | C | FND | 0001 | A | 6105AK124-6241-CFND-0001 | Q24050972-03-6241-C-FND-0001 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | Civil Foundation Design | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6241 | C | FND | 0002 | A | 6105AK124-6241-CFND-0002 | Q24050972-03-6241-C-FND-0002 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Civil Foundation Design | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0001 | A | 6105AK124-6241-CGAD-0001 | Q24050972-03-6241-C-GAD-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Cables, OHL and Fibre Route GA | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Cables, OHL and Fibre Route |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0002 | A | 6105AK124-6241-CGAD-0002 | Q24050972-03-6241-C-GAD-0002 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Terrace Equipment GA | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Terrace Equipment |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0003 | A | 6105AK124-6241-CGAD-0003 | Q24050972-03-6241-C-GAD-0003 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Laydown Areas and Temp Buildings GA | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Laydown Areas and Temp Buildings |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0004 | A | 6105AK124-6241-CGAD-0004 | Q24050972-03-6241-C-GAD-0004 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Buildings and Structures GA | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Buildings and Structures |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0005 | A | 6105AK124-6241-CGAD-0005 | Q24050972-03-6241-C-GAD-0005 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Cables, OHL and Fibre Route GA | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Cables, OHL and Fibre Route |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0006 | A | 6105AK124-6241-CGAD-0006 | Q24050972-03-6241-C-GAD-0006 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Key Emergency Points and Equipment | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Key Emergency Points and Equipment |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0007 | A | 6105AK124-6241-CGAD-0007 | Q24050972-03-6241-C-GAD-0007 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Terrace Equipment GA | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Terrace Equipment |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0008 | A | 6105AK124-6241-CGAD-0008 | Q24050972-03-6241-C-GAD-0008 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Disposal Areas General Arrangement | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Disposal Areas General Arrangement |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0009 | A | 6105AK124-6241-CGAD-0009 | Q24050972-03-6241-C-GAD-0009 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Laydown Areas and Temp Buildings GA | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Laydown Areas and Temp Buildings |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0010 | A | 6105AK124-6241-CGAD-0010 | Q24050972-03-6241-C-GAD-0010 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Stormwater and Effluent System Design | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Stormwater and Effluent System Design |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0011 | A | 6105AK124-6241-CGAD-0011 | Q24050972-03-6241-C-GAD-0011 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Lighting Design and Layout GA | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Lighting Design and Layout |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0012 | A | 6105AK124-6241-CGAD-0012 | Q24050972-03-6241-C-GAD-0012 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Roads, Pathways, Offloading Areas and Fences GA | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Roads, Pathways, Offloading Areas and Fences |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0013 | A | 6105AK124-6241-CGAD-0013 | Q24050972-03-6241-C-GAD-0013 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | Roads, Pathways, Offloading Areas and Fences GA | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Roads, Pathways, Offloading Areas and Fences |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0014 | A | 6105AK124-6241-CGAD-0014 | Q24050972-03-6241-C-GAD-0014 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | Lighting Design and Layout GA | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Lighting Design and Layout |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0015 | A | 6105AK124-6241-CGAD-0015 | Q24050972-03-6241-C-GAD-0015 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | Cables, OHL and Fibre Route GA | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Cables, OHL and Fibre Route |  |  |  | Pending
6105A | K124 | 6241 | C | GAD | 0016 | A | 6105AK124-6241-CGAD-0016 | Q24050972-03-6241-C-GAD-0016 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Stormwater and Effluent System Design | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Stormwater and Effluent System Design |  |  |  | Pending
6105A | K124 | 6241 | C | MDL | 0001 | A | 6105AK124-6241-CMDL-0001 | Q24050972-03-6241-C-MDL-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | 3D Designs and Drawings | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6241 | C | MDL | 0002 | A | 6105AK124-6241-CMDL-0002 | Q24050972-03-6241-C-MDL-0002 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | 3D Designs and Drawings | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6241 | C | MDL | 0003 | A | 6105AK124-6241-CMDL-0003 | Q24050972-03-6241-C-MDL-0003 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | 3D Designs and Drawings | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6241 | C | MDL | 0004 | A | 6105AK124-6241-CMDL-0004 | Q24050972-03-6241-C-MDL-0004 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | 3D Designs and Drawings | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6241 | C | PPL | 0001 | A | 6105AK124-6241-CPPL-0001 | Q24050972-03-6241-C-PPL-0001 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Operational & Maint Access Routes Design | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Operational & Maint Access Routes |  |  |  | Pending
6105A | K124 | 6241 | C | SEC | 0001 | A | 6105AK124-6241-CSEC-0001 | Q24050972-03-6241-C-SEC-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Structural Earthing and Bonding Design | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Structural Earthing and Bonding Design |  |  |  | Pending
6105A | K124 | 6241 | C | SHP | 0001 | A | 6105AK124-6241-CSHP-0001 | Q24050972-03-6241-C-SHP-0001 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | Equipment Assembly Drawings | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Equipment Assembly Drawings |  |  |  | Pending
6105A | K124 | 6241 | C | SPC | 0001 | A | 6105AK124-6241-CSPC-0001 | Q24050972-03-6241-C-SPC-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Excavation, Trenching and Compacting Design | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Excavation, Trenching and Compacting Design |  |  |  | Pending
6105A | K124 | 6241 | C | SPC | 0002 | A | 6105AK124-6241-CSPC-0002 | Q24050972-03-6241-C-SPC-0002 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Steel Structures Corrosion Protection Specification | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Protection Specification |  |  |  | Pending
6105A | K124 | 6241 | C | SPC | 0003 | A | 6105AK124-6241-CSPC-0003 | Q24050972-03-6241-C-SPC-0003 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Civil Design Requirements | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Civil Design Requirements |  |  |  | Pending
6105A | K124 | 6241 | C | SPC | 0004 | A | 6105AK124-6241-CSPC-0004 | Q24050972-03-6241-C-SPC-0004 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Excavation, Trenching and Compacting Design | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Excavation, Trenching and Compacting Design |  |  |  | Pending
6105A | K124 | 6241 | C | SPC | 0005 | A | 6105AK124-6241-CSPC-0005 | Q24050972-03-6241-C-SPC-0005 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Concrete Construction Material Specifications | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Material Specifications |  |  |  | Pending
6105A | K124 | 6241 | C | SPC | 0006 | A | 6105AK124-6241-CSPC-0006 | Q24050972-03-6241-C-SPC-0006 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | Excavation, Trenching and Compacting Design | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Excavation, Trenching and Compacting Design |  |  |  | Pending
6105A | K124 | 6241 | C | SPC | 0007 | A | 6105AK124-6241-CSPC-0007 | Q24050972-03-6241-C-SPC-0007 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | Concrete Construction Material Specifications | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Material Specifications |  |  |  | Pending
6105A | K124 | 6241 | C | SPC | 0008 | A | 6105AK124-6241-CSPC-0008 | Q24050972-03-6241-C-SPC-0008 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | Steel Structures Corrosion Protection Specification | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Protection Specification |  |  |  | Pending
6105A | K124 | 6241 | C | SPC | 0009 | A | 6105AK124-6241-CSPC-0009 | Q24050972-03-6241-C-SPC-0009 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Civil Design Requirements | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Civil Design Requirements |  |  |  | Pending
6105A | K124 | 6241 | C | SPC | 0010 | A | 6105AK124-6241-CSPC-0010 | Q24050972-03-6241-C-SPC-0010 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Excavation, Trenching and Compacting Design | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Excavation, Trenching and Compacting Design |  |  |  | Pending
6105A | K124 | 6241 | C | SPC | 0011 | A | 6105AK124-6241-CSPC-0011 | Q24050972-03-6241-C-SPC-0011 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Concrete Construction Material Specifications | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Material Specifications |  |  |  | Pending
6105A | K124 | 6241 | C | SSD | 0001 | A | 6105AK124-6241-CSSD-0001 | Q24050972-03-6241-C-SSD-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Steel Support Structures Design | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Steel Support Structures Design |  |  |  | Pending
6105A | K124 | 6241 | C | SSD | 0002 | A | 6105AK124-6241-CSSD-0002 | Q24050972-03-6241-C-SSD-0002 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | Steel Support Structures Design | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Steel Support Structures Design |  |  |  | Pending
6105A | K124 | 6241 | C | STD | 0001 | A | 6105AK124-6241-CSTD-0001 | Q24050972-03-6241-C-STD-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Underground Pipe Route and Cable Bedding Design | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Pipe Route and Cable Bedding Design |  |  |  | Pending
6105A | K124 | 6241 | C | STD | 0002 | A | 6105AK124-6241-CSTD-0002 | Q24050972-03-6241-C-STD-0002 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Bund-wall Requirements and Design | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Requirements and Design |  |  |  | Pending
6105A | K124 | 6241 | C | STD | 0003 | A | 6105AK124-6241-CSTD-0003 | Q24050972-03-6241-C-STD-0003 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Civil Construction Requirements | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Civil Construction Requirements |  |  |  | Pending
6105A | K124 | 6241 | C | STD | 0004 | A | 6105AK124-6241-CSTD-0004 | Q24050972-03-6241-C-STD-0004 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Underground Pipe Route and Cable Bedding Design | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Pipe Route and Cable Bedding Design |  |  |  | Pending
6105A | K124 | 6241 | C | STD | 0005 | A | 6105AK124-6241-CSTD-0005 | Q24050972-03-6241-C-STD-0005 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | Underground Pipe Route and Cable Bedding Design | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Pipe Route and Cable Bedding Design |  |  |  | Pending
6105A | K124 | 6241 | C | STD | 0006 | A | 6105AK124-6241-CSTD-0006 | Q24050972-03-6241-C-STD-0006 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Bund-wall Requirements and Design | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Requirements and Design |  |  |  | Pending
6105A | K124 | 6241 | C | STD | 0007 | A | 6105AK124-6241-CSTD-0007 | Q24050972-03-6241-C-STD-0007 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Fire Protection System Design (Civil Works) | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Fire Protection System Design |  |  |  | Pending
6105A | K124 | 6241 | C | STD | 0008 | A | 6105AK124-6241-CSTD-0008 | Q24050972-03-6241-C-STD-0008 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Civil Construction Requirements | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Civil Construction Requirements |  |  |  | Pending
6105A | K124 | 6241 | C | STD | 0009 | A | 6105AK124-6241-CSTD-0009 | Q24050972-03-6241-C-STD-0009 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Underground Pipe Route and Cable Bedding Design | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Pipe Route and Cable Bedding Design |  |  |  | Pending
6105A | K124 | 6241 | E | CAL | 0001 | A | 6105AK124-6241-ECAL-0001 | Q24050972-03-6241-E-CAL-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Cable and Conductor Sizing (incl Volt Drop Calcs) | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Cable and Conductor Sizing |  |  |  | Pending
6105A | K124 | 6241 | E | CAL | 0002 | A | 6105AK124-6241-ECAL-0002 | Q24050972-03-6241-E-CAL-0002 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Conductor Sag and Tension Plan | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Conductor Sag and Tension Plan |  |  |  | Pending
6105A | K124 | 6241 | E | DIA | 0001 | A | 6105AK124-6241-EDIA-0001 | Q24050972-03-6241-E-DIA-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Cable Block Diagrams and Schedules | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Cable Block Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6241 | E | DIA | 0002 | A | 6105AK124-6241-EDIA-0002 | Q24050972-03-6241-E-DIA-0002 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Electrical Circuit Diagrams (Schematics) | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Electrical Circuit Diagrams |  |  |  | Pending
6105A | K124 | 6241 | E | DIA | 0003 | A | 6105AK124-6241-EDIA-0003 | Q24050972-03-6241-E-DIA-0003 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Protection Relay Design | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Protection Relay Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Room and Solar PV Substation | Protection Relay Design |  |  |  | Pending
6105A | K124 | 0100 | Q | TMP | 0001 | A | 6105AK124-0100-QTMP-0001 | Q24050972-03-0100-Q-TMP-0001 |  | Project Site Wide | Inspection and Test Plan Library | Library | Project Site Wide - Inspection and Test Plan Library - Library | 2026-04-28 |  | IFR - Issued for Review | Reviewed | 33.33% | OC |  |  | Inspection and Test Plan | Library |  |  |  | Pending
6105A | K124 | 0100 | Q | TMP | 0002 | A | 6105AK124-0100-QTMP-0002 | Q24050972-03-0100-Q-TMP-0002 |  | Project Site Wide | Material and Test Certificates Register | Register | Project Site Wide - Material and Test Certificates Register - Register |  |  | RES - Reserved Placeholder | Pending | 0% | OC |  | 2026-05-15 | Material and Test Certificates | Register |  |  |  | Pending
6105A | K124 | 0100 | Q | TMP | 0003 | A | 6105AK124-0100-QTMP-0003 | Q24050972-03-0100-Q-TMP-0003 |  | Project Site Wide | Non-Conformance Report (NCR) Log | Report log | Project Site Wide - Non-Conformance Report (NCR) Log - Report log |  |  | RES - Reserved Placeholder | Pending | 0% | OC |  | 2026-05-15 | Non-Conformance | Report log |  |  |  | Pending
6105A | K124 | 0100 | Q | TMP | 0004 | A | 6105AK124-0100-QTMP-0004 | Q24050972-03-0100-Q-TMP-0004 |  | Project Site Wide | Quality Surveillance Report Log | Report log | Project Site Wide - Quality Surveillance Report Log - Report log |  |  | RES - Reserved Placeholder | Pending | 0% | OC |  | 2026-05-15 | Quality Surveillance | Report log |  |  |  | Pending
6105A | K124 | 0100 | Q | TMP | 0005 | A | 6105AK124-0100-QTMP-0005 | Q24050972-03-0100-Q-TMP-0005 |  | Project Site Wide | Engineering Quality Management Plan | Standard | Project Site Wide - Engineering Quality Management Plan - Standard | 2026-04-21 |  | IFR - Issued for Review | Reviewed | 33.33% | OC |  |  | Engineering Quality Management | Standard |  |  |  | Pending
6105A | K124 | 0100 | Q | TMP | 0006 | A | 6105AK124-0100-QTMP-0006 | Q24050972-03-0100-Q-TMP-0006 |  | Project Site Wide | QA/QC Coaching Form | Report | Project Site Wide - QA/QC Coaching Form - Report |  |  | RES - Reserved Placeholder | Pending | 0% | OC |  | 2026-05-15 | QA/QC Coaching Form | Report |  |  |  | Pending
6105A | K124 | 0100 | Q | TMP | 0007 | A | 6105AK124-0100-QTMP-0007 | Q24050972-03-0100-Q-TMP-0007 |  | Project Site Wide | QA Data Book Verification Record | Record | Project Site Wide - QA Data Book Verification Record - Record |  |  | RES - Reserved Placeholder | Pending | 0% | OC |  | 2026-05-15 | QA Data Book Verification | Record |  |  |  | Pending
6105A | K124 | 6200 | E | LAY | 0006 | A | 6105AK124-6200-ELAY-0006 | Q24050972-03-6200-E-LAY-0006 | Sht.1 of 1 | On-Site Power Supply and Transmission | Main Consumer Intake Power Complex | Road Crossings Layout | On-Site Power Supply and Transmission - Main Consumer Intake Power Complex - Road Crossings Layout | 2026-05-20 |  | IFR - Issued for Review | Pending | 33.33% | TV |  |  | Main Consumer Intake Power Complex | Layout |  |  |  | Pending
6105A | K124 | 6200 | E | GAD | 0002 | A | 6105AK124-6200-EGAD-0002 | Q24050972-03-6200-E-GAD-0002 | Sht.1 of 3 | On-Site Power Supply and Transmission | Road Crossings Layout | General Arrangement | On-Site Power Supply and Transmission - Road Crossings Layout - General Arrangement | 2026-05-20 |  | IFR - Issued for Review | Pending | 33.33% | TV |  |  | Road Crossings | General Arrangement |  |  |  | Pending
6105A | K124 | 6200 | E | GAD | 0003 | A | 6105AK124-6200-EGAD-0003 | Q24050972-03-6200-E-GAD-0003 | Sht.2 of 3 | On-Site Power Supply and Transmission | Road Crossings - MV & LV Compartments | General Arrangement | On-Site Power Supply and Transmission - Road Crossings - MV & LV Compartments - General Arrangement | 2026-05-20 |  | IFR - Issued for Review | Pending | 33.33% | TV |  |  | Road Crossings | General Arrangement |  |  |  | Pending
6105A | K124 | 6200 | E | GAD | 0004 | A | 6105AK124-6200-EGAD-0004 | Q24050972-03-6200-E-GAD-0004 | Sht.3 of 3 | On-Site Power Supply and Transmission | Road Crossings - LV Compartment | General Arrangement | On-Site Power Supply and Transmission - Road Crossings - LV Compartment - General Arrangement | 2026-05-20 |  | IFR - Issued for Review | Pending | 33.33% | TV |  |  | Road Crossings | General Arrangement |  |  |  | Pending
6105A | K124 | 6241 | E | MDL | 0001 | A | 6105AK124-6241-EMDL-0001 | Q24050972-03-6241-E-MDL-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | ETAP Network Model | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | E | QRA | 0001 | A | 6105AK124-6241-EQRA-0001 | Q24050972-03-6241-E-QRA-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Risk Assessment: Electrical Hazards | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | E | SLD | 0001 | A | 6105AK124-6241-ESLD-0001 | Q24050972-03-6241-E-SLD-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Electrical Single Line Diagram | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | E | SPC | 0001 | A | 6105AK124-6241-ESPC-0001 | Q24050972-03-6241-E-SPC-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Cable Termination Specifications | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | F | DIA | 0001 | A | 6105AK124-6241-FDIA-0001 | Q24050972-03-6241-F-DIA-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Control Network Architecture Design | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | F | DIA | 0002 | A | 6105AK124-6241-FDIA-0002 | Q24050972-03-6241-F-DIA-0002 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Control Network Communication Design | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | I | DIA | 0001 | A | 6105AK124-6241-IDIA-0001 | Q24050972-03-6241-I-DIA-0001 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | Closed Circuit Television (CCTV) Design | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - Closed Circuit Television (CCTV) Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | I | DIA | 0002 | A | 6105AK124-6241-IDIA-0002 | Q24050972-03-6241-I-DIA-0002 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Smoke and Fire Detection System Design | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | I | ITD | 0001 | A | 6105AK124-6241-IITD-0001 | Q24050972-03-6241-I-ITD-0001 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Instrument Wiring Loop Diagrams and Cable Schedule | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | I | LST | 0001 | A | 6105AK124-6241-ILST-0001 | Q24050972-03-6241-I-LST-0001 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Equipment Alarm and Trip Level Register | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | I | QRA | 0001 | A | 6105AK124-6241-IQRA-0001 | Q24050972-03-6241-I-QRA-0001 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Risk Assessment: Fire and Explosions | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | I | SPC | 0001 | A | 6105AK124-6241-ISPC-0001 | Q24050972-03-6241-I-SPC-0001 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Junction Box and Interface Cabinet Design | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | M | PRC | 0001 | A | 6105AK124-6241-MPRC-0001 | Q24050972-03-6241-M-PRC-0001 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Rigging Study and Lifting Equipment Design | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | M | SPC | 0001 | A | 6105AK124-6241-MSPC-0001 | Q24050972-03-6241-M-SPC-0001 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Manual Isolation Valve Design Specification | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Manual Isolation Valve Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | T | RPT | 0001 | A | 6105AK124-6241-TRPT-0001 | Q24050972-03-6241-T-RPT-0001 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Site Surveying & Geotechnical Report | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | T | RPT | 0002 | A | 6105AK124-6241-TRPT-0002 | Q24050972-03-6241-T-RPT-0002 |  | 33/220 kV Solar PV Substation | Perimeter Fencing for Solar PV Substation | Site Surveying & Geotechnical Report | 33/220 kV Solar PV Substation - Perimeter Fencing for Solar PV Substation - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | T | SPC | 0001 | A | 6105AK124-6241-TSPC-0001 | Q24050972-03-6241-T-SPC-0001 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Civil Design and Requirements | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | T | RPT | 0003 | A | 6105AK124-6241-TRPT-0003 | Q24050972-03-6241-T-RPT-0003 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Site Surveying & Geotechnical Report | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | W | ELE | 0001 | A | 6105AK124-6241-WELE-0001 | Q24050972-03-6241-W-ELE-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Bulk Earth Works Design and Report | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | W | ELE | 0002 | A | 6105AK124-6241-WELE-0002 | Q24050972-03-6241-W-ELE-0002 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Bulk Earth Works Design and Report | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | W | LAY | 0001 | A | 6105AK124-6241-WLAY-0001 | Q24050972-03-6241-W-LAY-0001 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Drainage, Run-off and Impoundment Design | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | W | TRP | 0001 | A | 6105AK124-6241-WTRP-0001 | Q24050972-03-6241-W-TRP-0001 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Soil Classification and Nomination Deliverables | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | W | TRP | 0002 | A | 6105AK124-6241-WTRP-0002 | Q24050972-03-6241-W-TRP-0002 |  | 33/220 kV Solar PV Substation | Terrace, Roads and Access-ways for Solar PV Substation | Soil Resistivity Testing Report | 33/220 kV Solar PV Substation - Terrace, Roads and Access-ways for Solar PV Substation - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | W | ELE | 0003 | A | 6105AK124-6241-WELE-0003 | Q24050972-03-6241-W-ELE-0003 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Bulk Earth Works Design and Report | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6241 | W | LAY | 0002 | A | 6105AK124-6241-WLAY-0002 | Q24050972-03-6241-W-LAY-0002 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Drainage, Run-off and Impoundment Design | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Solar PV Substation |  |  |  | Pending
6105A | K124 | 6212 | B | PHL | 0001 | A | 6105AK124-6212-BPHL-0001 | Q24050972-03-6212-B-PHL-0001 |  | Power Station 1 | Wartsila Project Package | Control Philosophy | Power Station 1 - Wartsila Project Package - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Project Package | Control Philosophy |  |  |  | Pending
6105A | K124 | 6212 | B | PHL | 0002 | A | 6105AK124-6212-BPHL-0002 | Q24050972-03-6212-B-PHL-0002 |  | Power Station 1 | Wartsila Project Package | Synchronization Philosophy | Power Station 1 - Wartsila Project Package - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Project Package | Synchronization Philosophy |  |  |  | Pending
6105A | K124 | 6212 | B | PHL | 0003 | A | 6105AK124-6212-BPHL-0003 | Q24050972-03-6212-B-PHL-0003 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Control Philosophy | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Control Philosophy |  |  |  | Pending
6105A | K124 | 6212 | B | PHL | 0004 | A | 6105AK124-6212-BPHL-0004 | Q24050972-03-6212-B-PHL-0004 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Synchronization Philosophy | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Synchronization Philosophy |  |  |  | Pending
6105A | K124 | 6212 | B | PHL | 0005 | A | 6105AK124-6212-BPHL-0005 | Q24050972-03-6212-B-PHL-0005 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Power Management System Philosophy | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Power Management System Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Power Management System Philosophy |  |  |  | Pending
6105A | K124 | 6212 | B | DBD | 0001 | A | 6105AK124-6212-BDBD-0001 | Q24050972-03-6212-B-DBD-0001 |  | Power Station 1 | Wartsila Project Package | Design Criteria / Basis of Design | Power Station 1 - Wartsila Project Package - Design Criteria / Basis of Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Project Package | Design Criteria / Basis of Design |  |  |  | Pending
6105A | K124 | 6212 | B | STD | 0001 | A | 6105AK124-6212-BSTD-0001 | Q24050972-03-6212-B-STD-0001 |  | Power Station 1 | Wartsila Project Package | System Detailed Engineering Design | Power Station 1 - Wartsila Project Package - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Project Package | System Detailed Engineering Design |  |  |  | Pending
6105A | K124 | 6212 | B | STD | 0002 | A | 6105AK124-6212-BSTD-0002 | Q24050972-03-6212-B-STD-0002 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | System Detailed Engineering Design | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | B | SPC | 0001 | A | 6105AK124-6212-BSPC-0001 | Q24050972-03-6212-B-SPC-0001 |  | Power Station 1 | Wartsila Project Package | Functional Design Specification | Power Station 1 - Wartsila Project Package - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Project Package | Functional Design Specification |  |  |  | Pending
6105A | K124 | 6212 | B | SPC | 0002 | A | 6105AK124-6212-BSPC-0002 | Q24050972-03-6212-B-SPC-0002 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Functional Design Specification | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | C | FND | 0001 | A | 6105AK124-6212-CFND-0001 | Q24050972-03-6212-C-FND-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Civil Foundation Design | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6212 | C | FND | 0002 | A | 6105AK124-6212-CFND-0002 | Q24050972-03-6212-C-FND-0002 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Civil Foundation Design | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0001 | A | 6105AK124-6212-CGAD-0001 | Q24050972-03-6212-C-GAD-0001 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Buildings and Structures GA | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0002 | A | 6105AK124-6212-CGAD-0002 | Q24050972-03-6212-C-GAD-0002 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Cables, OHL and Fibre Route GA | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Cables, OHL and Fibre Route GA |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0003 | A | 6105AK124-6212-CGAD-0003 | Q24050972-03-6212-C-GAD-0003 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Terrace Equipment GA | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0004 | A | 6105AK124-6212-CGAD-0004 | Q24050972-03-6212-C-GAD-0004 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Buildings and Structures GA | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0005 | A | 6105AK124-6212-CGAD-0005 | Q24050972-03-6212-C-GAD-0005 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Cables, OHL and Fibre Route GA | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Cables, OHL and Fibre Route GA |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0006 | A | 6105AK124-6212-CGAD-0006 | Q24050972-03-6212-C-GAD-0006 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Terrace Equipment GA | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0007 | A | 6105AK124-6212-CGAD-0007 | Q24050972-03-6212-C-GAD-0007 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Roads, Pathways, Offloading Areas and Fences GA | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Roads, Pathways, Offloading Areas and Fences GA |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0008 | A | 6105AK124-6212-CGAD-0008 | Q24050972-03-6212-C-GAD-0008 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Buildings and Structures GA | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0009 | A | 6105AK124-6212-CGAD-0009 | Q24050972-03-6212-C-GAD-0009 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Cables, OHL and Fibre Route GA | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Cables, OHL and Fibre Route GA |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0010 | A | 6105AK124-6212-CGAD-0010 | Q24050972-03-6212-C-GAD-0010 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Terrace Equipment GA | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0011 | A | 6105AK124-6212-CGAD-0011 | Q24050972-03-6212-C-GAD-0011 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Cables, OHL and Fibre Route GA | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0012 | A | 6105AK124-6212-CGAD-0012 | Q24050972-03-6212-C-GAD-0012 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Terrace Equipment GA | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0013 | A | 6105AK124-6212-CGAD-0013 | Q24050972-03-6212-C-GAD-0013 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Laydown Areas and Temp Buildings GA | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0014 | A | 6105AK124-6212-CGAD-0014 | Q24050972-03-6212-C-GAD-0014 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Buildings and Structures GA | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0015 | A | 6105AK124-6212-CGAD-0015 | Q24050972-03-6212-C-GAD-0015 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Cables, OHL and Fibre Route GA | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0016 | A | 6105AK124-6212-CGAD-0016 | Q24050972-03-6212-C-GAD-0016 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Terrace Equipment GA | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | GAD | 0017 | A | 6105AK124-6212-CGAD-0017 | Q24050972-03-6212-C-GAD-0017 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Roads, Pathways, Offloading Areas and Fences GA | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | MDL | 0001 | A | 6105AK124-6212-CMDL-0001 | Q24050972-03-6212-C-MDL-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | 3D Designs and Drawings | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6212 | C | MDL | 0002 | A | 6105AK124-6212-CMDL-0002 | Q24050972-03-6212-C-MDL-0002 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | 3D Designs and Drawings | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6212 | C | MDL | 0003 | A | 6105AK124-6212-CMDL-0003 | Q24050972-03-6212-C-MDL-0003 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | 3D Designs and Drawings | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | C | MDL | 0004 | A | 6105AK124-6212-CMDL-0004 | Q24050972-03-6212-C-MDL-0004 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | 3D Designs and Drawings | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | PLN | 0001 | A | 6105AK124-6212-CPLN-0001 | Q24050972-03-6212-C-PLN-0001 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Civil Works Execution Plan | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Civil Works Execution Plan |  |  |  | Pending
6105A | K124 | 6212 | C | PLN | 0002 | A | 6105AK124-6212-CPLN-0002 | Q24050972-03-6212-C-PLN-0002 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Civil Works Execution Plan | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | C | PPL | 0001 | A | 6105AK124-6212-CPPL-0001 | Q24050972-03-6212-C-PPL-0001 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Operational & Maint Access Routes Design | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Operational & Maint Access Routes Design |  |  |  | Pending
6105A | K124 | 6212 | C | PPL | 0002 | A | 6105AK124-6212-CPPL-0002 | Q24050972-03-6212-C-PPL-0002 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Operational & Maint Access Routes Design | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Operational & Maint Access Routes Design |  |  |  | Pending
6105A | K124 | 6212 | C | PPL | 0003 | A | 6105AK124-6212-CPPL-0003 | Q24050972-03-6212-C-PPL-0003 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Operational & Maint Access Routes Design | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | SEC | 0001 | A | 6105AK124-6212-CSEC-0001 | Q24050972-03-6212-C-SEC-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Corrosion Prevention and Protection Design | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Corrosion Prevention and Protection Design |  |  |  | Pending
6105A | K124 | 6212 | C | SEC | 0002 | A | 6105AK124-6212-CSEC-0002 | Q24050972-03-6212-C-SEC-0002 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Structural Earthing and Bonding Design | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Structural Earthing and Bonding Design |  |  |  | Pending
6105A | K124 | 6212 | C | SEC | 0003 | A | 6105AK124-6212-CSEC-0003 | Q24050972-03-6212-C-SEC-0003 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Corrosion Prevention and Protection Design | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Corrosion Prevention and Protection Design |  |  |  | Pending
6105A | K124 | 6212 | C | SEC | 0004 | A | 6105AK124-6212-CSEC-0004 | Q24050972-03-6212-C-SEC-0004 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Structural Earthing and Bonding Design | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Structural Earthing and Bonding Design |  |  |  | Pending
6105A | K124 | 6212 | C | SEC | 0005 | A | 6105AK124-6212-CSEC-0005 | Q24050972-03-6212-C-SEC-0005 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Structural Earthing and Bonding Design | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | C | SEC | 0006 | A | 6105AK124-6212-CSEC-0006 | Q24050972-03-6212-C-SEC-0006 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Corrosion Prevention and Protection Design | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | SEC | 0007 | A | 6105AK124-6212-CSEC-0007 | Q24050972-03-6212-C-SEC-0007 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Structural Earthing and Bonding Design | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | SHP | 0001 | A | 6105AK124-6212-CSHP-0001 | Q24050972-03-6212-C-SHP-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Equipment Assembly Drawings | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Equipment Assembly Drawings |  |  |  | Pending
6105A | K124 | 6212 | C | SHP | 0002 | A | 6105AK124-6212-CSHP-0002 | Q24050972-03-6212-C-SHP-0002 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Equipment Assembly Drawings | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | SPC | 0001 | A | 6105AK124-6212-CSPC-0001 | Q24050972-03-6212-C-SPC-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Civil Design Requirements | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Civil Design Requirements |  |  |  | Pending
6105A | K124 | 6212 | C | SPC | 0002 | A | 6105AK124-6212-CSPC-0002 | Q24050972-03-6212-C-SPC-0002 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Concrete Construction Material Specifications | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Concrete Construction Material Specifications |  |  |  | Pending
6105A | K124 | 6212 | C | SPC | 0003 | A | 6105AK124-6212-CSPC-0003 | Q24050972-03-6212-C-SPC-0003 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Steel Structures Corrosion Protection Specification | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Steel Structures Corrosion Protection Specification |  |  |  | Pending
6105A | K124 | 6212 | C | SPC | 0004 | A | 6105AK124-6212-CSPC-0004 | Q24050972-03-6212-C-SPC-0004 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Excavation, Trenching and Compacting Design | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | C | SPC | 0005 | A | 6105AK124-6212-CSPC-0005 | Q24050972-03-6212-C-SPC-0005 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Steel Structures Corrosion Protection Specification | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | C | SPC | 0006 | A | 6105AK124-6212-CSPC-0006 | Q24050972-03-6212-C-SPC-0006 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Civil Design Requirements | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | SPC | 0007 | A | 6105AK124-6212-CSPC-0007 | Q24050972-03-6212-C-SPC-0007 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Concrete Construction Material Specifications | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | SPC | 0008 | A | 6105AK124-6212-CSPC-0008 | Q24050972-03-6212-C-SPC-0008 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Steel Structures Corrosion Protection Specification | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | SSD | 0001 | A | 6105AK124-6212-CSSD-0001 | Q24050972-03-6212-C-SSD-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Steel Support Structures Design | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Steel Support Structures Design |  |  |  | Pending
6105A | K124 | 6212 | C | SSD | 0002 | A | 6105AK124-6212-CSSD-0002 | Q24050972-03-6212-C-SSD-0002 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Steel Support Structures Design | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | C | SSD | 0003 | A | 6105AK124-6212-CSSD-0003 | Q24050972-03-6212-C-SSD-0003 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Steel Support Structures Design | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | C | STD | 0001 | A | 6105AK124-6212-CSTD-0001 | Q24050972-03-6212-C-STD-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Underground Pipe Route and Cable Bedding Design | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Underground Pipe Route and Cable Bedding Design |  |  |  | Pending
6105A | K124 | 6212 | C | STD | 0002 | A | 6105AK124-6212-CSTD-0002 | Q24050972-03-6212-C-STD-0002 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Underground Pipe Route and Cable Bedding Design | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | C | STD | 0003 | A | 6105AK124-6212-CSTD-0003 | Q24050972-03-6212-C-STD-0003 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Underground Pipe Route and Cable Bedding Design | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | E | CAL | 0001 | A | 6105AK124-6212-ECAL-0001 | Q24050972-03-6212-E-CAL-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Cable and Conductor Sizing (incl Volt Drop Calcs) | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  |  | Pending
6105A | K124 | 6212 | E | CAL | 0002 | A | 6105AK124-6212-ECAL-0002 | Q24050972-03-6212-E-CAL-0002 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Cable and Conductor Sizing (incl Volt Drop Calcs) | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  |  | Pending
6105A | K124 | 6212 | E | CAL | 0003 | A | 6105AK124-6212-ECAL-0003 | Q24050972-03-6212-E-CAL-0003 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Cable and Conductor Sizing (incl Volt Drop Calcs) | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  |  | Pending
6105A | K124 | 6212 | E | CAL | 0004 | A | 6105AK124-6212-ECAL-0004 | Q24050972-03-6212-E-CAL-0004 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Impedance and Burn-off Calculations | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Impedance and Burn-off Calculations |  |  |  | Pending
6105A | K124 | 6212 | E | CAL | 0005 | A | 6105AK124-6212-ECAL-0005 | Q24050972-03-6212-E-CAL-0005 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Cable and Conductor Sizing (incl Volt Drop Calcs) | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0001 | A | 6105AK124-6212-EDIA-0001 | Q24050972-03-6212-E-DIA-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Cable Block Diagrams and Schedules | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Cable Block Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0002 | A | 6105AK124-6212-EDIA-0002 | Q24050972-03-6212-E-DIA-0002 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Circuit Diagrams (Schematics) | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Circuit Diagrams (Schematics) |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0003 | A | 6105AK124-6212-EDIA-0003 | Q24050972-03-6212-E-DIA-0003 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | E/I Termination Schedule | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | E/I Termination Schedule |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0004 | A | 6105AK124-6212-EDIA-0004 | Q24050972-03-6212-E-DIA-0004 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Block Diagram | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Block Diagram |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0005 | A | 6105AK124-6212-EDIA-0005 | Q24050972-03-6212-E-DIA-0005 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Cable Block Diagrams and Schedules | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Cable Block Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0006 | A | 6105AK124-6212-EDIA-0006 | Q24050972-03-6212-E-DIA-0006 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Circuit Diagrams (Schematics) | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Circuit Diagrams (Schematics) |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0007 | A | 6105AK124-6212-EDIA-0007 | Q24050972-03-6212-E-DIA-0007 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | E/I Termination Schedule | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | E/I Termination Schedule |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0008 | A | 6105AK124-6212-EDIA-0008 | Q24050972-03-6212-E-DIA-0008 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Block Diagram | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Block Diagram |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0009 | A | 6105AK124-6212-EDIA-0009 | Q24050972-03-6212-E-DIA-0009 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Cable Block Diagrams and Schedules | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Cable Block Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0010 | A | 6105AK124-6212-EDIA-0010 | Q24050972-03-6212-E-DIA-0010 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | E/I Termination Schedule | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | E/I Termination Schedule |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0011 | A | 6105AK124-6212-EDIA-0011 | Q24050972-03-6212-E-DIA-0011 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Cable Block Diagrams and Schedules | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Cable Block Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0012 | A | 6105AK124-6212-EDIA-0012 | Q24050972-03-6212-E-DIA-0012 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Electrical Circuit Diagrams (Schematics) | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Electrical Circuit Diagrams (Schematics) |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0013 | A | 6105AK124-6212-EDIA-0013 | Q24050972-03-6212-E-DIA-0013 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Cable Block Diagrams and Schedules | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0014 | A | 6105AK124-6212-EDIA-0014 | Q24050972-03-6212-E-DIA-0014 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Electrical Circuit Diagrams (Schematics) | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0015 | A | 6105AK124-6212-EDIA-0015 | Q24050972-03-6212-E-DIA-0015 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Protection Relay Design | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Protection Relay Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0016 | A | 6105AK124-6212-EDIA-0016 | Q24050972-03-6212-E-DIA-0016 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Cable Block Diagrams and Schedules | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0017 | A | 6105AK124-6212-EDIA-0017 | Q24050972-03-6212-E-DIA-0017 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | E/I Termination Schedule | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0018 | A | 6105AK124-6212-EDIA-0018 | Q24050972-03-6212-E-DIA-0018 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Electrical Circuit Diagrams (Schematics) | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Electrical Circuit Diagrams (Schematics) |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0019 | A | 6105AK124-6212-EDIA-0019 | Q24050972-03-6212-E-DIA-0019 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Electrical Block Diagram | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Electrical Block Diagram |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0020 | A | 6105AK124-6212-EDIA-0020 | Q24050972-03-6212-E-DIA-0020 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Electrical Network Architecture | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Electrical Network Architecture |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Electrical Network Architecture |  |  |  | Pending
6105A | K124 | 6212 | E | DIA | 0021 | A | 6105AK124-6212-EDIA-0021 | Q24050972-03-6212-E-DIA-0021 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Protection Relay Design | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Protection Relay Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Protection Relay Design |  |  |  | Pending
6105A | K124 | 6212 | E | DST | 0001 | A | 6105AK124-6212-EDST-0001 | Q24050972-03-6212-E-DST-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Equipment Register and Technical Specifications | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6212 | E | DST | 0002 | A | 6105AK124-6212-EDST-0002 | Q24050972-03-6212-E-DST-0002 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Equipment Register and Technical Specifications | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6212 | E | DST | 0003 | A | 6105AK124-6212-EDST-0003 | Q24050972-03-6212-E-DST-0003 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Equipment Register and Technical Specifications | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6212 | E | DST | 0004 | A | 6105AK124-6212-EDST-0004 | Q24050972-03-6212-E-DST-0004 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Equipment Register and Technical Specifications | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6212 | E | DST | 0005 | A | 6105AK124-6212-EDST-0005 | Q24050972-03-6212-E-DST-0005 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Equipment Register and Technical Specifications | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | E | DST | 0006 | A | 6105AK124-6212-EDST-0006 | Q24050972-03-6212-E-DST-0006 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | CT and PT Datasheets | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - CT and PT Datasheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | CT and PT Datasheets |  |  |  | Pending
6105A | K124 | 6212 | E | DST | 0007 | A | 6105AK124-6212-EDST-0007 | Q24050972-03-6212-E-DST-0007 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Equipment Register and Technical Specifications | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Equipment Register and Technical Specifications |  |  |  | Pending
6105A | K124 | 6212 | E | EQL | 0001 | A | 6105AK124-6212-EEQL-0001 | Q24050972-03-6212-E-EQL-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Equipment Load Register | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Equipment Load Register |  |  |  | Pending
6105A | K124 | 6212 | E | EQL | 0002 | A | 6105AK124-6212-EEQL-0002 | Q24050972-03-6212-E-EQL-0002 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Equipment Load Register | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Equipment Load Register |  |  |  | Pending
6105A | K124 | 6212 | E | GAD | 0001 | A | 6105AK124-6212-EGAD-0001 | Q24050972-03-6212-E-GAD-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Mobile Load Bank Electrical General Arrangement | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Mobile Load Bank Electrical General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Mobile Load Bank Electrical General Arrangement |  |  |  | Pending
6105A | K124 | 6212 | E | GAD | 0002 | A | 6105AK124-6212-EGAD-0002 | Q24050972-03-6212-E-GAD-0002 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Equipment Layout | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Electrical Equipment Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Equipment Layout |  |  |  | Pending
6105A | K124 | 6212 | E | GAD | 0003 | A | 6105AK124-6212-EGAD-0003 | Q24050972-03-6212-E-GAD-0003 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Mobile Load Bank Electrical General Arrangement | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Mobile Load Bank Electrical General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Mobile Load Bank Electrical General Arrangement |  |  |  | Pending
6105A | K124 | 6212 | E | GAD | 0004 | A | 6105AK124-6212-EGAD-0004 | Q24050972-03-6212-E-GAD-0004 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Equipment Layout | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Electrical Equipment Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Equipment Layout |  |  |  | Pending
6105A | K124 | 6212 | E | GAD | 0005 | A | 6105AK124-6212-EGAD-0005 | Q24050972-03-6212-E-GAD-0005 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Mobile Load Bank Electrical General Arrangement | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Mobile Load Bank Electrical General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Mobile Load Bank Electrical General Arrangement |  |  |  | Pending
6105A | K124 | 6212 | E | GAD | 0006 | A | 6105AK124-6212-EGAD-0006 | Q24050972-03-6212-E-GAD-0006 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Control Room Design | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Control Room Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Control Room Design |  |  |  | Pending
6105A | K124 | 6212 | E | MDL | 0001 | A | 6105AK124-6212-EMDL-0001 | Q24050972-03-6212-E-MDL-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | ETAP Network Model | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | ETAP Network Model |  |  |  | Pending
6105A | K124 | 6212 | E | MDL | 0002 | A | 6105AK124-6212-EMDL-0002 | Q24050972-03-6212-E-MDL-0002 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | ETAP Network Model | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | ETAP Network Model |  |  |  | Pending
6105A | K124 | 6212 | E | MDL | 0003 | A | 6105AK124-6212-EMDL-0003 | Q24050972-03-6212-E-MDL-0003 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | ETAP Network Model | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | E | MDL | 0004 | A | 6105AK124-6212-EMDL-0004 | Q24050972-03-6212-E-MDL-0004 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | ETAP Network Model | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | ETAP Network Model |  |  |  | Pending
6105A | K124 | 6212 | E | QRA | 0001 | A | 6105AK124-6212-EQRA-0001 | Q24050972-03-6212-E-QRA-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Risk Assessment: Electrical Hazards | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Risk Assessment: Electrical Hazards |  |  |  | Pending
6105A | K124 | 6212 | E | QRA | 0002 | A | 6105AK124-6212-EQRA-0002 | Q24050972-03-6212-E-QRA-0002 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Risk Assessment: Electrical Hazards | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Risk Assessment: Electrical Hazards |  |  |  | Pending
6105A | K124 | 6212 | E | QRA | 0003 | A | 6105AK124-6212-EQRA-0003 | Q24050972-03-6212-E-QRA-0003 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Lightning Protection Study and Risk Assessment | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Lightning Protection Study and Risk Assessment |  |  |  | Pending
6105A | K124 | 6212 | E | QRA | 0004 | A | 6105AK124-6212-EQRA-0004 | Q24050972-03-6212-E-QRA-0004 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Risk Assessment: Electrical Hazards | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Risk Assessment: Electrical Hazards |  |  |  | Pending
6105A | K124 | 6212 | E | QRA | 0005 | A | 6105AK124-6212-EQRA-0005 | Q24050972-03-6212-E-QRA-0005 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Risk Assessment: Electrical Hazards | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | E | QRA | 0006 | A | 6105AK124-6212-EQRA-0006 | Q24050972-03-6212-E-QRA-0006 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Lightning Protection Study and Risk Assessment | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | E | RPT | 0001 | A | 6105AK124-6212-ERPT-0001 | Q24050972-03-6212-E-RPT-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Load Bank Operational and Maintenance Study | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Load Bank Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Load Bank Operational and Maintenance Study |  |  |  | Pending
6105A | K124 | 6212 | E | RPT | 0002 | A | 6105AK124-6212-ERPT-0002 | Q24050972-03-6212-E-RPT-0002 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Load Bank Operational and Maintenance Study | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Load Bank Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Load Bank Operational and Maintenance Study |  |  |  | Pending
6105A | K124 | 6212 | E | RPT | 0003 | A | 6105AK124-6212-ERPT-0003 | Q24050972-03-6212-E-RPT-0003 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Load Bank Operational and Maintenance Study | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Load Bank Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Load Bank Operational and Maintenance Study |  |  |  | Pending
6105A | K124 | 6212 | E | RPT | 0004 | A | 6105AK124-6212-ERPT-0004 | Q24050972-03-6212-E-RPT-0004 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | HV/MV Operational and Maintenance Study | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - HV/MV Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | HV/MV Operational and Maintenance Study |  |  |  | Pending
6105A | K124 | 6212 | E | RPT | 0005 | A | 6105AK124-6212-ERPT-0005 | Q24050972-03-6212-E-RPT-0005 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Reactive Power Study | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Reactive Power Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Reactive Power Study |  |  |  | Pending
6105A | K124 | 6212 | E | SLD | 0001 | A | 6105AK124-6212-ESLD-0001 | Q24050972-03-6212-E-SLD-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Single Line Diagram | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Single Line Diagram |  |  |  | Pending
6105A | K124 | 6212 | E | SLD | 0002 | A | 6105AK124-6212-ESLD-0002 | Q24050972-03-6212-E-SLD-0002 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Single Line Diagram | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Single Line Diagram |  |  |  | Pending
6105A | K124 | 6212 | E | SLD | 0003 | A | 6105AK124-6212-ESLD-0003 | Q24050972-03-6212-E-SLD-0003 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Electrical Single Line Diagram | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Electrical Single Line Diagram |  |  |  | Pending
6105A | K124 | 6212 | E | SLD | 0004 | A | 6105AK124-6212-ESLD-0004 | Q24050972-03-6212-E-SLD-0004 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Electrical Single Line Diagram | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | E | SLD | 0005 | A | 6105AK124-6212-ESLD-0005 | Q24050972-03-6212-E-SLD-0005 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Electrical Single Line Diagram | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Electrical Single Line Diagram |  |  |  | Pending
6105A | K124 | 6212 | E | SPC | 0001 | A | 6105AK124-6212-ESPC-0001 | Q24050972-03-6212-E-SPC-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Cable and Conductor Specifications | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Cable and Conductor Specifications |  |  |  | Pending
6105A | K124 | 6212 | E | SPC | 0002 | A | 6105AK124-6212-ESPC-0002 | Q24050972-03-6212-E-SPC-0002 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Cable Termination Specifications | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Cable Termination Specifications |  |  |  | Pending
6105A | K124 | 6212 | E | SPC | 0003 | A | 6105AK124-6212-ESPC-0003 | Q24050972-03-6212-E-SPC-0003 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Equipment Communication Specification | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Electrical Equipment Communication Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Equipment Communication Specification |  |  |  | Pending
6105A | K124 | 6212 | E | SPC | 0004 | A | 6105AK124-6212-ESPC-0004 | Q24050972-03-6212-E-SPC-0004 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Cable and Conductor Specifications | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Cable and Conductor Specifications |  |  |  | Pending
6105A | K124 | 6212 | E | SPC | 0005 | A | 6105AK124-6212-ESPC-0005 | Q24050972-03-6212-E-SPC-0005 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Cable Termination Specifications | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Cable Termination Specifications |  |  |  | Pending
6105A | K124 | 6212 | E | SPC | 0006 | A | 6105AK124-6212-ESPC-0006 | Q24050972-03-6212-E-SPC-0006 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Equipment Communication Specification | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Electrical Equipment Communication Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Equipment Communication Specification |  |  |  | Pending
6105A | K124 | 6212 | E | SPC | 0007 | A | 6105AK124-6212-ESPC-0007 | Q24050972-03-6212-E-SPC-0007 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Cable and Conductor Specifications | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Cable and Conductor Specifications |  |  |  | Pending
6105A | K124 | 6212 | E | SPC | 0008 | A | 6105AK124-6212-ESPC-0008 | Q24050972-03-6212-E-SPC-0008 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Cable and Conductor Specifications | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Cable and Conductor Specifications |  |  |  | Pending
6105A | K124 | 6212 | E | SPC | 0009 | A | 6105AK124-6212-ESPC-0009 | Q24050972-03-6212-E-SPC-0009 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Cable Termination Specifications | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Cable Termination Specifications |  |  |  | Pending
6105A | K124 | 6212 | E | SPC | 0010 | A | 6105AK124-6212-ESPC-0010 | Q24050972-03-6212-E-SPC-0010 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Cable Termination Specifications | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | E | SPC | 0011 | A | 6105AK124-6212-ESPC-0011 | Q24050972-03-6212-E-SPC-0011 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Cable and Conductor Specifications | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | E | SPC | 0012 | A | 6105AK124-6212-ESPC-0012 | Q24050972-03-6212-E-SPC-0012 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Electrical Equipment Communication Specification | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Electrical Equipment Communication Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Electrical Equipment Communication Specification |  |  |  | Pending
6105A | K124 | 6212 | E | STD | 0001 | A | 6105AK124-6212-ESTD-0001 | Q24050972-03-6212-E-STD-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Equipment Installation Requirements | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Equipment Installation Requirements |  |  |  | Pending
6105A | K124 | 6212 | E | STD | 0002 | A | 6105AK124-6212-ESTD-0002 | Q24050972-03-6212-E-STD-0002 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Design Standards | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Electrical Design Standards |  |  |  | Pending
6105A | K124 | 6212 | E | STD | 0003 | A | 6105AK124-6212-ESTD-0003 | Q24050972-03-6212-E-STD-0003 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Equipment Installation Requirements | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Equipment Installation Requirements |  |  |  | Pending
6105A | K124 | 6212 | E | STD | 0004 | A | 6105AK124-6212-ESTD-0004 | Q24050972-03-6212-E-STD-0004 |  | Power Station 1 | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Design Standards | Power Station 1 - Wartsila 11kV Mobile Load Bank Interconnect Cables - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila 11kV Mobile Load Bank Interconnect Cables | Electrical Design Standards |  |  |  | Pending
6105A | K124 | 6212 | E | STD | 0005 | A | 6105AK124-6212-ESTD-0005 | Q24050972-03-6212-E-STD-0005 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Thermal Management and Fire Prevention Design | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Thermal Management and Fire Prevention Design |  |  |  | Pending
6105A | K124 | 6212 | E | STD | 0006 | A | 6105AK124-6212-ESTD-0006 | Q24050972-03-6212-E-STD-0006 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Earth Map and Bonding Design | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Earth Map and Bonding Design |  |  |  | Pending
6105A | K124 | 6212 | E | STD | 0007 | A | 6105AK124-6212-ESTD-0007 | Q24050972-03-6212-E-STD-0007 |  | Power Station 1 | Wartsila Mobile Load Bank Earthing Connection Points | Electrical Equipment Installation Requirements | Power Station 1 - Wartsila Mobile Load Bank Earthing Connection Points - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Earthing Connection Points | Electrical Equipment Installation Requirements |  |  |  | Pending
6105A | K124 | 6212 | E | STD | 0008 | A | 6105AK124-6212-ESTD-0008 | Q24050972-03-6212-E-STD-0008 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Thermal Management and Fire Prevention Design | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | E | STD | 0009 | A | 6105AK124-6212-ESTD-0009 | Q24050972-03-6212-E-STD-0009 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Electrical Equipment Installation Requirements | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Electrical Equipment Installation Requirements |  |  |  | Pending
6105A | K124 | 6212 | E | STD | 0010 | A | 6105AK124-6212-ESTD-0010 | Q24050972-03-6212-E-STD-0010 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Electrical Design Standards | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Electrical Design Standards |  |  |  | Pending
6105A | K124 | 6212 | F | DBD | 0001 | A | 6105AK124-6212-FDBD-0001 | Q24050972-03-6212-F-DBD-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Control System Configuration | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Control System Configuration |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0001 | A | 6105AK124-6212-FDIA-0001 | Q24050972-03-6212-F-DIA-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Control Network Architecture Design | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Control Network Architecture Design |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0002 | A | 6105AK124-6212-FDIA-0002 | Q24050972-03-6212-F-DIA-0002 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Control Network Communication Design | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Control Network Communication Design |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0003 | A | 6105AK124-6212-FDIA-0003 | Q24050972-03-6212-F-DIA-0003 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Interface Panel and I/O Schematics | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Interface Panel and I/O Schematics |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0004 | A | 6105AK124-6212-FDIA-0004 | Q24050972-03-6212-F-DIA-0004 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Control Network Architecture Design | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Control Network Architecture Design |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0005 | A | 6105AK124-6212-FDIA-0005 | Q24050972-03-6212-F-DIA-0005 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Control Network Architecture Design | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0006 | A | 6105AK124-6212-FDIA-0006 | Q24050972-03-6212-F-DIA-0006 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Control Network Communication Design | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0007 | A | 6105AK124-6212-FDIA-0007 | Q24050972-03-6212-F-DIA-0007 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Control Network Architecture Design | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Duc | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0008 | A | 6105AK124-6212-FDIA-0008 | Q24050972-03-6212-F-DIA-0008 |  | Power Station 1 | Wartsila Sub Station Switch Room Control System | Control System UPS & Back-up Systems Design | Power Station 1 - Wartsila Sub Station Switch Room Control System - Control System UPS & Back-up Systems Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station Switch Room Control System | Control System UPS & Back-up Systems Design |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0009 | A | 6105AK124-6212-FDIA-0009 | Q24050972-03-6212-F-DIA-0009 |  | Power Station 1 | Wartsila Sub Station Switch Room Control System | Control Network Architecture Design | Power Station 1 - Wartsila Sub Station Switch Room Control System - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station Switch Room Control System | Control Network Architecture Design |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0010 | A | 6105AK124-6212-FDIA-0010 | Q24050972-03-6212-F-DIA-0010 |  | Power Station 1 | Wartsila Sub Station Switch Room Control System | Control Network Communication Design | Power Station 1 - Wartsila Sub Station Switch Room Control System - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station Switch Room Control System | Control Network Communication Design |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0011 | A | 6105AK124-6212-FDIA-0011 | Q24050972-03-6212-F-DIA-0011 |  | Power Station 1 | Wartsila Sub Station Switch Room Control System | Interface Panel and I/O Schematics | Power Station 1 - Wartsila Sub Station Switch Room Control System - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station Switch Room Control System | Interface Panel and I/O Schematics |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0012 | A | 6105AK124-6212-FDIA-0012 | Q24050972-03-6212-F-DIA-0012 |  | Power Station 1 | Wartsila Sub Station SR Control System Comms Interface | Control Network Architecture Design | Power Station 1 - Wartsila Sub Station SR Control System Comms Interface - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station SR Control System Comms Interface | Control Network Architecture Design |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0013 | A | 6105AK124-6212-FDIA-0013 | Q24050972-03-6212-F-DIA-0013 |  | Power Station 1 | Wartsila Sub Station SR Control System Comms Interface | Control Network Communication Design | Power Station 1 - Wartsila Sub Station SR Control System Comms Interface - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station SR Control System Comms Interface | Control Network Communication Design |  |  |  | Pending
6105A | K124 | 6212 | F | DIA | 0014 | A | 6105AK124-6212-FDIA-0014 | Q24050972-03-6212-F-DIA-0014 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Control Network Communication Design | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Control Network Communication Design |  |  |  | Pending
6105A | K124 | 6212 | F | LAY | 0001 | A | 6105AK124-6212-FLAY-0001 | Q24050972-03-6212-F-LAY-0001 |  | Power Station 1 | Wartsila Sub Station Switch Room Control System | HMI and Graphics design | Power Station 1 - Wartsila Sub Station Switch Room Control System - HMI and Graphics design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station Switch Room Control System | HMI and Graphics design |  |  |  | Pending
6105A | K124 | 6212 | F | LAY | 0002 | A | 6105AK124-6212-FLAY-0002 | Q24050972-03-6212-F-LAY-0002 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | HMI and Graphics design | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - HMI and Graphics design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | HMI and Graphics design |  |  |  | Pending
6105A | K124 | 6212 | F | NAR | 0001 | A | 6105AK124-6212-FNAR-0001 | Q24050972-03-6212-F-NAR-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Control System Control Narrative & Interlock Design | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Control System Control Narrative & Interlock Design |  |  |  | Pending
6105A | K124 | 6212 | F | NAR | 0002 | A | 6105AK124-6212-FNAR-0002 | Q24050972-03-6212-F-NAR-0002 |  | Power Station 1 | Wartsila Sub Station Switch Room Control System | Control System Control Narrative & Interlock Design | Power Station 1 - Wartsila Sub Station Switch Room Control System - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station Switch Room Control System | Control System Control Narrative & Interlock Design |  |  |  | Pending
6105A | K124 | 6212 | F | NAR | 0003 | A | 6105AK124-6212-FNAR-0003 | Q24050972-03-6212-F-NAR-0003 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Control System Control Narrative & Interlock Design | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Control System Control Narrative & Interlock Design |  |  |  | Pending
6105A | K124 | 6212 | F | PHL | 0001 | A | 6105AK124-6212-FPHL-0001 | Q24050972-03-6212-F-PHL-0001 |  | Power Station 1 | Wartsila Sub Station Switch Room Control System | Control System Control Philosophy | Power Station 1 - Wartsila Sub Station Switch Room Control System - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station Switch Room Control System | Control System Control Philosophy |  |  |  | Pending
6105A | K124 | 6212 | F | PHL | 0002 | A | 6105AK124-6212-FPHL-0002 | Q24050972-03-6212-F-PHL-0002 |  | Power Station 1 | Wartsila Sub Station SR Control System Comms Interface | Control System Control Philosophy | Power Station 1 - Wartsila Sub Station SR Control System Comms Interface - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station SR Control System Comms Interface | Control System Control Philosophy |  |  |  | Pending
6105A | K124 | 6212 | F | PHL | 0003 | A | 6105AK124-6212-FPHL-0003 | Q24050972-03-6212-F-PHL-0003 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Control System Control Philosophy | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Control System Control Philosophy |  |  |  | Pending
6105A | K124 | 6212 | F | PRC | 0001 | A | 6105AK124-6212-FPRC-0001 | Q24050972-03-6212-F-PRC-0001 |  | Power Station 1 | Wartsila Sub Station Switch Room Control System | Alarm Classification Methodology | Power Station 1 - Wartsila Sub Station Switch Room Control System - Alarm Classification Methodology |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station Switch Room Control System | Alarm Classification Methodology |  |  |  | Pending
6105A | K124 | 6212 | F | PRC | 0002 | A | 6105AK124-6212-FPRC-0002 | Q24050972-03-6212-F-PRC-0002 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Alarm Classification Methodology | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Alarm Classification Methodology |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Alarm Classification Methodology |  |  |  | Pending
6105A | K124 | 6212 | F | SPC | 0001 | A | 6105AK124-6212-FSPC-0001 | Q24050972-03-6212-F-SPC-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Termination Bay Control Interface | Control System Design Requirements | Power Station 1 - Wartsila Mobile Load Bank Termination Bay Control Interface - Control System Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Termination Bay Control Interface | Control System Design Requirements |  |  |  | Pending
6105A | K124 | 6212 | F | SPC | 0002 | A | 6105AK124-6212-FSPC-0002 | Q24050972-03-6212-F-SPC-0002 |  | Power Station 1 | Wartsila Sub Station Switch Room Control System | Control System Design Requirements | Power Station 1 - Wartsila Sub Station Switch Room Control System - Control System Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station Switch Room Control System | Control System Design Requirements |  |  |  | Pending
6105A | K124 | 6212 | F | SPC | 0003 | A | 6105AK124-6212-FSPC-0003 | Q24050972-03-6212-F-SPC-0003 |  | Power Station 1 | Wartsila Sub Station Switch Room Control System | Historian and Server Design | Power Station 1 - Wartsila Sub Station Switch Room Control System - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Sub Station Switch Room Control System | Historian and Server Design |  |  |  | Pending
6105A | K124 | 6212 | F | SPC | 0004 | A | 6105AK124-6212-FSPC-0004 | Q24050972-03-6212-F-SPC-0004 |  | Power Station 1 | 33kV Wartsila Sub Station SR Protection Relays | Historian and Server Design | Power Station 1 - 33kV Wartsila Sub Station SR Protection Relays - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Wartsila Sub Station SR Protection Relays | Historian and Server Design |  |  |  | Pending
6105A | K124 | 6212 | M | PSP | 0001 | A | 6105AK124-6212-MPSP-0001 | Q24050972-03-6212-M-PSP-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Pipe and Cable Support Racks Design | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Pipe and Cable Support Racks Design |  |  |  | Pending
6105A | K124 | 6212 | M | SPC | 0001 | A | 6105AK124-6212-MSPC-0001 | Q24050972-03-6212-M-SPC-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Material Selection and Verification Specification | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Material Selection and Verification Specification |  |  |  | Pending
6105A | K124 | 6212 | M | CAL | 0001 | A | 6105AK124-6212-MCAL-0001 | Q24050972-03-6212-M-CAL-0001 |  | Power Station 1 | Wartsila Mobile Load Bank Cable Racks and Ducts | Vessel and Structure Design with Stress Analysis Calcs | Power Station 1 - Wartsila Mobile Load Bank Cable Racks and Ducts - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Wartsila Mobile Load Bank Cable Racks and Ducts | Vessel and Structure Design with Stress Analysis Calcs |  |  |  | Pending
6105A | K124 | 6212 | M | PSP | 0002 | A | 6105AK124-6212-MPSP-0002 | Q24050972-03-6212-M-PSP-0002 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Pipe and Cable Support Racks Design | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | M | SPC | 0002 | A | 6105AK124-6212-MSPC-0002 | Q24050972-03-6212-M-SPC-0002 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Material Selection and Verification Specification | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | M | CAL | 0002 | A | 6105AK124-6212-MCAL-0002 | Q24050972-03-6212-M-CAL-0002 |  | Power Station 1 | 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS | Vessel and Structure Design with Stress Analysis Calcs | Power Station 1 - 33kV Interconnect Cable Racks and Ducts between Wartsila and M-Intake SS - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cable Racks and Ducts | Wartsila and M-Intake SS |  |  |  | Pending
6105A | K124 | 6212 | W | ELE | 0001 | A | 6105AK124-6212-WELE-0001 | Q24050972-03-6212-W-ELE-0001 |  | Power Station 1 | 33kV Interconnect Cables between Wartsila and M-Intake Sub Station | Bulk Earth Works Design and Report | Power Station 1 - 33kV Interconnect Cables between Wartsila and M-Intake Sub Station - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and M-Intake Sub Station |  |  |  | Pending
6105A | K124 | 6242 | B | STD | 0001 | A | 6105AK124-6242-BSTD-0001 | Q24050972-03-6242-B-STD-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | System Detailed Engineering Design | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | B | SPC | 0001 | A | 6105AK124-6242-BSPC-0001 | Q24050972-03-6242-B-SPC-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Functional Design Specification | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | FND | 0001 | A | 6105AK124-6242-CFND-0001 | Q24050972-03-6242-C-FND-0001 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | Civil Foundation Design | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing for Power Station Substation | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6242 | C | FND | 0002 | A | 6105AK124-6242-CFND-0002 | Q24050972-03-6242-C-FND-0002 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Civil Foundation Design | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump from Bunds | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0001 | A | 6105AK124-6242-CGAD-0001 | Q24050972-03-6242-C-GAD-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Cables, OHL and Fibre Route GA | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0002 | A | 6105AK124-6242-CGAD-0002 | Q24050972-03-6242-C-GAD-0002 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Terrace Equipment GA | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0003 | A | 6105AK124-6242-CGAD-0003 | Q24050972-03-6242-C-GAD-0003 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Laydown Areas and Temp Buildings GA | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Wartsila and Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0004 | A | 6105AK124-6242-CGAD-0004 | Q24050972-03-6242-C-GAD-0004 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Buildings and Structures GA | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0005 | A | 6105AK124-6242-CGAD-0005 | Q24050972-03-6242-C-GAD-0005 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Cables, OHL and Fibre Route GA | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0006 | A | 6105AK124-6242-CGAD-0006 | Q24050972-03-6242-C-GAD-0006 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Key Emergency Points and Equipment | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0007 | A | 6105AK124-6242-CGAD-0007 | Q24050972-03-6242-C-GAD-0007 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Terrace Equipment GA | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0008 | A | 6105AK124-6242-CGAD-0008 | Q24050972-03-6242-C-GAD-0008 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Disposal Areas General Arrangement | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0009 | A | 6105AK124-6242-CGAD-0009 | Q24050972-03-6242-C-GAD-0009 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Laydown Areas and Temp Buildings GA | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0010 | A | 6105AK124-6242-CGAD-0010 | Q24050972-03-6242-C-GAD-0010 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Stormwater and Effluent System Design | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0011 | A | 6105AK124-6242-CGAD-0011 | Q24050972-03-6242-C-GAD-0011 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Lighting Design and Layout GA | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0012 | A | 6105AK124-6242-CGAD-0012 | Q24050972-03-6242-C-GAD-0012 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Roads, Pathways, Offloading Areas and Fences GA | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0013 | A | 6105AK124-6242-CGAD-0013 | Q24050972-03-6242-C-GAD-0013 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | Roads, Pathways, Offloading Areas and Fences GA | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0014 | A | 6105AK124-6242-CGAD-0014 | Q24050972-03-6242-C-GAD-0014 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | Lighting Design and Layout GA | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0015 | A | 6105AK124-6242-CGAD-0015 | Q24050972-03-6242-C-GAD-0015 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | Cables, OHL and Fibre Route GA | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | GAD | 0016 | A | 6105AK124-6242-CGAD-0016 | Q24050972-03-6242-C-GAD-0016 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Stormwater and Effluent System Design | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump from Bunds | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | MDL | 0001 | A | 6105AK124-6242-CMDL-0001 | Q24050972-03-6242-C-MDL-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | 3D Designs and Drawings | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | MDL | 0002 | A | 6105AK124-6242-CMDL-0002 | Q24050972-03-6242-C-MDL-0002 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | 3D Designs and Drawings | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | MDL | 0003 | A | 6105AK124-6242-CMDL-0003 | Q24050972-03-6242-C-MDL-0003 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | 3D Designs and Drawings | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | MDL | 0004 | A | 6105AK124-6242-CMDL-0004 | Q24050972-03-6242-C-MDL-0004 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | 3D Designs and Drawings | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | PLN | 0001 | A | 6105AK124-6242-CPLN-0001 | Q24050972-03-6242-C-PLN-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Civil Works Execution Plan | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | PLN | 0002 | A | 6105AK124-6242-CPLN-0002 | Q24050972-03-6242-C-PLN-0002 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Civil Works Execution Plan | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | PPL | 0001 | A | 6105AK124-6242-CPPL-0001 | Q24050972-03-6242-C-PPL-0001 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Operational & Maint Access Routes Design | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SEC | 0007 | A | 6105AK124-6242-CSEC-0007 | Q24050972-03-6242-C-SEC-0007 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Structural Earthing and Bonding Design | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SHP | 0001 | A | 6105AK124-6242-CSHP-0001 | Q24050972-03-6242-C-SHP-0001 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | Equipment Assembly Drawings | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SPC | 0001 | A | 6105AK124-6242-CSPC-0001 | Q24050972-03-6242-C-SPC-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Excavation, Trenching and Compacting Design | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SPC | 0002 | A | 6105AK124-6242-CSPC-0002 | Q24050972-03-6242-C-SPC-0002 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Steel Structures Corrosion Protection Specification | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Protection Specification |  |  |  | Pending
6105A | K124 | 6242 | C | SPC | 0003 | A | 6105AK124-6242-CSPC-0003 | Q24050972-03-6242-C-SPC-0003 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Civil Design Requirements | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SPC | 0004 | A | 6105AK124-6242-CSPC-0004 | Q24050972-03-6242-C-SPC-0004 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Excavation, Trenching and Compacting Design | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SPC | 0005 | A | 6105AK124-6242-CSPC-0005 | Q24050972-03-6242-C-SPC-0005 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Concrete Construction Material Specifications | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SSD | 0001 | A | 6105AK124-6242-CSSD-0001 | Q24050972-03-6242-C-SSD-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Steel Support Structures Design | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | STD | 0001 | A | 6105AK124-6242-CSTD-0001 | Q24050972-03-6242-C-STD-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Underground Pipe Route and Cable Bedding Design | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | STD | 0002 | A | 6105AK124-6242-CSTD-0002 | Q24050972-03-6242-C-STD-0002 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Bund-wall Requirements and Design | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | STD | 0003 | A | 6105AK124-6242-CSTD-0003 | Q24050972-03-6242-C-STD-0003 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Civil Construction Requirements | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | STD | 0004 | A | 6105AK124-6242-CSTD-0004 | Q24050972-03-6242-C-STD-0004 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Underground Pipe Route and Cable Bedding Design | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | STD | 0005 | A | 6105AK124-6242-CSTD-0005 | Q24050972-03-6242-C-STD-0005 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | Underground Pipe Route and Cable Bedding Design | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SPC | 0006 | A | 6105AK124-6242-CSPC-0006 | Q24050972-03-6242-C-SPC-0006 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | Excavation, Trenching and Compacting Design | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SPC | 0007 | A | 6105AK124-6242-CSPC-0007 | Q24050972-03-6242-C-SPC-0007 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | Concrete Construction Material Specifications | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SPC | 0008 | A | 6105AK124-6242-CSPC-0008 | Q24050972-03-6242-C-SPC-0008 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | Steel Structures Corrosion Protection Specification | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SPC | 0009 | A | 6105AK124-6242-CSPC-0009 | Q24050972-03-6242-C-SPC-0009 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Civil Design Requirements | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SPC | 0010 | A | 6105AK124-6242-CSPC-0010 | Q24050972-03-6242-C-SPC-0010 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Excavation, Trenching and Compacting Design | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SPC | 0011 | A | 6105AK124-6242-CSPC-0011 | Q24050972-03-6242-C-SPC-0011 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Concrete Construction Material Specifications | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | SSD | 0002 | A | 6105AK124-6242-CSSD-0002 | Q24050972-03-6242-C-SSD-0002 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | Steel Support Structures Design | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | STD | 0006 | A | 6105AK124-6242-CSTD-0006 | Q24050972-03-6242-C-STD-0006 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Bund-wall Requirements and Design | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | STD | 0007 | A | 6105AK124-6242-CSTD-0007 | Q24050972-03-6242-C-STD-0007 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Fire Protection System Design (Civil Works) | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | STD | 0008 | A | 6105AK124-6242-CSTD-0008 | Q24050972-03-6242-C-STD-0008 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Civil Construction Requirements | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | C | STD | 0009 | A | 6105AK124-6242-CSTD-0009 | Q24050972-03-6242-C-STD-0009 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Underground Pipe Route and Cable Bedding Design | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | E | CAL | 0001 | A | 6105AK124-6242-ECAL-0001 | Q24050972-03-6242-E-CAL-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Cable and Conductor Sizing (incl Volt Drop Calcs) | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | E | CAL | 0002 | A | 6105AK124-6242-ECAL-0002 | Q24050972-03-6242-E-CAL-0002 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Conductor Sag and Tension Plan | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | E | DIA | 0001 | A | 6105AK124-6242-EDIA-0001 | Q24050972-03-6242-E-DIA-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Cable Block Diagrams and Schedules | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | E | DIA | 0002 | A | 6105AK124-6242-EDIA-0002 | Q24050972-03-6242-E-DIA-0002 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Electrical Circuit Diagrams (Schematics) | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | E | DIA | 0003 | A | 6105AK124-6242-EDIA-0003 | Q24050972-03-6242-E-DIA-0003 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Protection Relay Design | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Protection Relay Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | E | MDL | 0001 | A | 6105AK124-6242-EMDL-0001 | Q24050972-03-6242-E-MDL-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | ETAP Network Model | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | E | QRA | 0001 | A | 6105AK124-6242-EQRA-0001 | Q24050972-03-6242-E-QRA-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Risk Assessment: Electrical Hazards | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | E | SLD | 0001 | A | 6105AK124-6242-ESLD-0001 | Q24050972-03-6242-E-SLD-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Electrical Single Line Diagram | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | E | SPC | 0001 | A | 6105AK124-6242-ESPC-0001 | Q24050972-03-6242-E-SPC-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Cable Termination Specifications | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | F | DIA | 0001 | A | 6105AK124-6242-FDIA-0001 | Q24050972-03-6242-F-DIA-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Control Network Architecture Design | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | F | DIA | 0002 | A | 6105AK124-6242-FDIA-0002 | Q24050972-03-6242-F-DIA-0002 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Control Network Communication Design | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | I | DIA | 0001 | A | 6105AK124-6242-IDIA-0001 | Q24050972-03-6242-I-DIA-0001 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | Closed Circuit Television (CCTV) Design | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - Closed Circuit Television (CCTV) Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing for Power Station Substation | Closed Circuit Television (CCTV) Design |  |  |  | Pending
6105A | K124 | 6242 | I | DIA | 0002 | A | 6105AK124-6242-IDIA-0002 | Q24050972-03-6242-I-DIA-0002 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Smoke and Fire Detection System Design | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | I | ITD | 0001 | A | 6105AK124-6242-IITD-0001 | Q24050972-03-6242-I-ITD-0001 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Instrument Wiring Loop Diagrams and Cable Schedule | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | I | SPC | 0001 | A | 6105AK124-6242-ISPC-0001 | Q24050972-03-6242-I-SPC-0001 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Junction Box and Interface Cabinet Design | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | I | LST | 0001 | A | 6105AK124-6242-ILST-0001 | Q24050972-03-6242-I-LST-0001 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Equipment Alarm and Trip Level Register | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | I | QRA | 0001 | A | 6105AK124-6242-IQRA-0001 | Q24050972-03-6242-I-QRA-0001 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Risk Assessment: Fire and Explosions | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | M | PRC | 0001 | A | 6105AK124-6242-MPRC-0001 | Q24050972-03-6242-M-PRC-0001 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Rigging Study and Lifting Equipment Design | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | T | RPT | 0001 | A | 6105AK124-6242-TRPT-0001 | Q24050972-03-6242-T-RPT-0001 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Site Surveying & Geotechnical Report | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | T | RPT | 0002 | A | 6105AK124-6242-TRPT-0002 | Q24050972-03-6242-T-RPT-0002 |  | 33/220 kV Power Station Substation | Perimeter Fencing for Power Station Substation | Site Surveying & Geotechnical Report | 33/220 kV Power Station Substation - Perimeter Fencing for Power Station Substation - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | T | RPT | 0003 | A | 6105AK124-6242-TRPT-0003 | Q24050972-03-6242-T-RPT-0003 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Site Surveying & Geotechnical Report | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | T | SPC | 0001 | A | 6105AK124-6242-TSPC-0001 | Q24050972-03-6242-T-SPC-0001 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Civil Design and Requirements | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | W | ELE | 0001 | A | 6105AK124-6242-WELE-0001 | Q24050972-03-6242-W-ELE-0001 |  | 33/220 kV Power Station Substation | 33kV Interconnect Cables between Wartsila and Power Station Substation | Bulk Earth Works Design and Report | 33/220 kV Power Station Substation - 33kV Interconnect Cables between Wartsila and Power Station Substation - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | W | ELE | 0002 | A | 6105AK124-6242-WELE-0002 | Q24050972-03-6242-W-ELE-0002 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Bulk Earth Works Design and Report | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | W | LAY | 0001 | A | 6105AK124-6242-WLAY-0001 | Q24050972-03-6242-W-LAY-0001 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Drainage, Run-off and Impoundment Design | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | W | TRP | 0001 | A | 6105AK124-6242-WTRP-0001 | Q24050972-03-6242-W-TRP-0001 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Soil Classification and Nomination Deliverables | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | W | TRP | 0002 | A | 6105AK124-6242-WTRP-0002 | Q24050972-03-6242-W-TRP-0002 |  | 33/220 kV Power Station Substation | Terrace, Roads and Access-ways for Power Station Substation | Soil Resistivity Testing Report | 33/220 kV Power Station Substation - Terrace, Roads and Access-ways for Power Station Substation - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | W | ELE | 0003 | A | 6105AK124-6242-WELE-0003 | Q24050972-03-6242-W-ELE-0003 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Bulk Earth Works Design and Report | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6242 | W | LAY | 0002 | A | 6105AK124-6242-WLAY-0002 | Q24050972-03-6242-W-LAY-0002 |  | 33/220 kV Power Station Substation | Oil Collection Sump from Bunds for Power Station Substation | Drainage, Run-off and Impoundment Design | 33/220 kV Power Station Substation - Oil Collection Sump from Bunds for Power Station Substation - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Oil Collection Sump | Power Station Substation |  |  |  | Pending
6105A | K124 | 6243 | B | STD | 0001 | A | 6105AK124-6243-BSTD-0001 | Q24050972-03-6243-B-STD-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | System Detailed Engineering Design | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | B | SPC | 0001 | A | 6105AK124-6243-BSPC-0001 | Q24050972-03-6243-B-SPC-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Functional Design Specification | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | C | FND | 0001 | A | 6105AK124-6243-CFND-0001 | Q24050972-03-6243-C-FND-0001 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | Civil Foundation Design | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0001 | A | 6105AK124-6243-CGAD-0001 | Q24050972-03-6243-C-GAD-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Cables, OHL and Fibre Route GA | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0002 | A | 6105AK124-6243-CGAD-0002 | Q24050972-03-6243-C-GAD-0002 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Terrace Equipment GA | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0003 | A | 6105AK124-6243-CGAD-0003 | Q24050972-03-6243-C-GAD-0003 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Laydown Areas and Temp Buildings GA | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0004 | A | 6105AK124-6243-CGAD-0004 | Q24050972-03-6243-C-GAD-0004 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Buildings and Structures GA | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0005 | A | 6105AK124-6243-CGAD-0005 | Q24050972-03-6243-C-GAD-0005 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Cables, OHL and Fibre Route GA | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0006 | A | 6105AK124-6243-CGAD-0006 | Q24050972-03-6243-C-GAD-0006 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Key Emergency Points and Equipment | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0007 | A | 6105AK124-6243-CGAD-0007 | Q24050972-03-6243-C-GAD-0007 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Terrace Equipment GA | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0008 | A | 6105AK124-6243-CGAD-0008 | Q24050972-03-6243-C-GAD-0008 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Disposal Areas General Arrangement | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0009 | A | 6105AK124-6243-CGAD-0009 | Q24050972-03-6243-C-GAD-0009 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Laydown Areas and Temp Buildings GA | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0010 | A | 6105AK124-6243-CGAD-0010 | Q24050972-03-6243-C-GAD-0010 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Stormwater and Effluent System Design | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0011 | A | 6105AK124-6243-CGAD-0011 | Q24050972-03-6243-C-GAD-0011 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Lighting Design and Layout GA | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0012 | A | 6105AK124-6243-CGAD-0012 | Q24050972-03-6243-C-GAD-0012 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Roads, Pathways, Offloading Areas and Fences GA | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0013 | A | 6105AK124-6243-CGAD-0013 | Q24050972-03-6243-C-GAD-0013 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | Roads, Pathways, Offloading Areas and Fences GA | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0014 | A | 6105AK124-6243-CGAD-0014 | Q24050972-03-6243-C-GAD-0014 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | Lighting Design and Layout GA | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | GAD | 0015 | A | 6105AK124-6243-CGAD-0015 | Q24050972-03-6243-C-GAD-0015 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | Cables, OHL and Fibre Route GA | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | MDL | 0001 | A | 6105AK124-6243-CMDL-0001 | Q24050972-03-6243-C-MDL-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | 3D Designs and Drawings | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | C | MDL | 0002 | A | 6105AK124-6243-CMDL-0002 | Q24050972-03-6243-C-MDL-0002 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | 3D Designs and Drawings | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | MDL | 0003 | A | 6105AK124-6243-CMDL-0003 | Q24050972-03-6243-C-MDL-0003 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | 3D Designs and Drawings | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | PLN | 0001 | A | 6105AK124-6243-CPLN-0001 | Q24050972-03-6243-C-PLN-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Civil Works Execution Plan | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | C | PPL | 0001 | A | 6105AK124-6243-CPPL-0001 | Q24050972-03-6243-C-PPL-0001 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Operational & Maint Access Routes Design | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | SEC | 0001 | A | 6105AK124-6243-CSEC-0001 | Q24050972-03-6243-C-SEC-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Structural Earthing and Bonding Design | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | C | SHP | 0001 | A | 6105AK124-6243-CSHP-0001 | Q24050972-03-6243-C-SHP-0001 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | Equipment Assembly Drawings | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | SPC | 0002 | A | 6105AK124-6243-CSPC-0002 | Q24050972-03-6243-C-SPC-0002 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Excavation, Trenching and Compacting Design | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | C | SPC | 0003 | A | 6105AK124-6243-CSPC-0003 | Q24050972-03-6243-C-SPC-0003 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Steel Structures Corrosion Protection Specification | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Protection Specification |  |  |  | Pending
6105A | K124 | 6243 | C | SPC | 0004 | A | 6105AK124-6243-CSPC-0004 | Q24050972-03-6243-C-SPC-0004 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Civil Design Requirements | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | SPC | 0005 | A | 6105AK124-6243-CSPC-0005 | Q24050972-03-6243-C-SPC-0005 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Excavation, Trenching and Compacting Design | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | SPC | 0006 | A | 6105AK124-6243-CSPC-0006 | Q24050972-03-6243-C-SPC-0006 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Concrete Construction Material Specifications | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | SPC | 0007 | A | 6105AK124-6243-CSPC-0007 | Q24050972-03-6243-C-SPC-0007 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | Excavation, Trenching and Compacting Design | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | SPC | 0008 | A | 6105AK124-6243-CSPC-0008 | Q24050972-03-6243-C-SPC-0008 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | Concrete Construction Material Specifications | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Material Specifications |  |  |  | Pending
6105A | K124 | 6243 | C | SPC | 0009 | A | 6105AK124-6243-CSPC-0009 | Q24050972-03-6243-C-SPC-0009 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | Steel Structures Corrosion Protection Specification | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Protection Specification |  |  |  | Pending
6105A | K124 | 6243 | C | SSD | 0001 | A | 6105AK124-6243-CSSD-0001 | Q24050972-03-6243-C-SSD-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Steel Support Structures Design | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | C | SSD | 0002 | A | 6105AK124-6243-CSSD-0002 | Q24050972-03-6243-C-SSD-0002 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | Steel Support Structures Design | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | STD | 0001 | A | 6105AK124-6243-CSTD-0001 | Q24050972-03-6243-C-STD-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Underground Pipe Route and Cable Bedding Design | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | C | STD | 0002 | A | 6105AK124-6243-CSTD-0002 | Q24050972-03-6243-C-STD-0002 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Bund-wall Requirements and Design | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | STD | 0003 | A | 6105AK124-6243-CSTD-0003 | Q24050972-03-6243-C-STD-0003 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Civil Construction Requirements | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | STD | 0004 | A | 6105AK124-6243-CSTD-0004 | Q24050972-03-6243-C-STD-0004 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Underground Pipe Route and Cable Bedding Design | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | C | STD | 0005 | A | 6105AK124-6243-CSTD-0005 | Q24050972-03-6243-C-STD-0005 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | Underground Pipe Route and Cable Bedding Design | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | E | CAL | 0001 | A | 6105AK124-6243-ECAL-0001 | Q24050972-03-6243-E-CAL-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Cable and Conductor Sizing (incl Volt Drop Calcs) | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | E | CAL | 0002 | A | 6105AK124-6243-ECAL-0002 | Q24050972-03-6243-E-CAL-0002 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Conductor Sag and Tension Plan | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | E | DIA | 0001 | A | 6105AK124-6243-EDIA-0001 | Q24050972-03-6243-E-DIA-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Cable Block Diagrams and Schedules | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Diagrams and Schedules |  |  |  | Pending
6105A | K124 | 6243 | E | DIA | 0002 | A | 6105AK124-6243-EDIA-0002 | Q24050972-03-6243-E-DIA-0002 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Electrical Circuit Diagrams (Schematics) | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | E | DIA | 0003 | A | 6105AK124-6243-EDIA-0003 | Q24050972-03-6243-E-DIA-0003 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Protection Relay Design | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Protection Relay Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | E | MDL | 0001 | A | 6105AK124-6243-EMDL-0001 | Q24050972-03-6243-E-MDL-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | ETAP Network Model | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | E | QRA | 0001 | A | 6105AK124-6243-EQRA-0001 | Q24050972-03-6243-E-QRA-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Risk Assessment: Electrical Hazards | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | E | SLD | 0004 | A | 6105AK124-6243-ESLD-0004 | Q24050972-03-6243-E-SLD-0004 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Electrical Single Line Diagram | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6243 | E | SPC | 0001 | A | 6105AK124-6243-ESPC-0001 | Q24050972-03-6243-E-SPC-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Cable Termination Specifications | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Specifications |  |  |  | Pending
6105A | K124 | 6243 | F | DIA | 0001 | A | 6105AK124-6243-FDIA-0001 | Q24050972-03-6243-F-DIA-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Control Network Architecture Design | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Architecture Design |  |  |  | Pending
6105A | K124 | 6243 | F | DIA | 0002 | A | 6105AK124-6243-FDIA-0002 | Q24050972-03-6243-F-DIA-0002 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Control Network Communication Design | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Communication Design |  |  |  | Pending
6105A | K124 | 6243 | I | DIA | 0001 | A | 6105AK124-6243-IDIA-0001 | Q24050972-03-6243-I-DIA-0001 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | Closed Circuit Television (CCTV) Design | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - Closed Circuit Television (CCTV) Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | M | PRC | 0001 | A | 6105AK124-6243-MPRC-0001 | Q24050972-03-6243-M-PRC-0001 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Rigging Study and Lifting Equipment Design | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | T | RPT | 0001 | A | 6105AK124-6243-TRPT-0001 | Q24050972-03-6243-T-RPT-0001 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Site Surveying & Geotechnical Report | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | T | RPT | 0002 | A | 6105AK124-6243-TRPT-0002 | Q24050972-03-6243-T-RPT-0002 |  | 220/33 kV Plant Main Substation | Perimeter Fencing for Plant Main Substation | Site Surveying & Geotechnical Report | 220/33 kV Plant Main Substation - Perimeter Fencing for Plant Main Substation - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | W | ELE | 0001 | A | 6105AK124-6243-WELE-0001 | Q24050972-03-6243-W-ELE-0001 |  | 220/33 kV Plant Main Substation | 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd | Bulk Earth Works Design and Report | 220/33 kV Plant Main Substation - 33kV Interconnect Cables between PM Substation and Main Cons Switch Yrd - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Interconnect Cables | Main Cons Switch Yrd |  |  |  | Pending
6105A | K124 | 6243 | W | ELE | 0002 | A | 6105AK124-6243-WELE-0002 | Q24050972-03-6243-W-ELE-0002 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Bulk Earth Works Design and Report | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation | Plant Main Substation | Plant Main Substation |  | Pending
6105A | K124 | 6243 | W | LAY | 0001 | A | 6105AK124-6243-WLAY-0001 | Q24050972-03-6243-W-LAY-0001 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Drainage, Run-off and Impoundment Design | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | W | TRP | 0001 | A | 6105AK124-6243-WTRP-0001 | Q24050972-03-6243-W-TRP-0001 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Soil Classification and Nomination Deliverables | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6243 | W | TRP | 0002 | A | 6105AK124-6243-WTRP-0002 | Q24050972-03-6243-W-TRP-0002 |  | 220/33 kV Plant Main Substation | Terrace, Roads and Access-ways for Plant Main Substation | Soil Resistivity Testing Report | 220/33 kV Plant Main Substation - Terrace, Roads and Access-ways for Plant Main Substation - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Plant Main Substation |  |  |  | Pending
6105A | K124 | 6251 | B | DBD | 0001 | A | 6105AK124-6251-BDBD-0001 | Q24050972-03-6251-B-DBD-0001 |  | Load Bank | Load Bank Project Package | Design Criteria / Basis of Design | Load Bank - Load Bank Project Package - Design Criteria / Basis of Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Load Bank Project Package | Basis of Design |  |  |  | Pending
6105A | K124 | 6251 | B | PHL | 0001 | A | 6105AK124-6251-BPHL-0001 | Q24050972-03-6251-B-PHL-0001 |  | Load Bank | Load Bank Project Package | Control Philosophy | Load Bank - Load Bank Project Package - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Load Bank Project Package | Control Philosophy |  |  |  | Pending
6105A | K124 | 6251 | B | PHL | 0002 | A | 6105AK124-6251-BPHL-0002 | Q24050972-03-6251-B-PHL-0002 |  | Load Bank | Load Bank Project Package | Synchronization Philosophy | Load Bank - Load Bank Project Package - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Load Bank Project Package | Synchronization Philosophy |  |  |  | Pending
6105A | K124 | 6251 | B | PHL | 0003 | A | 6105AK124-6251-BPHL-0003 | Q24050972-03-6251-B-PHL-0003 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Control Philosophy | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | B | PHL | 0004 | A | 6105AK124-6251-BPHL-0004 | Q24050972-03-6251-B-PHL-0004 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Synchronization Philosophy | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | B | PHL | 0005 | A | 6105AK124-6251-BPHL-0005 | Q24050972-03-6251-B-PHL-0005 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Power Management System Philosophy | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Power Management System Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | B | PHL | 0006 | A | 6105AK124-6251-BPHL-0006 | Q24050972-03-6251-B-PHL-0006 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Control Philosophy | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Control Philosophy |  |  |  | Pending
6105A | K124 | 6251 | B | PHL | 0007 | A | 6105AK124-6251-BPHL-0007 | Q24050972-03-6251-B-PHL-0007 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Synchronization Philosophy | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Synchronization Philosophy |  |  |  | Pending
6105A | K124 | 6251 | B | PHL | 0008 | A | 6105AK124-6251-BPHL-0008 | Q24050972-03-6251-B-PHL-0008 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Power Management System Philosophy | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Power Management System Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | System Philosophy |  |  |  | Pending
6105A | K124 | 6251 | B | PHL | 0009 | A | 6105AK124-6251-BPHL-0009 | Q24050972-03-6251-B-PHL-0009 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Control Philosophy | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Control Philosophy |  |  |  | Pending
6105A | K124 | 6251 | B | PHL | 0010 | A | 6105AK124-6251-BPHL-0010 | Q24050972-03-6251-B-PHL-0010 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Synchronization Philosophy | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Synchronization Philosophy |  |  |  | Pending
6105A | K124 | 6251 | B | PHL | 0011 | A | 6105AK124-6251-BPHL-0011 | Q24050972-03-6251-B-PHL-0011 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Power Management System Philosophy | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Power Management System Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | System Philosophy |  |  |  | Pending
6105A | K124 | 6251 | B | SPC | 0001 | A | 6105AK124-6251-BSPC-0001 | Q24050972-03-6251-B-SPC-0001 |  | Load Bank | Load Bank Project Package | Functional Design Specification | Load Bank - Load Bank Project Package - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Load Bank Project Package | Design Specification |  |  |  | Pending
6105A | K124 | 6251 | B | STD | 0001 | A | 6105AK124-6251-BSTD-0001 | Q24050972-03-6251-B-STD-0001 |  | Load Bank | Load Bank Project Package | System Detailed Engineering Design | Load Bank - Load Bank Project Package - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Load Bank Project Package | Engineering Design |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0001 | A | 6105AK124-6251-CFND-0001 | Q24050972-03-6251-C-FND-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Civil Foundation Design | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Foundation Design |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0002 | A | 6105AK124-6251-CFND-0002 | Q24050972-03-6251-C-FND-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Plinth Design and Layout | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Design and Layout |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0003 | A | 6105AK124-6251-CFND-0003 | Q24050972-03-6251-C-FND-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Civil Foundation Design | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Foundation Design |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0004 | A | 6105AK124-6251-CFND-0004 | Q24050972-03-6251-C-FND-0004 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Civil Foundation Design | Load Bank - Platform and Foundations for Wartsila Load Bank - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0005 | A | 6105AK124-6251-CFND-0005 | Q24050972-03-6251-C-FND-0005 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Plinth Design and Layout | Load Bank - Platform and Foundations for Wartsila Load Bank - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0006 | A | 6105AK124-6251-CFND-0006 | Q24050972-03-6251-C-FND-0006 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | Civil Foundation Design | Load Bank - Perimeter Fencing for for Wartsila Load Bank - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0007 | A | 6105AK124-6251-CFND-0007 | Q24050972-03-6251-C-FND-0007 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Civil Foundation Design | Load Bank - Small Power and Lighting for Wartsila Load Bank - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0008 | A | 6105AK124-6251-CFND-0008 | Q24050972-03-6251-C-FND-0008 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Civil Foundation Design | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0009 | A | 6105AK124-6251-CFND-0009 | Q24050972-03-6251-C-FND-0009 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Civil Foundation Design | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0010 | A | 6105AK124-6251-CFND-0010 | Q24050972-03-6251-C-FND-0010 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Plinth Design and Layout | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0011 | A | 6105AK124-6251-CFND-0011 | Q24050972-03-6251-C-FND-0011 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Civil Foundation Design | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0012 | A | 6105AK124-6251-CFND-0012 | Q24050972-03-6251-C-FND-0012 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Civil Foundation Design | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | FND | 0013 | A | 6105AK124-6251-CFND-0013 | Q24050972-03-6251-C-FND-0013 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Civil Foundation Design | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0001 | A | 6105AK124-6251-CGAD-0001 | Q24050972-03-6251-C-GAD-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Buildings and Structures GA | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0002 | A | 6105AK124-6251-CGAD-0002 | Q24050972-03-6251-C-GAD-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Cables, OHL and Fibre Route GA | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0003 | A | 6105AK124-6251-CGAD-0003 | Q24050972-03-6251-C-GAD-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Terrace Equipment GA | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0004 | A | 6105AK124-6251-CGAD-0004 | Q24050972-03-6251-C-GAD-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Terrace Equipment GA | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0005 | A | 6105AK124-6251-CGAD-0005 | Q24050972-03-6251-C-GAD-0005 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Roads, Pathways, Offloading Areas and Fences GA | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0006 | A | 6105AK124-6251-CGAD-0006 | Q24050972-03-6251-C-GAD-0006 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Buildings and Structures GA | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0007 | A | 6105AK124-6251-CGAD-0007 | Q24050972-03-6251-C-GAD-0007 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Cables, OHL and Fibre Route GA | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0008 | A | 6105AK124-6251-CGAD-0008 | Q24050972-03-6251-C-GAD-0008 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Terrace Equipment GA | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0009 | A | 6105AK124-6251-CGAD-0009 | Q24050972-03-6251-C-GAD-0009 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Buildings and Structures GA | Load Bank - Platform and Foundations for Wartsila Load Bank - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0010 | A | 6105AK124-6251-CGAD-0010 | Q24050972-03-6251-C-GAD-0010 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Platform and Foundations for Wartsila Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0011 | A | 6105AK124-6251-CGAD-0011 | Q24050972-03-6251-C-GAD-0011 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Terrace Equipment GA | Load Bank - Platform and Foundations for Wartsila Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0012 | A | 6105AK124-6251-CGAD-0012 | Q24050972-03-6251-C-GAD-0012 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Lighting Design and Layout GA | Load Bank - Platform and Foundations for Wartsila Load Bank - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6242 | E | SLD | 0002 | A | 6105AK124-6242-ESLD-0002 | Q24050972-03-6242-E-SLD-0002 |  | 33/220 kV Power Station Substation | 33/220 kV Power Station Substation | Auxiliary Supply - Single Line Diagram | 33/220 kV Power Station Substation - 33/220 kV Power Station Substation - Auxiliary Supply - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | 33/220 kV Power Station Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0013 | A | 6105AK124-6251-CGAD-0013 | Q24050972-03-6251-C-GAD-0013 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Roads, Pathways, Offloading Areas and Fences GA | Load Bank - Platform and Foundations for Wartsila Load Bank - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0014 | A | 6105AK124-6251-CGAD-0014 | Q24050972-03-6251-C-GAD-0014 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Stormwater and Effluent System Design | Load Bank - Platform and Foundations for Wartsila Load Bank - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | System Design |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0015 | A | 6105AK124-6251-CGAD-0015 | Q24050972-03-6251-C-GAD-0015 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Fire Detection and Suppression System | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0016 | A | 6105AK124-6251-CGAD-0016 | Q24050972-03-6251-C-GAD-0016 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | Roads, Pathways, Offloading Areas and Fences GA | Load Bank - Perimeter Fencing for for Wartsila Load Bank - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0017 | A | 6105AK124-6251-CGAD-0017 | Q24050972-03-6251-C-GAD-0017 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | Lighting Design and Layout GA | Load Bank - Perimeter Fencing for for Wartsila Load Bank - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0018 | A | 6105AK124-6251-CGAD-0018 | Q24050972-03-6251-C-GAD-0018 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Buildings and Structures GA | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Buildings and Structures |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0019 | A | 6105AK124-6251-CGAD-0019 | Q24050972-03-6251-C-GAD-0019 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Key Emergency Points and Equipment | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0020 | A | 6105AK124-6251-CGAD-0020 | Q24050972-03-6251-C-GAD-0020 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Terrace Equipment GA | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0021 | A | 6105AK124-6251-CGAD-0021 | Q24050972-03-6251-C-GAD-0021 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Disposal Areas General Arrangement | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0022 | A | 6105AK124-6251-CGAD-0022 | Q24050972-03-6251-C-GAD-0022 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Laydown Areas and Temp Buildings GA | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0023 | A | 6105AK124-6251-CGAD-0023 | Q24050972-03-6251-C-GAD-0023 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Stormwater and Effluent System Design | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0024 | A | 6105AK124-6251-CGAD-0024 | Q24050972-03-6251-C-GAD-0024 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Lighting Design and Layout GA | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0025 | A | 6105AK124-6251-CGAD-0025 | Q24050972-03-6251-C-GAD-0025 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Roads, Pathways, Offloading Areas and Fences GA | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0026 | A | 6105AK124-6251-CGAD-0026 | Q24050972-03-6251-C-GAD-0026 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Buildings and Structures GA | Load Bank - Small Power and Lighting for Wartsila Load Bank - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0027 | A | 6105AK124-6251-CGAD-0027 | Q24050972-03-6251-C-GAD-0027 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Small Power and Lighting for Wartsila Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0028 | A | 6105AK124-6251-CGAD-0028 | Q24050972-03-6251-C-GAD-0028 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Terrace Equipment GA | Load Bank - Small Power and Lighting for Wartsila Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0029 | A | 6105AK124-6251-CGAD-0029 | Q24050972-03-6251-C-GAD-0029 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Laydown Areas and Temp Buildings GA | Load Bank - Small Power and Lighting for Wartsila Load Bank - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0030 | A | 6105AK124-6251-CGAD-0030 | Q24050972-03-6251-C-GAD-0030 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Lighting Design and Layout GA | Load Bank - Small Power and Lighting for Wartsila Load Bank - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0031 | A | 6105AK124-6251-CGAD-0031 | Q24050972-03-6251-C-GAD-0031 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Roads, Pathways, Offloading Areas and Fences GA | Load Bank - Small Power and Lighting for Wartsila Load Bank - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6241 | E | SLD | 0002 | A | 6105AK124-6241-ESLD-0002 | Q24050972-03-6241-E-SLD-0002 |  | 33/220 kV Solar PV Substation | Solar PV 220kV Switch Yard | Auxiliary Supply - Single Line Diagram | 33/220 kV Solar PV Substation - Solar PV 220kV Switch Yard - Auxiliary Supply - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Solar PV 220kV Switch Yard | Single line Diagram |  |  |  | Pending
6105A | K124 | 0100 | B | CON | 0008 | A | 6105AK124-0100-BCON-0008 | Q24050972-03-0100-B-CON-0008 |  | Project Site Wide | Notice of Delay - RDMC Board Security Review | General | Project Site Wide - Notice of Delay - RDMC Board Security Review - General | 2026-04-15 |  | IFR - Issued for Review | Pending | 33.33% | JV |  |  | Notice of Delay | General |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0032 | A | 6105AK124-6251-CGAD-0032 | Q24050972-03-6251-C-GAD-0032 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Terrace Equipment GA | Load Bank - Metering Instruments for Wartsila Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0033 | A | 6105AK124-6251-CGAD-0033 | Q24050972-03-6251-C-GAD-0033 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Cables, OHL and Fibre Route GA | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0034 | A | 6105AK124-6251-CGAD-0034 | Q24050972-03-6251-C-GAD-0034 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Terrace Equipment GA | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0035 | A | 6105AK124-6251-CGAD-0035 | Q24050972-03-6251-C-GAD-0035 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Cables, OHL and Fibre Route GA | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0036 | A | 6105AK124-6251-CGAD-0036 | Q24050972-03-6251-C-GAD-0036 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Terrace Equipment GA | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0037 | A | 6105AK124-6251-CGAD-0037 | Q24050972-03-6251-C-GAD-0037 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Buildings and Structures GA | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0038 | A | 6105AK124-6251-CGAD-0038 | Q24050972-03-6251-C-GAD-0038 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0039 | A | 6105AK124-6251-CGAD-0039 | Q24050972-03-6251-C-GAD-0039 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Terrace Equipment GA | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0040 | A | 6105AK124-6251-CGAD-0040 | Q24050972-03-6251-C-GAD-0040 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Roads, Pathways, Offloading Areas and Fences GA | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0041 | A | 6105AK124-6251-CGAD-0041 | Q24050972-03-6251-C-GAD-0041 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Buildings and Structures GA | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0042 | A | 6105AK124-6251-CGAD-0042 | Q24050972-03-6251-C-GAD-0042 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0043 | A | 6105AK124-6251-CGAD-0043 | Q24050972-03-6251-C-GAD-0043 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Terrace Equipment GA | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0044 | A | 6105AK124-6251-CGAD-0044 | Q24050972-03-6251-C-GAD-0044 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Buildings and Structures GA | Load Bank - Lightning Protection System forWartsila Load Bank - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0045 | A | 6105AK124-6251-CGAD-0045 | Q24050972-03-6251-C-GAD-0045 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Lightning Protection System forWartsila Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0046 | A | 6105AK124-6251-CGAD-0046 | Q24050972-03-6251-C-GAD-0046 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Terrace Equipment GA | Load Bank - Lightning Protection System forWartsila Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0047 | A | 6105AK124-6251-CGAD-0047 | Q24050972-03-6251-C-GAD-0047 |  | Load Bank | Earthing System for Wartsila Load Bank | Lighting Design and Layout GA | Load Bank - Earthing System for Wartsila Load Bank - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0048 | A | 6105AK124-6251-CGAD-0048 | Q24050972-03-6251-C-GAD-0048 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Buildings and Structures GA | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0049 | A | 6105AK124-6251-CGAD-0049 | Q24050972-03-6251-C-GAD-0049 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0050 | A | 6105AK124-6251-CGAD-0050 | Q24050972-03-6251-C-GAD-0050 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Terrace Equipment GA | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0051 | A | 6105AK124-6251-CGAD-0051 | Q24050972-03-6251-C-GAD-0051 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Lighting Design and Layout GA | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0052 | A | 6105AK124-6251-CGAD-0052 | Q24050972-03-6251-C-GAD-0052 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Roads, Pathways, Offloading Areas and Fences GA | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0053 | A | 6105AK124-6251-CGAD-0053 | Q24050972-03-6251-C-GAD-0053 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Stormwater and Effluent System Design | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0054 | A | 6105AK124-6251-CGAD-0054 | Q24050972-03-6251-C-GAD-0054 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Fire Detection and Suppression System | Load Bank - Fire Protection System Emergency Gen Load Bank - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Gen Load Bank |  |  |  | Pending
6105A | K124 | 6241 | C | LAY | 0001 | A | 6105AK124-6241-CLAY-0001 | Q24050972-03-6241-C-LAY-0001 |  | 33/220 kV Solar PV Substation | PV Siemens switchyard | Layout | 33/220 kV Solar PV Substation - PV Siemens switchyard - Layout | 2026-04-16 |  | IFR - Issued for Review | Reviewed With Comments | 33.33% | CLR |  |  | PV Siemens switchyard | Layout |  |  |  | Pending
6105A | K124 | 6241 | C | LAY | 0002 | A | 6105AK124-6241-CLAY-0002 | Q24050972-03-6241-C-LAY-0002 | Sht.1 of 1 | 33/220 kV Solar PV Substation | PV Siemens switchyard | Bulk Eartworks Layout | 33/220 kV Solar PV Substation - PV Siemens switchyard - Bulk Eartworks Layout - Sht.1 of 1 | 2026-04-16 |  | IFR - Issued for Review | Reviewed | 33.33% | CLR |  |  | PV Siemens switchyard | Layout |  |  |  | Pending
6105A | K124 | 6241 | C | SEC | 0002 | A | 6105AK124-6241-CSEC-0002 | Q24050972-03-6241-C-SEC-0002 | Sht.1 of 1 | 33/220 kV Solar PV Substation | PV Siemens switchyard | Bulk Eartworks Profile Layout | 33/220 kV Solar PV Substation - PV Siemens switchyard - Bulk Eartworks Profile Layout | 2026-04-16 |  | IFR - Issued for Review | Reviewed | 33.33% | CLR |  |  | PV Siemens switchyard | Layout |  |  |  | Pending
6105A | K124 | 6241 | C | SEC | 0003 | A | 6105AK124-6241-CSEC-0003 | Q24050972-03-6241-C-SEC-0003 | Sht.1 of 4 | 33/220 kV Solar PV Substation | PV Siemens switchyard | Bulk Eartworks Profile Sections | 33/220 kV Solar PV Substation - PV Siemens switchyard - Bulk Eartworks Profile Sections - Sht.1 of 4 | 2026-04-16 |  | IFR - Issued for Review | Reviewed With Comments | 33.33% | CLR |  |  | PV Siemens switchyard | Layout |  |  |  | Pending
6105A | K124 | 6241 | C | SEC | 0004 | A | 6105AK124-6241-CSEC-0004 | Q24050972-03-6241-C-SEC-0004 | Sht.2 of 4 | 33/220 kV Solar PV Substation | PV Siemens switchyard | Bulk Eartworks Profile Sections | 33/220 kV Solar PV Substation - PV Siemens switchyard - Bulk Eartworks Profile Sections - Sht.2 of 4 | 2026-04-16 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | CLR |  |  | PV Siemens switchyard | Layout |  |  |  | Pending
6105A | K124 | 6241 | C | SEC | 0005 | A | 6105AK124-6241-CSEC-0005 | Q24050972-03-6241-C-SEC-0005 | Sht.3 of 4 | 33/220 kV Solar PV Substation | PV Siemens switchyard | Bulk Eartworks Profile Sections View | 33/220 kV Solar PV Substation - PV Siemens switchyard - Bulk Eartworks Profile Sections View - Sht.3 of 4 | 2026-04-16 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | CLR |  |  | PV Siemens switchyard | Layout |  |  |  | Pending
6105A | K124 | 6241 | C | SEC | 0006 | A | 6105AK124-6241-CSEC-0006 | Q24050972-03-6241-C-SEC-0006 | Sht.4 of 4 | 33/220 kV Solar PV Substation | PV Siemens switchyard | Bulk Eartworks Profile Sections View | 33/220 kV Solar PV Substation - PV Siemens switchyard - Bulk Eartworks Profile Sections View - Sht.4 of 4 | 2026-04-16 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | CLR |  |  | PV Siemens switchyard | Layout |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0055 | A | 6105AK124-6251-CGAD-0055 | Q24050972-03-6251-C-GAD-0055 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Buildings and Structures GA | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0056 | A | 6105AK124-6251-CGAD-0056 | Q24050972-03-6251-C-GAD-0056 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Key Emergency Points and Equipment | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0057 | A | 6105AK124-6251-CGAD-0057 | Q24050972-03-6251-C-GAD-0057 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Terrace Equipment GA | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0058 | A | 6105AK124-6251-CGAD-0058 | Q24050972-03-6251-C-GAD-0058 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Disposal Areas General Arrangement | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0059 | A | 6105AK124-6251-CGAD-0059 | Q24050972-03-6251-C-GAD-0059 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Laydown Areas and Temp Buildings GA | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0060 | A | 6105AK124-6251-CGAD-0060 | Q24050972-03-6251-C-GAD-0060 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Stormwater and Effluent System Design | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0061 | A | 6105AK124-6251-CGAD-0061 | Q24050972-03-6251-C-GAD-0061 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Buildings and Structures GA | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0062 | A | 6105AK124-6251-CGAD-0062 | Q24050972-03-6251-C-GAD-0062 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0063 | A | 6105AK124-6251-CGAD-0063 | Q24050972-03-6251-C-GAD-0063 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Terrace Equipment GA | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0064 | A | 6105AK124-6251-CGAD-0064 | Q24050972-03-6251-C-GAD-0064 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Laydown Areas and Temp Buildings GA | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0065 | A | 6105AK124-6251-CGAD-0065 | Q24050972-03-6251-C-GAD-0065 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Lighting Design and Layout GA | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0066 | A | 6105AK124-6251-CGAD-0066 | Q24050972-03-6251-C-GAD-0066 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Roads, Pathways, Offloading Areas and Fences GA | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0067 | A | 6105AK124-6251-CGAD-0067 | Q24050972-03-6251-C-GAD-0067 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Terrace Equipment GA | Load Bank - Metering Instruments for Emergency Gen Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0068 | A | 6105AK124-6251-CGAD-0068 | Q24050972-03-6251-C-GAD-0068 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Cables, OHL and Fibre Route GA | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0069 | A | 6105AK124-6251-CGAD-0069 | Q24050972-03-6251-C-GAD-0069 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Terrace Equipment GA | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0070 | A | 6105AK124-6251-CGAD-0070 | Q24050972-03-6251-C-GAD-0070 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Cables, OHL and Fibre Route GA | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0071 | A | 6105AK124-6251-CGAD-0071 | Q24050972-03-6251-C-GAD-0071 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Terrace Equipment GA | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0072 | A | 6105AK124-6251-CGAD-0072 | Q24050972-03-6251-C-GAD-0072 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Buildings and Structures GA | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0073 | A | 6105AK124-6251-CGAD-0073 | Q24050972-03-6251-C-GAD-0073 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0074 | A | 6105AK124-6251-CGAD-0074 | Q24050972-03-6251-C-GAD-0074 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Terrace Equipment GA | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0075 | A | 6105AK124-6251-CGAD-0075 | Q24050972-03-6251-C-GAD-0075 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Roads, Pathways, Offloading Areas and Fences GA | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0076 | A | 6105AK124-6251-CGAD-0076 | Q24050972-03-6251-C-GAD-0076 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Buildings and Structures GA | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0077 | A | 6105AK124-6251-CGAD-0077 | Q24050972-03-6251-C-GAD-0077 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0078 | A | 6105AK124-6251-CGAD-0078 | Q24050972-03-6251-C-GAD-0078 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Terrace Equipment GA | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0079 | A | 6105AK124-6251-CGAD-0079 | Q24050972-03-6251-C-GAD-0079 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Buildings and Structures GA | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0080 | A | 6105AK124-6251-CGAD-0080 | Q24050972-03-6251-C-GAD-0080 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0081 | A | 6105AK124-6251-CGAD-0081 | Q24050972-03-6251-C-GAD-0081 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Terrace Equipment GA | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | GAD | 0082 | A | 6105AK124-6251-CGAD-0082 | Q24050972-03-6251-C-GAD-0082 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Lighting Design and Layout GA | Load Bank - Earthing System forEmergency Gen Load Bank - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0001 | A | 6105AK124-6251-CMDL-0001 | Q24050972-03-6251-C-MDL-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | 3D Designs and Drawings | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Mobile Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0002 | A | 6105AK124-6251-CMDL-0002 | Q24050972-03-6251-C-MDL-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | 3D Designs and Drawings | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Mobile Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0003 | A | 6105AK124-6251-CMDL-0003 | Q24050972-03-6251-C-MDL-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | 3D Designs and Drawings | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Mobile Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0004 | A | 6105AK124-6251-CMDL-0004 | Q24050972-03-6251-C-MDL-0004 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | 3D Designs and Drawings | Load Bank - Platform and Foundations for Wartsila Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0005 | A | 6105AK124-6251-CMDL-0005 | Q24050972-03-6251-C-MDL-0005 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | 3D Designs and Drawings | Load Bank - Perimeter Fencing for for Wartsila Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0006 | A | 6105AK124-6251-CMDL-0006 | Q24050972-03-6251-C-MDL-0006 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | 3D Designs and Drawings | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0007 | A | 6105AK124-6251-CMDL-0007 | Q24050972-03-6251-C-MDL-0007 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | 3D Designs and Drawings | Load Bank - Small Power and Lighting for Wartsila Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0008 | A | 6105AK124-6251-CMDL-0008 | Q24050972-03-6251-C-MDL-0008 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | 3D Designs and Drawings | Load Bank - Cable Racks and Trays for Wartsila Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0009 | A | 6105AK124-6251-CMDL-0009 | Q24050972-03-6251-C-MDL-0009 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | 3D Designs and Drawings | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0010 | A | 6105AK124-6251-CMDL-0010 | Q24050972-03-6251-C-MDL-0010 |  | Load Bank | Lightning Protection System forWartsila Load Bank | 3D Designs and Drawings | Load Bank - Lightning Protection System forWartsila Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0011 | A | 6105AK124-6251-CMDL-0011 | Q24050972-03-6251-C-MDL-0011 |  | Load Bank | Earthing System for Wartsila Load Bank | 3D Designs and Drawings | Load Bank - Earthing System for Wartsila Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0012 | A | 6105AK124-6251-CMDL-0012 | Q24050972-03-6251-C-MDL-0012 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | 3D Designs and Drawings | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0013 | A | 6105AK124-6251-CMDL-0013 | Q24050972-03-6251-C-MDL-0013 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | 3D Designs and Drawings | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0014 | A | 6105AK124-6251-CMDL-0014 | Q24050972-03-6251-C-MDL-0014 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | 3D Designs and Drawings | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0015 | A | 6105AK124-6251-CMDL-0015 | Q24050972-03-6251-C-MDL-0015 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | 3D Designs and Drawings | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0016 | A | 6105AK124-6251-CMDL-0016 | Q24050972-03-6251-C-MDL-0016 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | 3D Designs and Drawings | Load Bank - Lightning Protection System for Emergency Gen Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | MDL | 0017 | A | 6105AK124-6251-CMDL-0017 | Q24050972-03-6251-C-MDL-0017 |  | Load Bank | Earthing System forEmergency Gen Load Bank | 3D Designs and Drawings | Load Bank - Earthing System forEmergency Gen Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6242 | C | SPC | 0012 | A | 6105AK124-6242-CSPC-0012 | Q24050972-03-6242-C-SPC-0012 |  | 33/220 kV Power Station Substation | Siemens Switchyard | Bulk Earthworks Specification | 33/220 kV Power Station Substation - Siemens Switchyard - Bulk Earthworks Specification | 2026-04-16 |  | IFR - Issued for Review | Pending | 33.33% | AS |  | 2026-05-15 | Bulk Earthworks | Bill of Material |  |  |  | Pending
6105A | K124 | 6242 | C | BOM | 0013 | A | 6105AK124-6242-CBOM-0013 | Q24050972-03-6242-C-BOM-0013 |  | 33/220 kV Power Station Substation | Siemens Switchyard | Bulk Earthworks Bill of Material | 33/220 kV Power Station Substation - Siemens Switchyard - Bulk Earthworks Bill of Material | 2026-04-16 |  | IFR - Issued for Review | Pending | 33.33% | AS |  |  | Siemens Switchyard | Bill of Material |  |  |  | Pending
6105A | K124 | 6241 | C | SPC | 0012 | A | 6105AK124-6241-CSPC-0012 | Q24050972-03-6241-C-SPC-0012 |  | 33/220 kV Solar PV Substation | PV Siemens Switchyard | Bulk Earthworks Specification | 33/220 kV Solar PV Substation - PV Siemens Switchyard - Bulk Earthworks Specification | 2026-04-16 |  | IFR - Issued for Review | Reviewed With Comments | 33.33% | AS |  |  | Solar PV Substation | Specifications |  |  |  | Pending
6105A | K124 | 6241 | C | BOM | 0001 | A | 6105AK124-6241-CBOM-0001 | Q24050972-03-6241-C-BOM-0001 |  | 33/220 kV Solar PV Substation | PV Siemens Switchyard | Bulk Earthworks Bill of Material | 33/220 kV Solar PV Substation - PV Siemens Switchyard - Bulk Earthworks Bill of Material | 2026-04-16 |  | IFR - Issued for Review | Reviewed | 33.33% | AS |  |  | PV Siemens Switchyard | Bill of Material |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0001 | A | 6105AK124-6286-CSPC-0001 | Q24050972-03-6286-C-SPC-0001 |  | Primary Crushing | 33/220 kV Switchyard | Bulk Earthworks Specification | Primary Crushing - 33/220 kV Switchyard - Bulk Earthworks Specification | 2026-04-16 |  | IFR - Issued for Review | Reviewed | 33.33% | AS |  |  | 33/220 kV Switchyard | Specification |  |  |  | Pending
6105A | K124 | 6286 | C | BOM | 0002 | A | 6105AK124-6286-CBOM-0002 | Q24050972-02-6286-C-BOM-0002 |  | Primary Crushing | 33/220 kV Switchyard | Bulk Earthworks Bill of Material | Primary Crushing - 33/220 kV Switchyard - Bulk Earthworks Bill of Material | 2026-04-16 |  | IFR - Issued for Review | Reviewed | 33.33% | AS |  |  | 33/220 kV Switchyard | Bill of Material |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0001 | A | 6105AK124-6251-CPLN-0001 | Q24050972-03-6251-C-PLN-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Civil Works Execution Plan | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0002 | A | 6105AK124-6251-CPLN-0002 | Q24050972-03-6251-C-PLN-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Civil Works Execution Plan | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0003 | A | 6105AK124-6251-CPLN-0003 | Q24050972-03-6251-C-PLN-0003 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Civil Works Execution Plan | Load Bank - Platform and Foundations for Wartsila Load Bank - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0004 | A | 6105AK124-6251-CPLN-0004 | Q24050972-03-6251-C-PLN-0004 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Civil Works Execution Plan | Load Bank - Small Power and Lighting for Wartsila Load Bank - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0005 | A | 6105AK124-6251-CPLN-0005 | Q24050972-03-6251-C-PLN-0005 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Civil Works Execution Plan | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0006 | A | 6105AK124-6251-CPLN-0006 | Q24050972-03-6251-C-PLN-0006 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Civil Works Execution Plan | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0007 | A | 6105AK124-6251-CPLN-0007 | Q24050972-03-6251-C-PLN-0007 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Civil Works Execution Plan | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0008 | A | 6105AK124-6251-CPLN-0008 | Q24050972-03-6251-C-PLN-0008 |  | Load Bank | Earthing System for Wartsila Load Bank | Civil Works Execution Plan | Load Bank - Earthing System for Wartsila Load Bank - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0009 | A | 6105AK124-6251-CPLN-0009 | Q24050972-03-6251-C-PLN-0009 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Civil Works Execution Plan | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0010 | A | 6105AK124-6251-CPLN-0010 | Q24050972-03-6251-C-PLN-0010 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Civil Works Execution Plan | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0011 | A | 6105AK124-6251-CPLN-0011 | Q24050972-03-6251-C-PLN-0011 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Civil Works Execution Plan | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0012 | A | 6105AK124-6251-CPLN-0012 | Q24050972-03-6251-C-PLN-0012 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Civil Works Execution Plan | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0013 | A | 6105AK124-6251-CPLN-0013 | Q24050972-03-6251-C-PLN-0013 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Civil Works Execution Plan | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PLN | 0014 | A | 6105AK124-6251-CPLN-0014 | Q24050972-03-6251-C-PLN-0014 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Civil Works Execution Plan | Load Bank - Earthing System forEmergency Gen Load Bank - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PPL | 0001 | A | 6105AK124-6251-CPPL-0001 | Q24050972-03-6251-C-PPL-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Operational & Maint Access Routes Design | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | C | PPL | 0002 | A | 6105AK124-6251-CPPL-0002 | Q24050972-03-6251-C-PPL-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Operational & Maint Access Routes Design | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | C | PPL | 0003 | A | 6105AK124-6251-CPPL-0003 | Q24050972-03-6251-C-PPL-0003 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Operational & Maint Access Routes Design | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PPL | 0004 | A | 6105AK124-6251-CPPL-0004 | Q24050972-03-6251-C-PPL-0004 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Operational & Maint Access Routes Design | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank | Wartsila Load Bank | Wartsila Load Bank |  | Pending
6105A | K124 | 6251 | C | PPL | 0005 | A | 6105AK124-6251-CPPL-0005 | Q24050972-03-6251-C-PPL-0005 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Operational & Maint Access Routes Design | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PPL | 0006 | A | 6105AK124-6251-CPPL-0006 | Q24050972-03-6251-C-PPL-0006 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Operational & Maint Access Routes Design | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PPL | 0007 | A | 6105AK124-6251-CPPL-0007 | Q24050972-03-6251-C-PPL-0007 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Operational & Maint Access Routes Design | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PPL | 0008 | A | 6105AK124-6251-CPPL-0008 | Q24050972-03-6251-C-PPL-0008 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Operational & Maint Access Routes Design | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0001 | A | 6105AK124-6251-CSEC-0001 | Q24050972-03-6251-C-SEC-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Corrosion Prevention and Protection Design | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0002 | A | 6105AK124-6251-CSEC-0002 | Q24050972-03-6251-C-SEC-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Structural Earthing and Bonding Design | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0003 | A | 6105AK124-6251-CSEC-0003 | Q24050972-03-6251-C-SEC-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Corrosion Prevention and Protection Design | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0004 | A | 6105AK124-6251-CSEC-0004 | Q24050972-03-6251-C-SEC-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Structural Earthing and Bonding Design | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0005 | A | 6105AK124-6251-CSEC-0005 | Q24050972-03-6251-C-SEC-0005 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Corrosion Prevention and Protection Design | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0006 | A | 6105AK124-6251-CSEC-0006 | Q24050972-03-6251-C-SEC-0006 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Corrosion Prevention and Protection Design | Load Bank - Small Power and Lighting for Wartsila Load Bank - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0007 | A | 6105AK124-6251-CSEC-0007 | Q24050972-03-6251-C-SEC-0007 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Structural Earthing and Bonding Design | Load Bank - Small Power and Lighting for Wartsila Load Bank - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0008 | A | 6105AK124-6251-CSEC-0008 | Q24050972-03-6251-C-SEC-0008 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Corrosion Prevention and Protection Design | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0009 | A | 6105AK124-6251-CSEC-0009 | Q24050972-03-6251-C-SEC-0009 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Structural Earthing and Bonding Design | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0010 | A | 6105AK124-6251-CSEC-0010 | Q24050972-03-6251-C-SEC-0010 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Corrosion Prevention and Protection Design | Load Bank - Lightning Protection System forWartsila Load Bank - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0011 | A | 6105AK124-6251-CSEC-0011 | Q24050972-03-6251-C-SEC-0011 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Structural Earthing and Bonding Design | Load Bank - Lightning Protection System forWartsila Load Bank - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0012 | A | 6105AK124-6251-CSEC-0012 | Q24050972-03-6251-C-SEC-0012 |  | Load Bank | Earthing System for Wartsila Load Bank | Corrosion Prevention and Protection Design | Load Bank - Earthing System for Wartsila Load Bank - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0013 | A | 6105AK124-6251-CSEC-0013 | Q24050972-03-6251-C-SEC-0013 |  | Load Bank | Earthing System for Wartsila Load Bank | Structural Earthing and Bonding Design | Load Bank - Earthing System for Wartsila Load Bank - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0014 | A | 6105AK124-6251-CSEC-0014 | Q24050972-03-6251-C-SEC-0014 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Corrosion Prevention and Protection Design | Load Bank - Fire Protection System Emergency Gen Load Bank - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0015 | A | 6105AK124-6251-CSEC-0015 | Q24050972-03-6251-C-SEC-0015 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Corrosion Prevention and Protection Design | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0016 | A | 6105AK124-6251-CSEC-0016 | Q24050972-03-6251-C-SEC-0016 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Structural Earthing and Bonding Design | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0017 | A | 6105AK124-6251-CSEC-0017 | Q24050972-03-6251-C-SEC-0017 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Corrosion Prevention and Protection Design | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0018 | A | 6105AK124-6251-CSEC-0018 | Q24050972-03-6251-C-SEC-0018 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Structural Earthing and Bonding Design | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0019 | A | 6105AK124-6251-CSEC-0019 | Q24050972-03-6251-C-SEC-0019 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Corrosion Prevention and Protection Design | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0020 | A | 6105AK124-6251-CSEC-0020 | Q24050972-03-6251-C-SEC-0020 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Structural Earthing and Bonding Design | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0021 | A | 6105AK124-6251-CSEC-0021 | Q24050972-03-6251-C-SEC-0021 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Corrosion Prevention and Protection Design | Load Bank - Earthing System forEmergency Gen Load Bank - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0022 | A | 6105AK124-6251-CSEC-0022 | Q24050972-03-6251-C-SEC-0022 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Structural Earthing and Bonding Design | Load Bank - Earthing System forEmergency Gen Load Bank - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SHP | 0001 | A | 6105AK124-6251-CSHP-0001 | Q24050972-03-6251-C-SHP-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Equipment Assembly Drawings | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | C | SHP | 0002 | A | 6105AK124-6251-CSHP-0002 | Q24050972-03-6251-C-SHP-0002 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | Equipment Assembly Drawings | Load Bank - Perimeter Fencing for for Wartsila Load Bank - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SHP | 0003 | A | 6105AK124-6251-CSHP-0003 | Q24050972-03-6251-C-SHP-0003 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Equipment Assembly Drawings | Load Bank - Small Power and Lighting for Wartsila Load Bank - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SHP | 0004 | A | 6105AK124-6251-CSHP-0004 | Q24050972-03-6251-C-SHP-0004 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Equipment Assembly Drawings | Load Bank - Metering Instruments for Wartsila Load Bank - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SHP | 0005 | A | 6105AK124-6251-CSHP-0005 | Q24050972-03-6251-C-SHP-0005 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Equipment Assembly Drawings | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SHP | 0006 | A | 6105AK124-6251-CSHP-0006 | Q24050972-03-6251-C-SHP-0006 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Equipment Assembly Drawings | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SHP | 0007 | A | 6105AK124-6251-CSHP-0007 | Q24050972-03-6251-C-SHP-0007 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Equipment Assembly Drawings | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SHP | 0008 | A | 6105AK124-6251-CSHP-0008 | Q24050972-03-6251-C-SHP-0008 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Equipment Assembly Drawings | Load Bank - Metering Instruments for Emergency Gen Load Bank - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SHP | 0009 | A | 6105AK124-6251-CSHP-0009 | Q24050972-03-6251-C-SHP-0009 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Equipment Assembly Drawings | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0001 | A | 6105AK124-6251-CSPC-0001 | Q24050972-03-6251-C-SPC-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Civil Design Requirements | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0002 | A | 6105AK124-6251-CSPC-0002 | Q24050972-03-6251-C-SPC-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Excavation, Trenching and Compacting Design | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0003 | A | 6105AK124-6251-CSPC-0003 | Q24050972-03-6251-C-SPC-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Concrete Construction Material Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0004 | A | 6105AK124-6251-CSPC-0004 | Q24050972-03-6251-C-SPC-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Civil Design Requirements | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0005 | A | 6105AK124-6251-CSPC-0005 | Q24050972-03-6251-C-SPC-0005 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Concrete Construction Material Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0006 | A | 6105AK124-6251-CSPC-0006 | Q24050972-03-6251-C-SPC-0006 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Steel Structures Corrosion Protection Specification | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0007 | A | 6105AK124-6251-CSPC-0007 | Q24050972-03-6251-C-SPC-0007 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Civil Design Requirements | Load Bank - Platform and Foundations for Wartsila Load Bank - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0008 | A | 6105AK124-6251-CSPC-0008 | Q24050972-03-6251-C-SPC-0008 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Excavation, Trenching and Compacting Design | Load Bank - Platform and Foundations for Wartsila Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0009 | A | 6105AK124-6251-CSPC-0009 | Q24050972-03-6251-C-SPC-0009 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Concrete Construction Material Specifications | Load Bank - Platform and Foundations for Wartsila Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0010 | A | 6105AK124-6251-CSPC-0010 | Q24050972-03-6251-C-SPC-0010 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | Excavation, Trenching and Compacting Design | Load Bank - Perimeter Fencing for for Wartsila Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0011 | A | 6105AK124-6251-CSPC-0011 | Q24050972-03-6251-C-SPC-0011 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | Concrete Construction Material Specifications | Load Bank - Perimeter Fencing for for Wartsila Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0012 | A | 6105AK124-6251-CSPC-0012 | Q24050972-03-6251-C-SPC-0012 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | Steel Structures Corrosion Protection Specification | Load Bank - Perimeter Fencing for for Wartsila Load Bank - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0013 | A | 6105AK124-6251-CSPC-0013 | Q24050972-03-6251-C-SPC-0013 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Civil Design Requirements | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0014 | A | 6105AK124-6251-CSPC-0014 | Q24050972-03-6251-C-SPC-0014 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Excavation, Trenching and Compacting Design | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0015 | A | 6105AK124-6251-CSPC-0015 | Q24050972-03-6251-C-SPC-0015 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Concrete Construction Material Specifications | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0016 | A | 6105AK124-6251-CSPC-0016 | Q24050972-03-6251-C-SPC-0016 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Concrete Construction Material Specifications | Load Bank - Small Power and Lighting for Wartsila Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0017 | A | 6105AK124-6251-CSPC-0017 | Q24050972-03-6251-C-SPC-0017 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Excavation, Trenching and Compacting Design | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0018 | A | 6105AK124-6251-CSPC-0018 | Q24050972-03-6251-C-SPC-0018 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Concrete Construction Material Specifications | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0019 | A | 6105AK124-6251-CSPC-0019 | Q24050972-03-6251-C-SPC-0019 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Excavation, Trenching and Compacting Design | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0020 | A | 6105AK124-6251-CSPC-0020 | Q24050972-03-6251-C-SPC-0020 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Concrete Construction Material Specifications | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0021 | A | 6105AK124-6251-CSPC-0021 | Q24050972-03-6251-C-SPC-0021 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Civil Design Requirements | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0022 | A | 6105AK124-6251-CSPC-0022 | Q24050972-03-6251-C-SPC-0022 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Concrete Construction Material Specifications | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0023 | A | 6105AK124-6251-CSPC-0023 | Q24050972-03-6251-C-SPC-0023 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Steel Structures Corrosion Protection Specification | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0024 | A | 6105AK124-6251-CSPC-0024 | Q24050972-03-6251-C-SPC-0024 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Civil Design Requirements | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0025 | A | 6105AK124-6251-CSPC-0025 | Q24050972-03-6251-C-SPC-0025 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Excavation, Trenching and Compacting Design | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0026 | A | 6105AK124-6251-CSPC-0026 | Q24050972-03-6251-C-SPC-0026 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Concrete Construction Material Specifications | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0027 | A | 6105AK124-6251-CSPC-0027 | Q24050972-03-6251-C-SPC-0027 |  | Load Bank | Earthing System for Wartsila Load Bank | Concrete Construction Material Specifications | Load Bank - Earthing System for Wartsila Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0028 | A | 6105AK124-6251-CSPC-0028 | Q24050972-03-6251-C-SPC-0028 |  | Load Bank | Earthing System for Wartsila Load Bank | Excavation, Trenching and Compacting Design | Load Bank - Earthing System for Wartsila Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0029 | A | 6105AK124-6251-CSPC-0029 | Q24050972-03-6251-C-SPC-0029 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Civil Design Requirements | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0030 | A | 6105AK124-6251-CSPC-0030 | Q24050972-03-6251-C-SPC-0030 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Excavation, Trenching and Compacting Design | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0031 | A | 6105AK124-6251-CSPC-0031 | Q24050972-03-6251-C-SPC-0031 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Concrete Construction Material Specifications | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0032 | A | 6105AK124-6251-CSPC-0032 | Q24050972-03-6251-C-SPC-0032 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Steel Structures Corrosion Protection Specification | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0033 | A | 6105AK124-6251-CSPC-0033 | Q24050972-03-6251-C-SPC-0033 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Civil Design Requirements | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0034 | A | 6105AK124-6251-CSPC-0034 | Q24050972-03-6251-C-SPC-0034 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Concrete Construction Material Specifications | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0035 | A | 6105AK124-6251-CSPC-0035 | Q24050972-03-6251-C-SPC-0035 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Excavation, Trenching and Compacting Design | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0036 | A | 6105AK124-6251-CSPC-0036 | Q24050972-03-6251-C-SPC-0036 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Concrete Construction Material Specifications | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0037 | A | 6105AK124-6251-CSPC-0037 | Q24050972-03-6251-C-SPC-0037 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Excavation, Trenching and Compacting Design | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0038 | A | 6105AK124-6251-CSPC-0038 | Q24050972-03-6251-C-SPC-0038 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Concrete Construction Material Specifications | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0039 | A | 6105AK124-6251-CSPC-0039 | Q24050972-03-6251-C-SPC-0039 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Civil Design Requirements | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0040 | A | 6105AK124-6251-CSPC-0040 | Q24050972-03-6251-C-SPC-0040 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Concrete Construction Material Specifications | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0041 | A | 6105AK124-6251-CSPC-0041 | Q24050972-03-6251-C-SPC-0041 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Steel Structures Corrosion Protection Specification | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0042 | A | 6105AK124-6251-CSPC-0042 | Q24050972-03-6251-C-SPC-0042 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Civil Design Requirements | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6187 | G | RPT | 0001 | A | 6105AK124-6187-GRPT-0001 | Q24050972-09-6187-G-RPT-0001 |  | General | PPE - RDMC - Phase One - Temporary Facilities | Plan | General - PPE - RDMC - Phase One - Temporary Facilities | 2026-04-14 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | FV |  |  | Support Facilities | Plan |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0043 | A | 6105AK124-6251-CSPC-0043 | Q24050972-03-6251-C-SPC-0043 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Excavation, Trenching and Compacting Design | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0044 | A | 6105AK124-6251-CSPC-0044 | Q24050972-03-6251-C-SPC-0044 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Concrete Construction Material Specifications | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0045 | A | 6105AK124-6251-CSPC-0045 | Q24050972-03-6251-C-SPC-0045 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Concrete Construction Material Specifications | Load Bank - Earthing System forEmergency Gen Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0046 | A | 6105AK124-6251-CSPC-0046 | Q24050972-03-6251-C-SPC-0046 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Excavation, Trenching and Compacting Design | Load Bank - Earthing System forEmergency Gen Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SSD | 0001 | A | 6105AK124-6251-CSSD-0001 | Q24050972-03-6251-C-SSD-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Steel Support Structures Design | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | C | SSD | 0002 | A | 6105AK124-6251-CSSD-0002 | Q24050972-03-6251-C-SSD-0002 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | Steel Support Structures Design | Load Bank - Perimeter Fencing for for Wartsila Load Bank - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SSD | 0003 | A | 6105AK124-6251-CSSD-0003 | Q24050972-03-6251-C-SSD-0003 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Steel Support Structures Design | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SSD | 0004 | A | 6105AK124-6251-CSSD-0004 | Q24050972-03-6251-C-SSD-0004 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Steel Support Structures Design | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SSD | 0005 | A | 6105AK124-6251-CSSD-0005 | Q24050972-03-6251-C-SSD-0005 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Steel Support Structures Design | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0001 | A | 6105AK124-6251-CSTD-0001 | Q24050972-03-6251-C-STD-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Civil Construction Requirements | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0002 | A | 6105AK124-6251-CSTD-0002 | Q24050972-03-6251-C-STD-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Underground Pipe Route and Cable Bedding Design | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0003 | A | 6105AK124-6251-CSTD-0003 | Q24050972-03-6251-C-STD-0003 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Civil Construction Requirements | Load Bank - Platform and Foundations for Wartsila Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0004 | A | 6105AK124-6251-CSTD-0004 | Q24050972-03-6251-C-STD-0004 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Fire Protection System Design (Civil Works) | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0005 | A | 6105AK124-6251-CSTD-0005 | Q24050972-03-6251-C-STD-0005 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Civil Construction Requirements | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0006 | A | 6105AK124-6251-CSTD-0006 | Q24050972-03-6251-C-STD-0006 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - Perimeter Fencing for for Wartsila Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0007 | A | 6105AK124-6251-CSTD-0007 | Q24050972-03-6251-C-STD-0007 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Bund-wall Requirements and Design | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0008 | A | 6105AK124-6251-CSTD-0008 | Q24050972-03-6251-C-STD-0008 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Civil Construction Requirements | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0009 | A | 6105AK124-6251-CSTD-0009 | Q24050972-03-6251-C-STD-0009 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0010 | A | 6105AK124-6251-CSTD-0010 | Q24050972-03-6251-C-STD-0010 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Civil Construction Requirements | Load Bank - Small Power and Lighting for Wartsila Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0011 | A | 6105AK124-6251-CSTD-0011 | Q24050972-03-6251-C-STD-0011 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - Small Power and Lighting for Wartsila Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0012 | A | 6105AK124-6251-CSTD-0012 | Q24050972-03-6251-C-STD-0012 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Civil Construction Requirements | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0013 | A | 6105AK124-6251-CSTD-0013 | Q24050972-03-6251-C-STD-0013 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0014 | A | 6105AK124-6251-CSTD-0014 | Q24050972-03-6251-C-STD-0014 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Civil Construction Requirements | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0015 | A | 6105AK124-6251-CSTD-0015 | Q24050972-03-6251-C-STD-0015 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0016 | A | 6105AK124-6251-CSTD-0016 | Q24050972-03-6251-C-STD-0016 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0017 | A | 6105AK124-6251-CSTD-0017 | Q24050972-03-6251-C-STD-0017 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Civil Construction Requirements | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0018 | A | 6105AK124-6251-CSTD-0018 | Q24050972-03-6251-C-STD-0018 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0019 | A | 6105AK124-6251-CSTD-0019 | Q24050972-03-6251-C-STD-0019 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Civil Construction Requirements | Load Bank - Lightning Protection System forWartsila Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0020 | A | 6105AK124-6251-CSTD-0020 | Q24050972-03-6251-C-STD-0020 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - Lightning Protection System forWartsila Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0021 | A | 6105AK124-6251-CSTD-0021 | Q24050972-03-6251-C-STD-0021 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Civil Construction Requirements | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0022 | A | 6105AK124-6251-CSTD-0022 | Q24050972-03-6251-C-STD-0022 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Fire Protection System Design (Civil Works) | Load Bank - Fire Protection System Emergency Gen Load Bank - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0023 | A | 6105AK124-6251-CSTD-0023 | Q24050972-03-6251-C-STD-0023 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Civil Construction Requirements | Load Bank - Fire Protection System Emergency Gen Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0024 | A | 6105AK124-6251-CSTD-0024 | Q24050972-03-6251-C-STD-0024 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Bund-wall Requirements and Design | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0025 | A | 6105AK124-6251-CSTD-0025 | Q24050972-03-6251-C-STD-0025 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Civil Construction Requirements | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0026 | A | 6105AK124-6251-CSTD-0026 | Q24050972-03-6251-C-STD-0026 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Civil Construction Requirements | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0027 | A | 6105AK124-6251-CSTD-0027 | Q24050972-03-6251-C-STD-0027 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0028 | A | 6105AK124-6251-CSTD-0028 | Q24050972-03-6251-C-STD-0028 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Civil Construction Requirements | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0029 | A | 6105AK124-6251-CSTD-0029 | Q24050972-03-6251-C-STD-0029 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0030 | A | 6105AK124-6251-CSTD-0030 | Q24050972-03-6251-C-STD-0030 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Civil Construction Requirements | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0031 | A | 6105AK124-6251-CSTD-0031 | Q24050972-03-6251-C-STD-0031 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0032 | A | 6105AK124-6251-CSTD-0032 | Q24050972-03-6251-C-STD-0032 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0033 | A | 6105AK124-6251-CSTD-0033 | Q24050972-03-6251-C-STD-0033 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Civil Construction Requirements | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0034 | A | 6105AK124-6251-CSTD-0034 | Q24050972-03-6251-C-STD-0034 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0035 | A | 6105AK124-6251-CSTD-0035 | Q24050972-03-6251-C-STD-0035 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Civil Construction Requirements | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0036 | A | 6105AK124-6251-CSTD-0036 | Q24050972-03-6251-C-STD-0036 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0001 | A | 6105AK124-6251-ECAL-0001 | Q24050972-03-6251-E-CAL-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Cable and Conductor Sizing (incl Volt Drop Calcs) | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0002 | A | 6105AK124-6251-ECAL-0002 | Q24050972-03-6251-E-CAL-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Cable and Conductor Sizing (incl Volt Drop Calcs) | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0003 | A | 6105AK124-6251-ECAL-0003 | Q24050972-03-6251-E-CAL-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Cable and Conductor Sizing (incl Volt Drop Calcs) | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0004 | A | 6105AK124-6251-ECAL-0004 | Q24050972-03-6251-E-CAL-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Impedance and Burn-off Calculations | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0005 | A | 6105AK124-6251-ECAL-0005 | Q24050972-03-6251-E-CAL-0005 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Conductor Sag and Tension Plan | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0006 | A | 6105AK124-6251-ECAL-0006 | Q24050972-03-6251-E-CAL-0006 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Cable and Conductor Sizing (incl Volt Drop Calcs) | Load Bank - Small Power and Lighting for Wartsila Load Bank - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0007 | A | 6105AK124-6251-ECAL-0007 | Q24050972-03-6251-E-CAL-0007 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Conductor Sag and Tension Plan | Load Bank - Small Power and Lighting for Wartsila Load Bank - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0008 | A | 6105AK124-6251-ECAL-0008 | Q24050972-03-6251-E-CAL-0008 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Cable and Conductor Sizing (incl Volt Drop Calcs) | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0009 | A | 6105AK124-6251-ECAL-0009 | Q24050972-03-6251-E-CAL-0009 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Impedance and Burn-off Calculations | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0010 | A | 6105AK124-6251-ECAL-0010 | Q24050972-03-6251-E-CAL-0010 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Cable and Conductor Sizing (incl Volt Drop Calcs) | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0011 | A | 6105AK124-6251-ECAL-0011 | Q24050972-03-6251-E-CAL-0011 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Impedance and Burn-off Calculations | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0012 | A | 6105AK124-6251-ECAL-0012 | Q24050972-03-6251-E-CAL-0012 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Impedance and Burn-off Calculations | Load Bank - Lightning Protection System forWartsila Load Bank - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0013 | A | 6105AK124-6251-ECAL-0013 | Q24050972-03-6251-E-CAL-0013 |  | Load Bank | Earthing System for Wartsila Load Bank | Cable and Conductor Sizing (incl Volt Drop Calcs) | Load Bank - Earthing System for Wartsila Load Bank - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0014 | A | 6105AK124-6251-ECAL-0014 | Q24050972-03-6251-E-CAL-0014 |  | Load Bank | Earthing System for Wartsila Load Bank | Impedance and Burn-off Calculations | Load Bank - Earthing System for Wartsila Load Bank - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0015 | A | 6105AK124-6251-ECAL-0015 | Q24050972-03-6251-E-CAL-0015 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Conductor Sag and Tension Plan | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0016 | A | 6105AK124-6251-ECAL-0016 | Q24050972-03-6251-E-CAL-0016 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Cable and Conductor Sizing (incl Volt Drop Calcs) | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0017 | A | 6105AK124-6251-ECAL-0017 | Q24050972-03-6251-E-CAL-0017 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Conductor Sag and Tension Plan | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0018 | A | 6105AK124-6251-ECAL-0018 | Q24050972-03-6251-E-CAL-0018 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Cable and Conductor Sizing (incl Volt Drop Calcs) | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0019 | A | 6105AK124-6251-ECAL-0019 | Q24050972-03-6251-E-CAL-0019 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Impedance and Burn-off Calculations | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0020 | A | 6105AK124-6251-ECAL-0020 | Q24050972-03-6251-E-CAL-0020 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Cable and Conductor Sizing (incl Volt Drop Calcs) | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0021 | A | 6105AK124-6251-ECAL-0021 | Q24050972-03-6251-E-CAL-0021 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Impedance and Burn-off Calculations | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0022 | A | 6105AK124-6251-ECAL-0022 | Q24050972-03-6251-E-CAL-0022 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Impedance and Burn-off Calculations | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0023 | A | 6105AK124-6251-ECAL-0023 | Q24050972-03-6251-E-CAL-0023 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Cable and Conductor Sizing (incl Volt Drop Calcs) | Load Bank - Earthing System forEmergency Gen Load Bank - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | CAL | 0024 | A | 6105AK124-6251-ECAL-0024 | Q24050972-03-6251-E-CAL-0024 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Impedance and Burn-off Calculations | Load Bank - Earthing System forEmergency Gen Load Bank - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0001 | A | 6105AK124-6251-EDIA-0001 | Q24050972-03-6251-E-DIA-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Cable Block Diagrams and Schedules | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0002 | A | 6105AK124-6251-EDIA-0002 | Q24050972-03-6251-E-DIA-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Cable Block Diagrams and Schedules | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0003 | A | 6105AK124-6251-EDIA-0003 | Q24050972-03-6251-E-DIA-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Electrical Circuit Diagrams (Schematics) | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0004 | A | 6105AK124-6251-EDIA-0004 | Q24050972-03-6251-E-DIA-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | E/I Termination Schedule | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0005 | A | 6105AK124-6251-EDIA-0005 | Q24050972-03-6251-E-DIA-0005 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Electrical Block Diagram | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0006 | A | 6105AK124-6251-EDIA-0006 | Q24050972-03-6251-E-DIA-0006 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Cable Block Diagrams and Schedules | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0007 | A | 6105AK124-6251-EDIA-0007 | Q24050972-03-6251-E-DIA-0007 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Electrical Circuit Diagrams (Schematics) | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0008 | A | 6105AK124-6251-EDIA-0008 | Q24050972-03-6251-E-DIA-0008 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | E/I Termination Schedule | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables | Wartsila Load Bank | Wartsila Load Bank |  | Pending
6105A | K124 | 6251 | E | DIA | 0009 | A | 6105AK124-6251-EDIA-0009 | Q24050972-03-6251-E-DIA-0009 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Electrical Block Diagram | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0010 | A | 6105AK124-6251-EDIA-0010 | Q24050972-03-6251-E-DIA-0010 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Cable Block Diagrams and Schedules | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0011 | A | 6105AK124-6251-EDIA-0011 | Q24050972-03-6251-E-DIA-0011 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | E/I Termination Schedule | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0012 | A | 6105AK124-6251-EDIA-0012 | Q24050972-03-6251-E-DIA-0012 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Cable Block Diagrams and Schedules | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0013 | A | 6105AK124-6251-EDIA-0013 | Q24050972-03-6251-E-DIA-0013 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Electrical Circuit Diagrams (Schematics) | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0014 | A | 6105AK124-6251-EDIA-0014 | Q24050972-03-6251-E-DIA-0014 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Cable Block Diagrams and Schedules | Load Bank - Platform and Foundations for Wartsila Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0015 | A | 6105AK124-6251-EDIA-0015 | Q24050972-03-6251-E-DIA-0015 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Cable Block Diagrams and Schedules | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0016 | A | 6105AK124-6251-EDIA-0016 | Q24050972-03-6251-E-DIA-0016 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0017 | A | 6105AK124-6251-EDIA-0017 | Q24050972-03-6251-E-DIA-0017 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | E/I Termination Schedule | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0018 | A | 6105AK124-6251-EDIA-0018 | Q24050972-03-6251-E-DIA-0018 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Cable Block Diagrams and Schedules | Load Bank - Small Power and Lighting for Wartsila Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0019 | A | 6105AK124-6251-EDIA-0019 | Q24050972-03-6251-E-DIA-0019 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Electrical Block Diagram | Load Bank - Small Power and Lighting for Wartsila Load Bank - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0020 | A | 6105AK124-6251-EDIA-0020 | Q24050972-03-6251-E-DIA-0020 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - Small Power and Lighting for Wartsila Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0021 | A | 6105AK124-6251-EDIA-0021 | Q24050972-03-6251-E-DIA-0021 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | E/I Termination Schedule | Load Bank - Small Power and Lighting for Wartsila Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0022 | A | 6105AK124-6251-EDIA-0022 | Q24050972-03-6251-E-DIA-0022 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Cable Block Diagrams and Schedules | Load Bank - Metering Instruments for Wartsila Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0023 | A | 6105AK124-6251-EDIA-0023 | Q24050972-03-6251-E-DIA-0023 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - Metering Instruments for Wartsila Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0021 | A | 6105AK124-6200-EDIA-0021 | Q24050972-03-6200-E-DIA-0021 |  | On-Site Power Supply and Transmission | Main Consumer Intake Power Complex | 33kV Cable Block Diagram | On-Site Power Supply and Transmission - Main Consumer Intake Power Complex - 33kV Cable Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Main Consumer Intake | 33kV Cable Block |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0022 | A | 6105AK124-6200-EDIA-0022 | Q24050972-03-6200-E-DIA-0022 |  | On-Site Power Supply and Transmission | Main Consumer Intake Power Complex | 11kV Cable Block Diagram | On-Site Power Supply and Transmission - Main Consumer Intake Power Complex - 11kV Cable Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Main Consumer Intake | 11kV Cable Block |  |  |  | Pending
6105A | K124 | 6200 | E | SEC | 0001 | A | 6105AK124-6200-ESEC-0001 | Q24050972-03-6200-E-SEC-0001 |  | On-Site Power Supply and Transmission | Main Consumer Intake Power Complex | Cable Trench Cable Detail - Generartor Area | On-Site Power Supply and Transmission - Main Consumer Intake Power Complex - Cable Trench Cable Detail - Generartor Area |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Main Consumer Intake | CablE Trench |  |  |  | Pending
6105A | K124 | 6200 | E | SEC | 0002 | A | 6105AK124-6200-ESEC-0002 | Q24050972-03-6200-E-SEC-0002 |  | On-Site Power Supply and Transmission | Main Consumer Intake Power Complex | MV Cable Road Crossing Cable Detail - 220/33kV 80MVA Transformers | On-Site Power Supply and Transmission - Main Consumer Intake Power Complex - MV Cable Road Crossing Cable Detail - 220/33kV 80MVA Transformers |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Main Consumer Intake | MV Cable Road Crossing |  |  |  | Pending
6105A | K124 | 6200 | E | SEC | 0003 | A | 6105AK124-6200-ESEC-0003 | Q24050972-03-6200-E-SEC-0003 |  | On-Site Power Supply and Transmission | Main Consumer Intake Power Complex | MV Cable Trench Cable Detail - 220/33kV 80MVA Transformers | On-Site Power Supply and Transmission - Main Consumer Intake Power Complex - MV Cable Trench Cable Detail - 220/33kV 80MVA Transformers |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Main Consumer Intake | MV Cable Trench Cable |  |  |  | Pending
6105A | K124 | 6200 | E | SEC | 0004 | A | 6105AK124-6200-ESEC-0004 | Q24050972-03-6200-E-SEC-0004 |  | On-Site Power Supply and Transmission | Main Consumer Intake Power Complex | Cable Trench Cable Detail - Syncon Cables | On-Site Power Supply and Transmission - Main Consumer Intake Power Complex - Cable Trench Cable Detail - Syncon Cables |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Main Consumer Intake | Cable Trench |  |  |  | Pending
6105A | K124 | 6200 | E | SEC | 0005 | A | 6105AK124-6200-ESEC-0005 | Q24050972-03-6200-E-SEC-0005 |  | On-Site Power Supply and Transmission | Main Consumer Intake Power Complex | Cable Gantry A Cable Detail | On-Site Power Supply and Transmission - Main Consumer Intake Power Complex - Cable Gantry A Cable Detail |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Main Consumer Intake | Cable Gantry A |  |  |  | Pending
6105A | K124 | 6200 | E | SEC | 0006 | A | 6105AK124-6200-ESEC-0006 | Q24050972-03-6200-E-SEC-0006 |  | On-Site Power Supply and Transmission | Main Consumer Intake Power Complex | Cable Gantry B Cable Detail | On-Site Power Supply and Transmission - Main Consumer Intake Power Complex - Cable Gantry B Cable Detail |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Main Consumer Intake | Cable Gantry B |  |  |  | Pending
6105A | K124 | 6200 | E | DIA | 0023 | A | 6105AK124-6200-EDIA-0023 | Q24050972-03-6200-E-DIA-0023 |  | On-Site Power Supply and Transmission | Main Consumer Substation | LV Cable Block Diagram | On-Site Power Supply and Transmission - Main Consumer Substation - LV Cable Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | TM |  | 2026-05-29 | Main Consumer Substation | LV Cable Block Diagram |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0024 | A | 6105AK124-6251-EDIA-0024 | Q24050972-03-6251-E-DIA-0024 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Electrical Block Diagram | Load Bank - Metering Instruments for Wartsila Load Bank - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0025 | A | 6105AK124-6251-EDIA-0025 | Q24050972-03-6251-E-DIA-0025 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0026 | A | 6105AK124-6251-EDIA-0026 | Q24050972-03-6251-E-DIA-0026 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Electrical Block Diagram | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0027 | A | 6105AK124-6251-EDIA-0027 | Q24050972-03-6251-E-DIA-0027 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Electrical Network Architecture | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Electrical Network Architecture |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0028 | A | 6105AK124-6251-EDIA-0028 | Q24050972-03-6251-E-DIA-0028 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Protection Relay Design | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Protection Relay Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0029 | A | 6105AK124-6251-EDIA-0029 | Q24050972-03-6251-E-DIA-0029 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0030 | A | 6105AK124-6251-EDIA-0030 | Q24050972-03-6251-E-DIA-0030 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Electrical Block Diagram | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0031 | A | 6105AK124-6251-EDIA-0031 | Q24050972-03-6251-E-DIA-0031 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Electrical Network Architecture | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Electrical Network Architecture |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0032 | A | 6105AK124-6251-EDIA-0032 | Q24050972-03-6251-E-DIA-0032 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Protection Relay Design | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Protection Relay Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0033 | A | 6105AK124-6251-EDIA-0033 | Q24050972-03-6251-E-DIA-0033 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Cable Block Diagrams and Schedules | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0034 | A | 6105AK124-6251-EDIA-0034 | Q24050972-03-6251-E-DIA-0034 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0035 | A | 6105AK124-6251-EDIA-0035 | Q24050972-03-6251-E-DIA-0035 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Electrical Block Diagram | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0036 | A | 6105AK124-6251-EDIA-0036 | Q24050972-03-6251-E-DIA-0036 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | E/I Termination Schedule | Load Bank - MV Cabling and Termination for Wartsila Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0037 | A | 6105AK124-6251-EDIA-0037 | Q24050972-03-6251-E-DIA-0037 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Cable Block Diagrams and Schedules | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0038 | A | 6105AK124-6251-EDIA-0038 | Q24050972-03-6251-E-DIA-0038 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0039 | A | 6105AK124-6251-EDIA-0039 | Q24050972-03-6251-E-DIA-0039 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Electrical Block Diagram | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0040 | A | 6105AK124-6251-EDIA-0040 | Q24050972-03-6251-E-DIA-0040 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | E/I Termination Schedule | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0041 | A | 6105AK124-6251-EDIA-0041 | Q24050972-03-6251-E-DIA-0041 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Cable Block Diagrams and Schedules | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0042 | A | 6105AK124-6251-EDIA-0042 | Q24050972-03-6251-E-DIA-0042 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | E/I Termination Schedule | Load Bank - Cable Racks and Trays for Wartsila Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0043 | A | 6105AK124-6251-EDIA-0043 | Q24050972-03-6251-E-DIA-0043 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Cable Block Diagrams and Schedules | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0044 | A | 6105AK124-6251-EDIA-0044 | Q24050972-03-6251-E-DIA-0044 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | E/I Termination Schedule | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank | Wartsila Load Bank | Wartsila Load Bank |  | Pending
6105A | K124 | 6251 | E | DIA | 0045 | A | 6105AK124-6251-EDIA-0045 | Q24050972-03-6251-E-DIA-0045 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Cable Block Diagrams and Schedules | Load Bank - Lightning Protection System forWartsila Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0046 | A | 6105AK124-6251-EDIA-0046 | Q24050972-03-6251-E-DIA-0046 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - Lightning Protection System forWartsila Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0047 | A | 6105AK124-6251-EDIA-0047 | Q24050972-03-6251-E-DIA-0047 |  | Load Bank | Earthing System for Wartsila Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - Earthing System for Wartsila Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0048 | A | 6105AK124-6251-EDIA-0048 | Q24050972-03-6251-E-DIA-0048 |  | Load Bank | Earthing System for Wartsila Load Bank | Cable Block Diagrams and Schedules | Load Bank - Earthing System for Wartsila Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0049 | A | 6105AK124-6251-EDIA-0049 | Q24050972-03-6251-E-DIA-0049 |  | Load Bank | Earthing System for Wartsila Load Bank | E/I Termination Schedule | Load Bank - Earthing System for Wartsila Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0050 | A | 6105AK124-6251-EDIA-0050 | Q24050972-03-6251-E-DIA-0050 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Cable Block Diagrams and Schedules | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0051 | A | 6105AK124-6251-EDIA-0051 | Q24050972-03-6251-E-DIA-0051 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Cable Block Diagrams and Schedules | Load Bank - Fire Protection System Emergency Gen Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0052 | A | 6105AK124-6251-EDIA-0052 | Q24050972-03-6251-E-DIA-0052 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - Fire Protection System Emergency Gen Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0053 | A | 6105AK124-6251-EDIA-0053 | Q24050972-03-6251-E-DIA-0053 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | E/I Termination Schedule | Load Bank - Fire Protection System Emergency Gen Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank | Emergency Gen Load Bank | Emergency Gen Load Bank |  | Pending
6105A | K124 | 6251 | E | DIA | 0054 | A | 6105AK124-6251-EDIA-0054 | Q24050972-03-6251-E-DIA-0054 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Cable Block Diagrams and Schedules | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0055 | A | 6105AK124-6251-EDIA-0055 | Q24050972-03-6251-E-DIA-0055 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Electrical Block Diagram | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0056 | A | 6105AK124-6251-EDIA-0056 | Q24050972-03-6251-E-DIA-0056 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0057 | A | 6105AK124-6251-EDIA-0057 | Q24050972-03-6251-E-DIA-0057 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | E/I Termination Schedule | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0058 | A | 6105AK124-6251-EDIA-0058 | Q24050972-03-6251-E-DIA-0058 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Cable Block Diagrams and Schedules | Load Bank - Metering Instruments for Emergency Gen Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0059 | A | 6105AK124-6251-EDIA-0059 | Q24050972-03-6251-E-DIA-0059 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - Metering Instruments for Emergency Gen Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0060 | A | 6105AK124-6251-EDIA-0060 | Q24050972-03-6251-E-DIA-0060 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Electrical Block Diagram | Load Bank - Metering Instruments for Emergency Gen Load Bank - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0061 | A | 6105AK124-6251-EDIA-0061 | Q24050972-03-6251-E-DIA-0061 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0062 | A | 6105AK124-6251-EDIA-0062 | Q24050972-03-6251-E-DIA-0062 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Electrical Block Diagram | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0063 | A | 6105AK124-6251-EDIA-0063 | Q24050972-03-6251-E-DIA-0063 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Electrical Network Architecture | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Electrical Network Architecture |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0064 | A | 6105AK124-6251-EDIA-0064 | Q24050972-03-6251-E-DIA-0064 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Protection Relay Design | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Protection Relay Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0065 | A | 6105AK124-6251-EDIA-0065 | Q24050972-03-6251-E-DIA-0065 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Cable Block Diagrams and Schedules | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0066 | A | 6105AK124-6251-EDIA-0066 | Q24050972-03-6251-E-DIA-0066 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0067 | A | 6105AK124-6251-EDIA-0067 | Q24050972-03-6251-E-DIA-0067 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Electrical Block Diagram | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0068 | A | 6105AK124-6251-EDIA-0068 | Q24050972-03-6251-E-DIA-0068 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | E/I Termination Schedule | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0069 | A | 6105AK124-6251-EDIA-0069 | Q24050972-03-6251-E-DIA-0069 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Cable Block Diagrams and Schedules | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0070 | A | 6105AK124-6251-EDIA-0070 | Q24050972-03-6251-E-DIA-0070 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0071 | A | 6105AK124-6251-EDIA-0071 | Q24050972-03-6251-E-DIA-0071 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Electrical Block Diagram | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0072 | A | 6105AK124-6251-EDIA-0072 | Q24050972-03-6251-E-DIA-0072 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | E/I Termination Schedule | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0073 | A | 6105AK124-6251-EDIA-0073 | Q24050972-03-6251-E-DIA-0073 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Cable Block Diagrams and Schedules | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0074 | A | 6105AK124-6251-EDIA-0074 | Q24050972-03-6251-E-DIA-0074 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | E/I Termination Schedule | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0075 | A | 6105AK124-6251-EDIA-0075 | Q24050972-03-6251-E-DIA-0075 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Cable Block Diagrams and Schedules | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0076 | A | 6105AK124-6251-EDIA-0076 | Q24050972-03-6251-E-DIA-0076 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | E/I Termination Schedule | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0077 | A | 6105AK124-6251-EDIA-0077 | Q24050972-03-6251-E-DIA-0077 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Cable Block Diagrams and Schedules | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0078 | A | 6105AK124-6251-EDIA-0078 | Q24050972-03-6251-E-DIA-0078 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0079 | A | 6105AK124-6251-EDIA-0079 | Q24050972-03-6251-E-DIA-0079 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Electrical Circuit Diagrams (Schematics) | Load Bank - Earthing System forEmergency Gen Load Bank - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0080 | A | 6105AK124-6251-EDIA-0080 | Q24050972-03-6251-E-DIA-0080 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Cable Block Diagrams and Schedules | Load Bank - Earthing System forEmergency Gen Load Bank - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DIA | 0081 | A | 6105AK124-6251-EDIA-0081 | Q24050972-03-6251-E-DIA-0081 |  | Load Bank | Earthing System forEmergency Gen Load Bank | E/I Termination Schedule | Load Bank - Earthing System forEmergency Gen Load Bank - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0001 | A | 6105AK124-6251-EDST-0001 | Q24050972-03-6251-E-DST-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Equipment Register and Technical Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0002 | A | 6105AK124-6251-EDST-0002 | Q24050972-03-6251-E-DST-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Equipment Register and Technical Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0003 | A | 6105AK124-6251-EDST-0003 | Q24050972-03-6251-E-DST-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Equipment Register and Technical Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0004 | A | 6105AK124-6251-EDST-0004 | Q24050972-03-6251-E-DST-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Equipment Register and Technical Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0005 | A | 6105AK124-6251-EDST-0005 | Q24050972-03-6251-E-DST-0005 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Equipment Register and Technical Specifications | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank | Wartsila Load Bank | Wartsila Load Bank |  | Pending
6105A | K124 | 6251 | E | DST | 0006 | A | 6105AK124-6251-EDST-0006 | Q24050972-03-6251-E-DST-0006 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Equipment Register and Technical Specifications | Load Bank - Small Power and Lighting for Wartsila Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0007 | A | 6105AK124-6251-EDST-0007 | Q24050972-03-6251-E-DST-0007 |  | Load Bank | Metering Instruments for Wartsila Load Bank | CT and PT Datasheets | Load Bank - Metering Instruments for Wartsila Load Bank - CT and PT Datasheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0008 | A | 6105AK124-6251-EDST-0008 | Q24050972-03-6251-E-DST-0008 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Equipment Register and Technical Specifications | Load Bank - Metering Instruments for Wartsila Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0009 | A | 6105AK124-6251-EDST-0009 | Q24050972-03-6251-E-DST-0009 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | CT and PT Datasheets | Load Bank - 11kV Protection Relays for Wartsila Load Bank - CT and PT Datasheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0010 | A | 6105AK124-6251-EDST-0010 | Q24050972-03-6251-E-DST-0010 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Equipment Register and Technical Specifications | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0011 | A | 6105AK124-6251-EDST-0011 | Q24050972-03-6251-E-DST-0011 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | CT and PT Datasheets | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - CT and PT Datasheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0012 | A | 6105AK124-6251-EDST-0012 | Q24050972-03-6251-E-DST-0012 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Equipment Register and Technical Specifications | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0013 | A | 6105AK124-6251-EDST-0013 | Q24050972-03-6251-E-DST-0013 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Equipment Register and Technical Specifications | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0014 | A | 6105AK124-6251-EDST-0014 | Q24050972-03-6251-E-DST-0014 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Equipment Register and Technical Specifications | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank | Wartsila Load Bank | Wartsila Load Bank |  | Pending
6105A | K124 | 6251 | E | DST | 0015 | A | 6105AK124-6251-EDST-0015 | Q24050972-03-6251-E-DST-0015 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Equipment Register and Technical Specifications | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0016 | A | 6105AK124-6251-EDST-0016 | Q24050972-03-6251-E-DST-0016 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Equipment Register and Technical Specifications | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0017 | A | 6105AK124-6251-EDST-0017 | Q24050972-03-6251-E-DST-0017 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Equipment Register and Technical Specifications | Load Bank - Lightning Protection System forWartsila Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0018 | A | 6105AK124-6251-EDST-0018 | Q24050972-03-6251-E-DST-0018 |  | Load Bank | Earthing System for Wartsila Load Bank | Equipment Register and Technical Specifications | Load Bank - Earthing System for Wartsila Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0019 | A | 6105AK124-6251-EDST-0019 | Q24050972-03-6251-E-DST-0019 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Equipment Register and Technical Specifications | Load Bank - Fire Protection System Emergency Gen Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0020 | A | 6105AK124-6251-EDST-0020 | Q24050972-03-6251-E-DST-0020 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Equipment Register and Technical Specifications | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0021 | A | 6105AK124-6251-EDST-0021 | Q24050972-03-6251-E-DST-0021 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | CT and PT Datasheets | Load Bank - Metering Instruments for Emergency Gen Load Bank - CT and PT Datasheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0022 | A | 6105AK124-6251-EDST-0022 | Q24050972-03-6251-E-DST-0022 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Equipment Register and Technical Specifications | Load Bank - Metering Instruments for Emergency Gen Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0023 | A | 6105AK124-6251-EDST-0023 | Q24050972-03-6251-E-DST-0023 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | CT and PT Datasheets | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - CT and PT Datasheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0024 | A | 6105AK124-6251-EDST-0024 | Q24050972-03-6251-E-DST-0024 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Equipment Register and Technical Specifications | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0025 | A | 6105AK124-6251-EDST-0025 | Q24050972-03-6251-E-DST-0025 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Equipment Register and Technical Specifications | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0026 | A | 6105AK124-6251-EDST-0026 | Q24050972-03-6251-E-DST-0026 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Equipment Register and Technical Specifications | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0027 | A | 6105AK124-6251-EDST-0027 | Q24050972-03-6251-E-DST-0027 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Equipment Register and Technical Specifications | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0028 | A | 6105AK124-6251-EDST-0028 | Q24050972-03-6251-E-DST-0028 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Equipment Register and Technical Specifications | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0029 | A | 6105AK124-6251-EDST-0029 | Q24050972-03-6251-E-DST-0029 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Equipment Register and Technical Specifications | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | DST | 0030 | A | 6105AK124-6251-EDST-0030 | Q24050972-03-6251-E-DST-0030 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Equipment Register and Technical Specifications | Load Bank - Earthing System forEmergency Gen Load Bank - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6200 | G | LST | 0001 | A | 6105AK124-6200-GLST-0001 | Q24050972-03-6200-G-LST-0001 |  | On-Site Power Supply and Transmission | Plant-Wide Substations Document Register | Document and Drawing Register | On-Site Power Supply and Transmission - Plant-Wide Substations Document Register - Document and Drawing Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Construction Doc Register | Document and Drawing Register |  |  |  | Pending
6105A | K124 | 6251 | E | EQL | 0001 | A | 6105AK124-6251-EEQL-0001 | Q24050972-03-6251-E-EQL-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Electrical Equipment Load Register | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | EQL | 0002 | A | 6105AK124-6251-EEQL-0002 | Q24050972-03-6251-E-EQL-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Electrical Equipment Load Register | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | EQL | 0003 | A | 6105AK124-6251-EEQL-0003 | Q24050972-03-6251-E-EQL-0003 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Electrical Equipment Load Register | Load Bank - Small Power and Lighting for Wartsila Load Bank - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | EQL | 0004 | A | 6105AK124-6251-EEQL-0004 | Q24050972-03-6251-E-EQL-0004 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Electrical Equipment Load Register | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | EQL | 0005 | A | 6105AK124-6251-EEQL-0005 | Q24050972-03-6251-E-EQL-0005 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Electrical Equipment Load Register | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | EQL | 0006 | A | 6105AK124-6251-EEQL-0006 | Q24050972-03-6251-E-EQL-0006 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Electrical Equipment Load Register | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | EQL | 0007 | A | 6105AK124-6251-EEQL-0007 | Q24050972-03-6251-E-EQL-0007 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Electrical Equipment Load Register | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | EQL | 0008 | A | 6105AK124-6251-EEQL-0008 | Q24050972-03-6251-E-EQL-0008 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Electrical Equipment Load Register | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | GAD | 0001 | A | 6105AK124-6251-EGAD-0001 | Q24050972-03-6251-E-GAD-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Mobile Load Bank Electrical General Arrangement | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Mobile Load Bank Electrical General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | GAD | 0002 | A | 6105AK124-6251-EGAD-0002 | Q24050972-03-6251-E-GAD-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Electrical Equipment Layout | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Electrical Equipment Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | GAD | 0003 | A | 6105AK124-6251-EGAD-0003 | Q24050972-03-6251-E-GAD-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Mobile Load Bank Electrical General Arrangement | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Mobile Load Bank Electrical General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | GAD | 0004 | A | 6105AK124-6251-EGAD-0004 | Q24050972-03-6251-E-GAD-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Electrical Equipment Layout | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Electrical Equipment Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | GAD | 0005 | A | 6105AK124-6251-EGAD-0005 | Q24050972-03-6251-E-GAD-0005 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Mobile Load Bank Electrical General Arrangement | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Mobile Load Bank Electrical General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | GAD | 0006 | A | 6105AK124-6251-EGAD-0006 | Q24050972-03-6251-E-GAD-0006 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Control Room Design | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Control Room Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | GAD | 0007 | A | 6105AK124-6251-EGAD-0007 | Q24050972-03-6251-E-GAD-0007 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Control Room Design | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Control Room Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | GAD | 0008 | A | 6105AK124-6251-EGAD-0008 | Q24050972-03-6251-E-GAD-0008 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Control Room Design | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Control Room Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | LAY | 0002 | A | 6105AK124-6251-ELAY-0002 | Q24050972-03-6251-E-LAY-0002 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Control Room Power and Earthing Design | Load Bank - Small Power and Lighting for Wartsila Load Bank - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | LAY | 0003 | A | 6105AK124-6251-ELAY-0003 | Q24050972-03-6251-E-LAY-0003 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Switch Room (PCC and MCC) Detail Design | Load Bank - Metering Instruments for Wartsila Load Bank - Switch Room (PCC and MCC) Detail Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | LAY | 0004 | A | 6105AK124-6251-ELAY-0004 | Q24050972-03-6251-E-LAY-0004 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Control Room Power and Earthing Design | Load Bank - Lightning Protection System forWartsila Load Bank - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | LAY | 0005 | A | 6105AK124-6251-ELAY-0005 | Q24050972-03-6251-E-LAY-0005 |  | Load Bank | Earthing System for Wartsila Load Bank | Control Room Power and Earthing Design | Load Bank - Earthing System for Wartsila Load Bank - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | LAY | 0006 | A | 6105AK124-6251-ELAY-0006 | Q24050972-03-6251-E-LAY-0006 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Control Room Power and Earthing Design | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | LAY | 0007 | A | 6105AK124-6251-ELAY-0007 | Q24050972-03-6251-E-LAY-0007 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Switch Room (PCC and MCC) Detail Design | Load Bank - Metering Instruments for Emergency Gen Load Bank - Switch Room (PCC and MCC) Detail Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | LAY | 0008 | A | 6105AK124-6251-ELAY-0008 | Q24050972-03-6251-E-LAY-0008 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Control Room Power and Earthing Design | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | LAY | 0009 | A | 6105AK124-6251-ELAY-0009 | Q24050972-03-6251-E-LAY-0009 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Control Room Power and Earthing Design | Load Bank - Earthing System forEmergency Gen Load Bank - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | MDL | 0001 | A | 6105AK124-6251-EMDL-0001 | Q24050972-03-6251-E-MDL-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | ETAP Network Model | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | MDL | 0002 | A | 6105AK124-6251-EMDL-0002 | Q24050972-03-6251-E-MDL-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | ETAP Network Model | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | MDL | 0003 | A | 6105AK124-6251-EMDL-0003 | Q24050972-03-6251-E-MDL-0003 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | ETAP Network Model | Load Bank - 11kV Protection Relays for Wartsila Load Bank - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | MDL | 0004 | A | 6105AK124-6251-EMDL-0004 | Q24050972-03-6251-E-MDL-0004 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | ETAP Network Model | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | MDL | 0005 | A | 6105AK124-6251-EMDL-0005 | Q24050972-03-6251-E-MDL-0005 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | ETAP Network Model | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0001 | A | 6105AK124-6251-EQRA-0001 | Q24050972-03-6251-E-QRA-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Lightning Protection Study and Risk Assessment | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0002 | A | 6105AK124-6251-EQRA-0002 | Q24050972-03-6251-E-QRA-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Risk Assessment: Electrical Hazards | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0003 | A | 6105AK124-6251-EQRA-0003 | Q24050972-03-6251-E-QRA-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Risk Assessment: Electrical Hazards | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0004 | A | 6105AK124-6251-EQRA-0004 | Q24050972-03-6251-E-QRA-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Lightning Protection Study and Risk Assessment | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0005 | A | 6105AK124-6251-EQRA-0005 | Q24050972-03-6251-E-QRA-0005 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Risk Assessment: Electrical Hazards | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0006 | A | 6105AK124-6251-EQRA-0006 | Q24050972-03-6251-E-QRA-0006 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Lightning Protection Study and Risk Assessment | Load Bank - Platform and Foundations for Wartsila Load Bank - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0007 | A | 6105AK124-6251-EQRA-0007 | Q24050972-03-6251-E-QRA-0007 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Risk Assessment: Electrical Hazards | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0008 | A | 6105AK124-6251-EQRA-0008 | Q24050972-03-6251-E-QRA-0008 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Lightning Protection Study and Risk Assessment | Load Bank - Small Power and Lighting for Wartsila Load Bank - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0009 | A | 6105AK124-6251-EQRA-0009 | Q24050972-03-6251-E-QRA-0009 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Lightning Protection Study and Risk Assessment | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0010 | A | 6105AK124-6251-EQRA-0010 | Q24050972-03-6251-E-QRA-0010 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Risk Assessment: Electrical Hazards | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0011 | A | 6105AK124-6251-EQRA-0011 | Q24050972-03-6251-E-QRA-0011 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Lightning Protection Study and Risk Assessment | Load Bank - Lightning Protection System forWartsila Load Bank - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0012 | A | 6105AK124-6251-EQRA-0012 | Q24050972-03-6251-E-QRA-0012 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Lightning Protection Study and Risk Assessment | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0013 | A | 6105AK124-6251-EQRA-0013 | Q24050972-03-6251-E-QRA-0013 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Risk Assessment: Electrical Hazards | Load Bank - Fire Protection System Emergency Gen Load Bank - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0014 | A | 6105AK124-6251-EQRA-0014 | Q24050972-03-6251-E-QRA-0014 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Lightning Protection Study and Risk Assessment | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0015 | A | 6105AK124-6251-EQRA-0015 | Q24050972-03-6251-E-QRA-0015 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Lightning Protection Study and Risk Assessment | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0016 | A | 6105AK124-6251-EQRA-0016 | Q24050972-03-6251-E-QRA-0016 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Risk Assessment: Electrical Hazards | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | QRA | 0017 | A | 6105AK124-6251-EQRA-0017 | Q24050972-03-6251-E-QRA-0017 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Lightning Protection Study and Risk Assessment | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | RPT | 0001 | A | 6105AK124-6251-ERPT-0001 | Q24050972-03-6251-E-RPT-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Load Bank Operational and Maintenance Study | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Load Bank Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | E | RPT | 0002 | A | 6105AK124-6251-ERPT-0002 | Q24050972-03-6251-E-RPT-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Load Bank Operational and Maintenance Study | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Load Bank Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | RPT | 0003 | A | 6105AK124-6251-ERPT-0003 | Q24050972-03-6251-E-RPT-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Load Bank Operational and Maintenance Study | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Load Bank Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | RPT | 0004 | A | 6105AK124-6251-ERPT-0004 | Q24050972-03-6251-E-RPT-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Load Bank Operational and Maintenance Study | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Load Bank Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | RPT | 0005 | A | 6105AK124-6251-ERPT-0005 | Q24050972-03-6251-E-RPT-0005 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Load Bank Operational and Maintenance Study | Load Bank - Platform and Foundations for Wartsila Load Bank - Load Bank Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | RPT | 0006 | A | 6105AK124-6251-ERPT-0006 | Q24050972-03-6251-E-RPT-0006 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | HV/MV Operational and Maintenance Study | Load Bank - 11kV Protection Relays for Wartsila Load Bank - HV/MV Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | RPT | 0007 | A | 6105AK124-6251-ERPT-0007 | Q24050972-03-6251-E-RPT-0007 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Reactive Power Study | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Reactive Power Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | RPT | 0008 | A | 6105AK124-6251-ERPT-0008 | Q24050972-03-6251-E-RPT-0008 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | HV/MV Operational and Maintenance Study | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - HV/MV Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | RPT | 0009 | A | 6105AK124-6251-ERPT-0009 | Q24050972-03-6251-E-RPT-0009 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Reactive Power Study | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Reactive Power Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | RPT | 0010 | A | 6105AK124-6251-ERPT-0010 | Q24050972-03-6251-E-RPT-0010 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Load Bank Operational and Maintenance Study | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Load Bank Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | RPT | 0011 | A | 6105AK124-6251-ERPT-0011 | Q24050972-03-6251-E-RPT-0011 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | HV/MV Operational and Maintenance Study | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - HV/MV Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | RPT | 0012 | A | 6105AK124-6251-ERPT-0012 | Q24050972-03-6251-E-RPT-0012 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Reactive Power Study | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Reactive Power Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0002 | A | 6105AK124-6251-ESLD-0002 | Q24050972-03-6251-E-SLD-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Electrical Single Line Diagram | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0003 | A | 6105AK124-6251-ESLD-0003 | Q24050972-03-6251-E-SLD-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Electrical Single Line Diagram | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0004 | A | 6105AK124-6251-ESLD-0004 | Q24050972-03-6251-E-SLD-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Electrical Single Line Diagram | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0005 | A | 6105AK124-6251-ESLD-0005 | Q24050972-03-6251-E-SLD-0005 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Electrical Single Line Diagram | Load Bank - Small Power and Lighting for Wartsila Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0006 | A | 6105AK124-6251-ESLD-0006 | Q24050972-03-6251-E-SLD-0006 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Electrical Single Line Diagram | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0007 | A | 6105AK124-6251-ESLD-0007 | Q24050972-03-6251-E-SLD-0007 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Electrical Single Line Diagram | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0008 | A | 6105AK124-6251-ESLD-0008 | Q24050972-03-6251-E-SLD-0008 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Electrical Single Line Diagram | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0009 | A | 6105AK124-6251-ESLD-0009 | Q24050972-03-6251-E-SLD-0009 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Electrical Single Line Diagram | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0010 | A | 6105AK124-6251-ESLD-0010 | Q24050972-03-6251-E-SLD-0010 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Electrical Single Line Diagram | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0011 | A | 6105AK124-6251-ESLD-0011 | Q24050972-03-6251-E-SLD-0011 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Electrical Single Line Diagram | Load Bank - Lightning Protection System forWartsila Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0012 | A | 6105AK124-6251-ESLD-0012 | Q24050972-03-6251-E-SLD-0012 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Electrical Single Line Diagram | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0013 | A | 6105AK124-6251-ESLD-0013 | Q24050972-03-6251-E-SLD-0013 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Electrical Single Line Diagram | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0014 | A | 6105AK124-6251-ESLD-0014 | Q24050972-03-6251-E-SLD-0014 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Electrical Single Line Diagram | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0015 | A | 6105AK124-6251-ESLD-0015 | Q24050972-03-6251-E-SLD-0015 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Electrical Single Line Diagram | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0016 | A | 6105AK124-6251-ESLD-0016 | Q24050972-03-6251-E-SLD-0016 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Electrical Single Line Diagram | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SLD | 0017 | A | 6105AK124-6251-ESLD-0017 | Q24050972-03-6251-E-SLD-0017 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Electrical Single Line Diagram | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0001 | A | 6105AK124-6251-ESPC-0001 | Q24050972-03-6251-E-SPC-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Lighting and Luminaire Design | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0002 | A | 6105AK124-6251-ESPC-0002 | Q24050972-03-6251-E-SPC-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Cable and Conductor Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0003 | A | 6105AK124-6251-ESPC-0003 | Q24050972-03-6251-E-SPC-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Cable Termination Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0004 | A | 6105AK124-6251-ESPC-0004 | Q24050972-03-6251-E-SPC-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Electrical Equipment Communication Specification | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Electrical Equipment Communication Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0005 | A | 6105AK124-6251-ESPC-0005 | Q24050972-03-6251-E-SPC-0005 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Cable and Conductor Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0006 | A | 6105AK124-6251-ESPC-0006 | Q24050972-03-6251-E-SPC-0006 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Cable Termination Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0007 | A | 6105AK124-6251-ESPC-0007 | Q24050972-03-6251-E-SPC-0007 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Electrical Equipment Communication Specification | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Electrical Equipment Communication Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0008 | A | 6105AK124-6251-ESPC-0008 | Q24050972-03-6251-E-SPC-0008 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Cable and Conductor Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0009 | A | 6105AK124-6251-ESPC-0009 | Q24050972-03-6251-E-SPC-0009 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Cable and Conductor Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0010 | A | 6105AK124-6251-ESPC-0010 | Q24050972-03-6251-E-SPC-0010 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Cable Termination Specifications | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0011 | A | 6105AK124-6251-ESPC-0011 | Q24050972-03-6251-E-SPC-0011 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Lighting and Luminaire Design | Load Bank - Platform and Foundations for Wartsila Load Bank - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0012 | A | 6105AK124-6251-ESPC-0012 | Q24050972-03-6251-E-SPC-0012 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Cable Termination Specifications | Load Bank - Small Power and Lighting for Wartsila Load Bank - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0013 | A | 6105AK124-6251-ESPC-0013 | Q24050972-03-6251-E-SPC-0013 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Cable and Conductor Specifications | Load Bank - Small Power and Lighting for Wartsila Load Bank - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0014 | A | 6105AK124-6251-ESPC-0014 | Q24050972-03-6251-E-SPC-0014 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Lighting and Luminaire Design | Load Bank - Small Power and Lighting for Wartsila Load Bank - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0015 | A | 6105AK124-6251-ESPC-0015 | Q24050972-03-6251-E-SPC-0015 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Cable Termination Specifications | Load Bank - Metering Instruments for Wartsila Load Bank - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0016 | A | 6105AK124-6251-ESPC-0016 | Q24050972-03-6251-E-SPC-0016 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Electrical Equipment Communication Specification | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Electrical Equipment Communication Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0017 | A | 6105AK124-6251-ESPC-0017 | Q24050972-03-6251-E-SPC-0017 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Electrical Equipment Communication Specification | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Electrical Equipment Communication Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0018 | A | 6105AK124-6251-ESPC-0018 | Q24050972-03-6251-E-SPC-0018 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Cable Termination Specifications | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0019 | A | 6105AK124-6251-ESPC-0019 | Q24050972-03-6251-E-SPC-0019 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Cable Termination Specifications | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0020 | A | 6105AK124-6251-ESPC-0020 | Q24050972-03-6251-E-SPC-0020 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Cable and Conductor Specifications | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0021 | A | 6105AK124-6251-ESPC-0021 | Q24050972-03-6251-E-SPC-0021 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Cable and Conductor Specifications | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0022 | A | 6105AK124-6251-ESPC-0022 | Q24050972-03-6251-E-SPC-0022 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Lighting and Luminaire Design | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0023 | A | 6105AK124-6251-ESPC-0023 | Q24050972-03-6251-E-SPC-0023 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Lighting and Luminaire Design | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0024 | A | 6105AK124-6251-ESPC-0024 | Q24050972-03-6251-E-SPC-0024 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Cable Termination Specifications | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0025 | A | 6105AK124-6251-ESPC-0025 | Q24050972-03-6251-E-SPC-0025 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Cable and Conductor Specifications | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0026 | A | 6105AK124-6251-ESPC-0026 | Q24050972-03-6251-E-SPC-0026 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Lighting and Luminaire Design | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0027 | A | 6105AK124-6251-ESPC-0027 | Q24050972-03-6251-E-SPC-0027 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Cable Termination Specifications | Load Bank - Metering Instruments for Emergency Gen Load Bank - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0028 | A | 6105AK124-6251-ESPC-0028 | Q24050972-03-6251-E-SPC-0028 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Electrical Equipment Communication Specification | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Electrical Equipment Communication Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0029 | A | 6105AK124-6251-ESPC-0029 | Q24050972-03-6251-E-SPC-0029 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Cable Termination Specifications | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0030 | A | 6105AK124-6251-ESPC-0030 | Q24050972-03-6251-E-SPC-0030 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Cable Termination Specifications | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0031 | A | 6105AK124-6251-ESPC-0031 | Q24050972-03-6251-E-SPC-0031 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Cable and Conductor Specifications | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0032 | A | 6105AK124-6251-ESPC-0032 | Q24050972-03-6251-E-SPC-0032 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Cable and Conductor Specifications | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | SPC | 0033 | A | 6105AK124-6251-ESPC-0033 | Q24050972-03-6251-E-SPC-0033 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Lighting and Luminaire Design | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0001 | A | 6105AK124-6251-ESTD-0001 | Q24050972-03-6251-E-STD-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Earth Map and Bonding Design | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0002 | A | 6105AK124-6251-ESTD-0002 | Q24050972-03-6251-E-STD-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Electrical Equipment Installation Requirements | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0003 | A | 6105AK124-6251-ESTD-0003 | Q24050972-03-6251-E-STD-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Thermal Management and Fire Prevention Design | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0004 | A | 6105AK124-6251-ESTD-0004 | Q24050972-03-6251-E-STD-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Electrical Equipment Installation Requirements | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0005 | A | 6105AK124-6251-ESTD-0005 | Q24050972-03-6251-E-STD-0005 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Electrical Design Standards | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Control Interface |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0006 | A | 6105AK124-6251-ESTD-0006 | Q24050972-03-6251-E-STD-0006 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Electrical Equipment Installation Requirements | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0007 | A | 6105AK124-6251-ESTD-0007 | Q24050972-03-6251-E-STD-0007 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Connection Cables | Electrical Design Standards | Load Bank - 36 MVA Power Station Mobile Load Bank Connection Cables - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Connection Cables |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0008 | A | 6105AK124-6251-ESTD-0008 | Q24050972-03-6251-E-STD-0008 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Thermal Management and Fire Prevention Design | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0009 | A | 6105AK124-6251-ESTD-0009 | Q24050972-03-6251-E-STD-0009 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Earth Map and Bonding Design | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0010 | A | 6105AK124-6251-ESTD-0010 | Q24050972-03-6251-E-STD-0010 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Earthing System | Electrical Equipment Installation Requirements | Load Bank - 36 MVA Power Station Mobile Load Bank Earthing System - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Earthing System |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0011 | A | 6105AK124-6251-ESTD-0011 | Q24050972-03-6251-E-STD-0011 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Earth Map and Bonding Design | Load Bank - Platform and Foundations for Wartsila Load Bank - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0012 | A | 6105AK124-6251-ESTD-0012 | Q24050972-03-6251-E-STD-0012 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Electrical Equipment Installation Requirements | Load Bank - Platform and Foundations for Wartsila Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0013 | A | 6105AK124-6251-ESTD-0013 | Q24050972-03-6251-E-STD-0013 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Thermal Management and Fire Prevention Design | Load Bank - Platform and Foundations for Wartsila Load Bank - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0014 | A | 6105AK124-6251-ESTD-0014 | Q24050972-03-6251-E-STD-0014 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Thermal Management and Fire Prevention Design | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0015 | A | 6105AK124-6251-ESTD-0015 | Q24050972-03-6251-E-STD-0015 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Electrical Equipment Installation Requirements | Load Bank - Small Power and Lighting for Wartsila Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0016 | A | 6105AK124-6251-ESTD-0016 | Q24050972-03-6251-E-STD-0016 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Earth Map and Bonding Design | Load Bank - Small Power and Lighting for Wartsila Load Bank - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0017 | A | 6105AK124-6251-ESTD-0017 | Q24050972-03-6251-E-STD-0017 |  | Load Bank | Small Power and Lighting for Wartsila Load Bank | Electrical Design Standards | Load Bank - Small Power and Lighting for Wartsila Load Bank - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0018 | A | 6105AK124-6251-ESTD-0018 | Q24050972-03-6251-E-STD-0018 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Electrical Equipment Installation Requirements | Load Bank - Metering Instruments for Wartsila Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0019 | A | 6105AK124-6251-ESTD-0019 | Q24050972-03-6251-E-STD-0019 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Electrical Equipment Installation Requirements | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0020 | A | 6105AK124-6251-ESTD-0020 | Q24050972-03-6251-E-STD-0020 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Electrical Design Standards | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0021 | A | 6105AK124-6251-ESTD-0021 | Q24050972-03-6251-E-STD-0021 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Electrical Equipment Installation Requirements | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0022 | A | 6105AK124-6251-ESTD-0022 | Q24050972-03-6251-E-STD-0022 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Electrical Design Standards | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0023 | A | 6105AK124-6251-ESTD-0023 | Q24050972-03-6251-E-STD-0023 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Electrical Equipment Installation Requirements | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0024 | A | 6105AK124-6251-ESTD-0024 | Q24050972-03-6251-E-STD-0024 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Electrical Equipment Installation Requirements | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0025 | A | 6105AK124-6251-ESTD-0025 | Q24050972-03-6251-E-STD-0025 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Thermal Management and Fire Prevention Design | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0026 | A | 6105AK124-6251-ESTD-0026 | Q24050972-03-6251-E-STD-0026 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Electrical Equipment Installation Requirements | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0027 | A | 6105AK124-6251-ESTD-0027 | Q24050972-03-6251-E-STD-0027 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Electrical Design Standards | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0028 | A | 6105AK124-6251-ESTD-0028 | Q24050972-03-6251-E-STD-0028 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Thermal Management and Fire Prevention Design | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0029 | A | 6105AK124-6251-ESTD-0029 | Q24050972-03-6251-E-STD-0029 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Electrical Design Standards | Load Bank - Lightning Protection System forWartsila Load Bank - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0030 | A | 6105AK124-6251-ESTD-0030 | Q24050972-03-6251-E-STD-0030 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Earth Map and Bonding Design | Load Bank - Lightning Protection System forWartsila Load Bank - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0031 | A | 6105AK124-6251-ESTD-0031 | Q24050972-03-6251-E-STD-0031 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Thermal Management and Fire Prevention Design | Load Bank - Lightning Protection System forWartsila Load Bank - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0032 | A | 6105AK124-6251-ESTD-0032 | Q24050972-03-6251-E-STD-0032 |  | Load Bank | Earthing System for Wartsila Load Bank | Earth Map and Bonding Design | Load Bank - Earthing System for Wartsila Load Bank - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0033 | A | 6105AK124-6251-ESTD-0033 | Q24050972-03-6251-E-STD-0033 |  | Load Bank | Earthing System for Wartsila Load Bank | Electrical Design Standards | Load Bank - Earthing System for Wartsila Load Bank - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0034 | A | 6105AK124-6251-ESTD-0034 | Q24050972-03-6251-E-STD-0034 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Earth Map and Bonding Design | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0035 | A | 6105AK124-6251-ESTD-0035 | Q24050972-03-6251-E-STD-0035 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Electrical Equipment Installation Requirements | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0036 | A | 6105AK124-6251-ESTD-0036 | Q24050972-03-6251-E-STD-0036 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Thermal Management and Fire Prevention Design | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0037 | A | 6105AK124-6251-ESTD-0037 | Q24050972-03-6251-E-STD-0037 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Thermal Management and Fire Prevention Design | Load Bank - Fire Protection System Emergency Gen Load Bank - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0038 | A | 6105AK124-6251-ESTD-0038 | Q24050972-03-6251-E-STD-0038 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Electrical Equipment Installation Requirements | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0039 | A | 6105AK124-6251-ESTD-0039 | Q24050972-03-6251-E-STD-0039 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Earth Map and Bonding Design | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0040 | A | 6105AK124-6251-ESTD-0040 | Q24050972-03-6251-E-STD-0040 |  | Load Bank | Small Power and Lighting forEmergency Gen Load Bank | Electrical Design Standards | Load Bank - Small Power and Lighting forEmergency Gen Load Bank - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0041 | A | 6105AK124-6251-ESTD-0041 | Q24050972-03-6251-E-STD-0041 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Electrical Equipment Installation Requirements | Load Bank - Metering Instruments for Emergency Gen Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0042 | A | 6105AK124-6251-ESTD-0042 | Q24050972-03-6251-E-STD-0042 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Electrical Equipment Installation Requirements | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0043 | A | 6105AK124-6251-ESTD-0043 | Q24050972-03-6251-E-STD-0043 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Electrical Design Standards | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0044 | A | 6105AK124-6251-ESTD-0044 | Q24050972-03-6251-E-STD-0044 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Electrical Equipment Installation Requirements | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0045 | A | 6105AK124-6251-ESTD-0045 | Q24050972-03-6251-E-STD-0045 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Electrical Equipment Installation Requirements | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0046 | A | 6105AK124-6251-ESTD-0046 | Q24050972-03-6251-E-STD-0046 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Thermal Management and Fire Prevention Design | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0047 | A | 6105AK124-6251-ESTD-0047 | Q24050972-03-6251-E-STD-0047 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Electrical Equipment Installation Requirements | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0048 | A | 6105AK124-6251-ESTD-0048 | Q24050972-03-6251-E-STD-0048 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Electrical Design Standards | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0049 | A | 6105AK124-6251-ESTD-0049 | Q24050972-03-6251-E-STD-0049 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Thermal Management and Fire Prevention Design | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0050 | A | 6105AK124-6251-ESTD-0050 | Q24050972-03-6251-E-STD-0050 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Electrical Design Standards | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0051 | A | 6105AK124-6251-ESTD-0051 | Q24050972-03-6251-E-STD-0051 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Earth Map and Bonding Design | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0052 | A | 6105AK124-6251-ESTD-0052 | Q24050972-03-6251-E-STD-0052 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Thermal Management and Fire Prevention Design | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0053 | A | 6105AK124-6251-ESTD-0053 | Q24050972-03-6251-E-STD-0053 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Earth Map and Bonding Design | Load Bank - Earthing System forEmergency Gen Load Bank - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | E | STD | 0054 | A | 6105AK124-6251-ESTD-0054 | Q24050972-03-6251-E-STD-0054 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Electrical Design Standards | Load Bank - Earthing System forEmergency Gen Load Bank - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DBD | 0001 | A | 6105AK124-6251-FDBD-0001 | Q24050972-03-6251-F-DBD-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Control System Configuration | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Control Interface |  |  |  | Pending
6105A | K124 | 6251 | F | DBD | 0002 | A | 6105AK124-6251-FDBD-0002 | Q24050972-03-6251-F-DBD-0002 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Control System Configuration | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DBD | 0003 | A | 6105AK124-6251-FDBD-0003 | Q24050972-03-6251-F-DBD-0003 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Control System Configuration | Load Bank - Fire Protection System Emergency Gen Load Bank - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0001 | A | 6105AK124-6251-FDIA-0001 | Q24050972-03-6251-F-DIA-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Control Network Architecture Design | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Control Interface |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0002 | A | 6105AK124-6251-FDIA-0002 | Q24050972-03-6251-F-DIA-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Control Network Communication Design | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Control Interface |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0003 | A | 6105AK124-6251-FDIA-0003 | Q24050972-03-6251-F-DIA-0003 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Interface Panel and I/O Schematics | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Control Interface |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0004 | A | 6105AK124-6251-FDIA-0004 | Q24050972-03-6251-F-DIA-0004 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Control Network Architecture Design | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0005 | A | 6105AK124-6251-FDIA-0005 | Q24050972-03-6251-F-DIA-0005 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Control Network Architecture Design | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0006 | A | 6105AK124-6251-FDIA-0006 | Q24050972-03-6251-F-DIA-0006 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Control Network Communication Design | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0007 | A | 6105AK124-6251-FDIA-0007 | Q24050972-03-6251-F-DIA-0007 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Emergency Shutdown System Design | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Emergency Shutdown System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0008 | A | 6105AK124-6251-FDIA-0008 | Q24050972-03-6251-F-DIA-0008 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Control Network Communication Design | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0009 | A | 6105AK124-6251-FDIA-0009 | Q24050972-03-6251-F-DIA-0009 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Control Network Communication Design | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0010 | A | 6105AK124-6251-FDIA-0010 | Q24050972-03-6251-F-DIA-0010 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Control Network Architecture Design | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0011 | A | 6105AK124-6251-FDIA-0011 | Q24050972-03-6251-F-DIA-0011 |  | Load Bank | Earthing System for Wartsila Load Bank | Interface Panel and I/O Schematics | Load Bank - Earthing System for Wartsila Load Bank - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0012 | A | 6105AK124-6251-FDIA-0012 | Q24050972-03-6251-F-DIA-0012 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Control Network Architecture Design | Load Bank - Fire Protection System Emergency Gen Load Bank - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0013 | A | 6105AK124-6251-FDIA-0013 | Q24050972-03-6251-F-DIA-0013 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Control Network Communication Design | Load Bank - Fire Protection System Emergency Gen Load Bank - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0014 | A | 6105AK124-6251-FDIA-0014 | Q24050972-03-6251-F-DIA-0014 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Emergency Shutdown System Design | Load Bank - Fire Protection System Emergency Gen Load Bank - Emergency Shutdown System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0015 | A | 6105AK124-6251-FDIA-0015 | Q24050972-03-6251-F-DIA-0015 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Control Network Communication Design | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0016 | A | 6105AK124-6251-FDIA-0016 | Q24050972-03-6251-F-DIA-0016 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Control Network Architecture Design | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | DIA | 0017 | A | 6105AK124-6251-FDIA-0017 | Q24050972-03-6251-F-DIA-0017 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Interface Panel and I/O Schematics | Load Bank - Earthing System forEmergency Gen Load Bank - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | LAY | 0001 | A | 6105AK124-6251-FLAY-0001 | Q24050972-03-6251-F-LAY-0001 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | HMI and Graphics design | Load Bank - 11kV Protection Relays for Wartsila Load Bank - HMI and Graphics design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | LAY | 0002 | A | 6105AK124-6251-FLAY-0002 | Q24050972-03-6251-F-LAY-0002 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | HMI and Graphics design | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - HMI and Graphics design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | LAY | 0003 | A | 6105AK124-6251-FLAY-0003 | Q24050972-03-6251-F-LAY-0003 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | HMI and Graphics design | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - HMI and Graphics design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | NAR | 0001 | A | 6105AK124-6251-FNAR-0001 | Q24050972-03-6251-F-NAR-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Control System Control Narrative & Interlock Design | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Control Interface |  |  |  | Pending
6105A | K124 | 6251 | F | NAR | 0002 | A | 6105AK124-6251-FNAR-0002 | Q24050972-03-6251-F-NAR-0002 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Control System Control Narrative & Interlock Design | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | NAR | 0003 | A | 6105AK124-6251-FNAR-0003 | Q24050972-03-6251-F-NAR-0003 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Emergency Shutdown System Control Narrative | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | NAR | 0004 | A | 6105AK124-6251-FNAR-0004 | Q24050972-03-6251-F-NAR-0004 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Control System Control Narrative & Interlock Design | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | NAR | 0005 | A | 6105AK124-6251-FNAR-0005 | Q24050972-03-6251-F-NAR-0005 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Control System Control Narrative & Interlock Design | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | NAR | 0006 | A | 6105AK124-6251-FNAR-0006 | Q24050972-03-6251-F-NAR-0006 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Control System Control Narrative & Interlock Design | Load Bank - Fire Protection System Emergency Gen Load Bank - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | NAR | 0007 | A | 6105AK124-6251-FNAR-0007 | Q24050972-03-6251-F-NAR-0007 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Emergency Shutdown System Control Narrative | Load Bank - Fire Protection System Emergency Gen Load Bank - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | NAR | 0008 | A | 6105AK124-6251-FNAR-0008 | Q24050972-03-6251-F-NAR-0008 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Control System Control Narrative & Interlock Design | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | PHL | 0001 | A | 6105AK124-6251-FPHL-0001 | Q24050972-03-6251-F-PHL-0001 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Control System Control Philosophy | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | PHL | 0002 | A | 6105AK124-6251-FPHL-0002 | Q24050972-03-6251-F-PHL-0002 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Control System Control Philosophy | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | PHL | 0003 | A | 6105AK124-6251-FPHL-0003 | Q24050972-03-6251-F-PHL-0003 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Control System Control Philosophy | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | PRC | 0001 | A | 6105AK124-6251-FPRC-0001 | Q24050972-03-6251-F-PRC-0001 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Alarm Classification Methodology | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Alarm Classification Methodology |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | PRC | 0002 | A | 6105AK124-6251-FPRC-0002 | Q24050972-03-6251-F-PRC-0002 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Alarm Classification Methodology | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Alarm Classification Methodology |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | PRC | 0003 | A | 6105AK124-6251-FPRC-0003 | Q24050972-03-6251-F-PRC-0003 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Alarm Classification Methodology | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Alarm Classification Methodology |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | SPC | 0001 | A | 6105AK124-6251-FSPC-0001 | Q24050972-03-6251-F-SPC-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Control Interface | Control System Design Requirements | Load Bank - 36 MVA Power Station Mobile Load Bank Control Interface - Control System Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Control Interface |  |  |  | Pending
6105A | K124 | 6251 | F | SPC | 0002 | A | 6105AK124-6251-FSPC-0002 | Q24050972-03-6251-F-SPC-0002 |  | Load Bank | 11kV Protection Relays for Wartsila Load Bank | Historian and Server Design | Load Bank - 11kV Protection Relays for Wartsila Load Bank - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | SPC | 0003 | A | 6105AK124-6251-FSPC-0003 | Q24050972-03-6251-F-SPC-0003 |  | Load Bank | 11kV Protection Relays for Emerg. Generation Load Bank | Historian and Server Design | Load Bank - 11kV Protection Relays for Emerg. Generation Load Bank - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emerg. Generation Load Bank |  |  |  | Pending
6105A | K124 | 6251 | F | SPC | 0004 | A | 6105AK124-6251-FSPC-0004 | Q24050972-03-6251-F-SPC-0004 |  | Load Bank | 11kV Protection Relays for Emergency Gen Load Bank | Historian and Server Design | Load Bank - 11kV Protection Relays for Emergency Gen Load Bank - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 11kV Protection Relays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | CAL | 0001 | A | 6105AK124-6251-ICAL-0001 | Q24050972-03-6251-I-CAL-0001 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Instrument Sizing and Specification Sheets | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | CAL | 0002 | A | 6105AK124-6251-ICAL-0002 | Q24050972-03-6251-I-CAL-0002 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Instrument Sizing and Specification Sheets | Load Bank - Metering Instruments for Wartsila Load Bank - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | CAL | 0003 | A | 6105AK124-6251-ICAL-0003 | Q24050972-03-6251-I-CAL-0003 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Instrument Sizing and Specification Sheets | Load Bank - Fire Protection System Emergency Gen Load Bank - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | CAL | 0004 | A | 6105AK124-6251-ICAL-0004 | Q24050972-03-6251-I-CAL-0004 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Instrument Sizing and Specification Sheets | Load Bank - Metering Instruments for Emergency Gen Load Bank - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0004 | A | 6105AK124-6200-CLAY-0004 | Q24050972-03-6200-C-LAY-0004 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Roads and Servitudes Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Roads and Servitudes Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Layout |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0005 | A | 6105AK124-6200-CLAY-0005 | Q24050972-03-6200-C-LAY-0005 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Storm Water Dainage Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Storm Water Dainage Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Layout |  |  |  | Pending
6105A | K124 | 6200 | C | DTL | 0001 | A | 6105AK124-6200-CDTL-0001 | Q24050972-03-6200-C-DTL-0001 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Storm Water Drainage Details | On-Site Power Supply and Transmission - Main Consumer Substation - Storm Water Drainage Details |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Storm Water Dainage Details |  |  |  | Pending
6105A | K124 | 6251 | I | DIA | 0001 | A | 6105AK124-6251-IDIA-0001 | Q24050972-03-6251-I-DIA-0001 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Smoke and Fire Detection System Design | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | DIA | 0002 | A | 6105AK124-6251-IDIA-0002 | Q24050972-03-6251-I-DIA-0002 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | Closed Circuit Television (CCTV) Design | Load Bank - Perimeter Fencing for for Wartsila Load Bank - Closed Circuit Television (CCTV) Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | DIA | 0003 | A | 6105AK124-6251-IDIA-0003 | Q24050972-03-6251-I-DIA-0003 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Smoke and Fire Detection System Design | Load Bank - Fire Protection System Emergency Gen Load Bank - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | DIA | 0004 | A | 6105AK124-6251-IDIA-0004 | Q24050972-03-6251-I-DIA-0004 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Closed Circuit Television (CCTV) Design | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Closed Circuit Television (CCTV) Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | HAC | 0001 | A | 6105AK124-6251-IHAC-0001 | Q24050972-03-6251-I-HAC-0001 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Process Safety Design Review (HAZOP & LOPA) | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | HAC | 0002 | A | 6105AK124-6251-IHAC-0002 | Q24050972-03-6251-I-HAC-0002 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Process Safety Design Review (HAZOP & LOPA) | Load Bank - Fire Protection System Emergency Gen Load Bank - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | ITD | 0001 | A | 6105AK124-6251-IITD-0001 | Q24050972-03-6251-I-ITD-0001 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Instrument Wiring Loop Diagrams and Cable Schedule | Load Bank - Metering Instruments for Wartsila Load Bank - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | ITD | 0002 | A | 6105AK124-6251-IITD-0002 | Q24050972-03-6251-I-ITD-0002 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Instrument Wiring Loop Diagrams and Cable Schedule | Load Bank - Metering Instruments for Emergency Gen Load Bank - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | LST | 0001 | A | 6105AK124-6251-ILST-0001 | Q24050972-03-6251-I-LST-0001 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Equipment Alarm and Trip Level Register | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | LST | 0002 | A | 6105AK124-6251-ILST-0002 | Q24050972-03-6251-I-LST-0002 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Instrumentation Equipment Tag Register | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | LST | 0003 | A | 6105AK124-6251-ILST-0003 | Q24050972-03-6251-I-LST-0003 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Instrumentation Equipment Tag Register | Load Bank - Metering Instruments for Wartsila Load Bank - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | LST | 0004 | A | 6105AK124-6251-ILST-0004 | Q24050972-03-6251-I-LST-0004 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Equipment Alarm and Trip Level Register | Load Bank - Metering Instruments for Wartsila Load Bank - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | LST | 0005 | A | 6105AK124-6251-ILST-0005 | Q24050972-03-6251-I-LST-0005 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Equipment Alarm and Trip Level Register | Load Bank - Fire Protection System Emergency Gen Load Bank - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | LST | 0006 | A | 6105AK124-6251-ILST-0006 | Q24050972-03-6251-I-LST-0006 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Instrumentation Equipment Tag Register | Load Bank - Fire Protection System Emergency Gen Load Bank - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | LST | 0007 | A | 6105AK124-6251-ILST-0007 | Q24050972-03-6251-I-LST-0007 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Instrumentation Equipment Tag Register | Load Bank - Metering Instruments for Emergency Gen Load Bank - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | LST | 0008 | A | 6105AK124-6251-ILST-0008 | Q24050972-03-6251-I-LST-0008 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Equipment Alarm and Trip Level Register | Load Bank - Metering Instruments for Emergency Gen Load Bank - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | QRA | 0001 | A | 6105AK124-6251-IQRA-0001 | Q24050972-03-6251-I-QRA-0001 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Risk Assessment: Fire and Explosions | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | QRA | 0002 | A | 6105AK124-6251-IQRA-0002 | Q24050972-03-6251-I-QRA-0002 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Risk Assessment: Fire and Explosions | Load Bank - Fire Protection System Emergency Gen Load Bank - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0026 | A | 6105AK124-6200-CSEC-0026 | Q24050972-03-6200-C-SEC-0026 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Roads and Servitudes Sections | On-Site Power Supply and Transmission - Main Consumer Substation - Roads and Servitudes Sections |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Sub Station | Roads and Servitudes |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0027 | A | 6105AK124-6200-CSEC-0027 | Q24050972-03-6200-C-SEC-0027 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Storm Water Dainage Sections | On-Site Power Supply and Transmission - Main Consumer Substation - Storm Water Dainage Sections |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Sub Station | Storm Water Dainage |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0028 | A | 6105AK124-6200-CSEC-0028 | Q24050972-03-6200-C-SEC-0028 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Underground Utilities and Piping Setion | On-Site Power Supply and Transmission - Main Consumer Substation - Underground Utilities and Piping Setion |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Sub Station | Underground Utilities and Piping |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0029 | A | 6105AK124-6200-CSEC-0029 | Q24050972-03-6200-C-SEC-0029 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Cable Trench Section | On-Site Power Supply and Transmission - Main Consumer Substation - Cable Trench Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Sub Station | Cable Trench |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0030 | A | 6105AK124-6200-CSEC-0030 | Q24050972-03-6200-C-SEC-0030 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Oil Treatment Facility Section | On-Site Power Supply and Transmission - Main Consumer Substation - Oil Treatment Facility Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Sub Station | Oil Treatment Facility |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0031 | A | 6105AK124-6200-CSEC-0031 | Q24050972-03-6200-C-SEC-0031 |  | On-Site Power Supply and Transmission | Main Consumer Substation | 33kV E-house Section | On-Site Power Supply and Transmission - Main Consumer Substation - 33kV E-house Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Sub Station | 33kV E-house |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0032 | A | 6105AK124-6200-CSEC-0032 | Q24050972-03-6200-C-SEC-0032 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Auxillary Power Section | On-Site Power Supply and Transmission - Main Consumer Substation - Auxillary Power Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Sub Station | Auxillary Power |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0033 | A | 6105AK124-6200-CSEC-0033 | Q24050972-03-6200-C-SEC-0033 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Control Room, Offices, Prayer Room and Ablutions Section | On-Site Power Supply and Transmission - Main Consumer Substation - Control Room, Offices, Prayer Room and Ablutions Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Sub Station | Control Room, Offices, Prayer Room and Ablutions |  |  |  | Pending
6105A | K124 | 6200 | C | SEC | 0034 | A | 6105AK124-6200-CSEC-0034 | Q24050972-03-6200-C-SEC-0034 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Oil Storage Room Section | On-Site Power Supply and Transmission - Main Consumer Substation - Oil Storage Room Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Sub Station | Oil Storage Room |  |  |  | Pending
6105A | K124 | 6200 | C | DTL | 0002 | A | 6105AK124-6200-CDTL-0002 | Q24050972-03-6200-C-DTL-0002 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Roads and Servitudes Detail | On-Site Power Supply and Transmission - Main Consumer Substation - Roads and Servitudes Detail |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Roads and Servitudes Detail |  |  |  | Pending
6105A | K124 | 6200 | C | DTL | 0003 | A | 6105AK124-6200-CDTL-0003 | Q24050972-03-6200-C-DTL-0003 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Underground Utilities and Piping Detail | On-Site Power Supply and Transmission - Main Consumer Substation - Underground Utilities and Piping Detail |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Underground Utilities and Piping Detail |  |  |  | Pending
6105A | K124 | 6200 | C | DTL | 0004 | A | 6105AK124-6200-CDTL-0004 | Q24050972-03-6200-C-DTL-0004 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Cable Gantry Details | On-Site Power Supply and Transmission - Main Consumer Substation - Cable Gantry Details |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Cable Gantry Details |  |  |  | Pending
6105A | K124 | 6200 | C | DTL | 0005 | A | 6105AK124-6200-CDTL-0005 | Q24050972-03-6200-C-DTL-0005 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Cable Trench Rebar Bending Schedule | On-Site Power Supply and Transmission - Main Consumer Substation - Cable Trench Rebar Bending Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Cable Trench Details |  |  |  | Pending
6105A | K124 | 6200 | C | DTL | 0006 | A | 6105AK124-6200-CDTL-0006 | Q24050972-03-6200-C-DTL-0006 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Fencing Details | On-Site Power Supply and Transmission - Main Consumer Substation - Fencing Details |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Fencing Details |  |  |  | Pending
6105A | K124 | 6200 | C | DTL | 0007 | A | 6105AK124-6200-CDTL-0007 | Q24050972-03-6200-C-DTL-0007 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Oil Treatment Facility Details | On-Site Power Supply and Transmission - Main Consumer Substation - Oil Treatment Facility Details |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Oil Treatment Facility |  |  |  | Pending
6105A | K124 | 6200 | C | DTL | 0008 | A | 6105AK124-6200-CDTL-0008 | Q24050972-03-6200-C-DTL-0008 |  | On-Site Power Supply and Transmission | Main Consumer Substation | 33kV E-house Details | On-Site Power Supply and Transmission - Main Consumer Substation - 33kV E-house Details |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | 33kV E-house |  |  |  | Pending
6105A | K124 | 6200 | C | DTL | 0009 | A | 6105AK124-6200-CDTL-0009 | Q24050972-03-6200-C-DTL-0009 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Auxillary Power Details | On-Site Power Supply and Transmission - Main Consumer Substation - Auxillary Power Details |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Auxillary Power |  |  |  | Pending
6105A | K124 | 6200 | C | DTL | 0010 | A | 6105AK124-6200-CDTL-0010 | Q24050972-03-6200-C-DTL-0010 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Control Room, Offices, Prayer Room and Ablutions Detail | On-Site Power Supply and Transmission - Main Consumer Substation - Control Room, Offices, Prayer Room and Ablutions Detail |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Control Room, Offices, Prayer Room and Ablution |  |  |  | Pending
6105A | K124 | 6200 | C | DTL | 0011 | A | 6105AK124-6200-CDTL-0011 | Q24050972-03-6200-C-DTL-0011 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Oil Storage Room Detail | On-Site Power Supply and Transmission - Main Consumer Substation - Oil Storage Room Detail |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Oil Storage Room |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0056 | A | 6105AK124-6200-CGAD-0056 | Q24050972-03-6200-C-GAD-0056 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Oil Storage Room General Arrangement | On-Site Power Supply and Transmission - Main Consumer Substation - Oil Storage Room General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Sub Station | Oil Storage Room |  |  |  | Pending
6105A | K124 | 6200 | C | ISO | 0001 | A | 6105AK124-6200-CISO-0001 | Q24050972-03-6200-C-ISO-0001 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Cable Gantry Isometric Arrangement | On-Site Power Supply and Transmission - Main Consumer Substation - Cable Gantry Isometric Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-06-15 | Main Consumer Sub Station | Cable Gantry |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0006 | A | 6105AK124-6200-CLAY-0006 | Q24050972-03-6200-C-LAY-0006 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Underground Utilities and Piping Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Underground Utilities and Piping Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Underground Utilities and Piping Layout |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0007 | A | 6105AK124-6200-CLAY-0007 | Q24050972-03-6200-C-LAY-0007 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Cable Trench Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Cable Trench Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Cable Trench Layout |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0008 | A | 6105AK124-6200-CLAY-0008 | Q24050972-03-6200-C-LAY-0008 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Fencing Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Fencing Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Fencing Layout |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0009 | A | 6105AK124-6200-CLAY-0009 | Q24050972-03-6200-C-LAY-0009 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Oil Treatment Facility Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Oil Treatment Facility Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Oil Treatment Facility Layout |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0010 | A | 6105AK124-6200-CLAY-0010 | Q24050972-03-6200-C-LAY-0010 |  | On-Site Power Supply and Transmission | Main Consumer Substation | 33kV E-house Layout | On-Site Power Supply and Transmission - Main Consumer Substation - 33kV E-house Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | 33kV E-house Layout |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0011 | A | 6105AK124-6200-CLAY-0011 | Q24050972-03-6200-C-LAY-0011 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Auxillary Power Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Auxillary Power Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Auxillary Power Layout |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0012 | A | 6105AK124-6200-CLAY-0012 | Q24050972-03-6200-C-LAY-0012 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Early Mining Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Early Mining Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Early Mining Layout |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0013 | A | 6105AK124-6200-CLAY-0013 | Q24050972-03-6200-C-LAY-0013 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Laydown Area Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Laydown Area Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Laydown Area Layout |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0014 | A | 6105AK124-6200-CLAY-0014 | Q24050972-03-6200-C-LAY-0014 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Contractor Interface Responsibility Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Contractor Interface Responsibility Layout | 2026-04-16 |  | IFR - Issued for Review | Reviewed With Comments | 33.33% | YB | [7 empty] | Pending
6105A | K124 | 6263 | C | DTL | 0001 | A | 6105AK124-6263-CDTL-0001 | Q24050972-03-6263-C-DTL-0001 |  | 36 MVA Power Station 1 | Main Consumer Substation | Bulk Diesel Generator Rebar Bending Schedule | 36 MVA Power Station 1 - Main Consumer Substation - Bulk Diesel Generator Rebar Bending Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Bulk Diesel Generator |  |  |  | Pending
6105A | K124 | 6263 | C | SEC | 0001 | A | 6105AK124-6263-CSEC-0001 | Q24050972-03-6263-C-SEC-0001 |  | 36 MVA Power Station 1 | Main Consumer Substation | Bulk Diesel Generator Section | 36 MVA Power Station 1 - Main Consumer Substation - Bulk Diesel Generator Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Bulk Diesel Generator |  |  |  | Pending
6105A | K124 | 6263 | C | LAY | 0001 | A | 6105AK124-6263-CLAY-0001 | Q24050972-03-6263-C-LAY-0001 |  | 36 MVA Power Station 1 | Main Consumer Substation | Bulk Diesel Generator Layout | 36 MVA Power Station 1 - Main Consumer Substation - Bulk Diesel Generator Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Bulk Diesel Generator |  |  |  | Pending
6105A | K124 | 6264 | C | DTL | 0001 | A | 6105AK124-6264-CDTL-0001 | Q24050972-03-6264-C-DTL-0001 |  | Bulk Diesel Storage 1 | Main Consumer Substation | Bulk Diesel Storage Rebar bending schedule | Bulk Diesel Storage 1 - Main Consumer Substation - Bulk Diesel Storage Rebar bending schedule |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Bulk Diesel Storage |  |  |  | Pending
6105A | K124 | 6264 | C | DTL | 0002 | A | 6105AK124-6264-CDTL-0002 | Q24050972-03-6264-C-DTL-0002 |  | Bulk Diesel Storage 1 | Main Consumer Substation | Diesel Spillage Facility Details | Bulk Diesel Storage 1 - Main Consumer Substation - Diesel Spillage Facility Details |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Diesel Spillage Facility |  |  |  | Pending
6105A | K124 | 6264 | C | LAY | 0001 | A | 6105AK124-6264-CLAY-0001 | Q24050972-03-6264-C-LAY-0001 |  | Bulk Diesel Storage 1 | Main Consumer Substation | Bulk Diesel Storage Layout | Bulk Diesel Storage 1 - Main Consumer Substation - Bulk Diesel Storage Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Bulk Diesel Storage |  |  |  | Pending
6105A | K124 | 6264 | C | LAY | 0002 | A | 6105AK124-6264-CLAY-0002 | Q24050972-03-6264-C-LAY-0002 |  | Bulk Diesel Storage 1 | Main Consumer Substation | Diesel Spillage Facility Layout | Bulk Diesel Storage 1 - Main Consumer Substation - Diesel Spillage Facility Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Diesel Spillage Facility |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0001 | A | 6105AK124-6264-CSEC-0001 | Q24050972-03-6264-C-SEC-0001 |  | Bulk Diesel Storage 1 | Main Consumer Substation | Bulk Diesel Storage Section | Bulk Diesel Storage 1 - Main Consumer Substation - Bulk Diesel Storage Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Bulk Diesel Storage |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0002 | A | 6105AK124-6264-CSEC-0002 | Q24050972-04-6264-C-SEC-0002 |  | Bulk Diesel Storage 1 | Main Consumer Substation | Diesel Spillage Facility Section | Bulk Diesel Storage 1 - Main Consumer Substation - Diesel Spillage Facility Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Diesel Spillage Facility |  |  |  | Pending
6105A | K124 | 6251 | C | LAY | 0001 | A | 6105AK124-6251-CLAY-0001 | Q24050972-03-6251-C-LAY-0001 |  | Load Bank | Main Consumer Substation | Load Bank Layout | Load Bank - Main Consumer Substation - Load Bank Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0023 | A | 6105AK124-6251-CSEC-0023 | Q24050972-03-6251-C-SEC-0023 |  | Load Bank | Main Consumer Substation | Load Bank Sections | Load Bank - Main Consumer Substation - Load Bank Sections |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | DTL | 0001 | A | 6105AK124-6251-CDTL-0001 | Q24050972-03-6251-C-DTL-0001 |  | Load Bank | Main Consumer Substation | Transformer Rebar Bending Schedule | Load Bank - Main Consumer Substation - Transformer Rebar Bending Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Load Bank |  |  |  | Pending
6105A | K124 | 6253 | C | DTL | 0001 | A | 6105AK124-6253-CDTL-0001 | Q24050972-03-6253-C-DTL-0001 |  | Synchronous Condenser 1 | Main Consumer Substation | Transformer Rebar Bending Schedule | Synchronous Condenser 1 - Main Consumer Substation - Transformer Rebar Bending Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Transformer |  |  |  | Pending
6105A | K124 | 6253 | C | DTL | 0002 | A | 6105AK124-6253-CDTL-0002 | Q24050972-03-6253-C-DTL-0002 |  | Synchronous Condenser 1 | Main Consumer Substation | Synchronous Condenser Rebar Bending Schedule | Synchronous Condenser 1 - Main Consumer Substation - Synchronous Condenser Rebar Bending Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Synchronous Condenser |  |  |  | Pending
6105A | K124 | 6253 | C | LAY | 0001 | A | 6105AK124-6253-CLAY-0001 | Q24050972-03-6253-C-LAY-0001 |  | Synchronous Condenser 1 | Main Consumer Substation | Transformer Layout | Synchronous Condenser 1 - Main Consumer Substation - Transformer Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Transformer |  |  |  | Pending
6105A | K124 | 6253 | C | LAY | 0002 | A | 6105AK124-6253-CLAY-0002 | Q24050972-03-6253-C-LAY-0002 |  | Synchronous Condenser 1 | Main Consumer Substation | Synchronous Condenser Layout | Synchronous Condenser 1 - Main Consumer Substation - Synchronous Condenser Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Synchronous Condenser |  |  |  | Pending
6105A | K124 | 6253 | C | SEC | 0001 | A | 6105AK124-6253-CSEC-0001 | Q24050972-03-6253-C-SEC-0001 |  | Synchronous Condenser 1 | Main Consumer Substation | Transformer Section | Synchronous Condenser 1 - Main Consumer Substation - Transformer Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07--31 | Main Consumer Substation | Transformer |  |  |  | Pending
6105A | K124 | 6253 | C | SEC | 0002 | A | 6105AK124-6253-CSEC-0002 | Q24050972-03-6253-C-SEC-0002 |  | Synchronous Condenser 1 | Main Consumer Substation | Synchronous Condenser Section | Synchronous Condenser 1 - Main Consumer Substation - Synchronous Condenser Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Synchronous Condenser |  |  |  | Pending
6105A | K124 | 6256 | C | DTL | 0001 | A | 6105AK124-6256-CDTL-0001 | Q24050972-03-6256-C-DTL-0001 |  | Synchronous Condenser 2 | Main Consumer Substation | Transformer Rebar Bending Schedule | Synchronous Condenser 2 - Main Consumer Substation - Transformer Rebar Bending Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Transformer |  |  |  | Pending
6105A | K124 | 6256 | C | DTL | 0002 | A | 6105AK124-6256-CDTL-0002 | Q24050972-03-6256-C-DTL-0002 |  | Synchronous Condenser 2 | Main Consumer Substation | Synchronous Condenser Rebar Bending Schedule | Synchronous Condenser 2 - Main Consumer Substation - Synchronous Condenser Rebar Bending Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Synchronous Condenser |  |  |  | Pending
6105A | K124 | 6256 | C | LAY | 0001 | A | 6105AK124-6256-CLAY-0001 | Q24050972-03-6256-C-LAY-0001 |  | Synchronous Condenser 2 | Main Consumer Substation | Transformer Layout | Synchronous Condenser 2 - Main Consumer Substation - Transformer Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Transformer |  |  |  | Pending
6105A | K124 | 6256 | C | LAY | 0002 | A | 6105AK124-6256-CLAY-0002 | Q24050972-03-6256-C-LAY-0002 |  | Synchronous Condenser 2 | Main Consumer Substation | Synchronous Condenser Layout | Synchronous Condenser 2 - Main Consumer Substation - Synchronous Condenser Layout |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Synchronous Condenser |  |  |  | Pending
6105A | K124 | 6256 | C | SEC | 0001 | A | 6105AK124-6256-CSEC-0001 | Q24050972-03-6256-C-SEC-0001 |  | Synchronous Condenser 2 | Main Consumer Substation | Transformer Section | Synchronous Condenser 2 - Main Consumer Substation - Transformer Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Transformer |  |  |  | Pending
6105A | K124 | 6256 | C | SEC | 0002 | A | 6105AK124-6256-CSEC-0002 | Q24050972-03-6256-C-SEC-0002 |  | Synchronous Condenser 2 | Main Consumer Substation | Synchronous Condenser Section | Synchronous Condenser 2 - Main Consumer Substation - Synchronous Condenser Section |  |  | RES - Reserved Placeholder | Pending | 0% | YB |  | 2026-07-31 | Main Consumer Substation | Synchronous Condenser |  |  |  | Pending
6105A | K124 | 0100 | B | CON | 0009 | A | 6105AK124-0100-BCON-0009 | Q24050972-03-0100-B-CON-0009 |  | Project Site Wide | Notice Delegation of Responsibilities to PMC (Fluor) | General | Project Site Wide - Notice Delegation of Responsibilities to PMC (Fluor) - General | 2026-05-13 |  | IFR - Issued for Review | Pending | 33.33% | JV |  |  | Notice Delegation of Responsibilities | General |  |  |  | Pending
6105A | K124 | 6200 | E | SEC | 0007 | A | 6105AK124-6200-ESEC-0007 | Q24050972-04-6200-E-SEC-0007 |  | On-Site Power Supply and Transmission | Main Consumer Intake Power Complex | Cable Trench Cable Detail - 33kV OHL Cables | On-Site Power Supply and Transmission - Main Consumer Intake Power Complex - Cable Trench Cable Detail - 33kV OHL Cables |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-30 | Main Consumer Intake | Cable Trench |  |  |  | Pending
6105A | K124 | 6241 | G | BOM | 0001 | A | 6105AK124-6241-GBOM-0001 | Q24050972-03-6241-G-BOM-0001 |  | 33/220 kV Solar PV Substation | Solar PV Substation Bill of Quantities | Bill of Material | 33/220 kV Solar PV Substation - Solar PV Substation Bill of Quantities - Bill of Material |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation Bill of Quantities | Bill of Material |  |  |  | Pending
6105A | K124 | 6241 | G | BOM | 0002 | A | 6105AK124-6241-GBOM-0002 | Q24050972-03-6241-G-BOM-0002 |  | 33/220 kV Solar PV Substation | Main Intake Substation Construction Bill of Quantities | Bill of Material | 33/220 kV Solar PV Substation - Main Intake Substation Construction Bill of Quantities - Bill of Material |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Intake Substation Construction Bill of Quantities | Bill of Material |  |  |  | Pending
6105A | K124 | 6242 | G | SCH | 0001 | A | 6105AK124-6242-GSCH-0001 | Q24050972-03-6242-G-SCH-0001 |  | 33/220 kV Power Station Substation | Solar PV Substation Cable Schedule | Schedule | 33/220 kV Power Station Substation - Solar PV Substation Cable Schedule - Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation Cable Schedule | Schedule |  |  |  | Pending
6105A | K124 | 6242 | G | SCH | 0002 | A | 6105AK124-6242-GSCH-0002 | Q24050972-03-6242-G-SCH-0002 |  | 33/220 kV Power Station Substation | Main Intake Substation Construction Cable Schedule | Schedule | 33/220 kV Power Station Substation - Main Intake Substation Construction Cable Schedule - Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Intake Substation Construction Cable Schedule | Schedule |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0001 | A | 6105AK124-6286-EDIA-0001 | Q24050972-04-6286-E-DIA-0001 |  | Primary Crushing | Mining Substation | LV Cable Block Diagram | Primary Crushing - Mining Substation - LV Cable Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | TM |  | 2026-05-29 | Mining Substation | Block Diagram |  |  |  | Pending
6105A | K124 | 0100 | Q | DBK | 0001 | A | 6105AK124-0100-QDBK-0001 | Q24050972-04-0100-Q-DBK-0001 |  | Project Site Wide | Fiber Optic and Manhole Installation | Data Book | Project Site Wide - Fiber Optic and Manhole Installation - Data Book |  |  | RES - Reserved Placeholder | Pending | 0% | OC |  | 2026-05-15 | Fiber Optic and Manhole Installation | Data Book |  |  |  | Pending
6105A | K124 | 0100 | Q | DBK | 0002 | 0 | 6105AK124-0100-QDBK-0002 | Q24050972-04-0100-Q-DBK-0002 |  | Project Site Wide | Cable Racking and Earthing | Data Book | Project Site Wide - Cable Racking and Earthing - Data Book | 2026-04-20 | 2026-05-25 | IFU - Issued for Use | Pending | 66.67% | OC |  |  | Cable Racking and Earthing | Data Book |  |  |  | Pending
6105A | K124 | 0100 | Q | DBK | 0003 | A | 6105AK124-0100-QDBK-0003 | Q24050972-04-0100-Q-DBK-0003 |  | Project Site Wide | Cathodic Protection | Data Book | Project Site Wide - Cathodic Protection - Data Book | 2026-04-20 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | OC |  |  | Cathodic Protection | Data Book |  |  |  | Pending
6105A | K124 | 6281 | Q | DBK | 0001 | A | 6105AK124-6281-QDBK-0001 | Q24050972-04-6281-Q-DBK-0001 |  | Booster Pump Station | Motors, Generators, NERs & VSDs | Data Book | Booster Pump Station - Motors, Generators, NERs & VSDs - Data Book |  |  | RES - Reserved Placeholder | Pending | 0% | OC |  | 2026-05-15 | Motors, Generators, NERs & VSDs | Data Book |  |  |  | Pending
6105A | K124 | 0100 | Q | TMP | 0008 | A | 6105AK124-0100-QTMP-0008 | Q24050972-04-0100-Q-TMP-0008 |  | Project Site Wide | Equipment List | Record | Project Site Wide - Equipment List - Record |  |  | RES - Reserved Placeholder | Pending | 0% | OC |  | 2026-05-15 | Equipment List | Record |  |  |  | Pending
6105A | K124 | 0100 | G | RPT | 0001 | A | 6105AK124-0100-GRPT-0001 | Q24050972-04-0100-G-RPT-0001 |  | Project Site Wide | Cost Flow - March 2026 | General | Project Site Wide - Cost Flow - March 2026 - General |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-06-15 | Cost Flow | General |  |  |  | Pending
6105A | K124 | 6242 | G | BOM | 0001 | A | 6105AK124-6242-GBOM-0001 | Q24050972-04-6242-G-BOM-0001 |  | 33/220 kV Power Station Substation | Wartsila Load Bank Substation | Bill of Material : Supply, install and Commissiong | 33/220 kV Power Station Substation - Wartsila Load Bank Substation - Bill of Material : Supply, install and Commissiong |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-17 | Wartsila Load Bank | Bill of Material |  |  |  | Pending
6105A | K124 | 6241 | G | BOM | 0003 | A | 6105AK124-6241-GBOM-0003 | Q24050972-04-6241-G-BOM-0003 |  | 33/220 kV Solar PV Substation | 33kV PV Solar Substation | Bill of Material : Supply, install and Commissiong | 33/220 kV Solar PV Substation - 33kV PV Solar Substation - Bill of Material : Supply, install and Commissiong |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-18 | 33kV PV Solar Substation | Bill of Material |  |  |  | Pending
6105A | K124 | 6241 | E | DIA | 0004 | A | 6105AK124-6241-EDIA-0004 | Q24050972-04-6241-E-DIA-0004 |  | 33/220 kV Solar PV Substation | Solar PV Substation | LV Cable Block Diagram | 33/220 kV Solar PV Substation - Solar PV Substation - LV Cable Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | TM |  | 2026-05-29 | Main Intake Substation | Block Diagram |  |  |  | Pending
6105A | K124 | 6242 | E | DIA | 0004 | A | 6105AK124-6242-EDIA-0004 | Q24050972-04-6242-E-DIA-0004 |  | 33/220 kV Power Station Substation | Main Intake Substation | LV Cable Block Diagram | 33/220 kV Power Station Substation - Main Intake Substation - LV Cable Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | TM |  | 2026-06-29 | Main Intake Substation | Block Diagram |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0005 | 0 | 6105AK124-0000-GRPT-0005 | Q24050972-04-0000-G-RPT-0005 |  | General | Monthly Report - March 2026 | Report | General - Monthly Report - March 2026 - Report | 2026-04-10 |  | IFI - Issued for Information | Pending | 33.33% | LC |  |  | Monthly Report | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0007 | 0 | 6105AK124-0000-GRPT-0007 | Q24050972-04-0000-G-RPT-0007 |  | General | Monthly Report - May 2026 | Report | General - Monthly Report - May 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-06-19 | Monthly Report | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0008 | 0 | 6105AK124-0000-GRPT-0008 | Q24050972-04-0000-G-RPT-0008 |  | General | Monthly Report - June 2026 | Report | General - Monthly Report - June 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-06-29 | Monthly Report | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0009 | 0 | 6105AK124-0000-GRPT-0009 | Q24050972-04-0000-G-RPT-0009 |  | General | Monthly Report - July 2026 | Report | General - Monthly Report - July 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-07-29 | Monthly Report | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0010 | 0 | 6105AK124-0000-GRPT-0010 | Q24050972-04-0000-G-RPT-0010 |  | General | Monthly Report - August 2026 | Report | General - Monthly Report - August 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-08-29 | Monthly Report | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0012 | 0 | 6105AK124-0000-GRPT-0012 | Q24050972-04-0000-G-RPT-0012 |  | General | Monthly Report - September 2026 | Report | General - Monthly Report - September 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-09-29 | Monthly Report | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0013 | 0 | 6105AK124-0000-GRPT-0013 | Q24050972-04-0000-G-RPT-0013 |  | General | Monthly Report - October 2026 | Report | General - Monthly Report - October 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-10-29 | Monthly Report | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0014 | 0 | 6105AK124-0000-GRPT-0014 | Q24050972-04-0000-G-RPT-0014 |  | General | Monthly Report - November 2026 | Report | General - Monthly Report - November 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-11-29 | Monthly Report | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0015 | 0 | 6105AK124-0000-GRPT-0015 | Q24050972-04-0000-G-RPT-0015 |  | General | Monthly Report - December 2026 | Report | General - Monthly Report - December 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-12-29 | Monthly Report | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0016 | 0 | 6105AK124-0000-GRPT-0016 | Q24050972-04-0000-G-RPT-0016 |  | General | Cost Forecast Basis - March 2026 | Report | General - Cost Forecast Basis - March 2026 - Report | 2026-04-16 |  | IFI - Issued for Information | Pending | 33.33% | LC |  |  | Cost Forecast Basis | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0017 | 1 | 6105AK124-0000-GRPT-0017 | Q24050972-04-0000-G-RPT-0017 |  | General | Cost Flow Forecast - April 2026 | Report | General - Cost Flow Forecast - April 2026 - Report | 2026-12-05 |  | IFI - Issued for Information | Pending | 33.33% | LC |  |  | Cost Forecast Basis | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0018 | 0 | 6105AK124-0000-GRPT-0018 | Q24050972-04-0000-G-RPT-0018 |  | General | Monthly Report - April 2026 | Report | General - Monthly Report - April 2026 - Report | 2026-12-05 |  | IFI - Issued for Information | Pending | 33.33% | LC |  |  | Cost Forecast Basis | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0019 | 0 | 6105AK124-0000-GRPT-0019 | Q24050972-04-0000-G-RPT-0019 |  | General | Cost Flow Forecast - May 2026 | Report | General - Cost Flow Forecast - May 2026 - Report | 2026-06-08 |  | IFI - Issued for Information | Pending | 33.33% | LC |  |  | Cost Forecast Basis | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0020 | 0 | 6105AK124-0000-GRPT-0020 | Q24050972-04-0000-G-RPT-0020 |  | General | Cost Flow Forecast - July 2026 | Report | General - Cost Flow Forecast - July 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-07-29 | Cost Forecast Basis | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0021 | 0 | 6105AK124-0000-GRPT-0021 | Q24050972-04-0000-G-RPT-0021 |  | General | Cost Flow Forecast - August 2026 | Report | General - Cost Flow Forecast - August 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-08-29 | Cost Forecast Basis | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0022 | 0 | 6105AK124-0000-GRPT-0022 | Q24050972-04-0000-G-RPT-0022 |  | General | Cost Flow Forecast -September 2026 | Report | General - Cost Flow Forecast -September 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-09-29 | Cost Forecast Basis | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0023 | 0 | 6105AK124-0000-GRPT-0023 | Q24050972-04-0000-G-RPT-0023 |  | General | Cost Flow Forecast - October 2026 | Report | General - Cost Flow Forecast - October 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-10-29 | Cost Forecast Basis | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0024 | 0 | 6105AK124-0000-GRPT-0024 | Q24050972-04-0000-G-RPT-0024 |  | General | Cost Flow Forecast - November 2026 | Report | General - Cost Flow Forecast - November 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-11-29 | Cost Forecast Basis | General |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0025 | 0 | 6105AK124-0000-GRPT-0025 | Q24050972-04-0000-G-RPT-0025 |  | General | Cost Flow Forecast - December 2026 | Report | General - Cost Flow Forecast - December 2026 - Report |  |  | RES - Reserved Placeholder | Pending | 0% | LC |  | 2026-12-29 | Cost Forecast Basis | General |  |  |  | Pending
6105A | K124 | 6251 | E | LAY | 0010 | A | 6105AK124-6251-ELAY-0010 | Q24050972-04-6251-E-LAY-0010 |  | Load Bank | Wartsila Power Plant 1 | Earthing layout | Load Bank - Wartsila Power Plant 1 - Earthing layout | 2026-05-25 |  | IFR - Issued for Review | Pending | 33.33% | TDK |  |  | Wartsila Power Plant 1 | Earthing layout |  |  |  | Pending
6105A | K124 | 6251 | E | LAY | 0011 | A | 6105AK124-6251-ELAY-0011 | Q24050972-04-6251-E-LAY-0011 |  | Load Bank | Wartsila Power Plant 1 | Overall Lighting Layout | Load Bank - Wartsila Power Plant 1 - Overall Lighting Layout | 2026-05-25 |  | IFR - Issued for Review | Pending | 33.33% | TDK |  |  | Wartsila Power Plant 1 | Overall Lighting Layout |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0002 | A | 6105AK124-6286-EDIA-0002 | Q24050972-04-6286-E-DIA-0002 |  | Primary Crushing | Mining Substation | 11kV Cable Block Diagram | Primary Crushing - Mining Substation - 11kV Cable Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-15 | Mining Substation | Block Diagram |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0003 | A | 6105AK124-6286-EDIA-0003 | Q24050972-04-6286-E-DIA-0003 |  | Primary Crushing | Mining Substation | 33kV Cable Block Diagram | Primary Crushing - Mining Substation - 33kV Cable Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-15 | Mining Substation | Block Diagram |  |  |  | Pending
6105A | K124 | 6286 | E | SEC | 0001 | A | 6105AK124-6286-ESEC-0001 | Q24050972-04-6286-E-SEC-0001 | Sht. 1 of 1 | Primary Crushing | Mining Substation | MV Cable Trench Cable Detail - 33kV OHL Trench | Primary Crushing - Mining Substation - MV Cable Trench Cable Detail - 33kV OHL Trench - Sht. 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-15 | Mining Substation | MV Cable Trench |  |  |  | Pending
6105A | K124 | 6286 | E | SEC | 0002 | A | 6105AK124-6286-ESEC-0002 | Q24050972-04-6286-E-SEC-0002 | Sht. 1 of 1 | Primary Crushing | Mining Substation | Cable Trench Cable Detail - 33kV Mining TX Trench | Primary Crushing - Mining Substation - Cable Trench Cable Detail - 33kV Mining TX Trench - Sht. 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-15 | Mining Substation | Cable Trench |  |  |  | Pending
6105A | K124 | 6286 | E | SEC | 0003 | A | 6105AK124-6286-ESEC-0003 | Q24050972-04-6286-E-SEC-0003 | Sht. 1 of 1 | Primary Crushing | Mining Substation | Cable Trench Cable Detail - 11kV Mining TX Trench | Primary Crushing - Mining Substation - Cable Trench Cable Detail - 11kV Mining TX Trench - Sht. 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-15 | Mining Substation | Cable Trench |  |  |  | Pending
6105A | K124 | 6286 | E | SEC | 0004 | A | 6105AK124-6286-ESEC-0004 | Q24050972-04-6286-E-SEC-0004 | Sht. 1 of 1 | Primary Crushing | Mining Substation | Cable Trench Cable Detail - 11kV Mining OHL Trench | Primary Crushing - Mining Substation - Cable Trench Cable Detail - 11kV Mining OHL Trench - Sht. 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-15 | Mining Substation | Cable Trench |  |  |  | Pending
6105A | K124 | 6242 | E | SCH | 0001 | A | 6105AK124-6242-ESCH-0001 | Q24050972-04-6242-E-SCH-0001 |  | 33/220 kV Power Station Substation | Main Intake Substation | Cable Schedule | 33/220 kV Power Station Substation - Main Intake Substation - Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-15 | Main Intake Substation | Cable Schedule |  |  |  | Pending
6105A | K124 | 6242 | E | DIA | 0005 | A | 6105AK124-6242-EDIA-0005 | Q24050972-04-6242-E-DIA-0005 | Sht. 1 of 1 | 33/220 kV Power Station Substation | Main Intake Substation | MV Cable Block Diagram | 33/220 kV Power Station Substation - Main Intake Substation - MV Cable Block Diagram - Sht. 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-15 | Main Intake Substation | Block Diagram |  |  |  | Pending
6105A | K124 | 6241 | E | SCH | 0001 | A | 6105AK124-6241-ESCH-0001 | Q24050972-04-6241-E-SCH-0001 |  | 33/220 kV Solar PV Substation | Solar PV Substation | Cable Schedule | 33/220 kV Solar PV Substation - Solar PV Substation - Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-15 | PV Substation | Cable Schedule |  |  |  | Pending
6105A | K124 | 6241 | E | DIA | 0005 | A | 6105AK124-6241-EDIA-0005 | Q24050972-04-6241-E-DIA-0005 | Sht. 1 of 1 | 33/220 kV Solar PV Substation | Solar PV Substation | 33kV Cable Block Diagram | 33/220 kV Solar PV Substation - Solar PV Substation - 33kV Cable Block Diagram - Sht. 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-15 | PV Substation | Block Diagram |  |  |  | Pending
6105A | K124 | 6241 | E | SEC | 0001 | A | 6105AK124-6241-ESEC-0001 | Q24050972-04-6241-E-SEC-0001 | Sht. 1 of 1 | 33/220 kV Solar PV Substation | Solar PV Substation | MV Cable Trench Cable Detail - 33kV OHL Trench | 33/220 kV Solar PV Substation - Solar PV Substation - MV Cable Trench Cable Detail - 33kV OHL Trench - Sht. 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | RS |  | 2026-06-15 | Solar PV Substation | Cable Detail |  |  |  | Pending
6105A | K124 | 6241 | E | LAY | 0001 | A | 6105AK124-6241-ELAY-0001 | Q24050972-04-6241-E-LAY-0001 |  | 33/220 kV Solar PV Substation | Solar PV Substation | Earthing layout | 33/220 kV Solar PV Substation - Solar PV Substation - Earthing layout |  |  | RES - Reserved Placeholder | Pending | 0% | TDK |  | 2026-06-15 | PV Substation | Earthing layout |  |  |  | Pending
6105A | K124 | 6241 | E | LAY | 0002 | A | 6105AK124-6241-ELAY-0002 | Q24050972-04-6241-E-LAY-0002 |  | 33/220 kV Solar PV Substation | Solar PV Substation | Overall Lighting Layout | 33/220 kV Solar PV Substation - Solar PV Substation - Overall Lighting Layout |  |  | RES - Reserved Placeholder | Pending | 0% | TDK |  | 2026-06-15 | PV Substation | Lighting Layout |  |  |  | Pending
6105A | K124 | 6242 | G | DDR | 0001 | A | 6105AK124-6242-GDDR-0001 | Q24050972-04-6242-G-DDR-0001 |  | 33/220 kV Power Station Substation | Wartsila Load Bank Substation | Construction Document Register - Sht 1 of 1 | 33/220 kV Power Station Substation - Wartsila Load Bank Substation - Construction Document Register - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-20 | Wartsila Load Bank | Document Register |  |  |  | Pending
6105A | K124 | 6241 | G | DDR | 0001 | A | 6105AK124-6241-GDDR-0001 | Q24050972-04-6241-G-DDR-0001 |  | 33/220 kV Solar PV Substation | 33kV PV Solar Substation | Construction Document Register - Sht 1 of 1 | 33/220 kV Solar PV Substation - 33kV PV Solar Substation - Construction Document Register - Sht 1 of 1 |  |  | RES - Reserved Placeholder | Pending | [9 empty] | Pending
6105A | K124 | 0100 | Q | TMP | 0009 | A | 6105AK124-0100-QTMP-0009 | Q24050972-04-0100-Q-TMP-0009 |  | Project Site Wide | EC&I QA/QC Templates | EC&I QA/QC Templates | Project Site Wide - EC&I QA/QC Templates - EC&I QA/QC Templates | 2026-05-08 |  | IFR - Issued for Review | Pending | 33.33% | OC |  |  | QA/QC Templates | Templates |  |  |  | Pending
6105A | K124 | 0000 | B | CON | 0003 | A | 6105AK124-0000-BCON-0003 | Q24050972-04-0000-B-CON-0003 |  | General | Notice of Delay - Delay Notification Contractual | General | General - Notice of Delay - Delay Notification Contractual - General | 2026-04-30 |  | IFR - Issued for Review | Pending | 33.33% | JV |  |  | Notice of Delay | General |  |  |  | Pending
6105A | K124 | 6251 | I | SPC | 0001 | A | 6105AK124-6251-ISPC-0001 | Q24050972-04-6251-I-SPC-0001 |  | Load Bank | Metering Instruments for Wartsila Load Bank | Junction Box and Interface Cabinet Design | Load Bank - Metering Instruments for Wartsila Load Bank - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | SPC | 0002 | A | 6105AK124-6251-ISPC-0002 | Q24050972-04-6251-I-SPC-0002 |  | Load Bank | Earthing System for Wartsila Load Bank | Junction Box and Interface Cabinet Design | Load Bank - Earthing System for Wartsila Load Bank - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | SPC | 0003 | A | 6105AK124-6251-ISPC-0003 | Q24050972-04-6251-I-SPC-0003 |  | Load Bank | Metering Instruments for Emergency Gen Load Bank | Junction Box and Interface Cabinet Design | Load Bank - Metering Instruments for Emergency Gen Load Bank - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | I | SPC | 0004 | A | 6105AK124-6251-ISPC-0004 | Q24050972-04-6251-I-SPC-0004 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Junction Box and Interface Cabinet Design | Load Bank - Earthing System forEmergency Gen Load Bank - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | CAL | 0001 | A | 6105AK124-6251-MCAL-0001 | Q24050972-04-6251-M-CAL-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Vessel and Structure Design with Stress Analysis Calcs | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | M | CAL | 0002 | A | 6105AK124-6251-MCAL-0002 | Q24050972-04-6251-M-CAL-0002 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Piping Pressure Drop Calculations | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | CAL | 0003 | A | 6105AK124-6251-MCAL-0003 | Q24050972-04-6251-M-CAL-0003 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Vessel and Structure Design with Stress Analysis Calcs | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | CAL | 0004 | A | 6105AK124-6251-MCAL-0004 | Q24050972-04-6251-M-CAL-0004 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Piping Pressure Drop Calculations | Load Bank - Fire Protection System Emergency Gen Load Bank - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank | Emergency Gen Load Bank | Emergency Gen Load Bank |  | Pending
6105A | K124 | 6251 | M | CAL | 0005 | A | 6105AK124-6251-MCAL-0005 | Q24050972-04-6251-M-CAL-0005 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Vessel and Structure Design with Stress Analysis Calcs | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | DST | 0001 | A | 6105AK124-6251-MDST-0001 | Q24050972-04-6251-M-DST-0001 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Pressure Relief Devices Design and Specification | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | DST | 0002 | A | 6105AK124-6251-MDST-0002 | Q24050972-04-6251-M-DST-0002 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Pressure Relief Devices Design and Specification | Load Bank - Fire Protection System Emergency Gen Load Bank - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | EQL | 0001 | A | 6105AK124-6251-MEQL-0001 | Q24050972-04-6251-M-EQL-0001 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Mechanical Equipment Register with Specifications | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | EQL | 0002 | A | 6105AK124-6251-MEQL-0002 | Q24050972-04-6251-M-EQL-0002 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Mechanical Equipment Register with Specifications | Load Bank - Fire Protection System Emergency Gen Load Bank - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | ISO | 0001 | A | 6105AK124-6251-MISO-0001 | Q24050972-04-6251-M-ISO-0001 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Piping Isometric Design and Layouts | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | ISO | 0002 | A | 6105AK124-6251-MISO-0002 | Q24050972-04-6251-M-ISO-0002 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Piping Isometric Design and Layouts | Load Bank - Fire Protection System Emergency Gen Load Bank - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | PRC | 0001 | A | 6105AK124-6251-MPRC-0001 | Q24050972-04-6251-M-PRC-0001 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Rigging Study and Lifting Equipment Design | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | PRC | 0002 | A | 6105AK124-6251-MPRC-0002 | Q24050972-04-6251-M-PRC-0002 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Rigging Study and Lifting Equipment Design | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | PSP | 0001 | A | 6105AK124-6251-MPSP-0001 | Q24050972-04-6251-M-PSP-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Pipe and Cable Support Racks Design | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | M | PSP | 0002 | A | 6105AK124-6251-MPSP-0002 | Q24050972-04-6251-M-PSP-0002 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Pipe and Cable Support Racks Design | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | PSP | 0003 | A | 6105AK124-6251-MPSP-0003 | Q24050972-04-6251-M-PSP-0003 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Pipe and Cable Support Racks Design | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | PSP | 0004 | A | 6105AK124-6251-MPSP-0004 | Q24050972-04-6251-M-PSP-0004 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Pipe and Cable Support Racks Design | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | PSP | 0005 | A | 6105AK124-6251-MPSP-0005 | Q24050972-04-6251-M-PSP-0005 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Pipe and Cable Support Racks Design | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | PSP | 0006 | A | 6105AK124-6251-MPSP-0006 | Q24050972-04-6251-M-PSP-0006 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Pipe and Cable Support Racks Design | Load Bank - Fire Protection System Emergency Gen Load Bank - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | PSP | 0007 | A | 6105AK124-6251-MPSP-0007 | Q24050972-04-6251-M-PSP-0007 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Pipe and Cable Support Racks Design | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | PSP | 0008 | A | 6105AK124-6251-MPSP-0008 | Q24050972-04-6251-M-PSP-0008 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Pipe and Cable Support Racks Design | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | PSP | 0009 | A | 6105AK124-6251-MPSP-0009 | Q24050972-04-6251-M-PSP-0009 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Pipe and Cable Support Racks Design | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | QAD | 0001 | A | 6105AK124-6251-MQAD-0001 | Q24050972-04-6251-M-QAD-0001 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Fabrication Inspection QC Pack (Incl. NDT) | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | QAD | 0002 | A | 6105AK124-6251-MQAD-0002 | Q24050972-04-6251-M-QAD-0002 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Fabrication Inspection QC Pack (Incl. NDT) | Load Bank - Fire Protection System Emergency Gen Load Bank - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | SPC | 0001 | A | 6105AK124-6251-MSPC-0001 | Q24050972-04-6251-M-SPC-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Material Selection and Verification Specification | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Cable Racks |  |  |  | Pending
6105A | K124 | 6251 | M | SPC | 0002 | A | 6105AK124-6251-MSPC-0002 | Q24050972-04-6251-M-SPC-0002 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Material Selection and Verification Specification | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | SPC | 0003 | A | 6105AK124-6251-MSPC-0003 | Q24050972-04-6251-M-SPC-0003 |  | Load Bank | Fire Protection and Detection System for Wartsila Load Bank | Gasket Schedule and Material Specification | Load Bank - Fire Protection and Detection System for Wartsila Load Bank - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection and Detection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | SPC | 0004 | A | 6105AK124-6251-MSPC-0004 | Q24050972-04-6251-M-SPC-0004 |  | Load Bank | Cable Racks and Trays for Wartsila Load Bank | Material Selection and Verification Specification | Load Bank - Cable Racks and Trays for Wartsila Load Bank - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | SPC | 0005 | A | 6105AK124-6251-MSPC-0005 | Q24050972-04-6251-M-SPC-0005 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Material Selection and Verification Specification | Load Bank - Fire Protection System Emergency Gen Load Bank - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | SPC | 0006 | A | 6105AK124-6251-MSPC-0006 | Q24050972-04-6251-M-SPC-0006 |  | Load Bank | Fire Protection System Emergency Gen Load Bank | Gasket Schedule and Material Specification | Load Bank - Fire Protection System Emergency Gen Load Bank - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | M | SPC | 0007 | A | 6105AK124-6251-MSPC-0007 | Q24050972-04-6251-M-SPC-0007 |  | Load Bank | Cable Racks and Trays for Emergency Gen Load Bank | Material Selection and Verification Specification | Load Bank - Cable Racks and Trays for Emergency Gen Load Bank - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | T | RPT | 0001 | A | 6105AK124-6251-TRPT-0001 | Q24050972-04-6251-T-RPT-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Site Surveying & Geotechnical Report | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | T | RPT | 0002 | A | 6105AK124-6251-TRPT-0002 | Q24050972-04-6251-T-RPT-0002 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Site Surveying & Geotechnical Report | Load Bank - Platform and Foundations for Wartsila Load Bank - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | T | RPT | 0003 | A | 6105AK124-6251-TRPT-0003 | Q24050972-04-6251-T-RPT-0003 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | Site Surveying & Geotechnical Report | Load Bank - Perimeter Fencing for for Wartsila Load Bank - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | T | RPT | 0004 | A | 6105AK124-6251-TRPT-0004 | Q24050972-04-6251-T-RPT-0004 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Site Surveying & Geotechnical Report | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | T | RPT | 0005 | A | 6105AK124-6251-TRPT-0005 | Q24050972-04-6251-T-RPT-0005 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Site Surveying & Geotechnical Report | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | T | SPC | 0001 | A | 6105AK124-6251-TSPC-0001 | Q24050972-04-6251-T-SPC-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Civil Design and Requirements | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | T | SPC | 0002 | A | 6105AK124-6251-TSPC-0002 | Q24050972-04-6251-T-SPC-0002 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Civil Design and Requirements | Load Bank - Platform and Foundations for Wartsila Load Bank - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | T | SPC | 0003 | A | 6105AK124-6251-TSPC-0003 | Q24050972-04-6251-T-SPC-0003 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Civil Design and Requirements | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | T | SPC | 0004 | A | 6105AK124-6251-TSPC-0004 | Q24050972-04-6251-T-SPC-0004 |  | Load Bank | Earthing System for Wartsila Load Bank | Civil Design and Requirements | Load Bank - Earthing System for Wartsila Load Bank - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | T | SPC | 0005 | A | 6105AK124-6251-TSPC-0005 | Q24050972-04-6251-T-SPC-0005 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Civil Design and Requirements | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | T | SPC | 0006 | A | 6105AK124-6251-TSPC-0006 | Q24050972-04-6251-T-SPC-0006 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Civil Design and Requirements | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | T | SPC | 0007 | A | 6105AK124-6251-TSPC-0007 | Q24050972-04-6251-T-SPC-0007 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Civil Design and Requirements | Load Bank - Earthing System forEmergency Gen Load Bank - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | ELE | 0001 | A | 6105AK124-6251-WELE-0001 | Q24050972-04-6251-W-ELE-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Bulk Earth Works Design and Report | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | W | ELE | 0002 | A | 6105AK124-6251-WELE-0002 | Q24050972-04-6251-W-ELE-0002 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Bulk Earth Works Design and Report | Load Bank - Platform and Foundations for Wartsila Load Bank - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | ELE | 0003 | A | 6105AK124-6251-WELE-0003 | Q24050972-04-6251-W-ELE-0003 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Bulk Earth Works Design and Report | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | ELE | 0004 | A | 6105AK124-6251-WELE-0004 | Q24050972-04-6251-W-ELE-0004 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Bulk Earth Works Design and Report | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | ELE | 0005 | A | 6105AK124-6251-WELE-0005 | Q24050972-04-6251-W-ELE-0005 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Bulk Earth Works Design and Report | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | ELE | 0006 | A | 6105AK124-6251-WELE-0006 | Q24050972-04-6251-W-ELE-0006 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Bulk Earth Works Design and Report | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | ELE | 0007 | A | 6105AK124-6251-WELE-0007 | Q24050972-04-6251-W-ELE-0007 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Bulk Earth Works Design and Report | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | LAY | 0001 | A | 6105AK124-6251-WLAY-0001 | Q24050972-04-6251-W-LAY-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Drainage, Run-off and Impoundment Design | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | W | LAY | 0002 | A | 6105AK124-6251-WLAY-0002 | Q24050972-04-6251-W-LAY-0002 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Drainage, Run-off and Impoundment Design | Load Bank - Platform and Foundations for Wartsila Load Bank - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | LAY | 0003 | A | 6105AK124-6251-WLAY-0003 | Q24050972-04-6251-W-LAY-0003 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Drainage, Run-off and Impoundment Design | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | LAY | 0004 | A | 6105AK124-6251-WLAY-0004 | Q24050972-04-6251-W-LAY-0004 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Drainage, Run-off and Impoundment Design | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | LAY | 0005 | A | 6105AK124-6251-WLAY-0005 | Q24050972-04-6251-W-LAY-0005 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Drainage, Run-off and Impoundment Design | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | LAY | 0006 | A | 6105AK124-6251-WLAY-0006 | Q24050972-04-6251-W-LAY-0006 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Drainage, Run-off and Impoundment Design | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | LAY | 0007 | A | 6105AK124-6251-WLAY-0007 | Q24050972-04-6251-W-LAY-0007 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Drainage, Run-off and Impoundment Design | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0001 | A | 6105AK124-6251-WTRP-0001 | Q24050972-04-6251-W-TRP-0001 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Soil Classification and Nomination Deliverables | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0002 | A | 6105AK124-6251-WTRP-0002 | Q24050972-04-6251-W-TRP-0002 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Soil Resistivity Testing Report | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Load Bank Concrete Pad |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0003 | A | 6105AK124-6251-WTRP-0003 | Q24050972-04-6251-W-TRP-0003 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Soil Classification and Nomination Deliverables | Load Bank - Platform and Foundations for Wartsila Load Bank - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0004 | A | 6105AK124-6251-WTRP-0004 | Q24050972-04-6251-W-TRP-0004 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Soil Resistivity Testing Report | Load Bank - Platform and Foundations for Wartsila Load Bank - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0005 | A | 6105AK124-6251-WTRP-0005 | Q24050972-04-6251-W-TRP-0005 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Soil Classification and Nomination Deliverables | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0006 | A | 6105AK124-6251-WTRP-0006 | Q24050972-04-6251-W-TRP-0006 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Soil Resistivity Testing Report | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0007 | A | 6105AK124-6251-WTRP-0007 | Q24050972-04-6251-W-TRP-0007 |  | Load Bank | MV Cabling and Termination for Wartsila Load Bank | Soil Classification and Nomination Deliverables | Load Bank - MV Cabling and Termination for Wartsila Load Bank - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0008 | A | 6105AK124-6251-WTRP-0008 | Q24050972-04-6251-W-TRP-0008 |  | Load Bank | LV, Control and Signal Cables for Wartsila Load Bank | Soil Classification and Nomination Deliverables | Load Bank - LV, Control and Signal Cables for Wartsila Load Bank - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0009 | A | 6105AK124-6251-WTRP-0009 | Q24050972-04-6251-W-TRP-0009 |  | Load Bank | Cable Trench and Tunnels for Wartsila Load Bank | Soil Classification and Nomination Deliverables | Load Bank - Cable Trench and Tunnels for Wartsila Load Bank - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0010 | A | 6105AK124-6251-WTRP-0010 | Q24050972-04-6251-W-TRP-0010 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Soil Classification and Nomination Deliverables | Load Bank - Lightning Protection System forWartsila Load Bank - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0011 | A | 6105AK124-6251-WTRP-0011 | Q24050972-04-6251-W-TRP-0011 |  | Load Bank | Lightning Protection System forWartsila Load Bank | Soil Resistivity Testing Report | Load Bank - Lightning Protection System forWartsila Load Bank - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0012 | A | 6105AK124-6251-WTRP-0012 | Q24050972-04-6251-W-TRP-0012 |  | Load Bank | Earthing System for Wartsila Load Bank | Soil Resistivity Testing Report | Load Bank - Earthing System for Wartsila Load Bank - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Wartsila Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0013 | A | 6105AK124-6251-WTRP-0013 | Q24050972-04-6251-W-TRP-0013 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Soil Classification and Nomination Deliverables | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0014 | A | 6105AK124-6251-WTRP-0014 | Q24050972-04-6251-W-TRP-0014 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Soil Resistivity Testing Report | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0015 | A | 6105AK124-6251-WTRP-0015 | Q24050972-04-6251-W-TRP-0015 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Soil Classification and Nomination Deliverables | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0016 | A | 6105AK124-6251-WTRP-0016 | Q24050972-04-6251-W-TRP-0016 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Soil Resistivity Testing Report | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0017 | A | 6105AK124-6251-WTRP-0017 | Q24050972-04-6251-W-TRP-0017 |  | Load Bank | MV Cabling and Termination for Emergency Gen Load Bank | Soil Classification and Nomination Deliverables | Load Bank - MV Cabling and Termination for Emergency Gen Load Bank - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cabling and Termination | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0018 | A | 6105AK124-6251-WTRP-0018 | Q24050972-04-6251-W-TRP-0018 |  | Load Bank | LV, Control and Signal Cables for Emergency Gen Load Bank | Soil Classification and Nomination Deliverables | Load Bank - LV, Control and Signal Cables for Emergency Gen Load Bank - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0019 | A | 6105AK124-6251-WTRP-0019 | Q24050972-04-6251-W-TRP-0019 |  | Load Bank | Cable Trench and Tunnels for Emergency Gen Load Bank | Soil Classification and Nomination Deliverables | Load Bank - Cable Trench and Tunnels for Emergency Gen Load Bank - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0020 | A | 6105AK124-6251-WTRP-0020 | Q24050972-04-6251-W-TRP-0020 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Soil Classification and Nomination Deliverables | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0021 | A | 6105AK124-6251-WTRP-0021 | Q24050972-04-6251-W-TRP-0021 |  | Load Bank | Lightning Protection System for Emergency Gen Load Bank | Soil Resistivity Testing Report | Load Bank - Lightning Protection System for Emergency Gen Load Bank - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | W | TRP | 0022 | A | 6105AK124-6251-WTRP-0022 | Q24050972-04-6251-W-TRP-0022 |  | Load Bank | Earthing System forEmergency Gen Load Bank | Soil Resistivity Testing Report | Load Bank - Earthing System forEmergency Gen Load Bank - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6253 | B | DBD | 0001 | A | 6105AK124-6253-BDBD-0001 | Q24050972-04-6253-B-DBD-0001 |  | Synchronous Condenser 1 | Synchronous Condensers Project Package | Design Criteria / Basis of Design | Synchronous Condenser 1 - Synchronous Condensers Project Package - Design Criteria / Basis of Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Synchronous Condensers | Design Criteria |  |  |  | Pending
6105A | K124 | 6253 | B | PHL | 0001 | A | 6105AK124-6253-BPHL-0001 | Q24050972-04-6253-B-PHL-0001 |  | Synchronous Condenser 1 | Synchronous Condensers Project Package | Control Philosophy | Synchronous Condenser 1 - Synchronous Condensers Project Package - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Synchronous Condensers | Control Philosophy |  |  |  | Pending
6105A | K124 | 6253 | B | PHL | 0002 | A | 6105AK124-6253-BPHL-0002 | Q24050972-04-6253-B-PHL-0002 |  | Synchronous Condenser 1 | Synchronous Condensers Project Package | Synchronization Philosophy | Synchronous Condenser 1 - Synchronous Condensers Project Package - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Synchronous Condensers | Synchronization Philosophy |  |  |  | Pending
6105A | K124 | 6253 | B | SPC | 0001 | A | 6105AK124-6253-BSPC-0001 | Q24050972-04-6253-B-SPC-0001 |  | Synchronous Condenser 1 | Synchronous Condensers Project Package | Functional Design Specification | Synchronous Condenser 1 - Synchronous Condensers Project Package - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Synchronous Condensers | Specification |  |  |  | Pending
6105A | K124 | 6253 | B | STD | 0001 | A | 6105AK124-6253-BSTD-0001 | Q24050972-04-6253-B-STD-0001 |  | Synchronous Condenser 1 | Synchronous Condensers Project Package | System Detailed Engineering Design | Synchronous Condenser 1 - Synchronous Condensers Project Package - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Synchronous Condensers | System Detailed Engineering Design |  |  |  | Pending
6105A | K124 | 6253 | C | FND | 0001 | A | 6105AK124-6253-CFND-0001 | Q24050972-04-6253-C-FND-0001 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Civil Foundation Design | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | FND | 0002 | A | 6105AK124-6253-CFND-0002 | Q24050972-04-6253-C-FND-0002 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Civil Foundation Design | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0001 | A | 6105AK124-6253-CGAD-0001 | Q24050972-04-6253-C-GAD-0001 |  | Synchronous Condenser 1 | Offloading Equipment and Spreader Beam for Synchronous Condensers | Terrace Equipment GA | Synchronous Condenser 1 - Offloading Equipment and Spreader Beam for Synchronous Condensers - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Synchronous Condensers |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0002 | A | 6105AK124-6253-CGAD-0002 | Q24050972-04-6253-C-GAD-0002 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Buildings and Structures GA | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0003 | A | 6105AK124-6253-CGAD-0003 | Q24050972-04-6253-C-GAD-0003 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Cables, OHL and Fibre Route GA | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0004 | A | 6105AK124-6253-CGAD-0004 | Q24050972-04-6253-C-GAD-0004 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Key Emergency Points and Equipment | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0005 | A | 6105AK124-6253-CGAD-0005 | Q24050972-04-6253-C-GAD-0005 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Terrace Equipment GA | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0006 | A | 6105AK124-6253-CGAD-0006 | Q24050972-04-6253-C-GAD-0006 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Disposal Areas General Arrangement | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0007 | A | 6105AK124-6253-CGAD-0007 | Q24050972-04-6253-C-GAD-0007 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Laydown Areas and Temp Buildings GA | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0008 | A | 6105AK124-6253-CGAD-0008 | Q24050972-04-6253-C-GAD-0008 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Stormwater and Effluent System Design | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0009 | A | 6105AK124-6253-CGAD-0009 | Q24050972-04-6253-C-GAD-0009 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Lighting Design and Layout GA | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0010 | A | 6105AK124-6253-CGAD-0010 | Q24050972-04-6253-C-GAD-0010 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Roads, Pathways, Offloading Areas and Fences GA | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0011 | A | 6105AK124-6253-CGAD-0011 | Q24050972-04-6253-C-GAD-0011 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Lighting Design and Layout GA | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0012 | A | 6105AK124-6253-CGAD-0012 | Q24050972-04-6253-C-GAD-0012 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Buildings and Structures GA | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0013 | A | 6105AK124-6253-CGAD-0013 | Q24050972-04-6253-C-GAD-0013 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Cables, OHL and Fibre Route GA | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0014 | A | 6105AK124-6253-CGAD-0014 | Q24050972-04-6253-C-GAD-0014 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Terrace Equipment GA | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0015 | A | 6105AK124-6253-CGAD-0015 | Q24050972-04-6253-C-GAD-0015 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Laydown Areas and Temp Buildings GA | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0016 | A | 6105AK124-6253-CGAD-0016 | Q24050972-04-6253-C-GAD-0016 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Lighting Design and Layout GA | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0017 | A | 6105AK124-6253-CGAD-0017 | Q24050972-04-6253-C-GAD-0017 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Roads, Pathways, Offloading Areas and Fences GA | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0018 | A | 6105AK124-6253-CGAD-0018 | Q24050972-04-6253-C-GAD-0018 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Buildings and Structures GA | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0019 | A | 6105AK124-6253-CGAD-0019 | Q24050972-04-6253-C-GAD-0019 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Cables, OHL and Fibre Route GA | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0020 | A | 6105AK124-6253-CGAD-0020 | Q24050972-04-6253-C-GAD-0020 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Terrace Equipment GA | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0021 | A | 6105AK124-6253-CGAD-0021 | Q24050972-04-6253-C-GAD-0021 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Roads, Pathways, Offloading Areas and Fences GA | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0022 | A | 6105AK124-6253-CGAD-0022 | Q24050972-04-6253-C-GAD-0022 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Buildings and Structures GA | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0023 | A | 6105AK124-6253-CGAD-0023 | Q24050972-04-6253-C-GAD-0023 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Cables, OHL and Fibre Route GA | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0024 | A | 6105AK124-6253-CGAD-0024 | Q24050972-04-6253-C-GAD-0024 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Terrace Equipment GA | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0025 | A | 6105AK124-6253-CGAD-0025 | Q24050972-04-6253-C-GAD-0025 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Buildings and Structures GA | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0026 | A | 6105AK124-6253-CGAD-0026 | Q24050972-04-6253-C-GAD-0026 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Cables, OHL and Fibre Route GA | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | GAD | 0027 | A | 6105AK124-6253-CGAD-0027 | Q24050972-04-6253-C-GAD-0027 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Terrace Equipment GA | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | MDL | 0001 | A | 6105AK124-6253-CMDL-0001 | Q24050972-04-6253-C-MDL-0001 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | 3D Designs and Drawings | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | MDL | 0002 | A | 6105AK124-6253-CMDL-0002 | Q24050972-04-6253-C-MDL-0002 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | 3D Designs and Drawings | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | MDL | 0003 | A | 6105AK124-6253-CMDL-0003 | Q24050972-04-6253-C-MDL-0003 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | 3D Designs and Drawings | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | MDL | 0004 | A | 6105AK124-6253-CMDL-0004 | Q24050972-04-6253-C-MDL-0004 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | 3D Designs and Drawings | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | MDL | 0005 | A | 6105AK124-6253-CMDL-0005 | Q24050972-04-6253-C-MDL-0005 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | 3D Designs and Drawings | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | MDL | 0006 | A | 6105AK124-6253-CMDL-0006 | Q24050972-04-6253-C-MDL-0006 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | 3D Designs and Drawings | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | PLN | 0001 | A | 6105AK124-6253-CPLN-0001 | Q24050972-04-6253-C-PLN-0001 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Civil Works Execution Plan | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | PLN | 0002 | A | 6105AK124-6253-CPLN-0002 | Q24050972-04-6253-C-PLN-0002 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Civil Works Execution Plan | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | PLN | 0003 | A | 6105AK124-6253-CPLN-0003 | Q24050972-04-6253-C-PLN-0003 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Civil Works Execution Plan | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | PPL | 0001 | A | 6105AK124-6253-CPPL-0001 | Q24050972-04-6253-C-PPL-0001 |  | Synchronous Condenser 1 | Offloading Equipment and Spreader Beam for Synchronous Condensers | Operational & Maint Access Routes Design | Synchronous Condenser 1 - Offloading Equipment and Spreader Beam for Synchronous Condensers - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Synchronous Condensers |  |  |  | Pending
6105A | K124 | 6253 | C | PPL | 0002 | A | 6105AK124-6253-CPPL-0002 | Q24050972-04-6253-C-PPL-0002 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Operational & Maint Access Routes Design | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | PPL | 0003 | A | 6105AK124-6253-CPPL-0003 | Q24050972-04-6253-C-PPL-0003 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Operational & Maint Access Routes Design | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | PPL | 0004 | A | 6105AK124-6253-CPPL-0004 | Q24050972-04-6253-C-PPL-0004 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Operational & Maint Access Routes Design | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SEC | 0003 | A | 6105AK124-6253-CSEC-0003 | Q24050972-04-6253-C-SEC-0003 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Corrosion Prevention and Protection Design | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SEC | 0004 | A | 6105AK124-6253-CSEC-0004 | Q24050972-04-6253-C-SEC-0004 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Structural Earthing and Bonding Design | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SEC | 0005 | A | 6105AK124-6253-CSEC-0005 | Q24050972-04-6253-C-SEC-0005 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Corrosion Prevention and Protection Design | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SEC | 0006 | A | 6105AK124-6253-CSEC-0006 | Q24050972-04-6253-C-SEC-0006 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Structural Earthing and Bonding Design | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SEC | 0007 | A | 6105AK124-6253-CSEC-0007 | Q24050972-04-6253-C-SEC-0007 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Corrosion Prevention and Protection Design | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SEC | 0008 | A | 6105AK124-6253-CSEC-0008 | Q24050972-04-6253-C-SEC-0008 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Structural Earthing and Bonding Design | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SEC | 0009 | A | 6105AK124-6253-CSEC-0009 | Q24050972-04-6253-C-SEC-0009 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Corrosion Prevention and Protection Design | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SEC | 0010 | A | 6105AK124-6253-CSEC-0010 | Q24050972-04-6253-C-SEC-0010 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Structural Earthing and Bonding Design | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SHP | 0001 | A | 6105AK124-6253-CSHP-0001 | Q24050972-04-6253-C-SHP-0001 |  | Synchronous Condenser 1 | Offloading Equipment and Spreader Beam for Synchronous Condensers | Equipment Assembly Drawings | Synchronous Condenser 1 - Offloading Equipment and Spreader Beam for Synchronous Condensers - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Synchronous Condensers |  |  |  | Pending
6105A | K124 | 6253 | C | SHP | 0002 | A | 6105AK124-6253-CSHP-0002 | Q24050972-04-6253-C-SHP-0002 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Equipment Assembly Drawings | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SHP | 0003 | A | 6105AK124-6253-CSHP-0003 | Q24050972-04-6253-C-SHP-0003 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Equipment Assembly Drawings | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SPC | 0001 | A | 6105AK124-6253-CSPC-0001 | Q24050972-04-6253-C-SPC-0001 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Civil Design Requirements | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SPC | 0002 | A | 6105AK124-6253-CSPC-0002 | Q24050972-04-6253-C-SPC-0002 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Excavation, Trenching and Compacting Design | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SPC | 0003 | A | 6105AK124-6253-CSPC-0003 | Q24050972-04-6253-C-SPC-0003 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Concrete Construction Material Specifications | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SPC | 0004 | A | 6105AK124-6253-CSPC-0004 | Q24050972-04-6253-C-SPC-0004 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Concrete Construction Material Specifications | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SPC | 0005 | A | 6105AK124-6253-CSPC-0005 | Q24050972-04-6253-C-SPC-0005 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Excavation, Trenching and Compacting Design | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SPC | 0006 | A | 6105AK124-6253-CSPC-0006 | Q24050972-04-6253-C-SPC-0006 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Concrete Construction Material Specifications | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SPC | 0007 | A | 6105AK124-6253-CSPC-0007 | Q24050972-04-6253-C-SPC-0007 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Civil Design Requirements | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SPC | 0008 | A | 6105AK124-6253-CSPC-0008 | Q24050972-04-6253-C-SPC-0008 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Concrete Construction Material Specifications | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SPC | 0009 | A | 6105AK124-6253-CSPC-0009 | Q24050972-04-6253-C-SPC-0009 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Steel Structures Corrosion Protection Specification | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SPC | 0010 | A | 6105AK124-6253-CSPC-0010 | Q24050972-04-6253-C-SPC-0010 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Civil Design Requirements | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SPC | 0011 | A | 6105AK124-6253-CSPC-0011 | Q24050972-04-6253-C-SPC-0011 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Excavation, Trenching and Compacting Design | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SPC | 0012 | A | 6105AK124-6253-CSPC-0012 | Q24050972-04-6253-C-SPC-0012 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Concrete Construction Material Specifications | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | SSD | 0001 | A | 6105AK124-6253-CSSD-0001 | Q24050972-04-6253-C-SSD-0001 |  | Synchronous Condenser 1 | Offloading Equipment and Spreader Beam for Synchronous Condensers | Steel Support Structures Design | Synchronous Condenser 1 - Offloading Equipment and Spreader Beam for Synchronous Condensers - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Synchronous Condensers |  |  |  | Pending
6105A | K124 | 6253 | C | SSD | 0002 | A | 6105AK124-6253-CSSD-0002 | Q24050972-04-6253-C-SSD-0002 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Steel Support Structures Design | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | STD | 0001 | A | 6105AK124-6253-CSTD-0001 | Q24050972-04-6253-C-STD-0001 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Bund-wall Requirements and Design | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | STD | 0002 | A | 6105AK124-6253-CSTD-0002 | Q24050972-04-6253-C-STD-0002 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Civil Construction Requirements | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | STD | 0003 | A | 6105AK124-6253-CSTD-0003 | Q24050972-04-6253-C-STD-0003 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Underground Pipe Route and Cable Bedding Design | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | STD | 0004 | A | 6105AK124-6253-CSTD-0004 | Q24050972-04-6253-C-STD-0004 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Civil Construction Requirements | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | STD | 0005 | A | 6105AK124-6253-CSTD-0005 | Q24050972-04-6253-C-STD-0005 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Underground Pipe Route and Cable Bedding Design | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | STD | 0006 | A | 6105AK124-6253-CSTD-0006 | Q24050972-04-6253-C-STD-0006 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Underground Pipe Route and Cable Bedding Design | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | STD | 0007 | A | 6105AK124-6253-CSTD-0007 | Q24050972-04-6253-C-STD-0007 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Civil Construction Requirements | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | STD | 0008 | A | 6105AK124-6253-CSTD-0008 | Q24050972-04-6253-C-STD-0008 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Underground Pipe Route and Cable Bedding Design | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | STD | 0009 | A | 6105AK124-6253-CSTD-0009 | Q24050972-04-6253-C-STD-0009 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Civil Construction Requirements | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | C | STD | 0010 | A | 6105AK124-6253-CSTD-0010 | Q24050972-04-6253-C-STD-0010 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Underground Pipe Route and Cable Bedding Design | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | CAL | 0001 | A | 6105AK124-6253-ECAL-0001 | Q24050972-04-6253-E-CAL-0001 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Conductor Sag and Tension Plan | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | CAL | 0002 | A | 6105AK124-6253-ECAL-0002 | Q24050972-04-6253-E-CAL-0002 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Cable and Conductor Sizing (incl Volt Drop Calcs) | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | CAL | 0003 | A | 6105AK124-6253-ECAL-0003 | Q24050972-04-6253-E-CAL-0003 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Impedance and Burn-off Calculations | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | CAL | 0004 | A | 6105AK124-6253-ECAL-0004 | Q24050972-04-6253-E-CAL-0004 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Cable and Conductor Sizing (incl Volt Drop Calcs) | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | CAL | 0005 | A | 6105AK124-6253-ECAL-0005 | Q24050972-04-6253-E-CAL-0005 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Conductor Sag and Tension Plan | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | CAL | 0006 | A | 6105AK124-6253-ECAL-0006 | Q24050972-04-6253-E-CAL-0006 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Impedance and Burn-off Calculations | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0001 | A | 6105AK124-6253-EDIA-0001 | Q24050972-04-6253-E-DIA-0001 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Electrical Circuit Diagrams (Schematics) | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0002 | A | 6105AK124-6253-EDIA-0002 | Q24050972-04-6253-E-DIA-0002 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Cable Block Diagrams and Schedules | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0003 | A | 6105AK124-6253-EDIA-0003 | Q24050972-04-6253-E-DIA-0003 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | E/I Termination Schedule | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0004 | A | 6105AK124-6253-EDIA-0004 | Q24050972-04-6253-E-DIA-0004 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Cable Block Diagrams and Schedules | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0005 | A | 6105AK124-6253-EDIA-0005 | Q24050972-04-6253-E-DIA-0005 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Electrical Block Diagram | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0006 | A | 6105AK124-6253-EDIA-0006 | Q24050972-04-6253-E-DIA-0006 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Electrical Circuit Diagrams (Schematics) | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0007 | A | 6105AK124-6253-EDIA-0007 | Q24050972-04-6253-E-DIA-0007 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | E/I Termination Schedule | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0008 | A | 6105AK124-6253-EDIA-0008 | Q24050972-04-6253-E-DIA-0008 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Cable Block Diagrams and Schedules | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0009 | A | 6105AK124-6253-EDIA-0009 | Q24050972-04-6253-E-DIA-0009 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | E/I Termination Schedule | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0010 | A | 6105AK124-6253-EDIA-0010 | Q24050972-04-6253-E-DIA-0010 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Cable Block Diagrams and Schedules | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0011 | A | 6105AK124-6253-EDIA-0011 | Q24050972-04-6253-E-DIA-0011 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | E/I Termination Schedule | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0012 | A | 6105AK124-6253-EDIA-0012 | Q24050972-04-6253-E-DIA-0012 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Cable Block Diagrams and Schedules | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DIA | 0013 | A | 6105AK124-6253-EDIA-0013 | Q24050972-04-6253-E-DIA-0013 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Electrical Circuit Diagrams (Schematics) | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 0000 | B | CON | 0004 | A | 6105AK124-0000-BCON-0004 | Q24050972-04-0000-B-CON-0004 |  | General | Formal Letter: Employer's Default Isak Mare | General | General - Formal Letter: Employer's Default Isak Mare - General | 2026-05-08 |  | IFR - Issued for Review | Acknowledged (Information Only) | 33.33% | JV |  |  | Notice of Intent to Claim | General |  |  |  | Pending
6105A | K124 | 6200 | B | LST | 0001 | 0 | 6105AK124-6200-BLST-0001 | Q24050972-04-6200-B-LST-0001 |  | On-Site Power Supply and Transmission | Interface Control Register (ICR) - April 2026 | Register | On-Site Power Supply and Transmission - Interface Control Register (ICR) - April 2026 - Register |  | 2026-05-12 | IFI - Issued for Information | Pending | 0% | VV |  |  | Interface Control Register | Register |  |  |  | Pending
6105A | K124 | 6200 | C | LAY | 0015 | A | 6105AK124-6200-CLAY-0015 | Q24050972-04-6200-C-LAY-0015 |  | On-Site Power Supply and Transmission | Main Consumer Substation | PPE temporary facilities layout | On-Site Power Supply and Transmission - Main Consumer Substation - PPE temporary facilities layout |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-15 | Main Consumer Substation | layout |  |  |  | Pending
6105A | K124 | 6280 | C | LAY | 0001 | A | 6105AK124-6280-CLAY-0001 | Q24050972-04-6280-C-LAY-0001 |  | Medium Voltage (33 kV) Overhead Powerlines | Right of way & Maintenace road | Layout | Medium Voltage (33 kV) Overhead Powerlines - Right of way & Maintenace road - Layout | 2026-05-11 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | CLR |  |  | Maintenace road | Layout |  |  |  | Pending
6105A | K124 | 6253 | E | DST | 0001 | A | 6105AK124-6253-EDST-0001 | Q24050972-04-6253-E-DST-0001 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Equipment Register and Technical Specifications | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DST | 0002 | A | 6105AK124-6253-EDST-0002 | Q24050972-04-6253-E-DST-0002 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Equipment Register and Technical Specifications | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DST | 0003 | A | 6105AK124-6253-EDST-0003 | Q24050972-04-6253-E-DST-0003 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Equipment Register and Technical Specifications | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DST | 0004 | A | 6105AK124-6253-EDST-0004 | Q24050972-04-6253-E-DST-0004 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Equipment Register and Technical Specifications | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | DST | 0005 | A | 6105AK124-6253-EDST-0005 | Q24050972-04-6253-E-DST-0005 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Equipment Register and Technical Specifications | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6280 | C | DTL | 0001 | A | 6105AK124-6280-CDTL-0001 | Q24050972-04-6280-C-DTL-0001 | Sht. 1 of 6 | Medium Voltage (33 kV) Overhead Powerlines | Right of way & Maintenace road | Detail | Medium Voltage (33 kV) Overhead Powerlines - Right of way & Maintenace road - Detail - Sht. 1 of 6 | 2026-05-11 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | CLR |  |  | Maintenace road | Detail |  |  |  | Pending
6105A | K124 | 6280 | C | DTL | 0002 | A | 6105AK124-6280-CDTL-0002 | Q24050972-04-6280-C-DTL-0002 | Sht. 2 of 6 | Medium Voltage (33 kV) Overhead Powerlines | Right of way & Maintenace road | Detail | Medium Voltage (33 kV) Overhead Powerlines - Right of way & Maintenace road - Detail - Sht. 2 of 6 | 2026-05-11 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | CLR |  |  | Maintenace road | Detail |  |  |  | Pending
6105A | K124 | 6280 | C | DTL | 0003 | A | 6105AK124-6280-CDTL-0003 | Q24050972-04-6280-C-DTL-0003 | Sht. 3 of 6 | Medium Voltage (33 kV) Overhead Powerlines | Right of way & Maintenace road | Detail | Medium Voltage (33 kV) Overhead Powerlines - Right of way & Maintenace road - Detail - Sht. 3 of 6 | 2026-05-11 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | CLR |  |  | Maintenace road | Detail |  |  |  | Pending
6105A | K124 | 6280 | C | DTL | 0004 | A | 6105AK124-6280-CDTL-0004 | Q24050972-04-6280-C-DTL-0004 | Sht. 4 of 6 | Medium Voltage (33 kV) Overhead Powerlines | Right of way & Maintenace road | Detail | Medium Voltage (33 kV) Overhead Powerlines - Right of way & Maintenace road - Detail - Sht. 4 of 6 | 2026-05-11 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | CLR |  |  | Maintenace road | Detail |  |  |  | Pending
6105A | K124 | 6280 | C | DTL | 0005 | A | 6105AK124-6280-CDTL-0005 | Q24050972-04-6280-C-DTL-0005 | Sht. 5 of 6 | Medium Voltage (33 kV) Overhead Powerlines | Right of way & Maintenace road | Detail | Medium Voltage (33 kV) Overhead Powerlines - Right of way & Maintenace road - Detail - Sht. 5 of 6 | 2026-05-11 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | CLR |  |  | Maintenace road | Detail |  |  |  | Pending
6105A | K124 | 6280 | C | DTL | 0006 | A | 6105AK124-6280-CDTL-0006 | Q24050972-04-6280-C-DTL-0006 | Sht. 6 of 6 | Medium Voltage (33 kV) Overhead Powerlines | Right of way & Maintenace road | Detail | Medium Voltage (33 kV) Overhead Powerlines - Right of way & Maintenace road - Detail - Sht. 6 of 6 | 2026-05-11 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | CLR |  |  | Maintenace road | Detail |  |  |  | Pending
6105A | K124 | 6253 | E | EQL | 0001 | A | 6105AK124-6253-EEQL-0001 | Q24050972-04-6253-E-EQL-0001 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Electrical Equipment Load Register | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | LAY | 0001 | A | 6105AK124-6253-ELAY-0001 | Q24050972-04-6253-E-LAY-0001 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Control Room Power and Earthing Design | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | LAY | 0002 | A | 6105AK124-6253-ELAY-0002 | Q24050972-04-6253-E-LAY-0002 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Control Room Power and Earthing Design | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | LAY | 0003 | A | 6105AK124-6253-ELAY-0003 | Q24050972-04-6253-E-LAY-0003 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Control Room Power and Earthing Design | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | QRA | 0001 | A | 6105AK124-6253-EQRA-0001 | Q24050972-04-6253-E-QRA-0001 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Lightning Protection Study and Risk Assessment | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | QRA | 0002 | A | 6105AK124-6253-EQRA-0002 | Q24050972-04-6253-E-QRA-0002 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Lightning Protection Study and Risk Assessment | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | QRA | 0003 | A | 6105AK124-6253-EQRA-0003 | Q24050972-04-6253-E-QRA-0003 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Risk Assessment: Electrical Hazards | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | QRA | 0004 | A | 6105AK124-6253-EQRA-0004 | Q24050972-04-6253-E-QRA-0004 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Lightning Protection Study and Risk Assessment | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | SLD | 0001 | A | 6105AK124-6253-ESLD-0001 | Q24050972-04-6253-E-SLD-0001 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Electrical Single Line Diagram | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | SLD | 0002 | A | 6105AK124-6253-ESLD-0002 | Q24050972-04-6253-E-SLD-0002 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Electrical Single Line Diagram | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | SLD | 0003 | A | 6105AK124-6253-ESLD-0003 | Q24050972-04-6253-E-SLD-0003 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Electrical Single Line Diagram | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | SPC | 0001 | A | 6105AK124-6253-ESPC-0001 | Q24050972-04-6253-E-SPC-0001 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Cable Termination Specifications | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | SPC | 0002 | A | 6105AK124-6253-ESPC-0002 | Q24050972-04-6253-E-SPC-0002 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Cable and Conductor Specifications | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | SPC | 0003 | A | 6105AK124-6253-ESPC-0003 | Q24050972-04-6253-E-SPC-0003 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Lighting and Luminaire Design | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | SPC | 0004 | A | 6105AK124-6253-ESPC-0004 | Q24050972-04-6253-E-SPC-0004 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Cable and Conductor Specifications | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | SPC | 0005 | A | 6105AK124-6253-ESPC-0005 | Q24050972-04-6253-E-SPC-0005 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Cable and Conductor Specifications | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | SPC | 0006 | A | 6105AK124-6253-ESPC-0006 | Q24050972-04-6253-E-SPC-0006 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Lighting and Luminaire Design | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | STD | 0001 | A | 6105AK124-6253-ESTD-0001 | Q24050972-04-6253-E-STD-0001 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Earth Map and Bonding Design | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | STD | 0002 | A | 6105AK124-6253-ESTD-0002 | Q24050972-04-6253-E-STD-0002 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Electrical Design Standards | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | STD | 0003 | A | 6105AK124-6253-ESTD-0003 | Q24050972-04-6253-E-STD-0003 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Electrical Equipment Installation Requirements | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | STD | 0004 | A | 6105AK124-6253-ESTD-0004 | Q24050972-04-6253-E-STD-0004 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Earth Map and Bonding Design | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | STD | 0005 | A | 6105AK124-6253-ESTD-0005 | Q24050972-04-6253-E-STD-0005 |  | Synchronous Condenser 1 | Small Power and Lighting for Synchronous Condensers Yard 1 | Electrical Design Standards | Synchronous Condenser 1 - Small Power and Lighting for Synchronous Condensers Yard 1 - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | STD | 0006 | A | 6105AK124-6253-ESTD-0006 | Q24050972-04-6253-E-STD-0006 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Thermal Management and Fire Prevention Design | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | STD | 0007 | A | 6105AK124-6253-ESTD-0007 | Q24050972-04-6253-E-STD-0007 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Electrical Equipment Installation Requirements | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | STD | 0008 | A | 6105AK124-6253-ESTD-0008 | Q24050972-04-6253-E-STD-0008 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Electrical Design Standards | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | STD | 0009 | A | 6105AK124-6253-ESTD-0009 | Q24050972-04-6253-E-STD-0009 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Thermal Management and Fire Prevention Design | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | STD | 0010 | A | 6105AK124-6253-ESTD-0010 | Q24050972-04-6253-E-STD-0010 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Electrical Design Standards | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | STD | 0011 | A | 6105AK124-6253-ESTD-0011 | Q24050972-04-6253-E-STD-0011 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Earth Map and Bonding Design | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | E | STD | 0012 | A | 6105AK124-6253-ESTD-0012 | Q24050972-04-6253-E-STD-0012 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Thermal Management and Fire Prevention Design | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | F | DIA | 0001 | A | 6105AK124-6253-FDIA-0001 | Q24050972-04-6253-F-DIA-0001 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Interface Panel and I/O Schematics | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | F | DIA | 0002 | A | 6105AK124-6253-FDIA-0002 | Q24050972-04-6253-F-DIA-0002 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Control Network Architecture Design | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | I | SPC | 0001 | A | 6105AK124-6253-ISPC-0001 | Q24050972-04-6253-I-SPC-0001 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Junction Box and Interface Cabinet Design | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | M | CAL | 0001 | A | 6105AK124-6253-MCAL-0001 | Q24050972-04-6253-M-CAL-0001 |  | Synchronous Condenser 1 | Offloading Equipment and Spreader Beam for Synchronous Condensers | Vessel and Structure Design with Stress Analysis Calcs | Synchronous Condenser 1 - Offloading Equipment and Spreader Beam for Synchronous Condensers - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Synchronous Condensers |  |  |  | Pending
6105A | K124 | 6253 | M | CAL | 0002 | A | 6105AK124-6253-MCAL-0002 | Q24050972-04-6253-M-CAL-0002 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Vessel and Structure Design with Stress Analysis Calcs | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | M | PRC | 0001 | A | 6105AK124-6253-MPRC-0001 | Q24050972-04-6253-M-PRC-0001 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Rigging Study and Lifting Equipment Design | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | M | PSP | 0001 | A | 6105AK124-6253-MPSP-0001 | Q24050972-04-6253-M-PSP-0001 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Pipe and Cable Support Racks Design | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | M | SHP | 0001 | A | 6105AK124-6253-MSHP-0001 | Q24050972-04-6253-M-SHP-0001 |  | Synchronous Condenser 1 | Offloading Equipment and Spreader Beam for Synchronous Condensers | Equipment Fabrication Drawings | Synchronous Condenser 1 - Offloading Equipment and Spreader Beam for Synchronous Condensers - Equipment Fabrication Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Synchronous Condensers |  |  |  | Pending
6105A | K124 | 6253 | M | SPC | 0001 | A | 6105AK124-6253-MSPC-0001 | Q24050972-04-6253-M-SPC-0001 |  | Synchronous Condenser 1 | Offloading Equipment and Spreader Beam for Synchronous Condensers | Lifting and Crawl Beam Design Specification | Synchronous Condenser 1 - Offloading Equipment and Spreader Beam for Synchronous Condensers - Lifting and Crawl Beam Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Synchronous Condensers |  |  |  | Pending
6105A | K124 | 6253 | M | SPC | 0002 | A | 6105AK124-6253-MSPC-0002 | Q24050972-04-6253-M-SPC-0002 |  | Synchronous Condenser 1 | Offloading Equipment and Spreader Beam for Synchronous Condensers | Material Selection and Verification Specification | Synchronous Condenser 1 - Offloading Equipment and Spreader Beam for Synchronous Condensers - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Synchronous Condensers |  |  |  | Pending
6105A | K124 | 6253 | M | SPC | 0003 | A | 6105AK124-6253-MSPC-0003 | Q24050972-04-6253-M-SPC-0003 |  | Synchronous Condenser 1 | Cable Racks and Trays for Synchronous Condensers Yard 1 | Material Selection and Verification Specification | Synchronous Condenser 1 - Cable Racks and Trays for Synchronous Condensers Yard 1 - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | T | RPT | 0001 | A | 6105AK124-6253-TRPT-0001 | Q24050972-04-6253-T-RPT-0001 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Site Surveying & Geotechnical Report | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | T | SPC | 0001 | A | 6105AK124-6253-TSPC-0001 | Q24050972-04-6253-T-SPC-0001 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Civil Design and Requirements | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | T | SPC | 0002 | A | 6105AK124-6253-TSPC-0002 | Q24050972-04-6253-T-SPC-0002 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Civil Design and Requirements | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | W | ELE | 0001 | A | 6105AK124-6253-WELE-0001 | Q24050972-04-6253-W-ELE-0001 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Bulk Earth Works Design and Report | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | W | ELE | 0002 | A | 6105AK124-6253-WELE-0002 | Q24050972-04-6253-W-ELE-0002 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Bulk Earth Works Design and Report | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | W | LAY | 0001 | A | 6105AK124-6253-WLAY-0001 | Q24050972-04-6253-W-LAY-0001 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Drainage, Run-off and Impoundment Design | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | W | LAY | 0002 | A | 6105AK124-6253-WLAY-0002 | Q24050972-04-6253-W-LAY-0002 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Drainage, Run-off and Impoundment Design | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | W | TRP | 0001 | A | 6105AK124-6253-WTRP-0001 | Q24050972-04-6253-W-TRP-0001 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Soil Classification and Nomination Deliverables | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | W | TRP | 0002 | A | 6105AK124-6253-WTRP-0002 | Q24050972-04-6253-W-TRP-0002 |  | Synchronous Condenser 1 | Terrace Roads and Access-ways for Synchronous Condensers Yard 1 | Soil Resistivity Testing Report | Synchronous Condenser 1 - Terrace Roads and Access-ways for Synchronous Condensers Yard 1 - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | W | TRP | 0003 | A | 6105AK124-6253-WTRP-0003 | Q24050972-04-6253-W-TRP-0003 |  | Synchronous Condenser 1 | Earthing System for Synchronous Condensers Yard 1 | Soil Resistivity Testing Report | Synchronous Condenser 1 - Earthing System for Synchronous Condensers Yard 1 - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | W | TRP | 0004 | A | 6105AK124-6253-WTRP-0004 | Q24050972-04-6253-W-TRP-0004 |  | Synchronous Condenser 1 | Cable Trench and Tunnels for Synchronous Condensers Yard 1 | Soil Classification and Nomination Deliverables | Synchronous Condenser 1 - Cable Trench and Tunnels for Synchronous Condensers Yard 1 - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | W | TRP | 0005 | A | 6105AK124-6253-WTRP-0005 | Q24050972-04-6253-W-TRP-0005 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Soil Classification and Nomination Deliverables | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6253 | W | TRP | 0006 | A | 6105AK124-6253-WTRP-0006 | Q24050972-04-6253-W-TRP-0006 |  | Synchronous Condenser 1 | Lightning Protection for Synchronous Condensers Yard 1 | Soil Resistivity Testing Report | Synchronous Condenser 1 - Lightning Protection for Synchronous Condensers Yard 1 - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 1 |  |  |  | Pending
6105A | K124 | 6256 | C | FND | 0001 | A | 6105AK124-6256-CFND-0001 | Q24050972-04-6256-C-FND-0001 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Civil Foundation Design | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | FND | 0002 | A | 6105AK124-6256-CFND-0002 | Q24050972-04-6256-C-FND-0002 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Civil Foundation Design | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0001 | A | 6105AK124-6256-CGAD-0001 | Q24050972-04-6256-C-GAD-0001 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Buildings and Structures GA | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0002 | A | 6105AK124-6256-CGAD-0002 | Q24050972-04-6256-C-GAD-0002 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Cables, OHL and Fibre Route GA | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0003 | A | 6105AK124-6256-CGAD-0003 | Q24050972-04-6256-C-GAD-0003 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Key Emergency Points and Equipment | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0004 | A | 6105AK124-6256-CGAD-0004 | Q24050972-04-6256-C-GAD-0004 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Terrace Equipment GA | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0005 | A | 6105AK124-6256-CGAD-0005 | Q24050972-04-6256-C-GAD-0005 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Disposal Areas General Arrangement | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0006 | A | 6105AK124-6256-CGAD-0006 | Q24050972-04-6256-C-GAD-0006 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Laydown Areas and Temp Buildings GA | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0007 | A | 6105AK124-6256-CGAD-0007 | Q24050972-04-6256-C-GAD-0007 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Stormwater and Effluent System Design | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0008 | A | 6105AK124-6256-CGAD-0008 | Q24050972-04-6256-C-GAD-0008 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Lighting Design and Layout GA | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0009 | A | 6105AK124-6256-CGAD-0009 | Q24050972-04-6256-C-GAD-0009 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Roads, Pathways, Offloading Areas and Fences GA | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0010 | A | 6105AK124-6256-CGAD-0010 | Q24050972-04-6256-C-GAD-0010 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Lighting Design and Layout GA | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0011 | A | 6105AK124-6256-CGAD-0011 | Q24050972-04-6256-C-GAD-0011 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Buildings and Structures GA | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0012 | A | 6105AK124-6256-CGAD-0012 | Q24050972-04-6256-C-GAD-0012 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Cables, OHL and Fibre Route GA | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0013 | A | 6105AK124-6256-CGAD-0013 | Q24050972-04-6256-C-GAD-0013 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Terrace Equipment GA | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0014 | A | 6105AK124-6256-CGAD-0014 | Q24050972-04-6256-C-GAD-0014 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Laydown Areas and Temp Buildings GA | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0015 | A | 6105AK124-6256-CGAD-0015 | Q24050972-04-6256-C-GAD-0015 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Lighting Design and Layout GA | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0016 | A | 6105AK124-6256-CGAD-0016 | Q24050972-04-6256-C-GAD-0016 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Roads, Pathways, Offloading Areas and Fences GA | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0017 | A | 6105AK124-6256-CGAD-0017 | Q24050972-04-6256-C-GAD-0017 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Buildings and Structures GA | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0018 | A | 6105AK124-6256-CGAD-0018 | Q24050972-04-6256-C-GAD-0018 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Cables, OHL and Fibre Route GA | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0019 | A | 6105AK124-6256-CGAD-0019 | Q24050972-04-6256-C-GAD-0019 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Terrace Equipment GA | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0020 | A | 6105AK124-6256-CGAD-0020 | Q24050972-04-6256-C-GAD-0020 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Roads, Pathways, Offloading Areas and Fences GA | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0021 | A | 6105AK124-6256-CGAD-0021 | Q24050972-04-6256-C-GAD-0021 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Buildings and Structures GA | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0022 | A | 6105AK124-6256-CGAD-0022 | Q24050972-04-6256-C-GAD-0022 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Cables, OHL and Fibre Route GA | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0023 | A | 6105AK124-6256-CGAD-0023 | Q24050972-04-6256-C-GAD-0023 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Terrace Equipment GA | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0024 | A | 6105AK124-6256-CGAD-0024 | Q24050972-04-6256-C-GAD-0024 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Buildings and Structures GA | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0025 | A | 6105AK124-6256-CGAD-0025 | Q24050972-04-6256-C-GAD-0025 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Cables, OHL and Fibre Route GA | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | GAD | 0026 | A | 6105AK124-6256-CGAD-0026 | Q24050972-04-6256-C-GAD-0026 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Terrace Equipment GA | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | MDL | 0001 | A | 6105AK124-6256-CMDL-0001 | Q24050972-04-6256-C-MDL-0001 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | 3D Designs and Drawings | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | MDL | 0002 | A | 6105AK124-6256-CMDL-0002 | Q24050972-04-6256-C-MDL-0002 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | 3D Designs and Drawings | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | MDL | 0003 | A | 6105AK124-6256-CMDL-0003 | Q24050972-04-6256-C-MDL-0003 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | 3D Designs and Drawings | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | MDL | 0004 | A | 6105AK124-6256-CMDL-0004 | Q24050972-04-6256-C-MDL-0004 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | 3D Designs and Drawings | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | MDL | 0005 | A | 6105AK124-6256-CMDL-0005 | Q24050972-04-6256-C-MDL-0005 |  | Synchronous Condenser 2 | Cable Trench / Tunnels for Synchronous Condensers Yard 2 | 3D Designs and Drawings | Synchronous Condenser 2 - Cable Trench / Tunnels for Synchronous Condensers Yard 2 - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | MDL | 0006 | A | 6105AK124-6256-CMDL-0006 | Q24050972-04-6256-C-MDL-0006 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | 3D Designs and Drawings | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | PLN | 0001 | A | 6105AK124-6256-CPLN-0001 | Q24050972-04-6256-C-PLN-0001 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Civil Works Execution Plan | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | PLN | 0002 | A | 6105AK124-6256-CPLN-0002 | Q24050972-04-6256-C-PLN-0002 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Civil Works Execution Plan | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | PLN | 0003 | A | 6105AK124-6256-CPLN-0003 | Q24050972-04-6256-C-PLN-0003 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Civil Works Execution Plan | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6282 | E | DTL | 0001 | A | 6105AK124-6282-EDTL-0001 | Q24050972-04-6282-E-DTL-0001 |  | Potable Water Treatment Plant | 33kV Overhead Line | 33kV OHL Transformer Structure | Potable Water Treatment Plant - 33kV Overhead Line - 33kV OHL Transformer Structure |  |  | RES - Reserved Placeholder | Pending | 0% | TDK |  | 2026-06-15 | 33kV Overhead Line | Transformer Structure |  |  |  | Pending
6105A | K124 | 6262 | E | DST | 0013 | A | 6105AK124-6262-EDST-0013 | Q24050972-04-6262-E-DST-0013 |  | Emergency Power Substation 1 and Control Room 1 | Mini-substation | Mini-substation, 630kVA, 11/0.4kV | Emergency Power Substation 1 and Control Room 1 - Mini-substation - Mini-substation, 630kVA, 11/0.4kV |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-21 | Mini-substation | 630kVA, 11/0.4kV |  |  |  | Pending
6105A | K124 | 0000 | B | CON | 0005 | A | 6105AK124-0000-BCON-0005 | Q24050972-04-0000-B-CON-0005 |  | General | Notice of EMPLOYER'S DELAY | General | General - Notice of EMPLOYER'S DELAY - General | 2026-05-08 |  | IFR - Issued for Review | Pending | 33.33% | JV |  |  | Notice of EMPLOYER'S DELAY | General |  |  |  | Pending
6105A | K124 | 0000 | B | CON | 0006 | A | 6105AK124-0000-BCON-0006 | Q24050972-04-0000-B-CON-0006 |  | General | Notice of Change Management System & Outstanding Variations | General | General - Notice of Change Management System & Outstanding Variations - General | 2026-05-08 |  | IFR - Issued for Review | Pending | 33.33% | JV |  |  | Notice of Change Management System | Outstanding Variations |  |  |  | Pending
6105A | K124 | 6256 | C | PPL | 0004 | A | 6105AK124-6256-CPPL-0004 | Q24050972-04-6256-C-PPL-0004 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Operational & Maint Access Routes Design | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | PPL | 0005 | A | 6105AK124-6256-CPPL-0005 | Q24050972-04-6256-C-PPL-0005 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Operational & Maint Access Routes Design | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | PPL | 0006 | A | 6105AK124-6256-CPPL-0006 | Q24050972-04-6256-C-PPL-0006 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Operational & Maint Access Routes Design | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SEC | 0003 | A | 6105AK124-6256-CSEC-0003 | Q24050972-04-6256-C-SEC-0003 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Corrosion Prevention and Protection Design | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SEC | 0004 | A | 6105AK124-6256-CSEC-0004 | Q24050972-04-6256-C-SEC-0004 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Structural Earthing and Bonding Design | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SEC | 0005 | A | 6105AK124-6256-CSEC-0005 | Q24050972-04-6256-C-SEC-0005 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Corrosion Prevention and Protection Design | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SEC | 0006 | A | 6105AK124-6256-CSEC-0006 | Q24050972-04-6256-C-SEC-0006 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Structural Earthing and Bonding Design | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SEC | 0007 | A | 6105AK124-6256-CSEC-0007 | Q24050972-04-6256-C-SEC-0007 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Corrosion Prevention and Protection Design | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SEC | 0008 | A | 6105AK124-6256-CSEC-0008 | Q24050972-04-6256-C-SEC-0008 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Structural Earthing and Bonding Design | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SEC | 0009 | A | 6105AK124-6256-CSEC-0009 | Q24050972-04-6256-C-SEC-0009 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Corrosion Prevention and Protection Design | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SEC | 0010 | A | 6105AK124-6256-CSEC-0010 | Q24050972-04-6256-C-SEC-0010 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Structural Earthing and Bonding Design | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SHP | 0001 | A | 6105AK124-6256-CSHP-0001 | Q24050972-04-6256-C-SHP-0001 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Equipment Assembly Drawings | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SHP | 0002 | A | 6105AK124-6256-CSHP-0002 | Q24050972-04-6256-C-SHP-0002 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Equipment Assembly Drawings | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SPC | 0001 | A | 6105AK124-6256-CSPC-0001 | Q24050972-04-6256-C-SPC-0001 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Civil Design Requirements | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SPC | 0002 | A | 6105AK124-6256-CSPC-0002 | Q24050972-04-6256-C-SPC-0002 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Excavation, Trenching and Compacting Design | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SPC | 0003 | A | 6105AK124-6256-CSPC-0003 | Q24050972-04-6256-C-SPC-0003 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Concrete Construction Material Specifications | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SPC | 0004 | A | 6105AK124-6256-CSPC-0004 | Q24050972-04-6256-C-SPC-0004 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Concrete Construction Material Specifications | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SPC | 0005 | A | 6105AK124-6256-CSPC-0005 | Q24050972-04-6256-C-SPC-0005 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Excavation, Trenching and Compacting Design | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SPC | 0006 | A | 6105AK124-6256-CSPC-0006 | Q24050972-04-6256-C-SPC-0006 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Concrete Construction Material Specifications | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SPC | 0007 | A | 6105AK124-6256-CSPC-0007 | Q24050972-04-6256-C-SPC-0007 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Civil Design Requirements | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SPC | 0008 | A | 6105AK124-6256-CSPC-0008 | Q24050972-04-6256-C-SPC-0008 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Concrete Construction Material Specifications | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SPC | 0009 | A | 6105AK124-6256-CSPC-0009 | Q24050972-04-6256-C-SPC-0009 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Steel Structures Corrosion Protection Specification | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SPC | 0010 | A | 6105AK124-6256-CSPC-0010 | Q24050972-04-6256-C-SPC-0010 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Civil Design Requirements | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SPC | 0011 | A | 6105AK124-6256-CSPC-0011 | Q24050972-04-6256-C-SPC-0011 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Excavation, Trenching and Compacting Design | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SPC | 0012 | A | 6105AK124-6256-CSPC-0012 | Q24050972-04-6256-C-SPC-0012 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Concrete Construction Material Specifications | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | SSD | 0001 | A | 6105AK124-6256-CSSD-0001 | Q24050972-04-6256-C-SSD-0001 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Steel Support Structures Design | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | STD | 0001 | A | 6105AK124-6256-CSTD-0001 | Q24050972-04-6256-C-STD-0001 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Bund-wall Requirements and Design | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | STD | 0002 | A | 6105AK124-6256-CSTD-0002 | Q24050972-04-6256-C-STD-0002 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Civil Construction Requirements | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | STD | 0003 | A | 6105AK124-6256-CSTD-0003 | Q24050972-04-6256-C-STD-0003 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Underground Pipe Route and Cable Bedding Design | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | STD | 0004 | A | 6105AK124-6256-CSTD-0004 | Q24050972-04-6256-C-STD-0004 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Civil Construction Requirements | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | STD | 0005 | A | 6105AK124-6256-CSTD-0005 | Q24050972-04-6256-C-STD-0005 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Underground Pipe Route and Cable Bedding Design | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | STD | 0006 | A | 6105AK124-6256-CSTD-0006 | Q24050972-04-6256-C-STD-0006 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Underground Pipe Route and Cable Bedding Design | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | STD | 0007 | A | 6105AK124-6256-CSTD-0007 | Q24050972-04-6256-C-STD-0007 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Civil Construction Requirements | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | STD | 0008 | A | 6105AK124-6256-CSTD-0008 | Q24050972-04-6256-C-STD-0008 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Underground Pipe Route and Cable Bedding Design | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | STD | 0009 | A | 6105AK124-6256-CSTD-0009 | Q24050972-04-6256-C-STD-0009 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Civil Construction Requirements | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | C | STD | 0010 | A | 6105AK124-6256-CSTD-0010 | Q24050972-04-6256-C-STD-0010 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Underground Pipe Route and Cable Bedding Design | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6282 | E | DTL | 0002 | A | 6105AK124-6282-EDTL-0002 | Q24050972-04-6282-E-DTL-0002 |  | Potable Water Treatment Plant | 33kV Overhead Line | 33kV OHL Termination Pole | Potable Water Treatment Plant - 33kV Overhead Line - 33kV OHL Termination Pole |  |  | RES - Reserved Placeholder | Pending | 0% | TDK |  | 2026-06-15 | 33kV Overhead Line | Termination Pole |  |  |  | Pending
6105A | K124 | 6256 | E | CAL | 0001 | A | 6105AK124-6256-ECAL-0001 | Q24050972-04-6256-E-CAL-0001 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Conductor Sag and Tension Plan | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | CAL | 0002 | A | 6105AK124-6256-ECAL-0002 | Q24050972-04-6256-E-CAL-0002 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Cable and Conductor Sizing (incl Volt Drop Calcs) | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | CAL | 0003 | A | 6105AK124-6256-ECAL-0003 | Q24050972-04-6256-E-CAL-0003 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Impedance and Burn-off Calculations | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | CAL | 0004 | A | 6105AK124-6256-ECAL-0004 | Q24050972-04-6256-E-CAL-0004 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Cable and Conductor Sizing (incl Volt Drop Calcs) | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | CAL | 0005 | A | 6105AK124-6256-ECAL-0005 | Q24050972-04-6256-E-CAL-0005 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Conductor Sag and Tension Plan | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | CAL | 0006 | A | 6105AK124-6256-ECAL-0006 | Q24050972-04-6256-E-CAL-0006 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Impedance and Burn-off Calculations | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0001 | A | 6105AK124-6256-EDIA-0001 | Q24050972-04-6256-E-DIA-0001 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Electrical Circuit Diagrams (Schematics) | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0002 | A | 6105AK124-6256-EDIA-0002 | Q24050972-04-6256-E-DIA-0002 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Cable Block Diagrams and Schedules | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0003 | A | 6105AK124-6256-EDIA-0003 | Q24050972-04-6256-E-DIA-0003 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | E/I Termination Schedule | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0004 | A | 6105AK124-6256-EDIA-0004 | Q24050972-04-6256-E-DIA-0004 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Cable Block Diagrams and Schedules | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0005 | A | 6105AK124-6256-EDIA-0005 | Q24050972-04-6256-E-DIA-0005 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Electrical Block Diagram | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0006 | A | 6105AK124-6256-EDIA-0006 | Q24050972-04-6256-E-DIA-0006 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Electrical Circuit Diagrams (Schematics) | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0007 | A | 6105AK124-6256-EDIA-0007 | Q24050972-04-6256-E-DIA-0007 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | E/I Termination Schedule | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0008 | A | 6105AK124-6256-EDIA-0008 | Q24050972-04-6256-E-DIA-0008 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Cable Block Diagrams and Schedules | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0009 | A | 6105AK124-6256-EDIA-0009 | Q24050972-04-6256-E-DIA-0009 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | E/I Termination Schedule | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0010 | A | 6105AK124-6256-EDIA-0010 | Q24050972-04-6256-E-DIA-0010 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Cable Block Diagrams and Schedules | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0011 | A | 6105AK124-6256-EDIA-0011 | Q24050972-04-6256-E-DIA-0011 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | E/I Termination Schedule | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0012 | A | 6105AK124-6256-EDIA-0012 | Q24050972-04-6256-E-DIA-0012 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Cable Block Diagrams and Schedules | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DIA | 0013 | A | 6105AK124-6256-EDIA-0013 | Q24050972-04-6256-E-DIA-0013 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Electrical Circuit Diagrams (Schematics) | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DST | 0001 | A | 6105AK124-6256-EDST-0001 | Q24050972-04-6256-E-DST-0001 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Equipment Register and Technical Specifications | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DST | 0002 | A | 6105AK124-6256-EDST-0002 | Q24050972-04-6256-E-DST-0002 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Equipment Register and Technical Specifications | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DST | 0003 | A | 6105AK124-6256-EDST-0003 | Q24050972-04-6256-E-DST-0003 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Equipment Register and Technical Specifications | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DST | 0004 | A | 6105AK124-6256-EDST-0004 | Q24050972-04-6256-E-DST-0004 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Equipment Register and Technical Specifications | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | DST | 0005 | A | 6105AK124-6256-EDST-0005 | Q24050972-04-6256-E-DST-0005 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Equipment Register and Technical Specifications | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | EQL | 0001 | A | 6105AK124-6256-EEQL-0001 | Q24050972-04-6256-E-EQL-0001 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Electrical Equipment Load Register | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | LAY | 0001 | A | 6105AK124-6256-ELAY-0001 | Q24050972-04-6256-E-LAY-0001 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Control Room Power and Earthing Design | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | LAY | 0002 | A | 6105AK124-6256-ELAY-0002 | Q24050972-04-6256-E-LAY-0002 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Control Room Power and Earthing Design | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | LAY | 0003 | A | 6105AK124-6256-ELAY-0003 | Q24050972-04-6256-E-LAY-0003 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Control Room Power and Earthing Design | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | QRA | 0001 | A | 6105AK124-6256-EQRA-0001 | Q24050972-04-6256-E-QRA-0001 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Lightning Protection Study and Risk Assessment | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | QRA | 0002 | A | 6105AK124-6256-EQRA-0002 | Q24050972-04-6256-E-QRA-0002 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Lightning Protection Study and Risk Assessment | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | QRA | 0003 | A | 6105AK124-6256-EQRA-0003 | Q24050972-04-6256-E-QRA-0003 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Risk Assessment: Electrical Hazards | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | QRA | 0004 | A | 6105AK124-6256-EQRA-0004 | Q24050972-04-6256-E-QRA-0004 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Lightning Protection Study and Risk Assessment | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | SLD | 0001 | A | 6105AK124-6256-ESLD-0001 | Q24050972-04-6256-E-SLD-0001 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Electrical Single Line Diagram | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | SLD | 0002 | A | 6105AK124-6256-ESLD-0002 | Q24050972-04-6256-E-SLD-0002 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Electrical Single Line Diagram | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | SLD | 0003 | A | 6105AK124-6256-ESLD-0003 | Q24050972-04-6256-E-SLD-0003 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Electrical Single Line Diagram | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | SPC | 0001 | A | 6105AK124-6256-ESPC-0001 | Q24050972-04-6256-E-SPC-0001 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Cable Termination Specifications | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | SPC | 0002 | A | 6105AK124-6256-ESPC-0002 | Q24050972-04-6256-E-SPC-0002 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Cable and Conductor Specifications | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | SPC | 0003 | A | 6105AK124-6256-ESPC-0003 | Q24050972-04-6256-E-SPC-0003 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Lighting and Luminaire Design | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | SPC | 0004 | A | 6105AK124-6256-ESPC-0004 | Q24050972-04-6256-E-SPC-0004 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Cable and Conductor Specifications | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | SPC | 0005 | A | 6105AK124-6256-ESPC-0005 | Q24050972-04-6256-E-SPC-0005 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Cable and Conductor Specifications | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | SPC | 0006 | A | 6105AK124-6256-ESPC-0006 | Q24050972-04-6256-E-SPC-0006 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Lighting and Luminaire Design | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | STD | 0001 | A | 6105AK124-6256-ESTD-0001 | Q24050972-04-6256-E-STD-0001 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Earth Map and Bonding Design | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | STD | 0002 | A | 6105AK124-6256-ESTD-0002 | Q24050972-04-6256-E-STD-0002 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Electrical Design Standards | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | STD | 0003 | A | 6105AK124-6256-ESTD-0003 | Q24050972-04-6256-E-STD-0003 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Electrical Equipment Installation Requirements | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | STD | 0004 | A | 6105AK124-6256-ESTD-0004 | Q24050972-04-6256-E-STD-0004 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Earth Map and Bonding Design | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | STD | 0005 | A | 6105AK124-6256-ESTD-0005 | Q24050972-04-6256-E-STD-0005 |  | Synchronous Condenser 2 | Small Power and Lighting for Synchronous Condensers Yard 2 | Electrical Design Standards | Synchronous Condenser 2 - Small Power and Lighting for Synchronous Condensers Yard 2 - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | STD | 0006 | A | 6105AK124-6256-ESTD-0006 | Q24050972-04-6256-E-STD-0006 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Thermal Management and Fire Prevention Design | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | STD | 0007 | A | 6105AK124-6256-ESTD-0007 | Q24050972-04-6256-E-STD-0007 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Electrical Equipment Installation Requirements | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | STD | 0008 | A | 6105AK124-6256-ESTD-0008 | Q24050972-04-6256-E-STD-0008 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Electrical Design Standards | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | STD | 0009 | A | 6105AK124-6256-ESTD-0009 | Q24050972-04-6256-E-STD-0009 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Thermal Management and Fire Prevention Design | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | STD | 0010 | A | 6105AK124-6256-ESTD-0010 | Q24050972-04-6256-E-STD-0010 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Electrical Design Standards | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | STD | 0011 | A | 6105AK124-6256-ESTD-0011 | Q24050972-04-6256-E-STD-0011 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Earth Map and Bonding Design | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | E | STD | 0012 | A | 6105AK124-6256-ESTD-0012 | Q24050972-04-6256-E-STD-0012 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Thermal Management and Fire Prevention Design | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6252 | B | DBD | 0001 | A | 6105AK124-6252-BDBD-0001 | Q24050972-04-6252-B-DBD-0001 |  | Harmonic Filters 1 | Harmonic Filter Project Package | Design Criteria / Basis of Design | Harmonic Filters 1 - Harmonic Filter Project Package - Design Criteria / Basis of Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Harmonic Filter Project Package | Basis of Design |  |  |  | Pending
6105A | K124 | 6252 | B | PHL | 0001 | A | 6105AK124-6252-BPHL-0001 | Q24050972-04-6252-B-PHL-0001 |  | Harmonic Filters 1 | Harmonic Filter Project Package | Control Philosophy | Harmonic Filters 1 - Harmonic Filter Project Package - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Harmonic Filter Project Package | Control Philosophy |  |  |  | Pending
6105A | K124 | 6252 | B | PHL | 0002 | A | 6105AK124-6252-BPHL-0002 | Q24050972-04-6252-B-PHL-0002 |  | Harmonic Filters 1 | Harmonic Filter Project Package | Synchronization Philosophy | Harmonic Filters 1 - Harmonic Filter Project Package - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Harmonic Filter Project Package | Synchronization Philosophy |  |  |  | Pending
6105A | K124 | 6252 | B | SPC | 0001 | A | 6105AK124-6252-BSPC-0001 | Q24050972-04-6252-B-SPC-0001 |  | Harmonic Filters 1 | Harmonic Filter Project Package | Functional Design Specification | Harmonic Filters 1 - Harmonic Filter Project Package - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Harmonic Filter Project Package | Specification |  |  |  | Pending
6105A | K124 | 6252 | B | STD | 0001 | A | 6105AK124-6252-BSTD-0001 | Q24050972-04-6252-B-STD-0001 |  | Harmonic Filters 1 | Harmonic Filter Project Package | System Detailed Engineering Design | Harmonic Filters 1 - Harmonic Filter Project Package - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Harmonic Filter Project Package | Engineering Design |  |  |  | Pending
6105A | K124 | 6252 | C | FND | 0001 | A | 6105AK124-6252-CFND-0001 | Q24050972-04-6252-C-FND-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Civil Foundation Design | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | FND | 0002 | A | 6105AK124-6252-CFND-0002 | Q24050972-04-6252-C-FND-0002 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Civil Foundation Design | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | FND | 0003 | A | 6105AK124-6252-CFND-0003 | Q24050972-04-6252-C-FND-0003 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | Civil Foundation Design | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | FND | 0004 | A | 6105AK124-6252-CFND-0004 | Q24050972-04-6252-C-FND-0004 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Civil Foundation Design | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | FND | 0005 | A | 6105AK124-6252-CFND-0005 | Q24050972-04-6252-C-FND-0005 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Plinth Design and Layout | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0001 | A | 6105AK124-6252-CGAD-0001 | Q24050972-04-6252-C-GAD-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Buildings and Structures GA | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0002 | A | 6105AK124-6252-CGAD-0002 | Q24050972-04-6252-C-GAD-0002 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Cables, OHL and Fibre Route GA | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0003 | A | 6105AK124-6252-CGAD-0003 | Q24050972-04-6252-C-GAD-0003 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Terrace Equipment GA | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0004 | A | 6105AK124-6252-CGAD-0004 | Q24050972-04-6252-C-GAD-0004 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Laydown Areas and Temp Buildings GA | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0005 | A | 6105AK124-6252-CGAD-0005 | Q24050972-04-6252-C-GAD-0005 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Lighting Design and Layout GA | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0006 | A | 6105AK124-6252-CGAD-0006 | Q24050972-04-6252-C-GAD-0006 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Roads, Pathways, Offloading Areas and Fences GA | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0007 | A | 6105AK124-6252-CGAD-0007 | Q24050972-04-6252-C-GAD-0007 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Buildings and Structures GA | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0008 | A | 6105AK124-6252-CGAD-0008 | Q24050972-04-6252-C-GAD-0008 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Cables, OHL and Fibre Route GA | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0009 | A | 6105AK124-6252-CGAD-0009 | Q24050972-04-6252-C-GAD-0009 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Terrace Equipment GA | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0010 | A | 6105AK124-6252-CGAD-0010 | Q24050972-04-6252-C-GAD-0010 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Roads, Pathways, Offloading Areas and Fences GA | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0011 | A | 6105AK124-6252-CGAD-0011 | Q24050972-04-6252-C-GAD-0011 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Buildings and Structures GA | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0012 | A | 6105AK124-6252-CGAD-0012 | Q24050972-04-6252-C-GAD-0012 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Cables, OHL and Fibre Route GA | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0013 | A | 6105AK124-6252-CGAD-0013 | Q24050972-04-6252-C-GAD-0013 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Terrace Equipment GA | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0014 | A | 6105AK124-6252-CGAD-0014 | Q24050972-04-6252-C-GAD-0014 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Buildings and Structures GA | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0015 | A | 6105AK124-6252-CGAD-0015 | Q24050972-04-6252-C-GAD-0015 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Cables, OHL and Fibre Route GA | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0016 | A | 6105AK124-6252-CGAD-0016 | Q24050972-04-6252-C-GAD-0016 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Terrace Equipment GA | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0017 | A | 6105AK124-6252-CGAD-0017 | Q24050972-04-6252-C-GAD-0017 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Lighting Design and Layout GA | Harmonic Filters 1 - Earthing System for Harmonic Filters - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0018 | A | 6105AK124-6252-CGAD-0018 | Q24050972-04-6252-C-GAD-0018 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Fire Detection and Suppression System | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0019 | A | 6105AK124-6252-CGAD-0019 | Q24050972-04-6252-C-GAD-0019 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | Roads, Pathways, Offloading Areas and Fences GA | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0020 | A | 6105AK124-6252-CGAD-0020 | Q24050972-04-6252-C-GAD-0020 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | Lighting Design and Layout GA | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0021 | A | 6105AK124-6252-CGAD-0021 | Q24050972-04-6252-C-GAD-0021 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | Cables, OHL and Fibre Route GA | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0022 | A | 6105AK124-6252-CGAD-0022 | Q24050972-04-6252-C-GAD-0022 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Buildings and Structures GA | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0023 | A | 6105AK124-6252-CGAD-0023 | Q24050972-04-6252-C-GAD-0023 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Cables, OHL and Fibre Route GA | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0024 | A | 6105AK124-6252-CGAD-0024 | Q24050972-04-6252-C-GAD-0024 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Key Emergency Points and Equipment | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0025 | A | 6105AK124-6252-CGAD-0025 | Q24050972-04-6252-C-GAD-0025 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Terrace Equipment GA | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0026 | A | 6105AK124-6252-CGAD-0026 | Q24050972-04-6252-C-GAD-0026 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Disposal Areas General Arrangement | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0027 | A | 6105AK124-6252-CGAD-0027 | Q24050972-04-6252-C-GAD-0027 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Laydown Areas and Temp Buildings GA | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0028 | A | 6105AK124-6252-CGAD-0028 | Q24050972-04-6252-C-GAD-0028 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Stormwater and Effluent System Design | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0029 | A | 6105AK124-6252-CGAD-0029 | Q24050972-04-6252-C-GAD-0029 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Lighting Design and Layout GA | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0030 | A | 6105AK124-6252-CGAD-0030 | Q24050972-04-6252-C-GAD-0030 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Roads, Pathways, Offloading Areas and Fences GA | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0031 | A | 6105AK124-6252-CGAD-0031 | Q24050972-04-6252-C-GAD-0031 |  | Harmonic Filters 1 | Offloading Spreader Beam and Equipment for Harmonic Filters | Terrace Equipment GA | Harmonic Filters 1 - Offloading Spreader Beam and Equipment for Harmonic Filters - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0032 | A | 6105AK124-6252-CGAD-0032 | Q24050972-04-6252-C-GAD-0032 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Buildings and Structures GA | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0033 | A | 6105AK124-6252-CGAD-0033 | Q24050972-04-6252-C-GAD-0033 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Terrace Equipment GA | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0034 | A | 6105AK124-6252-CGAD-0034 | Q24050972-04-6252-C-GAD-0034 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Lighting Design and Layout GA | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0035 | A | 6105AK124-6252-CGAD-0035 | Q24050972-04-6252-C-GAD-0035 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Roads, Pathways, Offloading Areas and Fences GA | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | GAD | 0036 | A | 6105AK124-6252-CGAD-0036 | Q24050972-04-6252-C-GAD-0036 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Stormwater and Effluent System Design | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | MDL | 0001 | A | 6105AK124-6252-CMDL-0001 | Q24050972-04-6252-C-MDL-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | 3D Designs and Drawings | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | MDL | 0002 | A | 6105AK124-6252-CMDL-0002 | Q24050972-04-6252-C-MDL-0002 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | 3D Designs and Drawings | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | MDL | 0003 | A | 6105AK124-6252-CMDL-0003 | Q24050972-04-6252-C-MDL-0003 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | 3D Designs and Drawings | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | MDL | 0004 | A | 6105AK124-6252-CMDL-0004 | Q24050972-04-6252-C-MDL-0004 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | 3D Designs and Drawings | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | MDL | 0005 | A | 6105AK124-6252-CMDL-0005 | Q24050972-04-6252-C-MDL-0005 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | 3D Designs and Drawings | Harmonic Filters 1 - Earthing System for Harmonic Filters - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | MDL | 0006 | A | 6105AK124-6252-CMDL-0006 | Q24050972-04-6252-C-MDL-0006 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | 3D Designs and Drawings | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | MDL | 0007 | A | 6105AK124-6252-CMDL-0007 | Q24050972-04-6252-C-MDL-0007 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | 3D Designs and Drawings | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | MDL | 0008 | A | 6105AK124-6252-CMDL-0008 | Q24050972-04-6252-C-MDL-0008 |  | Harmonic Filters 1 | Offloading Spreader Beam and Equipment for Harmonic Filters | 3D Designs and Drawings | Harmonic Filters 1 - Offloading Spreader Beam and Equipment for Harmonic Filters - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | MDL | 0009 | A | 6105AK124-6252-CMDL-0009 | Q24050972-04-6252-C-MDL-0009 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | 3D Designs and Drawings | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | PLN | 0001 | A | 6105AK124-6252-CPLN-0001 | Q24050972-04-6252-C-PLN-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Civil Works Execution Plan | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | PLN | 0002 | A | 6105AK124-6252-CPLN-0002 | Q24050972-04-6252-C-PLN-0002 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Civil Works Execution Plan | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | PLN | 0003 | A | 6105AK124-6252-CPLN-0003 | Q24050972-04-6252-C-PLN-0003 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Civil Works Execution Plan | Harmonic Filters 1 - Earthing System for Harmonic Filters - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | PLN | 0004 | A | 6105AK124-6252-CPLN-0004 | Q24050972-04-6252-C-PLN-0004 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Civil Works Execution Plan | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | PPL | 0001 | A | 6105AK124-6252-CPPL-0001 | Q24050972-04-6252-C-PPL-0001 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Operational & Maint Access Routes Design | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | PPL | 0002 | A | 6105AK124-6252-CPPL-0002 | Q24050972-04-6252-C-PPL-0002 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Operational & Maint Access Routes Design | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | PPL | 0003 | A | 6105AK124-6252-CPPL-0003 | Q24050972-04-6252-C-PPL-0003 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Operational & Maint Access Routes Design | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | PPL | 0004 | A | 6105AK124-6252-CPPL-0004 | Q24050972-04-6252-C-PPL-0004 |  | Harmonic Filters 1 | Offloading Spreader Beam and Equipment for Harmonic Filters | Operational & Maint Access Routes Design | Harmonic Filters 1 - Offloading Spreader Beam and Equipment for Harmonic Filters - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SEC | 0001 | A | 6105AK124-6252-CSEC-0001 | Q24050972-04-6252-C-SEC-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Corrosion Prevention and Protection Design | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SEC | 0002 | A | 6105AK124-6252-CSEC-0002 | Q24050972-04-6252-C-SEC-0002 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Structural Earthing and Bonding Design | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SEC | 0003 | A | 6105AK124-6252-CSEC-0003 | Q24050972-04-6252-C-SEC-0003 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Corrosion Prevention and Protection Design | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SEC | 0004 | A | 6105AK124-6252-CSEC-0004 | Q24050972-04-6252-C-SEC-0004 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Structural Earthing and Bonding Design | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SEC | 0005 | A | 6105AK124-6252-CSEC-0005 | Q24050972-04-6252-C-SEC-0005 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Corrosion Prevention and Protection Design | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SEC | 0006 | A | 6105AK124-6252-CSEC-0006 | Q24050972-04-6252-C-SEC-0006 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Structural Earthing and Bonding Design | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SEC | 0007 | A | 6105AK124-6252-CSEC-0007 | Q24050972-04-6252-C-SEC-0007 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Corrosion Prevention and Protection Design | Harmonic Filters 1 - Earthing System for Harmonic Filters - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SEC | 0008 | A | 6105AK124-6252-CSEC-0008 | Q24050972-04-6252-C-SEC-0008 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Structural Earthing and Bonding Design | Harmonic Filters 1 - Earthing System for Harmonic Filters - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SEC | 0009 | A | 6105AK124-6252-CSEC-0009 | Q24050972-04-6252-C-SEC-0009 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Corrosion Prevention and Protection Design | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SHP | 0001 | A | 6105AK124-6252-CSHP-0001 | Q24050972-04-6252-C-SHP-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Equipment Assembly Drawings | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SHP | 0002 | A | 6105AK124-6252-CSHP-0002 | Q24050972-04-6252-C-SHP-0002 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Equipment Assembly Drawings | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SHP | 0003 | A | 6105AK124-6252-CSHP-0003 | Q24050972-04-6252-C-SHP-0003 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | Equipment Assembly Drawings | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SHP | 0004 | A | 6105AK124-6252-CSHP-0004 | Q24050972-04-6252-C-SHP-0004 |  | Harmonic Filters 1 | Offloading Spreader Beam and Equipment for Harmonic Filters | Equipment Assembly Drawings | Harmonic Filters 1 - Offloading Spreader Beam and Equipment for Harmonic Filters - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0001 | A | 6105AK124-6252-CSPC-0001 | Q24050972-04-6252-C-SPC-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Concrete Construction Material Specifications | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0002 | A | 6105AK124-6252-CSPC-0002 | Q24050972-04-6252-C-SPC-0002 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Civil Design Requirements | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0003 | A | 6105AK124-6252-CSPC-0003 | Q24050972-04-6252-C-SPC-0003 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Concrete Construction Material Specifications | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0004 | A | 6105AK124-6252-CSPC-0004 | Q24050972-04-6252-C-SPC-0004 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Steel Structures Corrosion Protection Specification | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0005 | A | 6105AK124-6252-CSPC-0005 | Q24050972-04-6252-C-SPC-0005 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Civil Design Requirements | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0006 | A | 6105AK124-6252-CSPC-0006 | Q24050972-04-6252-C-SPC-0006 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Excavation, Trenching and Compacting Design | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0007 | A | 6105AK124-6252-CSPC-0007 | Q24050972-04-6252-C-SPC-0007 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Concrete Construction Material Specifications | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0008 | A | 6105AK124-6252-CSPC-0008 | Q24050972-04-6252-C-SPC-0008 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Concrete Construction Material Specifications | Harmonic Filters 1 - Earthing System for Harmonic Filters - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0009 | A | 6105AK124-6252-CSPC-0009 | Q24050972-04-6252-C-SPC-0009 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Excavation, Trenching and Compacting Design | Harmonic Filters 1 - Earthing System for Harmonic Filters - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0010 | A | 6105AK124-6252-CSPC-0010 | Q24050972-04-6252-C-SPC-0010 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | Excavation, Trenching and Compacting Design | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0011 | A | 6105AK124-6252-CSPC-0011 | Q24050972-04-6252-C-SPC-0011 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | Concrete Construction Material Specifications | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0012 | A | 6105AK124-6252-CSPC-0012 | Q24050972-04-6252-C-SPC-0012 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | Steel Structures Corrosion Protection Specification | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0013 | A | 6105AK124-6252-CSPC-0013 | Q24050972-04-6252-C-SPC-0013 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Civil Design Requirements | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0014 | A | 6105AK124-6252-CSPC-0014 | Q24050972-04-6252-C-SPC-0014 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Excavation, Trenching and Compacting Design | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0015 | A | 6105AK124-6252-CSPC-0015 | Q24050972-04-6252-C-SPC-0015 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Concrete Construction Material Specifications | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0016 | A | 6105AK124-6252-CSPC-0016 | Q24050972-04-6252-C-SPC-0016 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Civil Design Requirements | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0017 | A | 6105AK124-6252-CSPC-0017 | Q24050972-04-6252-C-SPC-0017 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Excavation, Trenching and Compacting Design | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SPC | 0018 | A | 6105AK124-6252-CSPC-0018 | Q24050972-04-6252-C-SPC-0018 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Concrete Construction Material Specifications | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SSD | 0001 | A | 6105AK124-6252-CSSD-0001 | Q24050972-04-6252-C-SSD-0001 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Steel Support Structures Design | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SSD | 0002 | A | 6105AK124-6252-CSSD-0002 | Q24050972-04-6252-C-SSD-0002 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | Steel Support Structures Design | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SSD | 0003 | A | 6105AK124-6252-CSSD-0003 | Q24050972-04-6252-C-SSD-0003 |  | Harmonic Filters 1 | Offloading Spreader Beam and Equipment for Harmonic Filters | Steel Support Structures Design | Harmonic Filters 1 - Offloading Spreader Beam and Equipment for Harmonic Filters - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | SSD | 0004 | A | 6105AK124-6252-CSSD-0004 | Q24050972-04-6252-C-SSD-0004 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Steel Support Structures Design | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0001 | A | 6105AK124-6252-CSTD-0001 | Q24050972-04-6252-C-STD-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Civil Construction Requirements | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0002 | A | 6105AK124-6252-CSTD-0002 | Q24050972-04-6252-C-STD-0002 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Underground Pipe Route and Cable Bedding Design | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0003 | A | 6105AK124-6252-CSTD-0003 | Q24050972-04-6252-C-STD-0003 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Underground Pipe Route and Cable Bedding Design | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0004 | A | 6105AK124-6252-CSTD-0004 | Q24050972-04-6252-C-STD-0004 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Civil Construction Requirements | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0005 | A | 6105AK124-6252-CSTD-0005 | Q24050972-04-6252-C-STD-0005 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Underground Pipe Route and Cable Bedding Design | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0006 | A | 6105AK124-6252-CSTD-0006 | Q24050972-04-6252-C-STD-0006 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Civil Construction Requirements | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0007 | A | 6105AK124-6252-CSTD-0007 | Q24050972-04-6252-C-STD-0007 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Underground Pipe Route and Cable Bedding Design | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0008 | A | 6105AK124-6252-CSTD-0008 | Q24050972-04-6252-C-STD-0008 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Fire Protection System Design (Civil Works) | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0009 | A | 6105AK124-6252-CSTD-0009 | Q24050972-04-6252-C-STD-0009 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Civil Construction Requirements | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0010 | A | 6105AK124-6252-CSTD-0010 | Q24050972-04-6252-C-STD-0010 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | Underground Pipe Route and Cable Bedding Design | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0011 | A | 6105AK124-6252-CSTD-0011 | Q24050972-04-6252-C-STD-0011 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Bund-wall Requirements and Design | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0012 | A | 6105AK124-6252-CSTD-0012 | Q24050972-04-6252-C-STD-0012 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Civil Construction Requirements | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0013 | A | 6105AK124-6252-CSTD-0013 | Q24050972-04-6252-C-STD-0013 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Underground Pipe Route and Cable Bedding Design | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | C | STD | 0014 | A | 6105AK124-6252-CSTD-0014 | Q24050972-04-6252-C-STD-0014 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Civil Construction Requirements | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | CAL | 0001 | A | 6105AK124-6252-ECAL-0001 | Q24050972-04-6252-E-CAL-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Cable and Conductor Sizing (incl Volt Drop Calcs) | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | CAL | 0002 | A | 6105AK124-6252-ECAL-0002 | Q24050972-04-6252-E-CAL-0002 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Conductor Sag and Tension Plan | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | CAL | 0003 | A | 6105AK124-6252-ECAL-0003 | Q24050972-04-6252-E-CAL-0003 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Impedance and Burn-off Calculations | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | CAL | 0004 | A | 6105AK124-6252-ECAL-0004 | Q24050972-04-6252-E-CAL-0004 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Cable and Conductor Sizing (incl Volt Drop Calcs) | Harmonic Filters 1 - Earthing System for Harmonic Filters - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | CAL | 0005 | A | 6105AK124-6252-ECAL-0005 | Q24050972-04-6252-E-CAL-0005 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Impedance and Burn-off Calculations | Harmonic Filters 1 - Earthing System for Harmonic Filters - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | CAL | 0006 | A | 6105AK124-6252-ECAL-0006 | Q24050972-04-6252-E-CAL-0006 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Conductor Sag and Tension Plan | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0001 | A | 6105AK124-6252-EDIA-0001 | Q24050972-04-6252-E-DIA-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Cable Block Diagrams and Schedules | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0002 | A | 6105AK124-6252-EDIA-0002 | Q24050972-04-6252-E-DIA-0002 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Electrical Block Diagram | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0003 | A | 6105AK124-6252-EDIA-0003 | Q24050972-04-6252-E-DIA-0003 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Electrical Circuit Diagrams (Schematics) | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0004 | A | 6105AK124-6252-EDIA-0004 | Q24050972-04-6252-E-DIA-0004 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | E/I Termination Schedule | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0005 | A | 6105AK124-6252-EDIA-0005 | Q24050972-04-6252-E-DIA-0005 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Cable Block Diagrams and Schedules | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0006 | A | 6105AK124-6252-EDIA-0006 | Q24050972-04-6252-E-DIA-0006 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | E/I Termination Schedule | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0007 | A | 6105AK124-6252-EDIA-0007 | Q24050972-04-6252-E-DIA-0007 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Cable Block Diagrams and Schedules | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0008 | A | 6105AK124-6252-EDIA-0008 | Q24050972-04-6252-E-DIA-0008 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | E/I Termination Schedule | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0009 | A | 6105AK124-6252-EDIA-0009 | Q24050972-04-6252-E-DIA-0009 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Cable Block Diagrams and Schedules | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0010 | A | 6105AK124-6252-EDIA-0010 | Q24050972-04-6252-E-DIA-0010 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Electrical Circuit Diagrams (Schematics) | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0011 | A | 6105AK124-6252-EDIA-0011 | Q24050972-04-6252-E-DIA-0011 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Electrical Circuit Diagrams (Schematics) | Harmonic Filters 1 - Earthing System for Harmonic Filters - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0012 | A | 6105AK124-6252-EDIA-0012 | Q24050972-04-6252-E-DIA-0012 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Cable Block Diagrams and Schedules | Harmonic Filters 1 - Earthing System for Harmonic Filters - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0013 | A | 6105AK124-6252-EDIA-0013 | Q24050972-04-6252-E-DIA-0013 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | E/I Termination Schedule | Harmonic Filters 1 - Earthing System for Harmonic Filters - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0014 | A | 6105AK124-6252-EDIA-0014 | Q24050972-04-6252-E-DIA-0014 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Cable Block Diagrams and Schedules | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0015 | A | 6105AK124-6252-EDIA-0015 | Q24050972-04-6252-E-DIA-0015 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Electrical Circuit Diagrams (Schematics) | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DIA | 0016 | A | 6105AK124-6252-EDIA-0016 | Q24050972-04-6252-E-DIA-0016 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | E/I Termination Schedule | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DST | 0001 | A | 6105AK124-6252-EDST-0001 | Q24050972-04-6252-E-DST-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Equipment Register and Technical Specifications | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DST | 0002 | A | 6105AK124-6252-EDST-0002 | Q24050972-04-6252-E-DST-0002 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Equipment Register and Technical Specifications | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DST | 0003 | A | 6105AK124-6252-EDST-0003 | Q24050972-04-6252-E-DST-0003 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Equipment Register and Technical Specifications | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DST | 0004 | A | 6105AK124-6252-EDST-0004 | Q24050972-04-6252-E-DST-0004 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Equipment Register and Technical Specifications | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DST | 0005 | A | 6105AK124-6252-EDST-0005 | Q24050972-04-6252-E-DST-0005 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Equipment Register and Technical Specifications | Harmonic Filters 1 - Earthing System for Harmonic Filters - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | DST | 0006 | A | 6105AK124-6252-EDST-0006 | Q24050972-04-6252-E-DST-0006 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Equipment Register and Technical Specifications | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | EQL | 0001 | A | 6105AK124-6252-EEQL-0001 | Q24050972-04-6252-E-EQL-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Electrical Equipment Load Register | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | GAD | 0001 | A | 6105AK124-6252-EGAD-0001 | Q24050972-04-6252-E-GAD-0001 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Electrical Equipment Layout | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Electrical Equipment Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | LAY | 0001 | A | 6105AK124-6252-ELAY-0001 | Q24050972-04-6252-E-LAY-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Control Room Power and Earthing Design | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | LAY | 0002 | A | 6105AK124-6252-ELAY-0002 | Q24050972-04-6252-E-LAY-0002 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Control Room Power and Earthing Design | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | LAY | 0003 | A | 6105AK124-6252-ELAY-0003 | Q24050972-04-6252-E-LAY-0003 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Control Room Power and Earthing Design | Harmonic Filters 1 - Earthing System for Harmonic Filters - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6242 | C | SEC | 0008 | A | 6105AK124-6242-CSEC-0008 | Q24050972-04-6242-C-SEC-0008 |  | 33/220 kV Power Station Substation | Siemens Switchyard Access Road | Section | 33/220 kV Power Station Substation - Siemens Switchyard Access Road - Section | 2026-05-15 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 33.33% | YB |  |  | Siemens Switchyard | Access Road |  |  |  | Pending
6105A | K124 | 6242 | C | LAY | 0004 | A | 6105AK124-6242-CLAY-0004 | Q24050972-04-6242-C-LAY-0004 |  | 33/220 kV Power Station Substation | Siemens Switchyard Access Road | Layout | 33/220 kV Power Station Substation - Siemens Switchyard Access Road - Layout | 2026-05-15 |  | IFR - Issued for Review | Rejected - Revise & Resubmit | 0% | YB |  |  | Siemens switchyard | Layout |  |  |  | Pending
6105A | K124 | 6252 | E | QRA | 0001 | A | 6105AK124-6252-EQRA-0001 | Q24050972-04-6252-E-QRA-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Lightning Protection Study and Risk Assessment | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | QRA | 0002 | A | 6105AK124-6252-EQRA-0002 | Q24050972-04-6252-E-QRA-0002 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Lightning Protection Study and Risk Assessment | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | QRA | 0003 | A | 6105AK124-6252-EQRA-0003 | Q24050972-04-6252-E-QRA-0003 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Risk Assessment: Electrical Hazards | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | QRA | 0004 | A | 6105AK124-6252-EQRA-0004 | Q24050972-04-6252-E-QRA-0004 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Lightning Protection Study and Risk Assessment | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | QRA | 0005 | A | 6105AK124-6252-EQRA-0005 | Q24050972-04-6252-E-QRA-0005 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Risk Assessment: Electrical Hazards | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | SLD | 0001 | A | 6105AK124-6252-ESLD-0001 | Q24050972-04-6252-E-SLD-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Electrical Single Line Diagram | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | SLD | 0002 | A | 6105AK124-6252-ESLD-0002 | Q24050972-04-6252-E-SLD-0002 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Electrical Single Line Diagram | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | SLD | 0003 | A | 6105AK124-6252-ESLD-0003 | Q24050972-04-6252-E-SLD-0003 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Electrical Single Line Diagram | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | SPC | 0001 | A | 6105AK124-6252-ESPC-0001 | Q24050972-04-6252-E-SPC-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Cable Termination Specifications | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | SPC | 0002 | A | 6105AK124-6252-ESPC-0002 | Q24050972-04-6252-E-SPC-0002 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Cable and Conductor Specifications | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | SPC | 0003 | A | 6105AK124-6252-ESPC-0003 | Q24050972-04-6252-E-SPC-0003 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Lighting and Luminaire Design | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | SPC | 0004 | A | 6105AK124-6252-ESPC-0004 | Q24050972-04-6252-E-SPC-0004 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Cable and Conductor Specifications | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | SPC | 0005 | A | 6105AK124-6252-ESPC-0005 | Q24050972-04-6252-E-SPC-0005 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Cable and Conductor Specifications | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | SPC | 0006 | A | 6105AK124-6252-ESPC-0006 | Q24050972-04-6252-E-SPC-0006 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Lighting and Luminaire Design | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0001 | A | 6105AK124-6252-ESTD-0001 | Q24050972-04-6252-E-STD-0001 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Electrical Equipment Installation Requirements | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0002 | A | 6105AK124-6252-ESTD-0002 | Q24050972-04-6252-E-STD-0002 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Earth Map and Bonding Design | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0003 | A | 6105AK124-6252-ESTD-0003 | Q24050972-04-6252-E-STD-0003 |  | Harmonic Filters 1 | Small Power and Lighting for Harmonic Filters | Electrical Design Standards | Harmonic Filters 1 - Small Power and Lighting for Harmonic Filters - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0004 | A | 6105AK124-6252-ESTD-0004 | Q24050972-04-6252-E-STD-0004 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Thermal Management and Fire Prevention Design | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0005 | A | 6105AK124-6252-ESTD-0005 | Q24050972-04-6252-E-STD-0005 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Electrical Equipment Installation Requirements | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0006 | A | 6105AK124-6252-ESTD-0006 | Q24050972-04-6252-E-STD-0006 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Electrical Design Standards | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0007 | A | 6105AK124-6252-ESTD-0007 | Q24050972-04-6252-E-STD-0007 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Thermal Management and Fire Prevention Design | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0008 | A | 6105AK124-6252-ESTD-0008 | Q24050972-04-6252-E-STD-0008 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Electrical Design Standards | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0009 | A | 6105AK124-6252-ESTD-0009 | Q24050972-04-6252-E-STD-0009 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Earth Map and Bonding Design | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0010 | A | 6105AK124-6252-ESTD-0010 | Q24050972-04-6252-E-STD-0010 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Thermal Management and Fire Prevention Design | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0011 | A | 6105AK124-6252-ESTD-0011 | Q24050972-04-6252-E-STD-0011 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Earth Map and Bonding Design | Harmonic Filters 1 - Earthing System for Harmonic Filters - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0012 | A | 6105AK124-6252-ESTD-0012 | Q24050972-04-6252-E-STD-0012 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Electrical Design Standards | Harmonic Filters 1 - Earthing System for Harmonic Filters - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0013 | A | 6105AK124-6252-ESTD-0013 | Q24050972-04-6252-E-STD-0013 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Thermal Management and Fire Prevention Design | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | E | STD | 0014 | A | 6105AK124-6252-ESTD-0014 | Q24050972-04-6252-E-STD-0014 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Earth Map and Bonding Design | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | F | DBD | 0001 | A | 6105AK124-6252-FDBD-0001 | Q24050972-04-6252-F-DBD-0001 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Control System Configuration | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | F | DIA | 0001 | A | 6105AK124-6252-FDIA-0001 | Q24050972-04-6252-F-DIA-0001 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Control Network Architecture Design | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | F | DIA | 0002 | A | 6105AK124-6252-FDIA-0002 | Q24050972-04-6252-F-DIA-0002 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Interface Panel and I/O Schematics | Harmonic Filters 1 - Earthing System for Harmonic Filters - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | F | DIA | 0003 | A | 6105AK124-6252-FDIA-0003 | Q24050972-04-6252-F-DIA-0003 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Control Network Architecture Design | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | F | DIA | 0004 | A | 6105AK124-6252-FDIA-0004 | Q24050972-04-6252-F-DIA-0004 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Control Network Communication Design | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | F | DIA | 0005 | A | 6105AK124-6252-FDIA-0005 | Q24050972-04-6252-F-DIA-0005 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Emergency Shutdown System Design | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Emergency Shutdown System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | F | NAR | 0001 | A | 6105AK124-6252-FNAR-0001 | Q24050972-04-6252-F-NAR-0001 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Control System Control Narrative & Interlock Design | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | F | NAR | 0002 | A | 6105AK124-6252-FNAR-0002 | Q24050972-04-6252-F-NAR-0002 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Emergency Shutdown System Control Narrative | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | I | CAL | 0001 | A | 6105AK124-6252-ICAL-0001 | Q24050972-04-6252-I-CAL-0001 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Instrument Sizing and Specification Sheets | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | I | DIA | 0001 | A | 6105AK124-6252-IDIA-0001 | Q24050972-04-6252-I-DIA-0001 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Smoke and Fire Detection System Design | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | I | DIA | 0002 | A | 6105AK124-6252-IDIA-0002 | Q24050972-04-6252-I-DIA-0002 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | Closed Circuit Television (CCTV) Design | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - Closed Circuit Television (CCTV) Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | I | HAC | 0001 | A | 6105AK124-6252-IHAC-0001 | Q24050972-04-6252-I-HAC-0001 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Process Safety Design Review (HAZOP & LOPA) | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | I | LST | 0001 | A | 6105AK124-6252-ILST-0001 | Q24050972-04-6252-I-LST-0001 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Equipment Alarm and Trip Level Register | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | I | LST | 0002 | A | 6105AK124-6252-ILST-0002 | Q24050972-04-6252-I-LST-0002 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Instrumentation Equipment Tag Register | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | I | QRA | 0001 | A | 6105AK124-6252-IQRA-0001 | Q24050972-04-6252-I-QRA-0001 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Risk Assessment: Fire and Explosions | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | I | SPC | 0001 | A | 6105AK124-6252-ISPC-0001 | Q24050972-04-6252-I-SPC-0001 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Junction Box and Interface Cabinet Design | Harmonic Filters 1 - Earthing System for Harmonic Filters - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | CAL | 0001 | A | 6105AK124-6252-MCAL-0001 | Q24050972-04-6252-M-CAL-0001 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Vessel and Structure Design with Stress Analysis Calcs | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | CAL | 0002 | A | 6105AK124-6252-MCAL-0002 | Q24050972-04-6252-M-CAL-0002 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Piping Pressure Drop Calculations | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | CAL | 0003 | A | 6105AK124-6252-MCAL-0003 | Q24050972-04-6252-M-CAL-0003 |  | Harmonic Filters 1 | Offloading Spreader Beam and Equipment for Harmonic Filters | Vessel and Structure Design with Stress Analysis Calcs | Harmonic Filters 1 - Offloading Spreader Beam and Equipment for Harmonic Filters - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | DST | 0001 | A | 6105AK124-6252-MDST-0001 | Q24050972-04-6252-M-DST-0001 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Pressure Relief Devices Design and Specification | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | EQL | 0001 | A | 6105AK124-6252-MEQL-0001 | Q24050972-04-6252-M-EQL-0001 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Mechanical Equipment Register with Specifications | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | ISO | 0001 | A | 6105AK124-6252-MISO-0001 | Q24050972-04-6252-M-ISO-0001 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Piping Isometric Design and Layouts | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | PRC | 0001 | A | 6105AK124-6252-MPRC-0001 | Q24050972-04-6252-M-PRC-0001 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Rigging Study and Lifting Equipment Design | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | PSP | 0001 | A | 6105AK124-6252-MPSP-0001 | Q24050972-04-6252-M-PSP-0001 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Pipe and Cable Support Racks Design | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | PSP | 0002 | A | 6105AK124-6252-MPSP-0002 | Q24050972-04-6252-M-PSP-0002 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Pipe and Cable Support Racks Design | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | QAD | 0001 | A | 6105AK124-6252-MQAD-0001 | Q24050972-04-6252-M-QAD-0001 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Fabrication Inspection QC Pack (Incl. NDT) | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | SHP | 0001 | A | 6105AK124-6252-MSHP-0001 | Q24050972-04-6252-M-SHP-0001 |  | Harmonic Filters 1 | Offloading Spreader Beam and Equipment for Harmonic Filters | Equipment Fabrication Drawings | Harmonic Filters 1 - Offloading Spreader Beam and Equipment for Harmonic Filters - Equipment Fabrication Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | SPC | 0001 | A | 6105AK124-6252-MSPC-0001 | Q24050972-04-6252-M-SPC-0001 |  | Harmonic Filters 1 | Cable Racks and Trays for Harmonic Filters | Material Selection and Verification Specification | Harmonic Filters 1 - Cable Racks and Trays for Harmonic Filters - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | SPC | 0002 | A | 6105AK124-6252-MSPC-0002 | Q24050972-04-6252-M-SPC-0002 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Material Selection and Verification Specification | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | SPC | 0003 | A | 6105AK124-6252-MSPC-0003 | Q24050972-04-6252-M-SPC-0003 |  | Harmonic Filters 1 | Fire Protection System for Harmonic Filters | Gasket Schedule and Material Specification | Harmonic Filters 1 - Fire Protection System for Harmonic Filters - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | SPC | 0004 | A | 6105AK124-6252-MSPC-0004 | Q24050972-04-6252-M-SPC-0004 |  | Harmonic Filters 1 | Offloading Spreader Beam and Equipment for Harmonic Filters | Lifting and Crawl Beam Design Specification | Harmonic Filters 1 - Offloading Spreader Beam and Equipment for Harmonic Filters - Lifting and Crawl Beam Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | M | SPC | 0005 | A | 6105AK124-6252-MSPC-0005 | Q24050972-04-6252-M-SPC-0005 |  | Harmonic Filters 1 | Offloading Spreader Beam and Equipment for Harmonic Filters | Material Selection and Verification Specification | Harmonic Filters 1 - Offloading Spreader Beam and Equipment for Harmonic Filters - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | T | RPT | 0001 | A | 6105AK124-6252-TRPT-0001 | Q24050972-04-6252-T-RPT-0001 |  | Harmonic Filters 1 | Perimeter Fencing for Harmonic Filters | Site Surveying & Geotechnical Report | Harmonic Filters 1 - Perimeter Fencing for Harmonic Filters - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | T | RPT | 0002 | A | 6105AK124-6252-TRPT-0002 | Q24050972-04-6252-T-RPT-0002 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Site Surveying & Geotechnical Report | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | T | RPT | 0003 | A | 6105AK124-6252-TRPT-0003 | Q24050972-04-6252-T-RPT-0003 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Site Surveying & Geotechnical Report | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | T | SPC | 0001 | A | 6105AK124-6252-TSPC-0001 | Q24050972-04-6252-T-SPC-0001 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Civil Design and Requirements | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | T | SPC | 0002 | A | 6105AK124-6252-TSPC-0002 | Q24050972-04-6252-T-SPC-0002 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Civil Design and Requirements | Harmonic Filters 1 - Earthing System for Harmonic Filters - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | T | SPC | 0003 | A | 6105AK124-6252-TSPC-0003 | Q24050972-04-6252-T-SPC-0003 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Civil Design and Requirements | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | ELE | 0001 | A | 6105AK124-6252-WELE-0001 | Q24050972-04-6252-W-ELE-0001 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Bulk Earth Works Design and Report | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | ELE | 0002 | A | 6105AK124-6252-WELE-0002 | Q24050972-04-6252-W-ELE-0002 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Bulk Earth Works Design and Report | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | ELE | 0003 | A | 6105AK124-6252-WELE-0003 | Q24050972-04-6252-W-ELE-0003 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Bulk Earth Works Design and Report | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | LAY | 0001 | A | 6105AK124-6252-WLAY-0001 | Q24050972-04-6252-W-LAY-0001 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Drainage, Run-off and Impoundment Design | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | LAY | 0002 | A | 6105AK124-6252-WLAY-0002 | Q24050972-04-6252-W-LAY-0002 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Drainage, Run-off and Impoundment Design | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | LAY | 0003 | A | 6105AK124-6252-WLAY-0003 | Q24050972-04-6252-W-LAY-0003 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Drainage, Run-off and Impoundment Design | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | TRP | 0001 | A | 6105AK124-6252-WTRP-0001 | Q24050972-04-6252-W-TRP-0001 |  | Harmonic Filters 1 | Cable Trench and Tunnels for Harmonic Filters | Soil Classification and Nomination Deliverables | Harmonic Filters 1 - Cable Trench and Tunnels for Harmonic Filters - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | TRP | 0002 | A | 6105AK124-6252-WTRP-0002 | Q24050972-04-6252-W-TRP-0002 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Soil Classification and Nomination Deliverables | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | TRP | 0003 | A | 6105AK124-6252-WTRP-0003 | Q24050972-04-6252-W-TRP-0003 |  | Harmonic Filters 1 | Lightning Protection System for Harmonic Filters | Soil Resistivity Testing Report | Harmonic Filters 1 - Lightning Protection System for Harmonic Filters - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | TRP | 0004 | A | 6105AK124-6252-WTRP-0004 | Q24050972-04-6252-W-TRP-0004 |  | Harmonic Filters 1 | Earthing System for Harmonic Filters | Soil Resistivity Testing Report | Harmonic Filters 1 - Earthing System for Harmonic Filters - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | TRP | 0005 | A | 6105AK124-6252-WTRP-0005 | Q24050972-04-6252-W-TRP-0005 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Soil Classification and Nomination Deliverables | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | TRP | 0006 | A | 6105AK124-6252-WTRP-0006 | Q24050972-04-6252-W-TRP-0006 |  | Harmonic Filters 1 | Terrace, Roads and Access-ways for Harmonic Filters | Soil Resistivity Testing Report | Harmonic Filters 1 - Terrace, Roads and Access-ways for Harmonic Filters - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | TRP | 0007 | A | 6105AK124-6252-WTRP-0007 | Q24050972-04-6252-W-TRP-0007 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Soil Classification and Nomination Deliverables | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6252 | W | TRP | 0008 | A | 6105AK124-6252-WTRP-0008 | Q24050972-04-6252-W-TRP-0008 |  | Harmonic Filters 1 | Pad Platform and Foundations for Harmonic Filters | Soil Resistivity Testing Report | Harmonic Filters 1 - Pad Platform and Foundations for Harmonic Filters - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Harmonic Filters |  |  |  | Pending
6105A | K124 | 6254 | B | DBD | 0001 | A | 6105AK124-6254-BDBD-0001 | Q24050972-04-6254-B-DBD-0001 |  | Battery Energy Storage System 1 | Battery Energy Storage System Project Package | Design Criteria / Basis of Design | Battery Energy Storage System 1 - Battery Energy Storage System Project Package - Design Criteria / Basis of Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Battery Energy Storage System | Project Package |  |  |  | Pending
6105A | K124 | 6254 | B | PHL | 0001 | A | 6105AK124-6254-BPHL-0001 | Q24050972-04-6254-B-PHL-0001 |  | Battery Energy Storage System 1 | Battery Energy Storage System Project Package | Control Philosophy | Battery Energy Storage System 1 - Battery Energy Storage System Project Package - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Battery Energy Storage System | Project Package |  |  |  | Pending
6105A | K124 | 6254 | B | PHL | 0002 | A | 6105AK124-6254-BPHL-0002 | Q24050972-04-6254-B-PHL-0002 |  | Battery Energy Storage System 1 | Battery Energy Storage System Project Package | Synchronization Philosophy | Battery Energy Storage System 1 - Battery Energy Storage System Project Package - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Battery Energy Storage System | Project Package |  |  |  | Pending
6105A | K124 | 6254 | B | PHL | 0003 | A | 6105AK124-6254-BPHL-0003 | Q24050972-04-6254-B-PHL-0003 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Control Philosophy | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | B | PHL | 0004 | A | 6105AK124-6254-BPHL-0004 | Q24050972-04-6254-B-PHL-0004 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Synchronization Philosophy | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | B | PHL | 0005 | A | 6105AK124-6254-BPHL-0005 | Q24050972-04-6254-B-PHL-0005 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Power Management System Philosophy | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Power Management System Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | B | SPC | 0001 | A | 6105AK124-6254-BSPC-0001 | Q24050972-04-6254-B-SPC-0001 |  | Battery Energy Storage System 1 | Battery Energy Storage System Project Package | Functional Design Specification | Battery Energy Storage System 1 - Battery Energy Storage System Project Package - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Battery Energy Storage System | Project Package |  |  |  | Pending
6105A | K124 | 6254 | B | STD | 0001 | A | 6105AK124-6254-BSTD-0001 | Q24050972-04-6254-B-STD-0001 |  | Battery Energy Storage System 1 | Battery Energy Storage System Project Package | System Detailed Engineering Design | Battery Energy Storage System 1 - Battery Energy Storage System Project Package - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Battery Energy Storage System | Project Package |  |  |  | Pending
6105A | K124 | 6254 | C | FND | 0001 | A | 6105AK124-6254-CFND-0001 | Q24050972-04-6254-C-FND-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Civil Foundation Design | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | FND | 0002 | A | 6105AK124-6254-CFND-0002 | Q24050972-04-6254-C-FND-0002 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Plinth Design and Layout | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | FND | 0003 | A | 6105AK124-6254-CFND-0003 | Q24050972-04-6254-C-FND-0003 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Civil Foundation Design | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | FND | 0004 | A | 6105AK124-6254-CFND-0004 | Q24050972-04-6254-C-FND-0004 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | Civil Foundation Design | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | FND | 0005 | A | 6105AK124-6254-CFND-0005 | Q24050972-04-6254-C-FND-0005 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Civil Foundation Design | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0001 | A | 6105AK124-6254-CGAD-0001 | Q24050972-04-6254-C-GAD-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Buildings and Structures GA | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0002 | A | 6105AK124-6254-CGAD-0002 | Q24050972-04-6254-C-GAD-0002 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Terrace Equipment GA | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0003 | A | 6105AK124-6254-CGAD-0003 | Q24050972-04-6254-C-GAD-0003 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Lighting Design and Layout GA | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0004 | A | 6105AK124-6254-CGAD-0004 | Q24050972-04-6254-C-GAD-0004 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Roads, Pathways, Offloading Areas and Fences GA | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0005 | A | 6105AK124-6254-CGAD-0005 | Q24050972-04-6254-C-GAD-0005 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Stormwater and Effluent System Design | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0006 | A | 6105AK124-6254-CGAD-0006 | Q24050972-04-6254-C-GAD-0006 |  | Battery Energy Storage System 1 | Offloading Spreader Beam and Equipment for BESS | Terrace Equipment GA | Battery Energy Storage System 1 - Offloading Spreader Beam and Equipment for BESS - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0007 | A | 6105AK124-6254-CGAD-0007 | Q24050972-04-6254-C-GAD-0007 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Cables, OHL and Fibre Route GA | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0008 | A | 6105AK124-6254-CGAD-0008 | Q24050972-04-6254-C-GAD-0008 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Terrace Equipment GA | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0009 | A | 6105AK124-6254-CGAD-0009 | Q24050972-04-6254-C-GAD-0009 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Buildings and Structures GA | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0010 | A | 6105AK124-6254-CGAD-0010 | Q24050972-04-6254-C-GAD-0010 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Cables, OHL and Fibre Route GA | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0011 | A | 6105AK124-6254-CGAD-0011 | Q24050972-04-6254-C-GAD-0011 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Terrace Equipment GA | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0012 | A | 6105AK124-6254-CGAD-0012 | Q24050972-04-6254-C-GAD-0012 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Roads, Pathways, Offloading Areas and Fences GA | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0013 | A | 6105AK124-6254-CGAD-0013 | Q24050972-04-6254-C-GAD-0013 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Buildings and Structures GA | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0014 | A | 6105AK124-6254-CGAD-0014 | Q24050972-04-6254-C-GAD-0014 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Cables, OHL and Fibre Route GA | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0015 | A | 6105AK124-6254-CGAD-0015 | Q24050972-04-6254-C-GAD-0015 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Terrace Equipment GA | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0016 | A | 6105AK124-6254-CGAD-0016 | Q24050972-04-6254-C-GAD-0016 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Buildings and Structures GA | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0017 | A | 6105AK124-6254-CGAD-0017 | Q24050972-04-6254-C-GAD-0017 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Cables, OHL and Fibre Route GA | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0018 | A | 6105AK124-6254-CGAD-0018 | Q24050972-04-6254-C-GAD-0018 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Terrace Equipment GA | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0019 | A | 6105AK124-6254-CGAD-0019 | Q24050972-04-6254-C-GAD-0019 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Lighting Design and Layout GA | Battery Energy Storage System 1 - Earthing System for BESS Yard - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0020 | A | 6105AK124-6254-CGAD-0020 | Q24050972-04-6254-C-GAD-0020 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Fire Detection and Suppression System | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0021 | A | 6105AK124-6254-CGAD-0021 | Q24050972-04-6254-C-GAD-0021 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | Roads, Pathways, Offloading Areas and Fences GA | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0022 | A | 6105AK124-6254-CGAD-0022 | Q24050972-04-6254-C-GAD-0022 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | Lighting Design and Layout GA | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0023 | A | 6105AK124-6254-CGAD-0023 | Q24050972-04-6254-C-GAD-0023 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | Cables, OHL and Fibre Route GA | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0024 | A | 6105AK124-6254-CGAD-0024 | Q24050972-04-6254-C-GAD-0024 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Buildings and Structures GA | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0025 | A | 6105AK124-6254-CGAD-0025 | Q24050972-04-6254-C-GAD-0025 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Cables, OHL and Fibre Route GA | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0026 | A | 6105AK124-6254-CGAD-0026 | Q24050972-04-6254-C-GAD-0026 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Key Emergency Points and Equipment | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0027 | A | 6105AK124-6254-CGAD-0027 | Q24050972-04-6254-C-GAD-0027 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Terrace Equipment GA | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0028 | A | 6105AK124-6254-CGAD-0028 | Q24050972-04-6254-C-GAD-0028 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Disposal Areas General Arrangement | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0029 | A | 6105AK124-6254-CGAD-0029 | Q24050972-04-6254-C-GAD-0029 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Laydown Areas and Temp Buildings GA | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0030 | A | 6105AK124-6254-CGAD-0030 | Q24050972-04-6254-C-GAD-0030 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Stormwater and Effluent System Design | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0031 | A | 6105AK124-6254-CGAD-0031 | Q24050972-04-6254-C-GAD-0031 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Lighting Design and Layout GA | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0032 | A | 6105AK124-6254-CGAD-0032 | Q24050972-04-6254-C-GAD-0032 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Roads, Pathways, Offloading Areas and Fences GA | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0033 | A | 6105AK124-6254-CGAD-0033 | Q24050972-04-6254-C-GAD-0033 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Stormwater and Effluent System Design | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | GAD | 0034 | A | 6105AK124-6254-CGAD-0034 | Q24050972-04-6254-C-GAD-0034 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Terrace Equipment GA | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | MDL | 0001 | A | 6105AK124-6254-CMDL-0001 | Q24050972-04-6254-C-MDL-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | 3D Designs and Drawings | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | MDL | 0002 | A | 6105AK124-6254-CMDL-0002 | Q24050972-04-6254-C-MDL-0002 |  | Battery Energy Storage System 1 | Offloading Spreader Beam and Equipment for BESS | 3D Designs and Drawings | Battery Energy Storage System 1 - Offloading Spreader Beam and Equipment for BESS - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | MDL | 0003 | A | 6105AK124-6254-CMDL-0003 | Q24050972-04-6254-C-MDL-0003 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | 3D Designs and Drawings | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | MDL | 0004 | A | 6105AK124-6254-CMDL-0004 | Q24050972-04-6254-C-MDL-0004 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | 3D Designs and Drawings | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | MDL | 0005 | A | 6105AK124-6254-CMDL-0005 | Q24050972-04-6254-C-MDL-0005 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | 3D Designs and Drawings | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | MDL | 0006 | A | 6105AK124-6254-CMDL-0006 | Q24050972-04-6254-C-MDL-0006 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | 3D Designs and Drawings | Battery Energy Storage System 1 - Earthing System for BESS Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | MDL | 0007 | A | 6105AK124-6254-CMDL-0007 | Q24050972-04-6254-C-MDL-0007 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | 3D Designs and Drawings | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | MDL | 0008 | A | 6105AK124-6254-CMDL-0008 | Q24050972-04-6254-C-MDL-0008 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | 3D Designs and Drawings | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | MDL | 0009 | A | 6105AK124-6254-CMDL-0009 | Q24050972-04-6254-C-MDL-0009 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | 3D Designs and Drawings | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | PLN | 0001 | A | 6105AK124-6254-CPLN-0001 | Q24050972-04-6254-C-PLN-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Civil Works Execution Plan | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | PLN | 0002 | A | 6105AK124-6254-CPLN-0002 | Q24050972-04-6254-C-PLN-0002 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Civil Works Execution Plan | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | PLN | 0003 | A | 6105AK124-6254-CPLN-0003 | Q24050972-04-6254-C-PLN-0003 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Civil Works Execution Plan | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | PLN | 0004 | A | 6105AK124-6254-CPLN-0004 | Q24050972-04-6254-C-PLN-0004 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Civil Works Execution Plan | Battery Energy Storage System 1 - Earthing System for BESS Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | PLN | 0005 | A | 6105AK124-6254-CPLN-0005 | Q24050972-04-6254-C-PLN-0005 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Civil Works Execution Plan | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | PPL | 0001 | A | 6105AK124-6254-CPPL-0001 | Q24050972-04-6254-C-PPL-0001 |  | Battery Energy Storage System 1 | Offloading Spreader Beam and Equipment for BESS | Operational & Maint Access Routes Design | Battery Energy Storage System 1 - Offloading Spreader Beam and Equipment for BESS - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | PPL | 0002 | A | 6105AK124-6254-CPPL-0002 | Q24050972-04-6254-C-PPL-0002 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Operational & Maint Access Routes Design | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | PPL | 0003 | A | 6105AK124-6254-CPPL-0003 | Q24050972-04-6254-C-PPL-0003 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Operational & Maint Access Routes Design | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | PPL | 0004 | A | 6105AK124-6254-CPPL-0004 | Q24050972-04-6254-C-PPL-0004 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Operational & Maint Access Routes Design | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SEC | 0001 | A | 6105AK124-6254-CSEC-0001 | Q24050972-04-6254-C-SEC-0001 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Corrosion Prevention and Protection Design | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SEC | 0002 | A | 6105AK124-6254-CSEC-0002 | Q24050972-04-6254-C-SEC-0002 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Structural Earthing and Bonding Design | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SEC | 0003 | A | 6105AK124-6254-CSEC-0003 | Q24050972-04-6254-C-SEC-0003 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Corrosion Prevention and Protection Design | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SEC | 0004 | A | 6105AK124-6254-CSEC-0004 | Q24050972-04-6254-C-SEC-0004 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Structural Earthing and Bonding Design | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SEC | 0005 | A | 6105AK124-6254-CSEC-0005 | Q24050972-04-6254-C-SEC-0005 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Corrosion Prevention and Protection Design | Battery Energy Storage System 1 - Earthing System for BESS Yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SEC | 0006 | A | 6105AK124-6254-CSEC-0006 | Q24050972-04-6254-C-SEC-0006 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Structural Earthing and Bonding Design | Battery Energy Storage System 1 - Earthing System for BESS Yard - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SEC | 0007 | A | 6105AK124-6254-CSEC-0007 | Q24050972-04-6254-C-SEC-0007 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Corrosion Prevention and Protection Design | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SHP | 0001 | A | 6105AK124-6254-CSHP-0001 | Q24050972-04-6254-C-SHP-0001 |  | Battery Energy Storage System 1 | Offloading Spreader Beam and Equipment for BESS | Equipment Assembly Drawings | Battery Energy Storage System 1 - Offloading Spreader Beam and Equipment for BESS - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SHP | 0002 | A | 6105AK124-6254-CSHP-0002 | Q24050972-04-6254-C-SHP-0002 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Equipment Assembly Drawings | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SHP | 0003 | A | 6105AK124-6254-CSHP-0003 | Q24050972-04-6254-C-SHP-0003 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | Equipment Assembly Drawings | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SHP | 0004 | A | 6105AK124-6254-CSHP-0004 | Q24050972-04-6254-C-SHP-0004 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Equipment Assembly Drawings | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0001 | A | 6105AK124-6254-CSPC-0001 | Q24050972-04-6254-C-SPC-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Civil Design Requirements | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0002 | A | 6105AK124-6254-CSPC-0002 | Q24050972-04-6254-C-SPC-0002 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Excavation, Trenching and Compacting Design | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0003 | A | 6105AK124-6254-CSPC-0003 | Q24050972-04-6254-C-SPC-0003 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Concrete Construction Material Specifications | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0004 | A | 6105AK124-6254-CSPC-0004 | Q24050972-04-6254-C-SPC-0004 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Excavation, Trenching and Compacting Design | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0005 | A | 6105AK124-6254-CSPC-0005 | Q24050972-04-6254-C-SPC-0005 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Concrete Construction Material Specifications | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0006 | A | 6105AK124-6254-CSPC-0006 | Q24050972-04-6254-C-SPC-0006 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Civil Design Requirements | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0007 | A | 6105AK124-6254-CSPC-0007 | Q24050972-04-6254-C-SPC-0007 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Concrete Construction Material Specifications | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0008 | A | 6105AK124-6254-CSPC-0008 | Q24050972-04-6254-C-SPC-0008 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Steel Structures Corrosion Protection Specification | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0009 | A | 6105AK124-6254-CSPC-0009 | Q24050972-04-6254-C-SPC-0009 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Civil Design Requirements | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0010 | A | 6105AK124-6254-CSPC-0010 | Q24050972-04-6254-C-SPC-0010 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Excavation, Trenching and Compacting Design | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0011 | A | 6105AK124-6254-CSPC-0011 | Q24050972-04-6254-C-SPC-0011 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Concrete Construction Material Specifications | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0012 | A | 6105AK124-6254-CSPC-0012 | Q24050972-04-6254-C-SPC-0012 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Concrete Construction Material Specifications | Battery Energy Storage System 1 - Earthing System for BESS Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0013 | A | 6105AK124-6254-CSPC-0013 | Q24050972-04-6254-C-SPC-0013 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Excavation, Trenching and Compacting Design | Battery Energy Storage System 1 - Earthing System for BESS Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0014 | A | 6105AK124-6254-CSPC-0014 | Q24050972-04-6254-C-SPC-0014 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | Excavation, Trenching and Compacting Design | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0015 | A | 6105AK124-6254-CSPC-0015 | Q24050972-04-6254-C-SPC-0015 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | Concrete Construction Material Specifications | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0016 | A | 6105AK124-6254-CSPC-0016 | Q24050972-04-6254-C-SPC-0016 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | Steel Structures Corrosion Protection Specification | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0017 | A | 6105AK124-6254-CSPC-0017 | Q24050972-04-6254-C-SPC-0017 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Civil Design Requirements | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0018 | A | 6105AK124-6254-CSPC-0018 | Q24050972-04-6254-C-SPC-0018 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Excavation, Trenching and Compacting Design | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0019 | A | 6105AK124-6254-CSPC-0019 | Q24050972-04-6254-C-SPC-0019 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Concrete Construction Material Specifications | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0020 | A | 6105AK124-6254-CSPC-0020 | Q24050972-04-6254-C-SPC-0020 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Civil Design Requirements | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0021 | A | 6105AK124-6254-CSPC-0021 | Q24050972-04-6254-C-SPC-0021 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Excavation, Trenching and Compacting Design | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SPC | 0022 | A | 6105AK124-6254-CSPC-0022 | Q24050972-04-6254-C-SPC-0022 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Concrete Construction Material Specifications | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SSD | 0001 | A | 6105AK124-6254-CSSD-0001 | Q24050972-04-6254-C-SSD-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Steel Support Structures Design | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SSD | 0002 | A | 6105AK124-6254-CSSD-0002 | Q24050972-04-6254-C-SSD-0002 |  | Battery Energy Storage System 1 | Offloading Spreader Beam and Equipment for BESS | Steel Support Structures Design | Battery Energy Storage System 1 - Offloading Spreader Beam and Equipment for BESS - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SSD | 0003 | A | 6105AK124-6254-CSSD-0003 | Q24050972-04-6254-C-SSD-0003 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Steel Support Structures Design | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | SSD | 0004 | A | 6105AK124-6254-CSSD-0004 | Q24050972-04-6254-C-SSD-0004 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | Steel Support Structures Design | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0001 | A | 6105AK124-6254-CSTD-0001 | Q24050972-04-6254-C-STD-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Civil Construction Requirements | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0002 | A | 6105AK124-6254-CSTD-0002 | Q24050972-04-6254-C-STD-0002 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Civil Construction Requirements | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0003 | A | 6105AK124-6254-CSTD-0003 | Q24050972-04-6254-C-STD-0003 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Underground Pipe Route and Cable Bedding Design | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0004 | A | 6105AK124-6254-CSTD-0004 | Q24050972-04-6254-C-STD-0004 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Underground Pipe Route and Cable Bedding Design | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0005 | A | 6105AK124-6254-CSTD-0005 | Q24050972-04-6254-C-STD-0005 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Civil Construction Requirements | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0006 | A | 6105AK124-6254-CSTD-0006 | Q24050972-04-6254-C-STD-0006 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Underground Pipe Route and Cable Bedding Design | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0007 | A | 6105AK124-6254-CSTD-0007 | Q24050972-04-6254-C-STD-0007 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Civil Construction Requirements | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0008 | A | 6105AK124-6254-CSTD-0008 | Q24050972-04-6254-C-STD-0008 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Underground Pipe Route and Cable Bedding Design | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0009 | A | 6105AK124-6254-CSTD-0009 | Q24050972-04-6254-C-STD-0009 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Fire Protection System Design (Civil Works) | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0010 | A | 6105AK124-6254-CSTD-0010 | Q24050972-04-6254-C-STD-0010 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Civil Construction Requirements | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0011 | A | 6105AK124-6254-CSTD-0011 | Q24050972-04-6254-C-STD-0011 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | Underground Pipe Route and Cable Bedding Design | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0012 | A | 6105AK124-6254-CSTD-0012 | Q24050972-04-6254-C-STD-0012 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Bund-wall Requirements and Design | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0013 | A | 6105AK124-6254-CSTD-0013 | Q24050972-04-6254-C-STD-0013 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Civil Construction Requirements | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0014 | A | 6105AK124-6254-CSTD-0014 | Q24050972-04-6254-C-STD-0014 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Underground Pipe Route and Cable Bedding Design | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0015 | A | 6105AK124-6254-CSTD-0015 | Q24050972-04-6254-C-STD-0015 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Bund-wall Requirements and Design | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0016 | A | 6105AK124-6254-CSTD-0016 | Q24050972-04-6254-C-STD-0016 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Fire Protection System Design (Civil Works) | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0017 | A | 6105AK124-6254-CSTD-0017 | Q24050972-04-6254-C-STD-0017 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Civil Construction Requirements | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | C | STD | 0018 | A | 6105AK124-6254-CSTD-0018 | Q24050972-04-6254-C-STD-0018 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Underground Pipe Route and Cable Bedding Design | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | CAL | 0001 | A | 6105AK124-6254-ECAL-0001 | Q24050972-04-6254-E-CAL-0001 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Cable and Conductor Sizing (incl Volt Drop Calcs) | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | CAL | 0002 | A | 6105AK124-6254-ECAL-0002 | Q24050972-04-6254-E-CAL-0002 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Impedance and Burn-off Calculations | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | CAL | 0003 | A | 6105AK124-6254-ECAL-0003 | Q24050972-04-6254-E-CAL-0003 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Impedance and Burn-off Calculations | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | CAL | 0004 | A | 6105AK124-6254-ECAL-0004 | Q24050972-04-6254-E-CAL-0004 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Cable and Conductor Sizing (incl Volt Drop Calcs) | Battery Energy Storage System 1 - Earthing System for BESS Yard - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | CAL | 0005 | A | 6105AK124-6254-ECAL-0005 | Q24050972-04-6254-E-CAL-0005 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Impedance and Burn-off Calculations | Battery Energy Storage System 1 - Earthing System for BESS Yard - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | CAL | 0006 | A | 6105AK124-6254-ECAL-0006 | Q24050972-04-6254-E-CAL-0006 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Conductor Sag and Tension Plan | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0001 | A | 6105AK124-6254-EDIA-0001 | Q24050972-04-6254-E-DIA-0001 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Cable Block Diagrams and Schedules | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0002 | A | 6105AK124-6254-EDIA-0002 | Q24050972-04-6254-E-DIA-0002 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Electrical Circuit Diagrams (Schematics) | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0003 | A | 6105AK124-6254-EDIA-0003 | Q24050972-04-6254-E-DIA-0003 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Electrical Block Diagram | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0004 | A | 6105AK124-6254-EDIA-0004 | Q24050972-04-6254-E-DIA-0004 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | E/I Termination Schedule | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0005 | A | 6105AK124-6254-EDIA-0005 | Q24050972-04-6254-E-DIA-0005 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Cable Block Diagrams and Schedules | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0006 | A | 6105AK124-6254-EDIA-0006 | Q24050972-04-6254-E-DIA-0006 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | E/I Termination Schedule | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0007 | A | 6105AK124-6254-EDIA-0007 | Q24050972-04-6254-E-DIA-0007 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Cable Block Diagrams and Schedules | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0008 | A | 6105AK124-6254-EDIA-0008 | Q24050972-04-6254-E-DIA-0008 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | E/I Termination Schedule | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0009 | A | 6105AK124-6254-EDIA-0009 | Q24050972-04-6254-E-DIA-0009 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Cable Block Diagrams and Schedules | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0010 | A | 6105AK124-6254-EDIA-0010 | Q24050972-04-6254-E-DIA-0010 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Electrical Circuit Diagrams (Schematics) | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0011 | A | 6105AK124-6254-EDIA-0011 | Q24050972-04-6254-E-DIA-0011 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Electrical Circuit Diagrams (Schematics) | Battery Energy Storage System 1 - Earthing System for BESS Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0012 | A | 6105AK124-6254-EDIA-0012 | Q24050972-04-6254-E-DIA-0012 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Cable Block Diagrams and Schedules | Battery Energy Storage System 1 - Earthing System for BESS Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0013 | A | 6105AK124-6254-EDIA-0013 | Q24050972-04-6254-E-DIA-0013 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | E/I Termination Schedule | Battery Energy Storage System 1 - Earthing System for BESS Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0014 | A | 6105AK124-6254-EDIA-0014 | Q24050972-04-6254-E-DIA-0014 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Cable Block Diagrams and Schedules | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0015 | A | 6105AK124-6254-EDIA-0015 | Q24050972-04-6254-E-DIA-0015 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Electrical Circuit Diagrams (Schematics) | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0016 | A | 6105AK124-6254-EDIA-0016 | Q24050972-04-6254-E-DIA-0016 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | E/I Termination Schedule | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0017 | A | 6105AK124-6254-EDIA-0017 | Q24050972-04-6254-E-DIA-0017 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Cable Block Diagrams and Schedules | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0018 | A | 6105AK124-6254-EDIA-0018 | Q24050972-04-6254-E-DIA-0018 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Electrical Circuit Diagrams (Schematics) | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0019 | A | 6105AK124-6254-EDIA-0019 | Q24050972-04-6254-E-DIA-0019 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Electrical Block Diagram | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0020 | A | 6105AK124-6254-EDIA-0020 | Q24050972-04-6254-E-DIA-0020 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Electrical Circuit Diagrams (Schematics) | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0021 | A | 6105AK124-6254-EDIA-0021 | Q24050972-04-6254-E-DIA-0021 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Electrical Block Diagram | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0022 | A | 6105AK124-6254-EDIA-0022 | Q24050972-04-6254-E-DIA-0022 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Electrical Network Architecture | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Electrical Network Architecture |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0023 | A | 6105AK124-6254-EDIA-0023 | Q24050972-04-6254-E-DIA-0023 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Protection Relay Design | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Protection Relay Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0024 | A | 6105AK124-6254-EDIA-0024 | Q24050972-04-6254-E-DIA-0024 |  | Battery Energy Storage System 1 | 33kV Ring Main Unit CCCCV 1 for BESS Yard | Electrical Circuit Diagrams (Schematics) | Battery Energy Storage System 1 - 33kV Ring Main Unit CCCCV 1 for BESS Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Ring Main Unit CCCCV 1 | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DIA | 0025 | A | 6105AK124-6254-EDIA-0025 | Q24050972-04-6254-E-DIA-0025 |  | Battery Energy Storage System 1 | 33kV Ring Main Unit CCCCV 1 for BESS Yard | E/I Termination Schedule | Battery Energy Storage System 1 - 33kV Ring Main Unit CCCCV 1 for BESS Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Ring Main Unit CCCCV 1 | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DST | 0001 | A | 6105AK124-6254-EDST-0001 | Q24050972-04-6254-E-DST-0001 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Equipment Register and Technical Specifications | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DST | 0002 | A | 6105AK124-6254-EDST-0002 | Q24050972-04-6254-E-DST-0002 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Equipment Register and Technical Specifications | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DST | 0003 | A | 6105AK124-6254-EDST-0003 | Q24050972-04-6254-E-DST-0003 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Equipment Register and Technical Specifications | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DST | 0004 | A | 6105AK124-6254-EDST-0004 | Q24050972-04-6254-E-DST-0004 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Equipment Register and Technical Specifications | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DST | 0005 | A | 6105AK124-6254-EDST-0005 | Q24050972-04-6254-E-DST-0005 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Equipment Register and Technical Specifications | Battery Energy Storage System 1 - Earthing System for BESS Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DST | 0006 | A | 6105AK124-6254-EDST-0006 | Q24050972-04-6254-E-DST-0006 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Equipment Register and Technical Specifications | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DST | 0007 | A | 6105AK124-6254-EDST-0007 | Q24050972-04-6254-E-DST-0007 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | CT and PT Datasheets | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - CT and PT Datasheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DST | 0008 | A | 6105AK124-6254-EDST-0008 | Q24050972-04-6254-E-DST-0008 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Equipment Register and Technical Specifications | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DST | 0009 | A | 6105AK124-6254-EDST-0009 | Q24050972-04-6254-E-DST-0009 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | CT and PT Datasheets | Battery Energy Storage System 1 - Protection Relays for BESS Yard - CT and PT Datasheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DST | 0010 | A | 6105AK124-6254-EDST-0010 | Q24050972-04-6254-E-DST-0010 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Equipment Register and Technical Specifications | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | DST | 0011 | A | 6105AK124-6254-EDST-0011 | Q24050972-04-6254-E-DST-0011 |  | Battery Energy Storage System 1 | 33kV Ring Main Unit CCCCV 1 for BESS Yard | Equipment Register and Technical Specifications | Battery Energy Storage System 1 - 33kV Ring Main Unit CCCCV 1 for BESS Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Ring Main Unit CCCCV 1 | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | EQL | 0001 | A | 6105AK124-6254-EEQL-0001 | Q24050972-04-6254-E-EQL-0001 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Electrical Equipment Load Register | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | EQL | 0002 | A | 6105AK124-6254-EEQL-0002 | Q24050972-04-6254-E-EQL-0002 |  | Battery Energy Storage System 1 | 33kV Ring Main Unit CCCCV 1 for BESS Yard | Electrical Equipment Load Register | Battery Energy Storage System 1 - 33kV Ring Main Unit CCCCV 1 for BESS Yard - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Ring Main Unit CCCCV 1 | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | GAD | 0001 | A | 6105AK124-6254-EGAD-0001 | Q24050972-04-6254-E-GAD-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Electrical Equipment Layout | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Electrical Equipment Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | GAD | 0002 | A | 6105AK124-6254-EGAD-0002 | Q24050972-04-6254-E-GAD-0002 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Control Room Design | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Control Room Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | GAD | 0003 | A | 6105AK124-6254-EGAD-0003 | Q24050972-04-6254-E-GAD-0003 |  | Battery Energy Storage System 1 | 33kV Ring Main Unit CCCCV 1 for BESS Yard | Electrical Equipment Layout | Battery Energy Storage System 1 - 33kV Ring Main Unit CCCCV 1 for BESS Yard - Electrical Equipment Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Ring Main Unit CCCCV 1 | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | LAY | 0001 | A | 6105AK124-6254-ELAY-0001 | Q24050972-04-6254-E-LAY-0001 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Control Room Power and Earthing Design | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | LAY | 0002 | A | 6105AK124-6254-ELAY-0002 | Q24050972-04-6254-E-LAY-0002 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Control Room Power and Earthing Design | Battery Energy Storage System 1 - Earthing System for BESS Yard - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | LAY | 0003 | A | 6105AK124-6254-ELAY-0003 | Q24050972-04-6254-E-LAY-0003 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Switch Room (PCC and MCC) Detail Design | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Switch Room (PCC and MCC) Detail Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | LAY | 0004 | A | 6105AK124-6254-ELAY-0004 | Q24050972-04-6254-E-LAY-0004 |  | Battery Energy Storage System 1 | 33kV Ring Main Unit CCCCV 1 for BESS Yard | Switch Room (PCC and MCC) Detail Design | Battery Energy Storage System 1 - 33kV Ring Main Unit CCCCV 1 for BESS Yard - Switch Room (PCC and MCC) Detail Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Ring Main Unit CCCCV 1 | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | MDL | 0001 | A | 6105AK124-6254-EMDL-0001 | Q24050972-04-6254-E-MDL-0001 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | ETAP Network Model | Battery Energy Storage System 1 - Protection Relays for BESS Yard - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | MDL | 0002 | A | 6105AK124-6254-EMDL-0002 | Q24050972-04-6254-E-MDL-0002 |  | Battery Energy Storage System 1 | 33kV Ring Main Unit CCCCV 1 for BESS Yard | ETAP Network Model | Battery Energy Storage System 1 - 33kV Ring Main Unit CCCCV 1 for BESS Yard - ETAP Network Model |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Ring Main Unit CCCCV 1 | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | QRA | 0001 | A | 6105AK124-6254-EQRA-0001 | Q24050972-04-6254-E-QRA-0001 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Lightning Protection Study and Risk Assessment | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | QRA | 0002 | A | 6105AK124-6254-EQRA-0002 | Q24050972-04-6254-E-QRA-0002 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Risk Assessment: Electrical Hazards | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | QRA | 0003 | A | 6105AK124-6254-EQRA-0003 | Q24050972-04-6254-E-QRA-0003 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Lightning Protection Study and Risk Assessment | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | QRA | 0004 | A | 6105AK124-6254-EQRA-0004 | Q24050972-04-6254-E-QRA-0004 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Risk Assessment: Electrical Hazards | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | QRA | 0005 | A | 6105AK124-6254-EQRA-0005 | Q24050972-04-6254-E-QRA-0005 |  | Battery Energy Storage System 1 | 33kV Ring Main Unit CCCCV 1 for BESS Yard | Risk Assessment: Electrical Hazards | Battery Energy Storage System 1 - 33kV Ring Main Unit CCCCV 1 for BESS Yard - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Ring Main Unit CCCCV 1 | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | RPT | 0001 | A | 6105AK124-6254-ERPT-0001 | Q24050972-04-6254-E-RPT-0001 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | HV/MV Operational and Maintenance Study | Battery Energy Storage System 1 - Protection Relays for BESS Yard - HV/MV Operational and Maintenance Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | RPT | 0002 | A | 6105AK124-6254-ERPT-0002 | Q24050972-04-6254-E-RPT-0002 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Reactive Power Study | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Reactive Power Study |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | SLD | 0001 | A | 6105AK124-6254-ESLD-0001 | Q24050972-04-6254-E-SLD-0001 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Electrical Single Line Diagram | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | SLD | 0002 | A | 6105AK124-6254-ESLD-0002 | Q24050972-04-6254-E-SLD-0002 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Electrical Single Line Diagram | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | SLD | 0003 | A | 6105AK124-6254-ESLD-0003 | Q24050972-04-6254-E-SLD-0003 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Electrical Single Line Diagram | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | SLD | 0004 | A | 6105AK124-6254-ESLD-0004 | Q24050972-04-6254-E-SLD-0004 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Electrical Single Line Diagram | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | SLD | 0005 | A | 6105AK124-6254-ESLD-0005 | Q24050972-04-6254-E-SLD-0005 |  | Battery Energy Storage System 1 | 33kV Ring Main Unit CCCCV 1 for BESS Yard | Electrical Single Line Diagram | Battery Energy Storage System 1 - 33kV Ring Main Unit CCCCV 1 for BESS Yard - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Ring Main Unit CCCCV 1 | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | SPC | 0001 | A | 6105AK124-6254-ESPC-0001 | Q24050972-04-6254-E-SPC-0001 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Cable Termination Specifications | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | SPC | 0002 | A | 6105AK124-6254-ESPC-0002 | Q24050972-04-6254-E-SPC-0002 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Cable and Conductor Specifications | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | SPC | 0003 | A | 6105AK124-6254-ESPC-0003 | Q24050972-04-6254-E-SPC-0003 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Cable and Conductor Specifications | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | SPC | 0004 | A | 6105AK124-6254-ESPC-0004 | Q24050972-04-6254-E-SPC-0004 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Lighting and Luminaire Design | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | SPC | 0005 | A | 6105AK124-6254-ESPC-0005 | Q24050972-04-6254-E-SPC-0005 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Cable Termination Specifications | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | SPC | 0006 | A | 6105AK124-6254-ESPC-0006 | Q24050972-04-6254-E-SPC-0006 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Electrical Equipment Communication Specification | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Electrical Equipment Communication Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | SPC | 0007 | A | 6105AK124-6254-ESPC-0007 | Q24050972-04-6254-E-SPC-0007 |  | Battery Energy Storage System 1 | 33kV Ring Main Unit CCCCV 1 for BESS Yard | Electrical Equipment Communication Specification | Battery Energy Storage System 1 - 33kV Ring Main Unit CCCCV 1 for BESS Yard - Electrical Equipment Communication Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Ring Main Unit CCCCV 1 | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0001 | A | 6105AK124-6254-ESTD-0001 | Q24050972-04-6254-E-STD-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Earth Map and Bonding Design | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0002 | A | 6105AK124-6254-ESTD-0002 | Q24050972-04-6254-E-STD-0002 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Electrical Equipment Installation Requirements | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0003 | A | 6105AK124-6254-ESTD-0003 | Q24050972-04-6254-E-STD-0003 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Thermal Management and Fire Prevention Design | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0004 | A | 6105AK124-6254-ESTD-0004 | Q24050972-04-6254-E-STD-0004 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Electrical Equipment Installation Requirements | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0005 | A | 6105AK124-6254-ESTD-0005 | Q24050972-04-6254-E-STD-0005 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Electrical Design Standards | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0006 | A | 6105AK124-6254-ESTD-0006 | Q24050972-04-6254-E-STD-0006 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Thermal Management and Fire Prevention Design | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0007 | A | 6105AK124-6254-ESTD-0007 | Q24050972-04-6254-E-STD-0007 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Electrical Design Standards | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0008 | A | 6105AK124-6254-ESTD-0008 | Q24050972-04-6254-E-STD-0008 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Earth Map and Bonding Design | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0009 | A | 6105AK124-6254-ESTD-0009 | Q24050972-04-6254-E-STD-0009 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Thermal Management and Fire Prevention Design | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0010 | A | 6105AK124-6254-ESTD-0010 | Q24050972-04-6254-E-STD-0010 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Earth Map and Bonding Design | Battery Energy Storage System 1 - Earthing System for BESS Yard - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0011 | A | 6105AK124-6254-ESTD-0011 | Q24050972-04-6254-E-STD-0011 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Electrical Design Standards | Battery Energy Storage System 1 - Earthing System for BESS Yard - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0012 | A | 6105AK124-6254-ESTD-0012 | Q24050972-04-6254-E-STD-0012 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Thermal Management and Fire Prevention Design | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0013 | A | 6105AK124-6254-ESTD-0013 | Q24050972-04-6254-E-STD-0013 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Electrical Equipment Installation Requirements | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0014 | A | 6105AK124-6254-ESTD-0014 | Q24050972-04-6254-E-STD-0014 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Electrical Equipment Installation Requirements | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0015 | A | 6105AK124-6254-ESTD-0015 | Q24050972-04-6254-E-STD-0015 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Electrical Design Standards | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0016 | A | 6105AK124-6254-ESTD-0016 | Q24050972-04-6254-E-STD-0016 |  | Battery Energy Storage System 1 | 33kV Ring Main Unit CCCCV 1 for BESS Yard | Electrical Equipment Installation Requirements | Battery Energy Storage System 1 - 33kV Ring Main Unit CCCCV 1 for BESS Yard - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Ring Main Unit CCCCV 1 | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | E | STD | 0017 | A | 6105AK124-6254-ESTD-0017 | Q24050972-04-6254-E-STD-0017 |  | Battery Energy Storage System 1 | 33kV Ring Main Unit CCCCV 1 for BESS Yard | Thermal Management and Fire Prevention Design | Battery Energy Storage System 1 - 33kV Ring Main Unit CCCCV 1 for BESS Yard - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 33kV Ring Main Unit CCCCV 1 | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | DBD | 0001 | A | 6105AK124-6254-FDBD-0001 | Q24050972-04-6254-F-DBD-0001 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Control System Configuration | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | DIA | 0001 | A | 6105AK124-6254-FDIA-0001 | Q24050972-04-6254-F-DIA-0001 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Control Network Architecture Design | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | DIA | 0002 | A | 6105AK124-6254-FDIA-0002 | Q24050972-04-6254-F-DIA-0002 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Interface Panel and I/O Schematics | Battery Energy Storage System 1 - Earthing System for BESS Yard - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | DIA | 0003 | A | 6105AK124-6254-FDIA-0003 | Q24050972-04-6254-F-DIA-0003 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Control Network Architecture Design | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | DIA | 0004 | A | 6105AK124-6254-FDIA-0004 | Q24050972-04-6254-F-DIA-0004 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Control Network Communication Design | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | DIA | 0005 | A | 6105AK124-6254-FDIA-0005 | Q24050972-04-6254-F-DIA-0005 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Emergency Shutdown System Design | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Emergency Shutdown System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | DIA | 0006 | A | 6105AK124-6254-FDIA-0006 | Q24050972-04-6254-F-DIA-0006 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Control Network Communication Design | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | LAY | 0001 | A | 6105AK124-6254-FLAY-0001 | Q24050972-04-6254-F-LAY-0001 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | HMI and Graphics design | Battery Energy Storage System 1 - Protection Relays for BESS Yard - HMI and Graphics design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | NAR | 0001 | A | 6105AK124-6254-FNAR-0001 | Q24050972-04-6254-F-NAR-0001 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Control System Control Narrative & Interlock Design | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | NAR | 0002 | A | 6105AK124-6254-FNAR-0002 | Q24050972-04-6254-F-NAR-0002 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Emergency Shutdown System Control Narrative | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | NAR | 0003 | A | 6105AK124-6254-FNAR-0003 | Q24050972-04-6254-F-NAR-0003 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Control System Control Narrative & Interlock Design | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | PHL | 0001 | A | 6105AK124-6254-FPHL-0001 | Q24050972-04-6254-F-PHL-0001 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Control System Control Philosophy | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | PRC | 0001 | A | 6105AK124-6254-FPRC-0001 | Q24050972-04-6254-F-PRC-0001 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Alarm Classification Methodology | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Alarm Classification Methodology |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | F | SPC | 0001 | A | 6105AK124-6254-FSPC-0001 | Q24050972-04-6254-F-SPC-0001 |  | Battery Energy Storage System 1 | Protection Relays for BESS Yard | Historian and Server Design | Battery Energy Storage System 1 - Protection Relays for BESS Yard - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Protection Relays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | CAL | 0001 | A | 6105AK124-6254-ICAL-0001 | Q24050972-04-6254-I-CAL-0001 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Instrument Sizing and Specification Sheets | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | CAL | 0002 | A | 6105AK124-6254-ICAL-0002 | Q24050972-04-6254-I-CAL-0002 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Instrument Sizing and Specification Sheets | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | DIA | 0001 | A | 6105AK124-6254-IDIA-0001 | Q24050972-04-6254-I-DIA-0001 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Smoke and Fire Detection System Design | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | DIA | 0002 | A | 6105AK124-6254-IDIA-0002 | Q24050972-04-6254-I-DIA-0002 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | Closed Circuit Television (CCTV) Design | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - Closed Circuit Television (CCTV) Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | DIA | 0003 | A | 6105AK124-6254-IDIA-0003 | Q24050972-04-6254-I-DIA-0003 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Smoke and Fire Detection System Design | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | HAC | 0001 | A | 6105AK124-6254-IHAC-0001 | Q24050972-04-6254-I-HAC-0001 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Process Safety Design Review (HAZOP & LOPA) | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | ITD | 0001 | A | 6105AK124-6254-IITD-0001 | Q24050972-04-6254-I-ITD-0001 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Instrument Wiring Loop Diagrams and Cable Schedule | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | ITD | 0002 | A | 6105AK124-6254-IITD-0002 | Q24050972-04-6254-I-ITD-0002 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Instrument Wiring Loop Diagrams and Cable Schedule | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | LST | 0001 | A | 6105AK124-6254-ILST-0001 | Q24050972-04-6254-I-LST-0001 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Equipment Alarm and Trip Level Register | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | LST | 0002 | A | 6105AK124-6254-ILST-0002 | Q24050972-04-6254-I-LST-0002 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Instrumentation Equipment Tag Register | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | LST | 0003 | A | 6105AK124-6254-ILST-0003 | Q24050972-04-6254-I-LST-0003 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Equipment Alarm and Trip Level Register | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | LST | 0004 | A | 6105AK124-6254-ILST-0004 | Q24050972-04-6254-I-LST-0004 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Instrumentation Equipment Tag Register | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | LST | 0005 | A | 6105AK124-6254-ILST-0005 | Q24050972-04-6254-I-LST-0005 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Equipment Alarm and Trip Level Register | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | QRA | 0001 | A | 6105AK124-6254-IQRA-0001 | Q24050972-04-6254-I-QRA-0001 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Risk Assessment: Fire and Explosions | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | QRA | 0002 | A | 6105AK124-6254-IQRA-0002 | Q24050972-04-6254-I-QRA-0002 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Risk Assessment: Fire and Explosions | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | SPC | 0001 | A | 6105AK124-6254-ISPC-0001 | Q24050972-04-6254-I-SPC-0001 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Junction Box and Interface Cabinet Design | Battery Energy Storage System 1 - Earthing System for BESS Yard - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | SPC | 0002 | A | 6105AK124-6254-ISPC-0002 | Q24050972-04-6254-I-SPC-0002 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Junction Box and Interface Cabinet Design | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | I | SPC | 0003 | A | 6105AK124-6254-ISPC-0003 | Q24050972-04-6254-I-SPC-0003 |  | Battery Energy Storage System 1 | Metering Instruments for BESS Yard | Junction Box and Interface Cabinet Design | Battery Energy Storage System 1 - Metering Instruments for BESS Yard - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | CAL | 0001 | A | 6105AK124-6254-MCAL-0001 | Q24050972-04-6254-M-CAL-0001 |  | Battery Energy Storage System 1 | Offloading Spreader Beam and Equipment for BESS | Vessel and Structure Design with Stress Analysis Calcs | Battery Energy Storage System 1 - Offloading Spreader Beam and Equipment for BESS - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | CAL | 0002 | A | 6105AK124-6254-MCAL-0002 | Q24050972-04-6254-M-CAL-0002 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Vessel and Structure Design with Stress Analysis Calcs | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | CAL | 0003 | A | 6105AK124-6254-MCAL-0003 | Q24050972-04-6254-M-CAL-0003 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Piping Pressure Drop Calculations | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | DST | 0001 | A | 6105AK124-6254-MDST-0001 | Q24050972-04-6254-M-DST-0001 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Pressure Relief Devices Design and Specification | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | EQL | 0001 | A | 6105AK124-6254-MEQL-0001 | Q24050972-04-6254-M-EQL-0001 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Mechanical Equipment Register with Specifications | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | ISO | 0001 | A | 6105AK124-6254-MISO-0001 | Q24050972-04-6254-M-ISO-0001 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Piping Isometric Design and Layouts | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | PRC | 0001 | A | 6105AK124-6254-MPRC-0001 | Q24050972-04-6254-M-PRC-0001 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Rigging Study and Lifting Equipment Design | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | PSP | 0001 | A | 6105AK124-6254-MPSP-0001 | Q24050972-04-6254-M-PSP-0001 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Pipe and Cable Support Racks Design | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | PSP | 0002 | A | 6105AK124-6254-MPSP-0002 | Q24050972-04-6254-M-PSP-0002 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Pipe and Cable Support Racks Design | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | PSP | 0003 | A | 6105AK124-6254-MPSP-0003 | Q24050972-04-6254-M-PSP-0003 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Pipe and Cable Support Racks Design | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | QAD | 0001 | A | 6105AK124-6254-MQAD-0001 | Q24050972-04-6254-M-QAD-0001 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Fabrication Inspection QC Pack (Incl. NDT) | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | SHP | 0001 | A | 6105AK124-6254-MSHP-0001 | Q24050972-04-6254-M-SHP-0001 |  | Battery Energy Storage System 1 | Offloading Spreader Beam and Equipment for BESS | Equipment Fabrication Drawings | Battery Energy Storage System 1 - Offloading Spreader Beam and Equipment for BESS - Equipment Fabrication Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | SPC | 0001 | A | 6105AK124-6254-MSPC-0001 | Q24050972-04-6254-M-SPC-0001 |  | Battery Energy Storage System 1 | Offloading Spreader Beam and Equipment for BESS | Lifting and Crawl Beam Design Specification | Battery Energy Storage System 1 - Offloading Spreader Beam and Equipment for BESS - Lifting and Crawl Beam Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | SPC | 0002 | A | 6105AK124-6254-MSPC-0002 | Q24050972-04-6254-M-SPC-0002 |  | Battery Energy Storage System 1 | Offloading Spreader Beam and Equipment for BESS | Material Selection and Verification Specification | Battery Energy Storage System 1 - Offloading Spreader Beam and Equipment for BESS - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Spreader Beam and Equipment | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | SPC | 0003 | A | 6105AK124-6254-MSPC-0003 | Q24050972-04-6254-M-SPC-0003 |  | Battery Energy Storage System 1 | Cable Racks and Trays for BESS yard | Material Selection and Verification Specification | Battery Energy Storage System 1 - Cable Racks and Trays for BESS yard - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | SPC | 0004 | A | 6105AK124-6254-MSPC-0004 | Q24050972-04-6254-M-SPC-0004 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Material Selection and Verification Specification | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | M | SPC | 0005 | A | 6105AK124-6254-MSPC-0005 | Q24050972-04-6254-M-SPC-0005 |  | Battery Energy Storage System 1 | Fire Protection System for BESS Yard | Gasket Schedule and Material Specification | Battery Energy Storage System 1 - Fire Protection System for BESS Yard - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Fire Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | T | RPT | 0001 | A | 6105AK124-6254-TRPT-0001 | Q24050972-04-6254-T-RPT-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Site Surveying & Geotechnical Report | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | T | RPT | 0002 | A | 6105AK124-6254-TRPT-0002 | Q24050972-04-6254-T-RPT-0002 |  | Battery Energy Storage System 1 | Perimeter Fencing for BESS Yard | Site Surveying & Geotechnical Report | Battery Energy Storage System 1 - Perimeter Fencing for BESS Yard - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | T | RPT | 0003 | A | 6105AK124-6254-TRPT-0003 | Q24050972-04-6254-T-RPT-0003 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Site Surveying & Geotechnical Report | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | T | RPT | 0004 | A | 6105AK124-6254-TRPT-0004 | Q24050972-04-6254-T-RPT-0004 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Site Surveying & Geotechnical Report | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | T | SPC | 0001 | A | 6105AK124-6254-TSPC-0001 | Q24050972-04-6254-T-SPC-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Civil Design and Requirements | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | T | SPC | 0002 | A | 6105AK124-6254-TSPC-0002 | Q24050972-04-6254-T-SPC-0002 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Civil Design and Requirements | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | T | SPC | 0003 | A | 6105AK124-6254-TSPC-0003 | Q24050972-04-6254-T-SPC-0003 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Civil Design and Requirements | Battery Energy Storage System 1 - Earthing System for BESS Yard - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | T | SPC | 0004 | A | 6105AK124-6254-TSPC-0004 | Q24050972-04-6254-T-SPC-0004 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Civil Design and Requirements | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | ELE | 0001 | A | 6105AK124-6254-WELE-0001 | Q24050972-04-6254-W-ELE-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Bulk Earth Works Design and Report | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | ELE | 0002 | A | 6105AK124-6254-WELE-0002 | Q24050972-04-6254-W-ELE-0002 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Bulk Earth Works Design and Report | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | ELE | 0003 | A | 6105AK124-6254-WELE-0003 | Q24050972-04-6254-W-ELE-0003 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Bulk Earth Works Design and Report | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | ELE | 0004 | A | 6105AK124-6254-WELE-0004 | Q24050972-04-6254-W-ELE-0004 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Bulk Earth Works Design and Report | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | LAY | 0001 | A | 6105AK124-6254-WLAY-0001 | Q24050972-04-6254-W-LAY-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Drainage, Run-off and Impoundment Design | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | LAY | 0002 | A | 6105AK124-6254-WLAY-0002 | Q24050972-04-6254-W-LAY-0002 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Drainage, Run-off and Impoundment Design | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | LAY | 0003 | A | 6105AK124-6254-WLAY-0003 | Q24050972-04-6254-W-LAY-0003 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Drainage, Run-off and Impoundment Design | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | LAY | 0004 | A | 6105AK124-6254-WLAY-0004 | Q24050972-04-6254-W-LAY-0004 |  | Battery Energy Storage System 1 | Collection Sump from Bunds for BESS Yard | Drainage, Run-off and Impoundment Design | Battery Energy Storage System 1 - Collection Sump from Bunds for BESS Yard - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | TRP | 0001 | A | 6105AK124-6254-WTRP-0001 | Q24050972-04-6254-W-TRP-0001 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Soil Classification and Nomination Deliverables | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | TRP | 0002 | A | 6105AK124-6254-WTRP-0002 | Q24050972-04-6254-W-TRP-0002 |  | Battery Energy Storage System 1 | Pad Platform and Foundations for BESS Yard | Soil Resistivity Testing Report | Battery Energy Storage System 1 - Pad Platform and Foundations for BESS Yard - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | TRP | 0003 | A | 6105AK124-6254-WTRP-0003 | Q24050972-04-6254-W-TRP-0003 |  | Battery Energy Storage System 1 | LV, Control and Signal Cables for BESS Yard | Soil Classification and Nomination Deliverables | Battery Energy Storage System 1 - LV, Control and Signal Cables for BESS Yard - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | TRP | 0004 | A | 6105AK124-6254-WTRP-0004 | Q24050972-04-6254-W-TRP-0004 |  | Battery Energy Storage System 1 | Cable Trench and Tunnels for BESS yard | Soil Classification and Nomination Deliverables | Battery Energy Storage System 1 - Cable Trench and Tunnels for BESS yard - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | TRP | 0005 | A | 6105AK124-6254-WTRP-0005 | Q24050972-04-6254-W-TRP-0005 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Soil Classification and Nomination Deliverables | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | TRP | 0006 | A | 6105AK124-6254-WTRP-0006 | Q24050972-04-6254-W-TRP-0006 |  | Battery Energy Storage System 1 | Lightning Protection System for BESS Yard | Soil Resistivity Testing Report | Battery Energy Storage System 1 - Lightning Protection System for BESS Yard - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | TRP | 0007 | A | 6105AK124-6254-WTRP-0007 | Q24050972-04-6254-W-TRP-0007 |  | Battery Energy Storage System 1 | Earthing System for BESS Yard | Soil Resistivity Testing Report | Battery Energy Storage System 1 - Earthing System for BESS Yard - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | TRP | 0008 | A | 6105AK124-6254-WTRP-0008 | Q24050972-04-6254-W-TRP-0008 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Soil Classification and Nomination Deliverables | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6254 | W | TRP | 0009 | A | 6105AK124-6254-WTRP-0009 | Q24050972-04-6254-W-TRP-0009 |  | Battery Energy Storage System 1 | Terrace, Roads and Access-ways for BESS Yard | Soil Resistivity Testing Report | Battery Energy Storage System 1 - Terrace, Roads and Access-ways for BESS Yard - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace, Roads and Access-ways | BESS Yard |  |  |  | Pending
6105A | K124 | 6256 | F | DIA | 0001 | A | 6105AK124-6256-FDIA-0001 | Q24050972-04-6256-F-DIA-0001 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Interface Panel and I/O Schematics | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | F | DIA | 0002 | A | 6105AK124-6256-FDIA-0002 | Q24050972-04-6256-F-DIA-0002 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Control Network Architecture Design | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | I | SPC | 0001 | A | 6105AK124-6256-ISPC-0001 | Q24050972-04-6256-I-SPC-0001 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Junction Box and Interface Cabinet Design | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | M | CAL | 0001 | A | 6105AK124-6256-MCAL-0001 | Q24050972-04-6256-M-CAL-0001 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Vessel and Structure Design with Stress Analysis Calcs | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | M | PRC | 0001 | A | 6105AK124-6256-MPRC-0001 | Q24050972-04-6256-M-PRC-0001 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Rigging Study and Lifting Equipment Design | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | M | PSP | 0001 | A | 6105AK124-6256-MPSP-0001 | Q24050972-04-6256-M-PSP-0001 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Pipe and Cable Support Racks Design | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | M | SPC | 0001 | A | 6105AK124-6256-MSPC-0001 | Q24050972-04-6256-M-SPC-0001 |  | Synchronous Condenser 2 | Cable Racks and Trays for Synchronous Condensers Yard 2 | Material Selection and Verification Specification | Synchronous Condenser 2 - Cable Racks and Trays for Synchronous Condensers Yard 2 - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | T | RPT | 0001 | A | 6105AK124-6256-TRPT-0001 | Q24050972-04-6256-T-RPT-0001 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Site Surveying & Geotechnical Report | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | T | SPC | 0001 | A | 6105AK124-6256-TSPC-0001 | Q24050972-04-6256-T-SPC-0001 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Civil Design and Requirements | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | T | SPC | 0002 | A | 6105AK124-6256-TSPC-0002 | Q24050972-04-6256-T-SPC-0002 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Civil Design and Requirements | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | W | ELE | 0001 | A | 6105AK124-6256-WELE-0001 | Q24050972-04-6256-W-ELE-0001 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Bulk Earth Works Design and Report | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | W | ELE | 0002 | A | 6105AK124-6256-WELE-0002 | Q24050972-04-6256-W-ELE-0002 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Bulk Earth Works Design and Report | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | W | LAY | 0001 | A | 6105AK124-6256-WLAY-0001 | Q24050972-04-6256-W-LAY-0001 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Drainage, Run-off and Impoundment Design | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | W | LAY | 0002 | A | 6105AK124-6256-WLAY-0002 | Q24050972-04-6256-W-LAY-0002 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Drainage, Run-off and Impoundment Design | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | W | TRP | 0001 | A | 6105AK124-6256-WTRP-0001 | Q24050972-04-6256-W-TRP-0001 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Soil Classification and Nomination Deliverables | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | W | TRP | 0002 | A | 6105AK124-6256-WTRP-0002 | Q24050972-04-6256-W-TRP-0002 |  | Synchronous Condenser 2 | Terrace Roads and Access-ways for Synchronous Condensers Yard 2 | Soil Resistivity Testing Report | Synchronous Condenser 2 - Terrace Roads and Access-ways for Synchronous Condensers Yard 2 - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | W | TRP | 0003 | A | 6105AK124-6256-WTRP-0003 | Q24050972-04-6256-W-TRP-0003 |  | Synchronous Condenser 2 | Earthing System for Synchronous Condensers Yard 2 | Soil Resistivity Testing Report | Synchronous Condenser 2 - Earthing System for Synchronous Condensers Yard 2 - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | W | TRP | 0004 | A | 6105AK124-6256-WTRP-0004 | Q24050972-04-6256-W-TRP-0004 |  | Synchronous Condenser 2 | Cable Trench and Tunnels for Synchronous Condensers Yard 2 | Soil Classification and Nomination Deliverables | Synchronous Condenser 2 - Cable Trench and Tunnels for Synchronous Condensers Yard 2 - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench and Tunnels | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | W | TRP | 0005 | A | 6105AK124-6256-WTRP-0005 | Q24050972-04-6256-W-TRP-0005 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Soil Classification and Nomination Deliverables | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6256 | W | TRP | 0006 | A | 6105AK124-6256-WTRP-0006 | Q24050972-04-6256-W-TRP-0006 |  | Synchronous Condenser 2 | Lightning Protection System for Synchronous Condensers Yard 2 | Soil Resistivity Testing Report | Synchronous Condenser 2 - Lightning Protection System for Synchronous Condensers Yard 2 - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | Synchronous Condensers Yard 2 |  |  |  | Pending
6105A | K124 | 6261 | C | FND | 0001 | A | 6105AK124-6261-CFND-0001 | Q24050972-04-6261-C-FND-0001 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Civil Foundation Design | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | FND | 0002 | A | 6105AK124-6261-CFND-0002 | Q24050972-04-6261-C-FND-0002 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Civil Foundation Design | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | FND | 0003 | A | 6105AK124-6261-CFND-0003 | Q24050972-04-6261-C-FND-0003 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Civil Foundation Design | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | FND | 0004 | A | 6105AK124-6261-CFND-0004 | Q24050972-04-6261-C-FND-0004 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Plinth Design and Layout | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | FND | 0005 | A | 6105AK124-6261-CFND-0005 | Q24050972-04-6261-C-FND-0005 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Civil Foundation Design | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | FND | 0006 | A | 6105AK124-6261-CFND-0006 | Q24050972-04-6261-C-FND-0006 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Plinth Design and Layout | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0001 | A | 6105AK124-6261-CGAD-0001 | Q24050972-04-6261-C-GAD-0001 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Buildings and Structures GA | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0002 | A | 6105AK124-6261-CGAD-0002 | Q24050972-04-6261-C-GAD-0002 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Cables, OHL and Fibre Route GA | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0003 | A | 6105AK124-6261-CGAD-0003 | Q24050972-04-6261-C-GAD-0003 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Key Emergency Points and Equipment | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0004 | A | 6105AK124-6261-CGAD-0004 | Q24050972-04-6261-C-GAD-0004 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Terrace Equipment GA | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0005 | A | 6105AK124-6261-CGAD-0005 | Q24050972-04-6261-C-GAD-0005 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Disposal Areas General Arrangement | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0006 | A | 6105AK124-6261-CGAD-0006 | Q24050972-04-6261-C-GAD-0006 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Laydown Areas and Temp Buildings GA | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0007 | A | 6105AK124-6261-CGAD-0007 | Q24050972-04-6261-C-GAD-0007 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Stormwater and Effluent System Design | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0008 | A | 6105AK124-6261-CGAD-0008 | Q24050972-04-6261-C-GAD-0008 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Lighting Design and Layout GA | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0009 | A | 6105AK124-6261-CGAD-0009 | Q24050972-04-6261-C-GAD-0009 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Roads, Pathways, Offloading Areas and Fences GA | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0010 | A | 6105AK124-6261-CGAD-0010 | Q24050972-04-6261-C-GAD-0010 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Lighting Design and Layout GA | Administration and General Buildings - Earthing System for 36 MVA Power Station - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0011 | A | 6105AK124-6261-CGAD-0011 | Q24050972-04-6261-C-GAD-0011 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Buildings and Structures GA | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0012 | A | 6105AK124-6261-CGAD-0012 | Q24050972-04-6261-C-GAD-0012 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Cables, OHL and Fibre Route GA | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0013 | A | 6105AK124-6261-CGAD-0013 | Q24050972-04-6261-C-GAD-0013 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Terrace Equipment GA | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0014 | A | 6105AK124-6261-CGAD-0014 | Q24050972-04-6261-C-GAD-0014 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Laydown Areas and Temp Buildings GA | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0015 | A | 6105AK124-6261-CGAD-0015 | Q24050972-04-6261-C-GAD-0015 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Lighting Design and Layout GA | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0016 | A | 6105AK124-6261-CGAD-0016 | Q24050972-04-6261-C-GAD-0016 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Roads, Pathways, Offloading Areas and Fences GA | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0017 | A | 6105AK124-6261-CGAD-0017 | Q24050972-04-6261-C-GAD-0017 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Buildings and Structures GA | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0018 | A | 6105AK124-6261-CGAD-0018 | Q24050972-04-6261-C-GAD-0018 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Cables, OHL and Fibre Route GA | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0019 | A | 6105AK124-6261-CGAD-0019 | Q24050972-04-6261-C-GAD-0019 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Terrace Equipment GA | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0020 | A | 6105AK124-6261-CGAD-0020 | Q24050972-04-6261-C-GAD-0020 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Roads, Pathways, Offloading Areas and Fences GA | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0021 | A | 6105AK124-6261-CGAD-0021 | Q24050972-04-6261-C-GAD-0021 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Buildings and Structures GA | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0022 | A | 6105AK124-6261-CGAD-0022 | Q24050972-04-6261-C-GAD-0022 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Cables, OHL and Fibre Route GA | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0023 | A | 6105AK124-6261-CGAD-0023 | Q24050972-04-6261-C-GAD-0023 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Terrace Equipment GA | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0024 | A | 6105AK124-6261-CGAD-0024 | Q24050972-04-6261-C-GAD-0024 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Buildings and Structures GA | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0025 | A | 6105AK124-6261-CGAD-0025 | Q24050972-04-6261-C-GAD-0025 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Cables, OHL and Fibre Route GA | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0026 | A | 6105AK124-6261-CGAD-0026 | Q24050972-04-6261-C-GAD-0026 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Terrace Equipment GA | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0027 | A | 6105AK124-6261-CGAD-0027 | Q24050972-04-6261-C-GAD-0027 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Cables, OHL and Fibre Route GA | Administration and General Buildings - MV Cables for 36 MVA Power Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0028 | A | 6105AK124-6261-CGAD-0028 | Q24050972-04-6261-C-GAD-0028 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Terrace Equipment GA | Administration and General Buildings - MV Cables for 36 MVA Power Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0029 | A | 6105AK124-6261-CGAD-0029 | Q24050972-04-6261-C-GAD-0029 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Buildings and Structures GA | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0030 | A | 6105AK124-6261-CGAD-0030 | Q24050972-04-6261-C-GAD-0030 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Cables, OHL and Fibre Route GA | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0031 | A | 6105AK124-6261-CGAD-0031 | Q24050972-04-6261-C-GAD-0031 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Terrace Equipment GA | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0032 | A | 6105AK124-6261-CGAD-0032 | Q24050972-04-6261-C-GAD-0032 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Cables, OHL and Fibre Route GA | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0033 | A | 6105AK124-6261-CGAD-0033 | Q24050972-04-6261-C-GAD-0033 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Terrace Equipment GA | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0034 | A | 6105AK124-6261-CGAD-0034 | Q24050972-04-6261-C-GAD-0034 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Buildings and Structures GA | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0035 | A | 6105AK124-6261-CGAD-0035 | Q24050972-04-6261-C-GAD-0035 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Cables, OHL and Fibre Route GA | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0036 | A | 6105AK124-6261-CGAD-0036 | Q24050972-04-6261-C-GAD-0036 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Terrace Equipment GA | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0037 | A | 6105AK124-6261-CGAD-0037 | Q24050972-04-6261-C-GAD-0037 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Terrace Equipment GA | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | MDL | 0001 | A | 6105AK124-6261-CMDL-0001 | Q24050972-04-6261-C-MDL-0001 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | 3D Designs and Drawings | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | MDL | 0002 | A | 6105AK124-6261-CMDL-0002 | Q24050972-04-6261-C-MDL-0002 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | 3D Designs and Drawings | Administration and General Buildings - Earthing System for 36 MVA Power Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | MDL | 0003 | A | 6105AK124-6261-CMDL-0003 | Q24050972-04-6261-C-MDL-0003 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | 3D Designs and Drawings | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | MDL | 0004 | A | 6105AK124-6261-CMDL-0004 | Q24050972-04-6261-C-MDL-0004 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | 3D Designs and Drawings | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | MDL | 0005 | A | 6105AK124-6261-CMDL-0005 | Q24050972-04-6261-C-MDL-0005 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | 3D Designs and Drawings | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | MDL | 0006 | A | 6105AK124-6261-CMDL-0006 | Q24050972-04-6261-C-MDL-0006 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | 3D Designs and Drawings | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | PLN | 0001 | A | 6105AK124-6261-CPLN-0001 | Q24050972-04-6261-C-PLN-0001 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Civil Works Execution Plan | Administration and General Buildings - Earthing System for 36 MVA Power Station - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | PLN | 0002 | A | 6105AK124-6261-CPLN-0002 | Q24050972-04-6261-C-PLN-0002 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Civil Works Execution Plan | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | PLN | 0003 | A | 6105AK124-6261-CPLN-0003 | Q24050972-04-6261-C-PLN-0003 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Civil Works Execution Plan | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | PLN | 0004 | A | 6105AK124-6261-CPLN-0004 | Q24050972-04-6261-C-PLN-0004 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Civil Works Execution Plan | Administration and General Buildings - MV Cables for 36 MVA Power Station - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | PLN | 0005 | A | 6105AK124-6261-CPLN-0005 | Q24050972-04-6261-C-PLN-0005 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Civil Works Execution Plan | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | PLN | 0006 | A | 6105AK124-6261-CPLN-0006 | Q24050972-04-6261-C-PLN-0006 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Civil Works Execution Plan | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | PLN | 0007 | A | 6105AK124-6261-CPLN-0007 | Q24050972-04-6261-C-PLN-0007 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Civil Works Execution Plan | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | PPL | 0001 | A | 6105AK124-6261-CPPL-0001 | Q24050972-04-6261-C-PPL-0001 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Operational & Maint Access Routes Design | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | PPL | 0002 | A | 6105AK124-6261-CPPL-0002 | Q24050972-04-6261-C-PPL-0002 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Operational & Maint Access Routes Design | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | PPL | 0003 | A | 6105AK124-6261-CPPL-0003 | Q24050972-04-6261-C-PPL-0003 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Operational & Maint Access Routes Design | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | PPL | 0004 | A | 6105AK124-6261-CPPL-0004 | Q24050972-04-6261-C-PPL-0004 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Operational & Maint Access Routes Design | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | PPL | 0005 | A | 6105AK124-6261-CPPL-0005 | Q24050972-04-6261-C-PPL-0005 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Operational & Maint Access Routes Design | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SEC | 0001 | A | 6105AK124-6261-CSEC-0001 | Q24050972-04-6261-C-SEC-0001 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Corrosion Prevention and Protection Design | Administration and General Buildings - Earthing System for 36 MVA Power Station - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SEC | 0002 | A | 6105AK124-6261-CSEC-0002 | Q24050972-04-6261-C-SEC-0002 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Structural Earthing and Bonding Design | Administration and General Buildings - Earthing System for 36 MVA Power Station - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SEC | 0003 | A | 6105AK124-6261-CSEC-0003 | Q24050972-04-6261-C-SEC-0003 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Corrosion Prevention and Protection Design | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SEC | 0004 | A | 6105AK124-6261-CSEC-0004 | Q24050972-04-6261-C-SEC-0004 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Structural Earthing and Bonding Design | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SEC | 0005 | A | 6105AK124-6261-CSEC-0005 | Q24050972-04-6261-C-SEC-0005 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Corrosion Prevention and Protection Design | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SEC | 0006 | A | 6105AK124-6261-CSEC-0006 | Q24050972-04-6261-C-SEC-0006 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Structural Earthing and Bonding Design | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SEC | 0007 | A | 6105AK124-6261-CSEC-0007 | Q24050972-04-6261-C-SEC-0007 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Corrosion Prevention and Protection Design | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SEC | 0008 | A | 6105AK124-6261-CSEC-0008 | Q24050972-04-6261-C-SEC-0008 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Structural Earthing and Bonding Design | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SHP | 0001 | A | 6105AK124-6261-CSHP-0001 | Q24050972-04-6261-C-SHP-0001 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Equipment Assembly Drawings | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SHP | 0002 | A | 6105AK124-6261-CSHP-0002 | Q24050972-04-6261-C-SHP-0002 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Equipment Assembly Drawings | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SHP | 0003 | A | 6105AK124-6261-CSHP-0003 | Q24050972-04-6261-C-SHP-0003 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Equipment Assembly Drawings | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0001 | A | 6105AK124-6261-CSPC-0001 | Q24050972-04-6261-C-SPC-0001 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Civil Design Requirements | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0002 | A | 6105AK124-6261-CSPC-0002 | Q24050972-04-6261-C-SPC-0002 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Excavation, Trenching and Compacting Design | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0003 | A | 6105AK124-6261-CSPC-0003 | Q24050972-04-6261-C-SPC-0003 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Concrete Construction Material Specifications | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0004 | A | 6105AK124-6261-CSPC-0004 | Q24050972-04-6261-C-SPC-0004 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Concrete Construction Material Specifications | Administration and General Buildings - Earthing System for 36 MVA Power Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0005 | A | 6105AK124-6261-CSPC-0005 | Q24050972-04-6261-C-SPC-0005 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Excavation, Trenching and Compacting Design | Administration and General Buildings - Earthing System for 36 MVA Power Station - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0006 | A | 6105AK124-6261-CSPC-0006 | Q24050972-04-6261-C-SPC-0006 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Concrete Construction Material Specifications | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0007 | A | 6105AK124-6261-CSPC-0007 | Q24050972-04-6261-C-SPC-0007 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Civil Design Requirements | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0008 | A | 6105AK124-6261-CSPC-0008 | Q24050972-04-6261-C-SPC-0008 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Concrete Construction Material Specifications | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0009 | A | 6105AK124-6261-CSPC-0009 | Q24050972-04-6261-C-SPC-0009 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Steel Structures Corrosion Protection Specification | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0010 | A | 6105AK124-6261-CSPC-0010 | Q24050972-04-6261-C-SPC-0010 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Civil Design Requirements | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0011 | A | 6105AK124-6261-CSPC-0011 | Q24050972-04-6261-C-SPC-0011 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Excavation, Trenching and Compacting Design | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0012 | A | 6105AK124-6261-CSPC-0012 | Q24050972-04-6261-C-SPC-0012 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Concrete Construction Material Specifications | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0013 | A | 6105AK124-6261-CSPC-0013 | Q24050972-04-6261-C-SPC-0013 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Excavation, Trenching and Compacting Design | Administration and General Buildings - MV Cables for 36 MVA Power Station - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0014 | A | 6105AK124-6261-CSPC-0014 | Q24050972-04-6261-C-SPC-0014 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Concrete Construction Material Specifications | Administration and General Buildings - MV Cables for 36 MVA Power Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0015 | A | 6105AK124-6261-CSPC-0015 | Q24050972-04-6261-C-SPC-0015 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Concrete Construction Material Specifications | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0016 | A | 6105AK124-6261-CSPC-0016 | Q24050972-04-6261-C-SPC-0016 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Excavation, Trenching and Compacting Design | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0017 | A | 6105AK124-6261-CSPC-0017 | Q24050972-04-6261-C-SPC-0017 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Concrete Construction Material Specifications | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SPC | 0018 | A | 6105AK124-6261-CSPC-0018 | Q24050972-04-6261-C-SPC-0018 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Concrete Construction Material Specifications | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | SSD | 0001 | A | 6105AK124-6261-CSSD-0001 | Q24050972-04-6261-C-SSD-0001 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Steel Support Structures Design | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0001 | A | 6105AK124-6261-CSTD-0001 | Q24050972-04-6261-C-STD-0001 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Bund-wall Requirements and Design | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0002 | A | 6105AK124-6261-CSTD-0002 | Q24050972-04-6261-C-STD-0002 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Civil Construction Requirements | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0003 | A | 6105AK124-6261-CSTD-0003 | Q24050972-04-6261-C-STD-0003 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Underground Pipe Route and Cable Bedding Design | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0004 | A | 6105AK124-6261-CSTD-0004 | Q24050972-04-6261-C-STD-0004 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Civil Construction Requirements | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0005 | A | 6105AK124-6261-CSTD-0005 | Q24050972-04-6261-C-STD-0005 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Underground Pipe Route and Cable Bedding Design | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0006 | A | 6105AK124-6261-CSTD-0006 | Q24050972-04-6261-C-STD-0006 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Underground Pipe Route and Cable Bedding Design | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0007 | A | 6105AK124-6261-CSTD-0007 | Q24050972-04-6261-C-STD-0007 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Civil Construction Requirements | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0008 | A | 6105AK124-6261-CSTD-0008 | Q24050972-04-6261-C-STD-0008 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Underground Pipe Route and Cable Bedding Design | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0009 | A | 6105AK124-6261-CSTD-0009 | Q24050972-04-6261-C-STD-0009 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Civil Construction Requirements | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0010 | A | 6105AK124-6261-CSTD-0010 | Q24050972-04-6261-C-STD-0010 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Underground Pipe Route and Cable Bedding Design | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0011 | A | 6105AK124-6261-CSTD-0011 | Q24050972-04-6261-C-STD-0011 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Civil Construction Requirements | Administration and General Buildings - MV Cables for 36 MVA Power Station - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0012 | A | 6105AK124-6261-CSTD-0012 | Q24050972-04-6261-C-STD-0012 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Underground Pipe Route and Cable Bedding Design | Administration and General Buildings - MV Cables for 36 MVA Power Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0013 | A | 6105AK124-6261-CSTD-0013 | Q24050972-04-6261-C-STD-0013 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Civil Construction Requirements | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | C | STD | 0014 | A | 6105AK124-6261-CSTD-0014 | Q24050972-04-6261-C-STD-0014 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Underground Pipe Route and Cable Bedding Design | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | CAL | 0001 | A | 6105AK124-6261-ECAL-0001 | Q24050972-04-6261-E-CAL-0001 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Conductor Sag and Tension Plan | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | CAL | 0002 | A | 6105AK124-6261-ECAL-0002 | Q24050972-04-6261-E-CAL-0002 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Cable and Conductor Sizing (incl Volt Drop Calcs) | Administration and General Buildings - Earthing System for 36 MVA Power Station - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | CAL | 0003 | A | 6105AK124-6261-ECAL-0003 | Q24050972-04-6261-E-CAL-0003 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Impedance and Burn-off Calculations | Administration and General Buildings - Earthing System for 36 MVA Power Station - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | CAL | 0004 | A | 6105AK124-6261-ECAL-0004 | Q24050972-04-6261-E-CAL-0004 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Cable and Conductor Sizing (incl Volt Drop Calcs) | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | CAL | 0005 | A | 6105AK124-6261-ECAL-0005 | Q24050972-04-6261-E-CAL-0005 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Conductor Sag and Tension Plan | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | CAL | 0006 | A | 6105AK124-6261-ECAL-0006 | Q24050972-04-6261-E-CAL-0006 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Impedance and Burn-off Calculations | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | CAL | 0007 | A | 6105AK124-6261-ECAL-0007 | Q24050972-04-6261-E-CAL-0007 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Cable and Conductor Sizing (incl Volt Drop Calcs) | Administration and General Buildings - MV Cables for 36 MVA Power Station - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | CAL | 0008 | A | 6105AK124-6261-ECAL-0008 | Q24050972-04-6261-E-CAL-0008 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Impedance and Burn-off Calculations | Administration and General Buildings - MV Cables for 36 MVA Power Station - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | CAL | 0009 | A | 6105AK124-6261-ECAL-0009 | Q24050972-04-6261-E-CAL-0009 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Cable and Conductor Sizing (incl Volt Drop Calcs) | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | CAL | 0010 | A | 6105AK124-6261-ECAL-0010 | Q24050972-04-6261-E-CAL-0010 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Cable and Conductor Sizing (incl Volt Drop Calcs) | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | CAL | 0011 | A | 6105AK124-6261-ECAL-0011 | Q24050972-04-6261-E-CAL-0011 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Impedance and Burn-off Calculations | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | CAL | 0012 | A | 6105AK124-6261-ECAL-0012 | Q24050972-04-6261-E-CAL-0012 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Cable and Conductor Sizing (incl Volt Drop Calcs) | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0001 | A | 6105AK124-6261-EDIA-0001 | Q24050972-04-6261-E-DIA-0001 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Electrical Circuit Diagrams (Schematics) | Administration and General Buildings - Earthing System for 36 MVA Power Station - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0002 | A | 6105AK124-6261-EDIA-0002 | Q24050972-04-6261-E-DIA-0002 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Cable Block Diagrams and Schedules | Administration and General Buildings - Earthing System for 36 MVA Power Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0003 | A | 6105AK124-6261-EDIA-0003 | Q24050972-04-6261-E-DIA-0003 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | E/I Termination Schedule | Administration and General Buildings - Earthing System for 36 MVA Power Station - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0004 | A | 6105AK124-6261-EDIA-0004 | Q24050972-04-6261-E-DIA-0004 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Cable Block Diagrams and Schedules | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0005 | A | 6105AK124-6261-EDIA-0005 | Q24050972-04-6261-E-DIA-0005 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Electrical Block Diagram | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0006 | A | 6105AK124-6261-EDIA-0006 | Q24050972-04-6261-E-DIA-0006 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Electrical Circuit Diagrams (Schematics) | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0007 | A | 6105AK124-6261-EDIA-0007 | Q24050972-04-6261-E-DIA-0007 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | E/I Termination Schedule | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0008 | A | 6105AK124-6261-EDIA-0008 | Q24050972-04-6261-E-DIA-0008 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Cable Block Diagrams and Schedules | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0009 | A | 6105AK124-6261-EDIA-0009 | Q24050972-04-6261-E-DIA-0009 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | E/I Termination Schedule | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0010 | A | 6105AK124-6261-EDIA-0010 | Q24050972-04-6261-E-DIA-0010 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Cable Block Diagrams and Schedules | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0011 | A | 6105AK124-6261-EDIA-0011 | Q24050972-04-6261-E-DIA-0011 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | E/I Termination Schedule | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0012 | A | 6105AK124-6261-EDIA-0012 | Q24050972-04-6261-E-DIA-0012 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Cable Block Diagrams and Schedules | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0013 | A | 6105AK124-6261-EDIA-0013 | Q24050972-04-6261-E-DIA-0013 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Electrical Circuit Diagrams (Schematics) | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0014 | A | 6105AK124-6261-EDIA-0014 | Q24050972-04-6261-E-DIA-0014 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Cable Block Diagrams and Schedules | Administration and General Buildings - MV Cables for 36 MVA Power Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0015 | A | 6105AK124-6261-EDIA-0015 | Q24050972-04-6261-E-DIA-0015 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Electrical Circuit Diagrams (Schematics) | Administration and General Buildings - MV Cables for 36 MVA Power Station - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0016 | A | 6105AK124-6261-EDIA-0016 | Q24050972-04-6261-E-DIA-0016 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Electrical Block Diagram | Administration and General Buildings - MV Cables for 36 MVA Power Station - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0017 | A | 6105AK124-6261-EDIA-0017 | Q24050972-04-6261-E-DIA-0017 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | E/I Termination Schedule | Administration and General Buildings - MV Cables for 36 MVA Power Station - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0018 | A | 6105AK124-6261-EDIA-0018 | Q24050972-04-6261-E-DIA-0018 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Cable Block Diagrams and Schedules | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0019 | A | 6105AK124-6261-EDIA-0019 | Q24050972-04-6261-E-DIA-0019 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Electrical Circuit Diagrams (Schematics) | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0020 | A | 6105AK124-6261-EDIA-0020 | Q24050972-04-6261-E-DIA-0020 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | E/I Termination Schedule | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0021 | A | 6105AK124-6261-EDIA-0021 | Q24050972-04-6261-E-DIA-0021 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Electrical Block Diagram | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0022 | A | 6105AK124-6261-EDIA-0022 | Q24050972-04-6261-E-DIA-0022 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Cable Block Diagrams and Schedules | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0023 | A | 6105AK124-6261-EDIA-0023 | Q24050972-04-6261-E-DIA-0023 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Electrical Circuit Diagrams (Schematics) | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0024 | A | 6105AK124-6261-EDIA-0024 | Q24050972-04-6261-E-DIA-0024 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Electrical Block Diagram | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0025 | A | 6105AK124-6261-EDIA-0025 | Q24050972-04-6261-E-DIA-0025 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | E/I Termination Schedule | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0026 | A | 6105AK124-6261-EDIA-0026 | Q24050972-04-6261-E-DIA-0026 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Cable Block Diagrams and Schedules | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0027 | A | 6105AK124-6261-EDIA-0027 | Q24050972-04-6261-E-DIA-0027 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Electrical Circuit Diagrams (Schematics) | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0028 | A | 6105AK124-6261-EDIA-0028 | Q24050972-04-6261-E-DIA-0028 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | E/I Termination Schedule | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0029 | A | 6105AK124-6261-EDIA-0029 | Q24050972-04-6261-E-DIA-0029 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Electrical Block Diagram | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0030 | A | 6105AK124-6261-EDIA-0030 | Q24050972-04-6261-E-DIA-0030 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Cable Block Diagrams and Schedules | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0031 | A | 6105AK124-6261-EDIA-0031 | Q24050972-04-6261-E-DIA-0031 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Electrical Circuit Diagrams (Schematics) | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DIA | 0032 | A | 6105AK124-6261-EDIA-0032 | Q24050972-04-6261-E-DIA-0032 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Electrical Block Diagram | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DST | 0001 | A | 6105AK124-6261-EDST-0001 | Q24050972-04-6261-E-DST-0001 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Equipment Register and Technical Specifications | Administration and General Buildings - Earthing System for 36 MVA Power Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DST | 0002 | A | 6105AK124-6261-EDST-0002 | Q24050972-04-6261-E-DST-0002 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Equipment Register and Technical Specifications | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DST | 0003 | A | 6105AK124-6261-EDST-0003 | Q24050972-04-6261-E-DST-0003 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Equipment Register and Technical Specifications | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DST | 0004 | A | 6105AK124-6261-EDST-0004 | Q24050972-04-6261-E-DST-0004 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Equipment Register and Technical Specifications | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DST | 0005 | A | 6105AK124-6261-EDST-0005 | Q24050972-04-6261-E-DST-0005 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Equipment Register and Technical Specifications | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DST | 0006 | A | 6105AK124-6261-EDST-0006 | Q24050972-04-6261-E-DST-0006 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Equipment Register and Technical Specifications | Administration and General Buildings - MV Cables for 36 MVA Power Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DST | 0007 | A | 6105AK124-6261-EDST-0007 | Q24050972-04-6261-E-DST-0007 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Equipment Register and Technical Specifications | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DST | 0008 | A | 6105AK124-6261-EDST-0008 | Q24050972-04-6261-E-DST-0008 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Equipment Register and Technical Specifications | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DST | 0009 | A | 6105AK124-6261-EDST-0009 | Q24050972-04-6261-E-DST-0009 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Equipment Register and Technical Specifications | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DST | 0010 | A | 6105AK124-6261-EDST-0010 | Q24050972-04-6261-E-DST-0010 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | CT and PT Datasheets | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - CT and PT Datasheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | DST | 0011 | A | 6105AK124-6261-EDST-0011 | Q24050972-04-6261-E-DST-0011 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Equipment Register and Technical Specifications | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | EQL | 0001 | A | 6105AK124-6261-EEQL-0001 | Q24050972-04-6261-E-EQL-0001 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Electrical Equipment Load Register | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | EQL | 0002 | A | 6105AK124-6261-EEQL-0002 | Q24050972-04-6261-E-EQL-0002 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Electrical Equipment Load Register | Administration and General Buildings - MV Cables for 36 MVA Power Station - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | EQL | 0003 | A | 6105AK124-6261-EEQL-0003 | Q24050972-04-6261-E-EQL-0003 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Electrical Equipment Load Register | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | LAY | 0001 | A | 6105AK124-6261-ELAY-0001 | Q24050972-04-6261-E-LAY-0001 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Control Room Power and Earthing Design | Administration and General Buildings - Earthing System for 36 MVA Power Station - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | LAY | 0002 | A | 6105AK124-6261-ELAY-0002 | Q24050972-04-6261-E-LAY-0002 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Control Room Power and Earthing Design | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | LAY | 0003 | A | 6105AK124-6261-ELAY-0003 | Q24050972-04-6261-E-LAY-0003 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Control Room Power and Earthing Design | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | LAY | 0004 | A | 6105AK124-6261-ELAY-0004 | Q24050972-04-6261-E-LAY-0004 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Switch Room (PCC and MCC) Detail Design | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Switch Room (PCC and MCC) Detail Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | QRA | 0001 | A | 6105AK124-6261-EQRA-0001 | Q24050972-04-6261-E-QRA-0001 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Lightning Protection Study and Risk Assessment | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | QRA | 0002 | A | 6105AK124-6261-EQRA-0002 | Q24050972-04-6261-E-QRA-0002 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Lightning Protection Study and Risk Assessment | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | QRA | 0003 | A | 6105AK124-6261-EQRA-0003 | Q24050972-04-6261-E-QRA-0003 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Risk Assessment: Electrical Hazards | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | QRA | 0004 | A | 6105AK124-6261-EQRA-0004 | Q24050972-04-6261-E-QRA-0004 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Lightning Protection Study and Risk Assessment | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SLD | 0001 | A | 6105AK124-6261-ESLD-0001 | Q24050972-04-6261-E-SLD-0001 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Electrical Single Line Diagram | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SLD | 0002 | A | 6105AK124-6261-ESLD-0002 | Q24050972-04-6261-E-SLD-0002 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Electrical Single Line Diagram | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SLD | 0003 | A | 6105AK124-6261-ESLD-0003 | Q24050972-04-6261-E-SLD-0003 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Electrical Single Line Diagram | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SLD | 0004 | A | 6105AK124-6261-ESLD-0004 | Q24050972-04-6261-E-SLD-0004 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Electrical Single Line Diagram | Administration and General Buildings - MV Cables for 36 MVA Power Station - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SLD | 0005 | A | 6105AK124-6261-ESLD-0005 | Q24050972-04-6261-E-SLD-0005 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Electrical Single Line Diagram | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SLD | 0006 | A | 6105AK124-6261-ESLD-0006 | Q24050972-04-6261-E-SLD-0006 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Electrical Single Line Diagram | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SLD | 0007 | A | 6105AK124-6261-ESLD-0007 | Q24050972-04-6261-E-SLD-0007 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Electrical Single Line Diagram | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SPC | 0001 | A | 6105AK124-6261-ESPC-0001 | Q24050972-04-6261-E-SPC-0001 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Cable Termination Specifications | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SPC | 0002 | A | 6105AK124-6261-ESPC-0002 | Q24050972-04-6261-E-SPC-0002 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Cable and Conductor Specifications | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SPC | 0003 | A | 6105AK124-6261-ESPC-0003 | Q24050972-04-6261-E-SPC-0003 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Lighting and Luminaire Design | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SPC | 0004 | A | 6105AK124-6261-ESPC-0004 | Q24050972-04-6261-E-SPC-0004 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Cable and Conductor Specifications | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SPC | 0005 | A | 6105AK124-6261-ESPC-0005 | Q24050972-04-6261-E-SPC-0005 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Cable and Conductor Specifications | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SPC | 0006 | A | 6105AK124-6261-ESPC-0006 | Q24050972-04-6261-E-SPC-0006 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Lighting and Luminaire Design | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SPC | 0007 | A | 6105AK124-6261-ESPC-0007 | Q24050972-04-6261-E-SPC-0007 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Cable Termination Specifications | Administration and General Buildings - MV Cables for 36 MVA Power Station - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SPC | 0008 | A | 6105AK124-6261-ESPC-0008 | Q24050972-04-6261-E-SPC-0008 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Cable Termination Specifications | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SPC | 0009 | A | 6105AK124-6261-ESPC-0009 | Q24050972-04-6261-E-SPC-0009 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Cable Termination Specifications | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SPC | 0010 | A | 6105AK124-6261-ESPC-0010 | Q24050972-04-6261-E-SPC-0010 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Cable Termination Specifications | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | SPC | 0011 | A | 6105AK124-6261-ESPC-0011 | Q24050972-04-6261-E-SPC-0011 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Cable Termination Specifications | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0001 | A | 6105AK124-6261-ESTD-0001 | Q24050972-04-6261-E-STD-0001 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Earth Map and Bonding Design | Administration and General Buildings - Earthing System for 36 MVA Power Station - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0002 | A | 6105AK124-6261-ESTD-0002 | Q24050972-04-6261-E-STD-0002 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Electrical Design Standards | Administration and General Buildings - Earthing System for 36 MVA Power Station - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0003 | A | 6105AK124-6261-ESTD-0003 | Q24050972-04-6261-E-STD-0003 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Electrical Equipment Installation Requirements | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0004 | A | 6105AK124-6261-ESTD-0004 | Q24050972-04-6261-E-STD-0004 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Earth Map and Bonding Design | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0005 | A | 6105AK124-6261-ESTD-0005 | Q24050972-04-6261-E-STD-0005 |  | Administration and General Buildings | Small Power and Lighting for 36 MVA Power Station | Electrical Design Standards | Administration and General Buildings - Small Power and Lighting for 36 MVA Power Station - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Small Power and Lighting | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0006 | A | 6105AK124-6261-ESTD-0006 | Q24050972-04-6261-E-STD-0006 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Thermal Management and Fire Prevention Design | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0007 | A | 6105AK124-6261-ESTD-0007 | Q24050972-04-6261-E-STD-0007 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Electrical Equipment Installation Requirements | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0008 | A | 6105AK124-6261-ESTD-0008 | Q24050972-04-6261-E-STD-0008 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Electrical Design Standards | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0009 | A | 6105AK124-6261-ESTD-0009 | Q24050972-04-6261-E-STD-0009 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Thermal Management and Fire Prevention Design | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0010 | A | 6105AK124-6261-ESTD-0010 | Q24050972-04-6261-E-STD-0010 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Electrical Design Standards | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0011 | A | 6105AK124-6261-ESTD-0011 | Q24050972-04-6261-E-STD-0011 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Earth Map and Bonding Design | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0012 | A | 6105AK124-6261-ESTD-0012 | Q24050972-04-6261-E-STD-0012 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Thermal Management and Fire Prevention Design | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0013 | A | 6105AK124-6261-ESTD-0013 | Q24050972-04-6261-E-STD-0013 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Electrical Equipment Installation Requirements | Administration and General Buildings - MV Cables for 36 MVA Power Station - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0014 | A | 6105AK124-6261-ESTD-0014 | Q24050972-04-6261-E-STD-0014 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Earth Map and Bonding Design | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0015 | A | 6105AK124-6261-ESTD-0015 | Q24050972-04-6261-E-STD-0015 |  | Administration and General Buildings | MV Isolator Panel for 36 MVA Power Station | Electrical Equipment Installation Requirements | Administration and General Buildings - MV Isolator Panel for 36 MVA Power Station - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Isolator Panel | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0016 | A | 6105AK124-6261-ESTD-0016 | Q24050972-04-6261-E-STD-0016 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Electrical Equipment Installation Requirements | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0017 | A | 6105AK124-6261-ESTD-0017 | Q24050972-04-6261-E-STD-0017 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Earth Map and Bonding Design | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0018 | A | 6105AK124-6261-ESTD-0018 | Q24050972-04-6261-E-STD-0018 |  | Administration and General Buildings | Termination Cabinets for 36 MVA Power Station | Electrical Equipment Installation Requirements | Administration and General Buildings - Termination Cabinets for 36 MVA Power Station - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Termination Cabinets | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | E | STD | 0019 | A | 6105AK124-6261-ESTD-0019 | Q24050972-04-6261-E-STD-0019 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Electrical Equipment Installation Requirements | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | F | DIA | 0001 | A | 6105AK124-6261-FDIA-0001 | Q24050972-04-6261-F-DIA-0001 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Interface Panel and I/O Schematics | Administration and General Buildings - Earthing System for 36 MVA Power Station - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | F | DIA | 0002 | A | 6105AK124-6261-FDIA-0002 | Q24050972-04-6261-F-DIA-0002 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Control Network Architecture Design | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | I | CAL | 0001 | A | 6105AK124-6261-ICAL-0001 | Q24050972-04-6261-I-CAL-0001 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Instrument Sizing and Specification Sheets | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | I | ITD | 0001 | A | 6105AK124-6261-IITD-0001 | Q24050972-04-6261-I-ITD-0001 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Instrument Wiring Loop Diagrams and Cable Schedule | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | I | LST | 0001 | A | 6105AK124-6261-ILST-0001 | Q24050972-04-6261-I-LST-0001 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Instrumentation Equipment Tag Register | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | I | LST | 0002 | A | 6105AK124-6261-ILST-0002 | Q24050972-04-6261-I-LST-0002 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Equipment Alarm and Trip Level Register | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | I | SPC | 0001 | A | 6105AK124-6261-ISPC-0001 | Q24050972-04-6261-I-SPC-0001 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Junction Box and Interface Cabinet Design | Administration and General Buildings - Earthing System for 36 MVA Power Station - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | I | SPC | 0002 | A | 6105AK124-6261-ISPC-0002 | Q24050972-04-6261-I-SPC-0002 |  | Administration and General Buildings | Metering Instruments for 36 MVA Power Station | Junction Box and Interface Cabinet Design | Administration and General Buildings - Metering Instruments for 36 MVA Power Station - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Metering Instruments | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | M | CAL | 0001 | A | 6105AK124-6261-MCAL-0001 | Q24050972-04-6261-M-CAL-0001 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Vessel and Structure Design with Stress Analysis Calcs | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | M | PRC | 0001 | A | 6105AK124-6261-MPRC-0001 | Q24050972-04-6261-M-PRC-0001 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Rigging Study and Lifting Equipment Design | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | M | PSP | 0001 | A | 6105AK124-6261-MPSP-0001 | Q24050972-04-6261-M-PSP-0001 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Pipe and Cable Support Racks Design | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | M | PSP | 0002 | A | 6105AK124-6261-MPSP-0002 | Q24050972-04-6261-M-PSP-0002 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Pipe and Cable Support Racks Design | Administration and General Buildings - MV Cables for 36 MVA Power Station - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | M | PSP | 0003 | A | 6105AK124-6261-MPSP-0003 | Q24050972-04-6261-M-PSP-0003 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Pipe and Cable Support Racks Design | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | M | SPC | 0001 | A | 6105AK124-6261-MSPC-0001 | Q24050972-04-6261-M-SPC-0001 |  | Administration and General Buildings | Cable Racks and Trays for 36 MVA Power Station | Material Selection and Verification Specification | Administration and General Buildings - Cable Racks and Trays for 36 MVA Power Station - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Racks and Trays | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | T | RPT | 0001 | A | 6105AK124-6261-TRPT-0001 | Q24050972-04-6261-T-RPT-0001 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Site Surveying & Geotechnical Report | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | T | SPC | 0001 | A | 6105AK124-6261-TSPC-0001 | Q24050972-04-6261-T-SPC-0001 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Civil Design and Requirements | Administration and General Buildings - Earthing System for 36 MVA Power Station - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | T | SPC | 0002 | A | 6105AK124-6261-TSPC-0002 | Q24050972-04-6261-T-SPC-0002 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Civil Design and Requirements | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | W | ELE | 0001 | A | 6105AK124-6261-WELE-0001 | Q24050972-04-6261-W-ELE-0001 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Bulk Earth Works Design and Report | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | W | ELE | 0002 | A | 6105AK124-6261-WELE-0002 | Q24050972-04-6261-W-ELE-0002 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Bulk Earth Works Design and Report | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | W | LAY | 0001 | A | 6105AK124-6261-WLAY-0001 | Q24050972-04-6261-W-LAY-0001 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Drainage, Run-off and Impoundment Design | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | W | LAY | 0002 | A | 6105AK124-6261-WLAY-0002 | Q24050972-04-6261-W-LAY-0002 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Drainage, Run-off and Impoundment Design | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | W | TRP | 0001 | A | 6105AK124-6261-WTRP-0001 | Q24050972-04-6261-W-TRP-0001 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Soil Classification and Nomination Deliverables | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | W | TRP | 0002 | A | 6105AK124-6261-WTRP-0002 | Q24050972-04-6261-W-TRP-0002 |  | Administration and General Buildings | Terrace Roads and Access-ways for 36 MVA Power Station | Soil Resistivity Testing Report | Administration and General Buildings - Terrace Roads and Access-ways for 36 MVA Power Station - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | W | TRP | 0003 | A | 6105AK124-6261-WTRP-0003 | Q24050972-04-6261-W-TRP-0003 |  | Administration and General Buildings | Earthing System for 36 MVA Power Station | Soil Resistivity Testing Report | Administration and General Buildings - Earthing System for 36 MVA Power Station - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | W | TRP | 0004 | A | 6105AK124-6261-WTRP-0004 | Q24050972-04-6261-W-TRP-0004 |  | Administration and General Buildings | Cable Trench / Tunnels for 36 MVA Power Station | Soil Classification and Nomination Deliverables | Administration and General Buildings - Cable Trench / Tunnels for 36 MVA Power Station - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Cable Trench / Tunnels | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | W | TRP | 0005 | A | 6105AK124-6261-WTRP-0005 | Q24050972-04-6261-W-TRP-0005 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Soil Classification and Nomination Deliverables | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | W | TRP | 0006 | A | 6105AK124-6261-WTRP-0006 | Q24050972-04-6261-W-TRP-0006 |  | Administration and General Buildings | Lightning Protection System for 36 MVA Power Station | Soil Resistivity Testing Report | Administration and General Buildings - Lightning Protection System for 36 MVA Power Station - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Lightning Protection System | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | W | TRP | 0007 | A | 6105AK124-6261-WTRP-0007 | Q24050972-04-6261-W-TRP-0007 |  | Administration and General Buildings | MV Cables for 36 MVA Power Station | Soil Classification and Nomination Deliverables | Administration and General Buildings - MV Cables for 36 MVA Power Station - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | MV Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6261 | W | TRP | 0008 | A | 6105AK124-6261-WTRP-0008 | Q24050972-04-6261-W-TRP-0008 |  | Administration and General Buildings | LV, Control and Signal Cables for 36 MVA Power Station | Soil Classification and Nomination Deliverables | Administration and General Buildings - LV, Control and Signal Cables for 36 MVA Power Station - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | LV, Control and Signal Cables | 36 MVA Power Station |  |  |  | Pending
6105A | K124 | 6263 | B | PHL | 0001 | A | 6105AK124-6263-BPHL-0001 | Q24050972-04-6263-B-PHL-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Control Philosophy | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | B | PHL | 0002 | A | 6105AK124-6263-BPHL-0002 | Q24050972-04-6263-B-PHL-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Power Management System Philosophy | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Power Management System Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | B | PHL | 0003 | A | 6105AK124-6263-BPHL-0003 | Q24050972-04-6263-B-PHL-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Control Philosophy | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | B | PHL | 0004 | A | 6105AK124-6263-BPHL-0004 | Q24050972-04-6263-B-PHL-0004 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Power Management System Philosophy | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Power Management System Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | B | SPC | 0001 | A | 6105AK124-6263-BSPC-0001 | Q24050972-04-6263-B-SPC-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Functional Design Specification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | B | SPC | 0002 | A | 6105AK124-6263-BSPC-0002 | Q24050972-04-6263-B-SPC-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Functional Design Specification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | B | STD | 0001 | A | 6105AK124-6263-BSTD-0001 | Q24050972-04-6263-B-STD-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | System Detailed Engineering Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | B | STD | 0002 | A | 6105AK124-6263-BSTD-0002 | Q24050972-04-6263-B-STD-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | System Detailed Engineering Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | CAL | 0001 | A | 6105AK124-6263-CCAL-0001 | Q24050972-04-6263-C-CAL-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Structure Stress Calculations and Expansion Provisions | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | CAL | 0002 | A | 6105AK124-6263-CCAL-0002 | Q24050972-04-6263-C-CAL-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Structure Stress Calculations and Expansion Provisions | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | FND | 0001 | A | 6105AK124-6263-CFND-0001 | Q24050972-04-6263-C-FND-0001 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Civil Foundation Design | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | FND | 0002 | A | 6105AK124-6263-CFND-0002 | Q24050972-04-6263-C-FND-0002 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Plinth Design and Layout | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | FND | 0003 | A | 6105AK124-6263-CFND-0003 | Q24050972-04-6263-C-FND-0003 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Civil Foundation Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | FND | 0004 | A | 6105AK124-6263-CFND-0004 | Q24050972-04-6263-C-FND-0004 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Civil Foundation Design | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | FND | 0005 | A | 6105AK124-6263-CFND-0005 | Q24050972-04-6263-C-FND-0005 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Plinth Design and Layout | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | FND | 0006 | A | 6105AK124-6263-CFND-0006 | Q24050972-04-6263-C-FND-0006 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Civil Foundation Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0001 | A | 6105AK124-6263-CGAD-0001 | Q24050972-04-6263-C-GAD-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Terrace Equipment GA | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0002 | A | 6105AK124-6263-CGAD-0002 | Q24050972-04-6263-C-GAD-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Fire Detection and Suppression System | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0003 | A | 6105AK124-6263-CGAD-0003 | Q24050972-04-6263-C-GAD-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Pipe Routing General Arrangement | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Pipe Routing General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0004 | A | 6105AK124-6263-CGAD-0004 | Q24050972-04-6263-C-GAD-0004 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Utilities Connections and Battery Limits GA | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Utilities Connections and Battery Limits GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0005 | A | 6105AK124-6263-CGAD-0005 | Q24050972-04-6263-C-GAD-0005 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Buildings and Structures GA | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0006 | A | 6105AK124-6263-CGAD-0006 | Q24050972-04-6263-C-GAD-0006 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Terrace Equipment GA | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0007 | A | 6105AK124-6263-CGAD-0007 | Q24050972-04-6263-C-GAD-0007 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Stormwater and Effluent System Design | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0008 | A | 6105AK124-6263-CGAD-0008 | Q24050972-04-6263-C-GAD-0008 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Stormwater and Effluent System Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0009 | A | 6105AK124-6263-CGAD-0009 | Q24050972-04-6263-C-GAD-0009 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Terrace Equipment GA | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0010 | A | 6105AK124-6263-CGAD-0010 | Q24050972-04-6263-C-GAD-0010 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Fire Detection and Suppression System | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0011 | A | 6105AK124-6263-CGAD-0011 | Q24050972-04-6263-C-GAD-0011 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Pipe Routing General Arrangement | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Pipe Routing General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0012 | A | 6105AK124-6263-CGAD-0012 | Q24050972-04-6263-C-GAD-0012 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Utilities Connections and Battery Limits GA | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Utilities Connections and Battery Limits GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0013 | A | 6105AK124-6263-CGAD-0013 | Q24050972-04-6263-C-GAD-0013 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Buildings and Structures GA | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0014 | A | 6105AK124-6263-CGAD-0014 | Q24050972-04-6263-C-GAD-0014 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Terrace Equipment GA | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0015 | A | 6105AK124-6263-CGAD-0015 | Q24050972-04-6263-C-GAD-0015 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Stormwater and Effluent System Design | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | GAD | 0016 | A | 6105AK124-6263-CGAD-0016 | Q24050972-04-6263-C-GAD-0016 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Stormwater and Effluent System Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | MDL | 0001 | A | 6105AK124-6263-CMDL-0001 | Q24050972-04-6263-C-MDL-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | 3D Designs and Drawings | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | MDL | 0002 | A | 6105AK124-6263-CMDL-0002 | Q24050972-04-6263-C-MDL-0002 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | 3D Designs and Drawings | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | MDL | 0003 | A | 6105AK124-6263-CMDL-0003 | Q24050972-04-6263-C-MDL-0003 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | 3D Designs and Drawings | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | MDL | 0004 | A | 6105AK124-6263-CMDL-0004 | Q24050972-04-6263-C-MDL-0004 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | 3D Designs and Drawings | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | MDL | 0005 | A | 6105AK124-6263-CMDL-0005 | Q24050972-04-6263-C-MDL-0005 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | 3D Designs and Drawings | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | MDL | 0006 | A | 6105AK124-6263-CMDL-0006 | Q24050972-04-6263-C-MDL-0006 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | 3D Designs and Drawings | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | PLN | 0001 | A | 6105AK124-6263-CPLN-0001 | Q24050972-04-6263-C-PLN-0001 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Civil Works Execution Plan | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | PLN | 0002 | A | 6105AK124-6263-CPLN-0002 | Q24050972-04-6263-C-PLN-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Civil Works Execution Plan | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | PLN | 0003 | A | 6105AK124-6263-CPLN-0003 | Q24050972-04-6263-C-PLN-0003 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Civil Works Execution Plan | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | PLN | 0004 | A | 6105AK124-6263-CPLN-0004 | Q24050972-04-6263-C-PLN-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Civil Works Execution Plan | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | SEC | 0003 | A | 6105AK124-6263-CSEC-0003 | Q24050972-03-6263-C-SEC-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Corrosion Prevention and Protection Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | SEC | 0004 | A | 6105AK124-6263-CSEC-0004 | Q24050972-03-6263-C-SEC-0004 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Structural Earthing and Bonding Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | SEC | 0005 | A | 6105AK124-6263-CSEC-0005 | Q24050972-03-6263-C-SEC-0005 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Corrosion Prevention and Protection Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | SEC | 0006 | A | 6105AK124-6263-CSEC-0006 | Q24050972-03-6263-C-SEC-0006 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Structural Earthing and Bonding Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0001 | A | 6105AK124-6263-CSPC-0001 | Q24050972-03-6263-C-SPC-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Steel Structures Corrosion Protection Specification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0002 | A | 6105AK124-6263-CSPC-0002 | Q24050972-03-6263-C-SPC-0002 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Civil Design Requirements | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0003 | A | 6105AK124-6263-CSPC-0003 | Q24050972-03-6263-C-SPC-0003 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Excavation, Trenching and Compacting Design | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0004 | A | 6105AK124-6263-CSPC-0004 | Q24050972-03-6263-C-SPC-0004 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Concrete Construction Material Specifications | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0005 | A | 6105AK124-6263-CSPC-0005 | Q24050972-03-6263-C-SPC-0005 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Civil Design Requirements | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0006 | A | 6105AK124-6263-CSPC-0006 | Q24050972-03-6263-C-SPC-0006 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Excavation, Trenching and Compacting Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0007 | A | 6105AK124-6263-CSPC-0007 | Q24050972-03-6263-C-SPC-0007 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Concrete Construction Material Specifications | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0008 | A | 6105AK124-6263-CSPC-0008 | Q24050972-03-6263-C-SPC-0008 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Steel Structures Corrosion Protection Specification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0009 | A | 6105AK124-6263-CSPC-0009 | Q24050972-03-6263-C-SPC-0009 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Civil Design Requirements | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0010 | A | 6105AK124-6263-CSPC-0010 | Q24050972-03-6263-C-SPC-0010 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Excavation, Trenching and Compacting Design | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0011 | A | 6105AK124-6263-CSPC-0011 | Q24050972-03-6263-C-SPC-0011 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Concrete Construction Material Specifications | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0012 | A | 6105AK124-6263-CSPC-0012 | Q24050972-03-6263-C-SPC-0012 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Civil Design Requirements | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0013 | A | 6105AK124-6263-CSPC-0013 | Q24050972-03-6263-C-SPC-0013 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Excavation, Trenching and Compacting Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | SPC | 0014 | A | 6105AK124-6263-CSPC-0014 | Q24050972-03-6263-C-SPC-0014 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Concrete Construction Material Specifications | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | SPL | 0001 | A | 6105AK124-6263-CSPL-0001 | Q24050972-03-6263-C-SPL-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Pipe Fabrication and Field Installation Inspection | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Pipe Fabrication and Field Installation Inspection |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | SPL | 0002 | A | 6105AK124-6263-CSPL-0002 | Q24050972-03-6263-C-SPL-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Pipe Fabrication and Field Installation Inspection | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Pipe Fabrication and Field Installation Inspection |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | SSD | 0001 | A | 6105AK124-6263-CSSD-0001 | Q24050972-03-6263-C-SSD-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Steel Support Structures Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | SSD | 0002 | A | 6105AK124-6263-CSSD-0002 | Q24050972-03-6263-C-SSD-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Steel Support Structures Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0001 | A | 6105AK124-6263-CSTD-0001 | Q24050972-03-6263-C-STD-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Underground Pipe Route and Cable Bedding Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0002 | A | 6105AK124-6263-CSTD-0002 | Q24050972-03-6263-C-STD-0002 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Bund-wall Requirements and Design | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0003 | A | 6105AK124-6263-CSTD-0003 | Q24050972-03-6263-C-STD-0003 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Fire Protection System Design (Civil Works) | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0004 | A | 6105AK124-6263-CSTD-0004 | Q24050972-03-6263-C-STD-0004 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Civil Construction Requirements | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0005 | A | 6105AK124-6263-CSTD-0005 | Q24050972-03-6263-C-STD-0005 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Underground Pipe Route and Cable Bedding Design | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0006 | A | 6105AK124-6263-CSTD-0006 | Q24050972-03-6263-C-STD-0006 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Bund-wall Requirements and Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0007 | A | 6105AK124-6263-CSTD-0007 | Q24050972-03-6263-C-STD-0007 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Fire Protection System Design (Civil Works) | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0008 | A | 6105AK124-6263-CSTD-0008 | Q24050972-03-6263-C-STD-0008 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Civil Construction Requirements | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0009 | A | 6105AK124-6263-CSTD-0009 | Q24050972-03-6263-C-STD-0009 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Underground Pipe Route and Cable Bedding Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0010 | A | 6105AK124-6263-CSTD-0010 | Q24050972-03-6263-C-STD-0010 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Underground Pipe Route and Cable Bedding Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0011 | A | 6105AK124-6263-CSTD-0011 | Q24050972-03-6263-C-STD-0011 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Bund-wall Requirements and Design | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0012 | A | 6105AK124-6263-CSTD-0012 | Q24050972-03-6263-C-STD-0012 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Fire Protection System Design (Civil Works) | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0013 | A | 6105AK124-6263-CSTD-0013 | Q24050972-03-6263-C-STD-0013 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Civil Construction Requirements | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0014 | A | 6105AK124-6263-CSTD-0014 | Q24050972-03-6263-C-STD-0014 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Underground Pipe Route and Cable Bedding Design | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0015 | A | 6105AK124-6263-CSTD-0015 | Q24050972-03-6263-C-STD-0015 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Bund-wall Requirements and Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0016 | A | 6105AK124-6263-CSTD-0016 | Q24050972-03-6263-C-STD-0016 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Fire Protection System Design (Civil Works) | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0017 | A | 6105AK124-6263-CSTD-0017 | Q24050972-03-6263-C-STD-0017 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Civil Construction Requirements | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | C | STD | 0018 | A | 6105AK124-6263-CSTD-0018 | Q24050972-03-6263-C-STD-0018 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Underground Pipe Route and Cable Bedding Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | CAL | 0001 | A | 6105AK124-6263-ECAL-0001 | Q24050972-04-6263-E-CAL-0001 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Cable and Conductor Sizing (incl Volt Drop Calcs) | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | CAL | 0002 | A | 6105AK124-6263-ECAL-0002 | Q24050972-04-6263-E-CAL-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Cable and Conductor Sizing (incl Volt Drop Calcs) | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | DIA | 0001 | A | 6105AK124-6263-EDIA-0001 | Q24050972-04-6263-E-DIA-0001 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Cable Block Diagrams and Schedules | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | DIA | 0002 | A | 6105AK124-6263-EDIA-0002 | Q24050972-04-6263-E-DIA-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Electrical Circuit Diagrams (Schematics) | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | DIA | 0003 | A | 6105AK124-6263-EDIA-0003 | Q24050972-04-6263-E-DIA-0003 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | E/I Termination Schedule | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | DIA | 0004 | A | 6105AK124-6263-EDIA-0004 | Q24050972-04-6263-E-DIA-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Cable Block Diagrams and Schedules | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | DIA | 0005 | A | 6105AK124-6263-EDIA-0005 | Q24050972-04-6263-E-DIA-0005 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Electrical Circuit Diagrams (Schematics) | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | DIA | 0006 | A | 6105AK124-6263-EDIA-0006 | Q24050972-04-6263-E-DIA-0006 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | E/I Termination Schedule | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | DST | 0006 | A | 6105AK124-6263-EDST-0006 | Q24050972-04-6263-E-DST-0006 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Equipment Register and Technical Specifications | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | DST | 0007 | A | 6105AK124-6263-EDST-0007 | Q24050972-04-6263-E-DST-0007 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Equipment Register and Technical Specifications | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | DST | 0008 | A | 6105AK124-6263-EDST-0008 | Q24050972-04-6263-E-DST-0008 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Equipment Register and Technical Specifications | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | DST | 0009 | A | 6105AK124-6263-EDST-0009 | Q24050972-04-6263-E-DST-0009 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Equipment Register and Technical Specifications | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | QRA | 0001 | A | 6105AK124-6263-EQRA-0001 | Q24050972-04-6263-E-QRA-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Lightning Protection Study and Risk Assessment | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | QRA | 0002 | A | 6105AK124-6263-EQRA-0002 | Q24050972-04-6263-E-QRA-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Risk Assessment: Electrical Hazards | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | QRA | 0003 | A | 6105AK124-6263-EQRA-0003 | Q24050972-04-6263-E-QRA-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Lightning Protection Study and Risk Assessment | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | QRA | 0004 | A | 6105AK124-6263-EQRA-0004 | Q24050972-04-6263-E-QRA-0004 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Risk Assessment: Electrical Hazards | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0001 | A | 6105AK124-6263-ESTD-0001 | Q24050972-04-6263-E-STD-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Earth Map and Bonding Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0002 | A | 6105AK124-6263-ESTD-0002 | Q24050972-04-6263-E-STD-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Hazardous Area Classification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Hazardous Area Classification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0003 | A | 6105AK124-6263-ESTD-0003 | Q24050972-04-6263-E-STD-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Thermal Management and Fire Prevention Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0004 | A | 6105AK124-6263-ESTD-0004 | Q24050972-04-6263-E-STD-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Electrical Equipment Installation Requirements | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0005 | A | 6105AK124-6263-ESTD-0005 | Q24050972-04-6263-E-STD-0005 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Hazardous Area Classification | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Hazardous Area Classification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0006 | A | 6105AK124-6263-ESTD-0006 | Q24050972-04-6263-E-STD-0006 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Thermal Management and Fire Prevention Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0007 | A | 6105AK124-6263-ESTD-0007 | Q24050972-04-6263-E-STD-0007 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Earth Map and Bonding Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0008 | A | 6105AK124-6263-ESTD-0008 | Q24050972-04-6263-E-STD-0008 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Hazardous Area Classification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Hazardous Area Classification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0009 | A | 6105AK124-6263-ESTD-0009 | Q24050972-04-6263-E-STD-0009 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Thermal Management and Fire Prevention Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0010 | A | 6105AK124-6263-ESTD-0010 | Q24050972-04-6263-E-STD-0010 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Electrical Equipment Installation Requirements | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0011 | A | 6105AK124-6263-ESTD-0011 | Q24050972-04-6263-E-STD-0011 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Hazardous Area Classification | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Hazardous Area Classification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0012 | A | 6105AK124-6263-ESTD-0012 | Q24050972-04-6263-E-STD-0012 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Thermal Management and Fire Prevention Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | F | DBD | 0001 | A | 6105AK124-6263-FDBD-0001 | Q24050972-04-6263-F-DBD-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Control System Configuration | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | F | DBD | 0002 | A | 6105AK124-6263-FDBD-0002 | Q24050972-04-6263-F-DBD-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Control System Configuration | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | F | DIA | 0001 | A | 6105AK124-6263-FDIA-0001 | Q24050972-04-6263-F-DIA-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Emergency Shutdown System Design - Diagram | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Emergency Shutdown System Design - Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | F | DIA | 0002 | A | 6105AK124-6263-FDIA-0002 | Q24050972-04-6263-F-DIA-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Control Network Architecture Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | F | DIA | 0003 | A | 6105AK124-6263-FDIA-0003 | Q24050972-04-6263-F-DIA-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Control Network Communication Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | F | DIA | 0004 | A | 6105AK124-6263-FDIA-0004 | Q24050972-04-6263-F-DIA-0004 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Emergency Shutdown System Design - Diagram | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Emergency Shutdown System Design - Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | F | DIA | 0005 | A | 6105AK124-6263-FDIA-0005 | Q24050972-04-6263-F-DIA-0005 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Control Network Architecture Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | F | DIA | 0006 | A | 6105AK124-6263-FDIA-0006 | Q24050972-04-6263-F-DIA-0006 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Control Network Communication Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | F | LAY | 0001 | A | 6105AK124-6263-FLAY-0001 | Q24050972-04-6263-F-LAY-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | HMI and Graphics design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - HMI and Graphics design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | F | LAY | 0002 | A | 6105AK124-6263-FLAY-0002 | Q24050972-04-6263-F-LAY-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | HMI and Graphics design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - HMI and Graphics design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | F | LST | 0001 | A | 6105AK124-6263-FLST-0001 | Q24050972-04-6263-F-LST-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Control Loop Register and Tuning Parameters | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Control Loop Register and Tuning Parameters |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | F | LST | 0002 | A | 6105AK124-6263-FLST-0002 | Q24050972-04-6263-F-LST-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Control Loop Register and Tuning Parameters | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Control Loop Register and Tuning Parameters |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | F | NAR | 0001 | A | 6105AK124-6263-FNAR-0001 | Q24050972-04-6263-F-NAR-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Emergency Shutdown System Control Narrative | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | F | NAR | 0002 | A | 6105AK124-6263-FNAR-0002 | Q24050972-04-6263-F-NAR-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Control System Control Narrative & Interlock Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | F | NAR | 0003 | A | 6105AK124-6263-FNAR-0003 | Q24050972-04-6263-F-NAR-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Emergency Shutdown System Control Narrative | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | F | NAR | 0004 | A | 6105AK124-6263-FNAR-0004 | Q24050972-04-6263-F-NAR-0004 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Control System Control Narrative & Interlock Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | F | PHL | 0001 | A | 6105AK124-6263-FPHL-0001 | Q24050972-04-6263-F-PHL-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Control System Control Philosophy | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | F | PHL | 0002 | A | 6105AK124-6263-FPHL-0002 | Q24050972-04-6263-F-PHL-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Control System Control Philosophy | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6264 | C | CAL | 0001 | A | 6105AK124-6264-CCAL-0001 | Q24050972-04-6264-C-CAL-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Structure Stress Calculations and Expansion Provisions | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Expansion Provisions |  |  |  | Pending
6105A | K124 | 6264 | C | CAL | 0002 | A | 6105AK124-6264-CCAL-0002 | Q24050972-04-6264-C-CAL-0002 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Structure Stress Calculations and Expansion Provisions | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Expansion Provisions |  |  |  | Pending
6105A | K124 | 6264 | C | CAL | 0003 | A | 6105AK124-6264-CCAL-0003 | Q24050972-04-6264-C-CAL-0003 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | Structure Stress Calculations and Expansion Provisions | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Expansion Provisions |  |  |  | Pending
6105A | K124 | 6264 | C | CAL | 0004 | A | 6105AK124-6264-CCAL-0004 | Q24050972-04-6264-C-CAL-0004 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Structure Stress Calculations and Expansion Provisions | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Expansion Provisions |  |  |  | Pending
6105A | K124 | 6264 | C | CAL | 0005 | A | 6105AK124-6264-CCAL-0005 | Q24050972-04-6264-C-CAL-0005 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Structure Stress Calculations and Expansion Provisions | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Expansion Provisions |  |  |  | Pending
6105A | K124 | 6264 | C | CAL | 0006 | A | 6105AK124-6264-CCAL-0006 | Q24050972-04-6264-C-CAL-0006 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Structure Stress Calculations and Expansion Provisions | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Expansion Provisions |  |  |  | Pending
6105A | K124 | 6264 | C | CAL | 0007 | A | 6105AK124-6264-CCAL-0007 | Q24050972-04-6264-C-CAL-0007 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Structure Stress Calculations and Expansion Provisions | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Expansion Provisions |  |  |  | Pending
6105A | K124 | 6264 | C | CAL | 0008 | A | 6105AK124-6264-CCAL-0008 | Q24050972-04-6264-C-CAL-0008 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | Structure Stress Calculations and Expansion Provisions | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Expansion Provisions |  |  |  | Pending
6105A | K124 | 6264 | C | CAL | 0009 | A | 6105AK124-6264-CCAL-0009 | Q24050972-04-6264-C-CAL-0009 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Structure Stress Calculations and Expansion Provisions | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Expansion Provisions |  |  |  | Pending
6105A | K124 | 6264 | C | CAL | 0010 | A | 6105AK124-6264-CCAL-0010 | Q24050972-04-6264-C-CAL-0010 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Structure Stress Calculations and Expansion Provisions | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Structure Stress Calculations and Expansion Provisions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Expansion Provisions |  |  |  | Pending
6105A | K124 | 6263 | F | PRC | 0001 | A | 6105AK124-6263-FPRC-0001 | Q24050972-04-6263-F-PRC-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Alarm Classification Methodology | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Alarm Classification Methodology |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | F | PRC | 0002 | A | 6105AK124-6263-FPRC-0002 | Q24050972-04-6263-F-PRC-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Alarm Classification Methodology | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Alarm Classification Methodology |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | F | SPC | 0001 | A | 6105AK124-6263-FSPC-0001 | Q24050972-04-6263-F-SPC-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Control System Design Requirements | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Control System Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | F | SPC | 0002 | A | 6105AK124-6263-FSPC-0002 | Q24050972-04-6263-F-SPC-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Historian and Server Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | F | SPC | 0003 | A | 6105AK124-6263-FSPC-0003 | Q24050972-04-6263-F-SPC-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Control System Design Requirements | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Control System Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | F | SPC | 0004 | A | 6105AK124-6263-FSPC-0004 | Q24050972-04-6263-F-SPC-0004 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Historian and Server Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6264 | E | CAL | 0001 | A | 6105AK124-6264-ECAL-0001 | Q24050972-04-6264-E-CAL-0001 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Cable and Conductor Sizing (incl Volt Drop Calcs) | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | CAL | 0002 | A | 6105AK124-6264-ECAL-0002 | Q24050972-04-6264-E-CAL-0002 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Impedance and Burn-off Calculations | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | CAL | 0003 | A | 6105AK124-6264-ECAL-0003 | Q24050972-04-6264-E-CAL-0003 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Cable and Conductor Sizing (incl Volt Drop Calcs) | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | E | CAL | 0004 | A | 6105AK124-6264-ECAL-0004 | Q24050972-04-6264-E-CAL-0004 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Cable and Conductor Sizing (incl Volt Drop Calcs) | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | CAL | 0005 | A | 6105AK124-6264-ECAL-0005 | Q24050972-04-6264-E-CAL-0005 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Cable and Conductor Sizing (incl Volt Drop Calcs) | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | CAL | 0006 | A | 6105AK124-6264-ECAL-0006 | Q24050972-04-6264-E-CAL-0006 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Impedance and Burn-off Calculations | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | CAL | 0007 | A | 6105AK124-6264-ECAL-0007 | Q24050972-04-6264-E-CAL-0007 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Cable and Conductor Sizing (incl Volt Drop Calcs) | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | E | CAL | 0008 | A | 6105AK124-6264-ECAL-0008 | Q24050972-04-6264-E-CAL-0008 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Cable and Conductor Sizing (incl Volt Drop Calcs) | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6263 | I | CAL | 0001 | A | 6105AK124-6263-ICAL-0001 | Q24050972-04-6263-I-CAL-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Instrument Sizing and Specification Sheets | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | CAL | 0002 | A | 6105AK124-6263-ICAL-0002 | Q24050972-04-6263-I-CAL-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Safety Instrumented System Design and Calculations | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Safety Instrumented System Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | CAL | 0003 | A | 6105AK124-6263-ICAL-0003 | Q24050972-04-6263-I-CAL-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Hazardous Area Classification Design and Calculations | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | CAL | 0004 | A | 6105AK124-6263-ICAL-0004 | Q24050972-04-6263-I-CAL-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Instrument Sizing and Specification Sheets | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | CAL | 0005 | A | 6105AK124-6263-ICAL-0005 | Q24050972-04-6263-I-CAL-0005 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Hazardous Area Classification Design and Calculations | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | CAL | 0006 | A | 6105AK124-6263-ICAL-0006 | Q24050972-04-6263-I-CAL-0006 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Instrument Sizing and Specification Sheets | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | CAL | 0007 | A | 6105AK124-6263-ICAL-0007 | Q24050972-04-6263-I-CAL-0007 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Safety Instrumented System Design and Calculations | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Safety Instrumented System Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | CAL | 0008 | A | 6105AK124-6263-ICAL-0008 | Q24050972-04-6263-I-CAL-0008 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Hazardous Area Classification Design and Calculations | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | CAL | 0009 | A | 6105AK124-6263-ICAL-0009 | Q24050972-04-6263-I-CAL-0009 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Instrument Sizing and Specification Sheets | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | CAL | 0010 | A | 6105AK124-6263-ICAL-0010 | Q24050972-04-6263-I-CAL-0010 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Hazardous Area Classification Design and Calculations | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0001 | A | 6105AK124-6264-ICAL-0001 | Q24050972-04-6264-I-CAL-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Instrument Sizing and Specification Sheets | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0002 | A | 6105AK124-6264-ICAL-0002 | Q24050972-04-6264-I-CAL-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Safety Instrumented System Design and Calculations | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Safety Instrumented System Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0003 | A | 6105AK124-6264-ICAL-0003 | Q24050972-04-6264-I-CAL-0003 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Hazardous Area Classification Design and Calculations | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0004 | A | 6105AK124-6264-ICAL-0004 | Q24050972-04-6264-I-CAL-0004 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Instrument Sizing and Specification Sheets | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0005 | A | 6105AK124-6264-ICAL-0005 | Q24050972-04-6264-I-CAL-0005 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Hazardous Area Classification Design and Calculations | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0006 | A | 6105AK124-6264-ICAL-0006 | Q24050972-04-6264-I-CAL-0006 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Instrument Sizing and Specification Sheets | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0007 | A | 6105AK124-6264-ICAL-0007 | Q24050972-04-6264-I-CAL-0007 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Hazardous Area Classification Design and Calculations | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0008 | A | 6105AK124-6264-ICAL-0008 | Q24050972-04-6264-I-CAL-0008 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Instrument Sizing and Specification Sheets | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0009 | A | 6105AK124-6264-ICAL-0009 | Q24050972-04-6264-I-CAL-0009 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Hazardous Area Classification Design and Calculations | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0010 | A | 6105AK124-6264-ICAL-0010 | Q24050972-04-6264-I-CAL-0010 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Safety Instrumented System Design and Calculations | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Safety Instrumented System Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0011 | A | 6105AK124-6264-ICAL-0011 | Q24050972-04-6264-I-CAL-0011 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Instrument Sizing and Specification Sheets | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0012 | A | 6105AK124-6264-ICAL-0012 | Q24050972-04-6264-I-CAL-0012 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Hazardous Area Classification Design and Calculations | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0013 | A | 6105AK124-6264-ICAL-0013 | Q24050972-04-6264-I-CAL-0013 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Instrument Sizing and Specification Sheets | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0014 | A | 6105AK124-6264-ICAL-0014 | Q24050972-04-6264-I-CAL-0014 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Safety Instrumented System Design and Calculations | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Safety Instrumented System Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0015 | A | 6105AK124-6264-ICAL-0015 | Q24050972-04-6264-I-CAL-0015 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Hazardous Area Classification Design and Calculations | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0016 | A | 6105AK124-6264-ICAL-0016 | Q24050972-04-6264-I-CAL-0016 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Instrument Sizing and Specification Sheets | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0017 | A | 6105AK124-6264-ICAL-0017 | Q24050972-04-6264-I-CAL-0017 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Hazardous Area Classification Design and Calculations | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0018 | A | 6105AK124-6264-ICAL-0018 | Q24050972-04-6264-I-CAL-0018 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Instrument Sizing and Specification Sheets | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0019 | A | 6105AK124-6264-ICAL-0019 | Q24050972-04-6264-I-CAL-0019 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Hazardous Area Classification Design and Calculations | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0020 | A | 6105AK124-6264-ICAL-0020 | Q24050972-04-6264-I-CAL-0020 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Instrument Sizing and Specification Sheets | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0021 | A | 6105AK124-6264-ICAL-0021 | Q24050972-04-6264-I-CAL-0021 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Hazardous Area Classification Design and Calculations | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0022 | A | 6105AK124-6264-ICAL-0022 | Q24050972-04-6264-I-CAL-0022 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Safety Instrumented System Design and Calculations | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Safety Instrumented System Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0023 | A | 6105AK124-6264-ICAL-0023 | Q24050972-04-6264-I-CAL-0023 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Instrument Sizing and Specification Sheets | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | I | CAL | 0024 | A | 6105AK124-6264-ICAL-0024 | Q24050972-04-6264-I-CAL-0024 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Hazardous Area Classification Design and Calculations | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Hazardous Area Classification Design and Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0001 | A | 6105AK124-6264-MCAL-0001 | Q24050972-04-6264-M-CAL-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Piping Pressure Drop Calculations | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0002 | A | 6105AK124-6264-MCAL-0002 | Q24050972-04-6264-M-CAL-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Vessel and Structure Design with Stress Analysis Calcs | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0003 | A | 6105AK124-6264-MCAL-0003 | Q24050972-04-6264-M-CAL-0003 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Piping Pressure Drop Calculations | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0004 | A | 6105AK124-6264-MCAL-0004 | Q24050972-04-6264-M-CAL-0004 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Vessel and Structure Design with Stress Analysis Calcs | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0005 | A | 6105AK124-6264-MCAL-0005 | Q24050972-04-6264-M-CAL-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Piping Pressure Drop Calculations | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0006 | A | 6105AK124-6264-MCAL-0006 | Q24050972-04-6264-M-CAL-0006 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Vessel and Structure Design with Stress Analysis Calcs | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0007 | A | 6105AK124-6264-MCAL-0007 | Q24050972-04-6264-M-CAL-0007 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Piping Pressure Drop Calculations | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0008 | A | 6105AK124-6264-MCAL-0008 | Q24050972-04-6264-M-CAL-0008 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Piping Pressure Drop Calculations | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0009 | A | 6105AK124-6264-MCAL-0009 | Q24050972-04-6264-M-CAL-0009 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Vessel and Structure Design with Stress Analysis Calcs | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0010 | A | 6105AK124-6264-MCAL-0010 | Q24050972-04-6264-M-CAL-0010 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Piping Pressure Drop Calculations | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0011 | A | 6105AK124-6264-MCAL-0011 | Q24050972-04-6264-M-CAL-0011 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Vessel and Structure Design with Stress Analysis Calcs | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0012 | A | 6105AK124-6264-MCAL-0012 | Q24050972-04-6264-M-CAL-0012 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Piping Pressure Drop Calculations | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0013 | A | 6105AK124-6264-MCAL-0013 | Q24050972-04-6264-M-CAL-0013 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Vessel and Structure Design with Stress Analysis Calcs | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | CAL | 0014 | A | 6105AK124-6264-MCAL-0014 | Q24050972-04-6264-M-CAL-0014 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Piping Pressure Drop Calculations | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6263 | I | DIA | 0001 | A | 6105AK124-6263-IDIA-0001 | Q24050972-04-6263-I-DIA-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Smoke and Fire Detection System Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | DIA | 0002 | A | 6105AK124-6263-IDIA-0002 | Q24050972-04-6263-I-DIA-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Confined Space Protection System Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Confined Space Protection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | DIA | 0003 | A | 6105AK124-6263-IDIA-0003 | Q24050972-04-6263-I-DIA-0003 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Smoke and Fire Detection System Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | DIA | 0004 | A | 6105AK124-6263-IDIA-0004 | Q24050972-04-6263-I-DIA-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Confined Space Protection System Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Confined Space Protection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | DIA | 0005 | A | 6105AK124-6263-IDIA-0005 | Q24050972-04-6263-I-DIA-0005 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Smoke and Fire Detection System Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | DIA | 0006 | A | 6105AK124-6263-IDIA-0006 | Q24050972-04-6263-I-DIA-0006 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Confined Space Protection System Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Confined Space Protection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | DIA | 0007 | A | 6105AK124-6263-IDIA-0007 | Q24050972-04-6263-I-DIA-0007 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Smoke and Fire Detection System Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | DIA | 0008 | A | 6105AK124-6263-IDIA-0008 | Q24050972-04-6263-I-DIA-0008 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Confined Space Protection System Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Confined Space Protection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6264 | F | DBD | 0001 | A | 6105AK124-6264-FDBD-0001 | Q24050972-04-6264-F-DBD-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Control System Configuration | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control System Configuration |  |  |  | Pending
6105A | K124 | 6264 | F | DBD | 0002 | A | 6105AK124-6264-FDBD-0002 | Q24050972-04-6264-F-DBD-0002 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Control System Configuration | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control System Configuration |  |  |  | Pending
6105A | K124 | 6264 | F | DBD | 0003 | A | 6105AK124-6264-FDBD-0003 | Q24050972-04-6264-F-DBD-0003 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Control System Configuration | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control System Configuration |  |  |  | Pending
6105A | K124 | 6264 | F | DBD | 0004 | A | 6105AK124-6264-FDBD-0004 | Q24050972-04-6264-F-DBD-0004 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Control System Configuration | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control System Configuration |  |  |  | Pending
6105A | K124 | 6264 | F | DBD | 0005 | A | 6105AK124-6264-FDBD-0005 | Q24050972-04-6264-F-DBD-0005 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Control System Configuration | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control System Configuration |  |  |  | Pending
6105A | K124 | 6264 | F | DBD | 0006 | A | 6105AK124-6264-FDBD-0006 | Q24050972-04-6264-F-DBD-0006 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Control System Configuration | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Control System Configuration |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control System Configuration |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0001 | A | 6105AK124-6264-EDIA-0001 | Q24050972-04-6264-E-DIA-0001 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Electrical Circuit Diagrams (Schematics) | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0002 | A | 6105AK124-6264-EDIA-0002 | Q24050972-04-6264-E-DIA-0002 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Cable Block Diagrams and Schedules | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0003 | A | 6105AK124-6264-EDIA-0003 | Q24050972-04-6264-E-DIA-0003 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | E/I Termination Schedule | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0004 | A | 6105AK124-6264-EDIA-0004 | Q24050972-04-6264-E-DIA-0004 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Cable Block Diagrams and Schedules | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0005 | A | 6105AK124-6264-EDIA-0005 | Q24050972-04-6264-E-DIA-0005 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Electrical Circuit Diagrams (Schematics) | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0006 | A | 6105AK124-6264-EDIA-0006 | Q24050972-04-6264-E-DIA-0006 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | E/I Termination Schedule | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0007 | A | 6105AK124-6264-EDIA-0007 | Q24050972-04-6264-E-DIA-0007 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Cable Block Diagrams and Schedules | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0008 | A | 6105AK124-6264-EDIA-0008 | Q24050972-04-6264-E-DIA-0008 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Electrical Circuit Diagrams (Schematics) | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0009 | A | 6105AK124-6264-EDIA-0009 | Q24050972-04-6264-E-DIA-0009 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | E/I Termination Schedule | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0010 | A | 6105AK124-6264-EDIA-0010 | Q24050972-04-6264-E-DIA-0010 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Electrical Block Diagram | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0011 | A | 6105AK124-6264-EDIA-0011 | Q24050972-04-6264-E-DIA-0011 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Electrical Circuit Diagrams (Schematics) | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0012 | A | 6105AK124-6264-EDIA-0012 | Q24050972-04-6264-E-DIA-0012 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Electrical Circuit Diagrams (Schematics) | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0013 | A | 6105AK124-6264-EDIA-0013 | Q24050972-04-6264-E-DIA-0013 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Cable Block Diagrams and Schedules | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0014 | A | 6105AK124-6264-EDIA-0014 | Q24050972-04-6264-E-DIA-0014 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | E/I Termination Schedule | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0015 | A | 6105AK124-6264-EDIA-0015 | Q24050972-04-6264-E-DIA-0015 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Cable Block Diagrams and Schedules | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0016 | A | 6105AK124-6264-EDIA-0016 | Q24050972-04-6264-E-DIA-0016 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Electrical Circuit Diagrams (Schematics) | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0017 | A | 6105AK124-6264-EDIA-0017 | Q24050972-04-6264-E-DIA-0017 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | E/I Termination Schedule | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0018 | A | 6105AK124-6264-EDIA-0018 | Q24050972-04-6264-E-DIA-0018 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Cable Block Diagrams and Schedules | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0019 | A | 6105AK124-6264-EDIA-0019 | Q24050972-04-6264-E-DIA-0019 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Electrical Circuit Diagrams (Schematics) | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0020 | A | 6105AK124-6264-EDIA-0020 | Q24050972-04-6264-E-DIA-0020 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | E/I Termination Schedule | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0021 | A | 6105AK124-6264-EDIA-0021 | Q24050972-04-6264-E-DIA-0021 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Electrical Block Diagram | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | DIA | 0022 | A | 6105AK124-6264-EDIA-0022 | Q24050972-04-6264-E-DIA-0022 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Electrical Circuit Diagrams (Schematics) | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0001 | A | 6105AK124-6264-FDIA-0001 | Q24050972-04-6264-F-DIA-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Emergency Shutdown System Design - Diagram | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Emergency Shutdown System Design - Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0002 | A | 6105AK124-6264-FDIA-0002 | Q24050972-04-6264-F-DIA-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Control Network Architecture Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0003 | A | 6105AK124-6264-FDIA-0003 | Q24050972-04-6264-F-DIA-0003 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Control Network Communication Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0004 | A | 6105AK124-6264-FDIA-0004 | Q24050972-04-6264-F-DIA-0004 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Interface Panel and I/O Schematics | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0005 | A | 6105AK124-6264-FDIA-0005 | Q24050972-04-6264-F-DIA-0005 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Control Network Architecture Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0006 | A | 6105AK124-6264-FDIA-0006 | Q24050972-04-6264-F-DIA-0006 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Control Network Communication Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0007 | A | 6105AK124-6264-FDIA-0007 | Q24050972-04-6264-F-DIA-0007 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Emergency Shutdown System Design - Diagram | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Emergency Shutdown System Design - Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0008 | A | 6105AK124-6264-FDIA-0008 | Q24050972-04-6264-F-DIA-0008 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Control Network Architecture Design | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0009 | A | 6105AK124-6264-FDIA-0009 | Q24050972-04-6264-F-DIA-0009 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Control Network Communication Design | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0010 | A | 6105AK124-6264-FDIA-0010 | Q24050972-04-6264-F-DIA-0010 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Emergency Shutdown System Design | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Emergency Shutdown System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0011 | A | 6105AK124-6264-FDIA-0011 | Q24050972-04-6264-F-DIA-0011 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Emergency Shutdown System Design - Diagram | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Emergency Shutdown System Design - Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0012 | A | 6105AK124-6264-FDIA-0012 | Q24050972-04-6264-F-DIA-0012 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Control Network Architecture Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0013 | A | 6105AK124-6264-FDIA-0013 | Q24050972-04-6264-F-DIA-0013 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Control Network Communication Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0014 | A | 6105AK124-6264-FDIA-0014 | Q24050972-04-6264-F-DIA-0014 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Interface Panel and I/O Schematics | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0015 | A | 6105AK124-6264-FDIA-0015 | Q24050972-04-6264-F-DIA-0015 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Control Network Architecture Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0016 | A | 6105AK124-6264-FDIA-0016 | Q24050972-04-6264-F-DIA-0016 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Control Network Communication Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0017 | A | 6105AK124-6264-FDIA-0017 | Q24050972-04-6264-F-DIA-0017 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Emergency Shutdown System Design - Diagram | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Emergency Shutdown System Design - Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0018 | A | 6105AK124-6264-FDIA-0018 | Q24050972-04-6264-F-DIA-0018 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Control Network Architecture Design | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0019 | A | 6105AK124-6264-FDIA-0019 | Q24050972-04-6264-F-DIA-0019 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Control Network Communication Design | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | F | DIA | 0020 | A | 6105AK124-6264-FDIA-0020 | Q24050972-04-6264-F-DIA-0020 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Emergency Shutdown System Design | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Emergency Shutdown System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0001 | A | 6105AK124-6264-IDIA-0001 | Q24050972-04-6264-I-DIA-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Smoke and Fire Detection System Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0002 | A | 6105AK124-6264-IDIA-0002 | Q24050972-04-6264-I-DIA-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Confined Space Protection System Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Confined Space Protection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0003 | A | 6105AK124-6264-IDIA-0003 | Q24050972-04-6264-I-DIA-0003 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Smoke and Fire Detection System Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0004 | A | 6105AK124-6264-IDIA-0004 | Q24050972-04-6264-I-DIA-0004 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Confined Space Protection System Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Confined Space Protection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0005 | A | 6105AK124-6264-IDIA-0005 | Q24050972-04-6264-I-DIA-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Smoke and Fire Detection System Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0006 | A | 6105AK124-6264-IDIA-0006 | Q24050972-04-6264-I-DIA-0006 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Smoke and Fire Detection System Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0007 | A | 6105AK124-6264-IDIA-0007 | Q24050972-04-6264-I-DIA-0007 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Confined Space Protection System Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Confined Space Protection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0008 | A | 6105AK124-6264-IDIA-0008 | Q24050972-04-6264-I-DIA-0008 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Smoke and Fire Detection System Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0009 | A | 6105AK124-6264-IDIA-0009 | Q24050972-04-6264-I-DIA-0009 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Confined Space Protection System Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Confined Space Protection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0010 | A | 6105AK124-6264-IDIA-0010 | Q24050972-04-6264-I-DIA-0010 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Smoke and Fire Detection System Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0011 | A | 6105AK124-6264-IDIA-0011 | Q24050972-04-6264-I-DIA-0011 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Confined Space Protection System Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Confined Space Protection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0012 | A | 6105AK124-6264-IDIA-0012 | Q24050972-04-6264-I-DIA-0012 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Smoke and Fire Detection System Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0013 | A | 6105AK124-6264-IDIA-0013 | Q24050972-04-6264-I-DIA-0013 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Smoke and Fire Detection System Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | DIA | 0014 | A | 6105AK124-6264-IDIA-0014 | Q24050972-04-6264-I-DIA-0014 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Confined Space Protection System Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Confined Space Protection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | E | DST | 0002 | A | 6105AK124-6264-EDST-0002 | Q24050972-08-6264-E-DST-0002 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Equipment Register and Technical Specifications | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | DST | 0003 | A | 6105AK124-6264-EDST-0003 | Q24050972-08-6264-E-DST-0003 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Equipment Register and Technical Specifications | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | E | DST | 0004 | A | 6105AK124-6264-EDST-0004 | Q24050972-08-6264-E-DST-0004 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Equipment Register and Technical Specifications | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | E | DST | 0005 | A | 6105AK124-6264-EDST-0005 | Q24050972-08-6264-E-DST-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Equipment Register and Technical Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | DST | 0006 | A | 6105AK124-6264-EDST-0006 | Q24050972-08-6264-E-DST-0006 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Equipment Register and Technical Specifications | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | DST | 0007 | A | 6105AK124-6264-EDST-0007 | Q24050972-08-6264-E-DST-0007 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Equipment Register and Technical Specifications | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | E | DST | 0008 | A | 6105AK124-6264-EDST-0008 | Q24050972-08-6264-E-DST-0008 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Equipment Register and Technical Specifications | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump |  |  |  | Pending
6105A | K124 | 6264 | E | DST | 0009 | A | 6105AK124-6264-EDST-0009 | Q24050972-08-6264-E-DST-0009 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Equipment Register and Technical Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | DST | 0001 | A | 6105AK124-6264-MDST-0001 | Q24050972-08-6264-M-DST-0001 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Pressure Relief Devices Design and Specification | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Pressure Relief Devices |  |  |  | Pending
6105A | K124 | 6264 | M | DST | 0002 | A | 6105AK124-6264-MDST-0002 | Q24050972-08-6264-M-DST-0002 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Pressure Relief Devices Design and Specification | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Pressure Relief Devices |  |  |  | Pending
6105A | K124 | 6264 | M | DST | 0003 | A | 6105AK124-6264-MDST-0003 | Q24050972-08-6264-M-DST-0003 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Pressure Relief Devices Design and Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Pressure Relief Devices |  |  |  | Pending
6105A | K124 | 6264 | M | DST | 0004 | A | 6105AK124-6264-MDST-0004 | Q24050972-08-6264-M-DST-0004 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Pressure Relief Devices Design and Specification | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Pressure Relief Devices |  |  |  | Pending
6105A | K124 | 6264 | M | DST | 0005 | A | 6105AK124-6264-MDST-0005 | Q24050972-08-6264-M-DST-0005 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Pressure Relief Devices Design and Specification | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Pressure Relief Devices |  |  |  | Pending
6105A | K124 | 6264 | W | ELE | 0001 | A | 6105AK124-6264-WELE-0001 | Q24050972-08-6264-W-ELE-0001 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Bulk Earth Works Design and Report | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bulk Earth Works |  |  |  | Pending
6105A | K124 | 6264 | W | ELE | 0002 | A | 6105AK124-6264-WELE-0002 | Q24050972-08-6264-W-ELE-0002 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Bulk Earth Works Design and Report | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bulk Earth Works |  |  |  | Pending
6105A | K124 | 6264 | W | ELE | 0003 | A | 6105AK124-6264-WELE-0003 | Q24050972-08-6264-W-ELE-0003 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Bulk Earth Works Design and Report | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bulk Earth Works |  |  |  | Pending
6105A | K124 | 6264 | W | ELE | 0004 | A | 6105AK124-6264-WELE-0004 | Q24050972-08-6264-W-ELE-0004 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Bulk Earth Works Design and Report | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bulk Earth Works |  |  |  | Pending
6105A | K124 | 6264 | M | EQL | 0001 | A | 6105AK124-6264-MEQL-0001 | Q24050972-08-6264-M-EQL-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Mechanical Equipment Register with Specifications | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Mechanical Equipment Register |  |  |  | Pending
6105A | K124 | 6264 | M | EQL | 0002 | A | 6105AK124-6264-MEQL-0002 | Q24050972-08-6264-M-EQL-0002 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Mechanical Equipment Register with Specifications | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Mechanical Equipment Register |  |  |  | Pending
6105A | K124 | 6264 | M | EQL | 0003 | A | 6105AK124-6264-MEQL-0003 | Q24050972-08-6264-M-EQL-0003 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Mechanical Equipment Register with Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Mechanical Equipment Register |  |  |  | Pending
6105A | K124 | 6264 | M | EQL | 0004 | A | 6105AK124-6264-MEQL-0004 | Q24050972-08-6264-M-EQL-0004 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Mechanical Equipment Register with Specifications | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Mechanical Equipment Register |  |  |  | Pending
6105A | K124 | 6264 | M | EQL | 0005 | A | 6105AK124-6264-MEQL-0005 | Q24050972-08-6264-M-EQL-0005 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Mechanical Equipment Register with Specifications | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Mechanical Equipment Register |  |  |  | Pending
6105A | K124 | 6264 | M | EQL | 0006 | A | 6105AK124-6264-MEQL-0006 | Q24050972-08-6264-M-EQL-0006 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Mechanical Equipment Register with Specifications | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Mechanical Equipment Register |  |  |  | Pending
6105A | K124 | 6264 | M | EQL | 0007 | A | 6105AK124-6264-MEQL-0007 | Q24050972-08-6264-M-EQL-0007 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Mechanical Equipment Register with Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Mechanical Equipment Register |  |  |  | Pending
6105A | K124 | 6264 | M | EQL | 0008 | A | 6105AK124-6264-MEQL-0008 | Q24050972-04-6264-M-EQL-0008 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Mechanical Equipment Register with Specifications | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Mechanical Equipment Register |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0001 | A | 6105AK124-6264-CFND-0001 | Q24050972-04-6264-C-FND-0001 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Civil Foundation Design | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0002 | A | 6105AK124-6264-CFND-0002 | Q24050972-04-6264-C-FND-0002 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Plinth Design and Layout | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Plinth Design and Layout |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0003 | A | 6105AK124-6264-CFND-0003 | Q24050972-04-6264-C-FND-0003 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Civil Foundation Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0004 | A | 6105AK124-6264-CFND-0004 | Q24050972-04-6264-C-FND-0004 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Plinth Design and Layout | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Plinth Design and Layout |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0005 | A | 6105AK124-6264-CFND-0005 | Q24050972-04-6264-C-FND-0005 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | Civil Foundation Design | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0006 | A | 6105AK124-6264-CFND-0006 | Q24050972-04-6264-C-FND-0006 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Civil Foundation Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0007 | A | 6105AK124-6264-CFND-0007 | Q24050972-04-6264-C-FND-0007 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Plinth Design and Layout | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Plinth Design and Layout |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0008 | A | 6105AK124-6264-CFND-0008 | Q24050972-04-6264-C-FND-0008 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Civil Foundation Design | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0009 | A | 6105AK124-6264-CFND-0009 | Q24050972-04-6264-C-FND-0009 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Plinth Design and Layout | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Plinth Design and Layout |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0010 | A | 6105AK124-6264-CFND-0010 | Q24050972-04-6264-C-FND-0010 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Civil Foundation Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0011 | A | 6105AK124-6264-CFND-0011 | Q24050972-04-6264-C-FND-0011 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Plinth Design and Layout | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Plinth Design and Layout |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0012 | A | 6105AK124-6264-CFND-0012 | Q24050972-04-6264-C-FND-0012 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | Civil Foundation Design | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0013 | A | 6105AK124-6264-CFND-0013 | Q24050972-04-6264-C-FND-0013 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Civil Foundation Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Civil Foundation Design |  |  |  | Pending
6105A | K124 | 6264 | C | FND | 0014 | A | 6105AK124-6264-CFND-0014 | Q24050972-04-6264-C-FND-0014 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Plinth Design and Layout | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Plinth Design and Layout |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0001 | A | 6105AK124-6264-CGAD-0001 | Q24050972-04-6264-C-GAD-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Terrace Equipment GA | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0002 | A | 6105AK124-6264-CGAD-0002 | Q24050972-04-6264-C-GAD-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Fire Detection and Suppression System | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection and Suppression System |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0003 | A | 6105AK124-6264-CGAD-0003 | Q24050972-04-6264-C-GAD-0003 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Pipe Routing General Arrangement | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Pipe Routing General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Pipe Routing General Arrangement |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0004 | A | 6105AK124-6264-CGAD-0004 | Q24050972-04-6264-C-GAD-0004 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Utilities Connections and Battery Limits GA | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Utilities Connections and Battery Limits GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Utilities Connections and Battery Limits GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0005 | A | 6105AK124-6264-CGAD-0005 | Q24050972-04-6264-C-GAD-0005 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Lighting Design and Layout GA | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Lighting Design and Layout GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0006 | A | 6105AK124-6264-CGAD-0006 | Q24050972-04-6264-C-GAD-0006 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Buildings and Structures GA | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0007 | A | 6105AK124-6264-CGAD-0007 | Q24050972-04-6264-C-GAD-0007 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Terrace Equipment GA | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0008 | A | 6105AK124-6264-CGAD-0008 | Q24050972-04-6264-C-GAD-0008 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Stormwater and Effluent System Design | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Stormwater and Effluent System Design |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0009 | A | 6105AK124-6264-CGAD-0009 | Q24050972-04-6264-C-GAD-0009 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Stormwater and Effluent System Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Stormwater and Effluent System Design |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0010 | A | 6105AK124-6264-CGAD-0010 | Q24050972-04-6264-C-GAD-0010 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Buildings and Structures GA | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0011 | A | 6105AK124-6264-CGAD-0011 | Q24050972-04-6264-C-GAD-0011 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Lighting Design and Layout GA | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Lighting Design and Layout GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0012 | A | 6105AK124-6264-CGAD-0012 | Q24050972-04-6264-C-GAD-0012 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Key Emergency Points and Equipment | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Key Emergency Points and Equipment |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0013 | A | 6105AK124-6264-CGAD-0013 | Q24050972-04-6264-C-GAD-0013 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Fire Detection and Suppression System | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection and Suppression System |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0014 | A | 6105AK124-6264-CGAD-0014 | Q24050972-04-6264-C-GAD-0014 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | Buildings and Structures GA | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0015 | A | 6105AK124-6264-CGAD-0015 | Q24050972-04-6264-C-GAD-0015 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | Terrace Equipment GA | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0016 | A | 6105AK124-6264-CGAD-0016 | Q24050972-04-6264-C-GAD-0016 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Buildings and Structures GA | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0017 | A | 6105AK124-6264-CGAD-0017 | Q24050972-04-6264-C-GAD-0017 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Terrace Equipment GA | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0018 | A | 6105AK124-6264-CGAD-0018 | Q24050972-04-6264-C-GAD-0018 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Fire Detection and Suppression System | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection and Suppression System |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0019 | A | 6105AK124-6264-CGAD-0019 | Q24050972-04-6264-C-GAD-0019 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Pipe Routing General Arrangement | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Pipe Routing General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Pipe Routing General Arrangement |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0020 | A | 6105AK124-6264-CGAD-0020 | Q24050972-04-6264-C-GAD-0020 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Water Reticulation & Sewer System Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Water Reticulation & Sewer System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Water Reticulation & Sewer System Design |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0021 | A | 6105AK124-6264-CGAD-0021 | Q24050972-04-6264-C-GAD-0021 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Terrace Equipment GA | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0022 | A | 6105AK124-6264-CGAD-0022 | Q24050972-04-6264-C-GAD-0022 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Terrace Equipment GA | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0023 | A | 6105AK124-6264-CGAD-0023 | Q24050972-04-6264-C-GAD-0023 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Fire Detection and Suppression System | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection and Suppression System |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0024 | A | 6105AK124-6264-CGAD-0024 | Q24050972-04-6264-C-GAD-0024 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Pipe Routing General Arrangement | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Pipe Routing General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Pipe Routing General Arrangement |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0025 | A | 6105AK124-6264-CGAD-0025 | Q24050972-04-6264-C-GAD-0025 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Utilities Connections and Battery Limits GA | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Utilities Connections and Battery Limits GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Utilities Connections and Battery Limits GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0026 | A | 6105AK124-6264-CGAD-0026 | Q24050972-04-6264-C-GAD-0026 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Lighting Design and Layout GA | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Lighting Design and Layout GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0027 | A | 6105AK124-6264-CGAD-0027 | Q24050972-04-6264-C-GAD-0027 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Buildings and Structures GA | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0028 | A | 6105AK124-6264-CGAD-0028 | Q24050972-04-6264-C-GAD-0028 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Terrace Equipment GA | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0029 | A | 6105AK124-6264-CGAD-0029 | Q24050972-04-6264-C-GAD-0029 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Stormwater and Effluent System Design | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Stormwater and Effluent System Design |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0030 | A | 6105AK124-6264-CGAD-0030 | Q24050972-04-6264-C-GAD-0030 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Stormwater and Effluent System Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Stormwater and Effluent System Design |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0031 | A | 6105AK124-6264-CGAD-0031 | Q24050972-04-6264-C-GAD-0031 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Buildings and Structures GA | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0032 | A | 6105AK124-6264-CGAD-0032 | Q24050972-04-6264-C-GAD-0032 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Lighting Design and Layout GA | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Lighting Design and Layout GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0033 | A | 6105AK124-6264-CGAD-0033 | Q24050972-04-6264-C-GAD-0033 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Key Emergency Points and Equipment | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Key Emergency Points and Equipment |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0034 | A | 6105AK124-6264-CGAD-0034 | Q24050972-04-6264-C-GAD-0034 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Fire Detection and Suppression System | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection and Suppression System |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0035 | A | 6105AK124-6264-CGAD-0035 | Q24050972-04-6264-C-GAD-0035 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | Buildings and Structures GA | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0036 | A | 6105AK124-6264-CGAD-0036 | Q24050972-04-6264-C-GAD-0036 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | Terrace Equipment GA | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0037 | A | 6105AK124-6264-CGAD-0037 | Q24050972-04-6264-C-GAD-0037 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Buildings and Structures GA | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Buildings and Structures GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0038 | A | 6105AK124-6264-CGAD-0038 | Q24050972-04-6264-C-GAD-0038 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Terrace Equipment GA | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0039 | A | 6105AK124-6264-CGAD-0039 | Q24050972-04-6264-C-GAD-0039 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Fire Detection and Suppression System | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Fire Detection and Suppression System |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection and Suppression System |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0040 | A | 6105AK124-6264-CGAD-0040 | Q24050972-04-6264-C-GAD-0040 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Pipe Routing General Arrangement | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Pipe Routing General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Pipe Routing General Arrangement |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0041 | A | 6105AK124-6264-CGAD-0041 | Q24050972-04-6264-C-GAD-0041 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Water Reticulation & Sewer System Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Water Reticulation & Sewer System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Water Reticulation & Sewer System Design |  |  |  | Pending
6105A | K124 | 6264 | C | GAD | 0042 | A | 6105AK124-6264-CGAD-0042 | Q24050972-04-6264-C-GAD-0042 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Terrace Equipment GA | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Terrace Equipment GA |  |  |  | Pending
6105A | K124 | 6264 | I | HAC | 0001 | A | 6105AK124-6264-IHAC-0001 | Q24050972-04-6264-I-HAC-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Process Safety Design Review (HAZOP & LOPA) | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Process Safety Design Review (HAZOP & LOPA) |  |  |  | Pending
6105A | K124 | 6264 | I | HAC | 0002 | A | 6105AK124-6264-IHAC-0002 | Q24050972-04-6264-I-HAC-0002 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Process Safety Design Review (HAZOP & LOPA) | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Process Safety Design Review (HAZOP & LOPA) |  |  |  | Pending
6105A | K124 | 6264 | I | HAC | 0003 | A | 6105AK124-6264-IHAC-0003 | Q24050972-04-6264-I-HAC-0003 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Process Safety Design Review (HAZOP & LOPA) | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Process Safety Design Review (HAZOP & LOPA) |  |  |  | Pending
6105A | K124 | 6264 | I | HAC | 0004 | A | 6105AK124-6264-IHAC-0004 | Q24050972-04-6264-I-HAC-0004 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Process Safety Design Review (HAZOP & LOPA) | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Process Safety Design Review (HAZOP & LOPA) |  |  |  | Pending
6105A | K124 | 6264 | I | HAC | 0005 | A | 6105AK124-6264-IHAC-0005 | Q24050972-04-6264-I-HAC-0005 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Process Safety Design Review (HAZOP & LOPA) | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Process Safety Design Review (HAZOP & LOPA) |  |  |  | Pending
6105A | K124 | 6264 | I | HAC | 0006 | A | 6105AK124-6264-IHAC-0006 | Q24050972-04-6264-I-HAC-0006 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Process Safety Design Review (HAZOP & LOPA) | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Process Safety Design Review (HAZOP & LOPA) |  |  |  | Pending
6105A | K124 | 6264 | I | HAC | 0007 | A | 6105AK124-6264-IHAC-0007 | Q24050972-04-6264-I-HAC-0007 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Process Safety Design Review (HAZOP & LOPA) | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Process Safety Design Review (HAZOP & LOPA) |  |  |  | Pending
6105A | K124 | 6264 | I | HAC | 0008 | A | 6105AK124-6264-IHAC-0008 | Q24050972-04-6264-I-HAC-0008 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Process Safety Design Review (HAZOP & LOPA) | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Process Safety Design Review (HAZOP & LOPA) |  |  |  | Pending
6105A | K124 | 6264 | M | ISO | 0001 | A | 6105AK124-6264-MISO-0001 | Q24050972-04-6264-M-ISO-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Piping Isometric Design and Layouts | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Piping Isometric Design and Layouts |  |  |  | Pending
6105A | K124 | 6264 | M | ISO | 0002 | A | 6105AK124-6264-MISO-0002 | Q24050972-04-6264-M-ISO-0002 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Piping Isometric Design and Layouts | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Piping Isometric Design and Layouts |  |  |  | Pending
6105A | K124 | 6264 | M | ISO | 0003 | A | 6105AK124-6264-MISO-0003 | Q24050972-04-6264-M-ISO-0003 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Piping Isometric Design and Layouts | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Piping Isometric Design and Layouts |  |  |  | Pending
6105A | K124 | 6264 | M | ISO | 0004 | A | 6105AK124-6264-MISO-0004 | Q24050972-04-6264-M-ISO-0004 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Piping Isometric Design and Layouts | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Piping Isometric Design and Layouts |  |  |  | Pending
6105A | K124 | 6264 | M | ISO | 0005 | A | 6105AK124-6264-MISO-0005 | Q24050972-04-6264-M-ISO-0005 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Piping Isometric Design and Layouts | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Piping Isometric Design and Layouts |  |  |  | Pending
6105A | K124 | 6264 | M | ISO | 0006 | A | 6105AK124-6264-MISO-0006 | Q24050972-04-6264-M-ISO-0006 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Piping Isometric Design and Layouts | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Piping Isometric Design and Layouts |  |  |  | Pending
6105A | K124 | 6264 | M | ISO | 0007 | A | 6105AK124-6264-MISO-0007 | Q24050972-04-6264-M-ISO-0007 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Piping Isometric Design and Layouts | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Piping Isometric Design and Layouts |  |  |  | Pending
6105A | K124 | 6264 | M | ISO | 0008 | A | 6105AK124-6264-MISO-0008 | Q24050972-04-6264-M-ISO-0008 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Piping Isometric Design and Layouts | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Piping Isometric Design and Layouts |  |  |  | Pending
6105A | K124 | 6264 | I | ITD | 0001 | A | 6105AK124-6264-IITD-0001 | Q24050972-04-6264-I-ITD-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Instrument Wiring Loop Diagrams and Cable Schedule | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrument Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6264 | I | ITD | 0002 | A | 6105AK124-6264-IITD-0002 | Q24050972-04-6264-I-ITD-0002 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Instrument Wiring Loop Diagrams and Cable Schedule | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrument Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6264 | I | ITD | 0003 | A | 6105AK124-6264-IITD-0003 | Q24050972-04-6264-I-ITD-0003 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Instrument Wiring Loop Diagrams and Cable Schedule | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrument Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6264 | I | ITD | 0004 | A | 6105AK124-6264-IITD-0004 | Q24050972-04-6264-I-ITD-0004 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Instrument Wiring Loop Diagrams and Cable Schedule | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrument Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6264 | I | ITD | 0005 | A | 6105AK124-6264-IITD-0005 | Q24050972-04-6264-I-ITD-0005 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Instrument Wiring Loop Diagrams and Cable Schedule | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrument Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6264 | I | ITD | 0006 | A | 6105AK124-6264-IITD-0006 | Q24050972-04-6264-I-ITD-0006 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Instrument Wiring Loop Diagrams and Cable Schedule | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrument Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6264 | I | ITD | 0007 | A | 6105AK124-6264-IITD-0007 | Q24050972-04-6264-I-ITD-0007 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Instrument Wiring Loop Diagrams and Cable Schedule | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrument Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6264 | I | ITD | 0008 | A | 6105AK124-6264-IITD-0008 | Q24050972-04-6264-I-ITD-0008 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Instrument Wiring Loop Diagrams and Cable Schedule | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrument Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6264 | I | ITD | 0009 | A | 6105AK124-6264-IITD-0009 | Q24050972-04-6264-I-ITD-0009 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Instrument Wiring Loop Diagrams and Cable Schedule | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrument Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6264 | I | ITD | 0010 | A | 6105AK124-6264-IITD-0010 | Q24050972-04-6264-I-ITD-0010 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Instrument Wiring Loop Diagrams and Cable Schedule | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrument Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6264 | I | ITD | 0011 | A | 6105AK124-6264-IITD-0011 | Q24050972-04-6264-I-ITD-0011 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Instrument Wiring Loop Diagrams and Cable Schedule | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrument Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6264 | I | ITD | 0012 | A | 6105AK124-6264-IITD-0012 | Q24050972-04-6264-I-ITD-0012 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Instrument Wiring Loop Diagrams and Cable Schedule | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrument Wiring Loop Diagrams and Cable Schedule |  |  |  | Pending
6105A | K124 | 6264 | E | LAY | 0001 | A | 6105AK124-6264-ELAY-0001 | Q24050972-03-6264-E-LAY-0001 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Control Room Power and Earthing Design | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control Room Power and Earthing Design |  |  |  | Pending
6105A | K124 | 6264 | E | LAY | 0002 | A | 6105AK124-6264-ELAY-0002 | Q24050972-03-6264-E-LAY-0002 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Control Room Power and Earthing Design | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control Room Power and Earthing Design |  |  |  | Pending
6105A | K124 | 6264 | F | LAY | 0001 | A | 6105AK124-6264-FLAY-0001 | Q24050972-03-6264-F-LAY-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | HMI and Graphics design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - HMI and Graphics design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | HMI and Graphics design |  |  |  | Pending
6105A | K124 | 6264 | F | LAY | 0002 | A | 6105AK124-6264-FLAY-0002 | Q24050972-03-6264-F-LAY-0002 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | HMI and Graphics design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - HMI and Graphics design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | HMI and Graphics design |  |  |  | Pending
6105A | K124 | 6264 | F | LAY | 0003 | A | 6105AK124-6264-FLAY-0003 | Q24050972-03-6264-F-LAY-0003 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | HMI and Graphics design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - HMI and Graphics design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | HMI and Graphics design |  |  |  | Pending
6105A | K124 | 6264 | F | LAY | 0004 | A | 6105AK124-6264-FLAY-0004 | Q24050972-03-6264-F-LAY-0004 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | HMI and Graphics design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - HMI and Graphics design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | HMI and Graphics design |  |  |  | Pending
6105A | K124 | 6264 | W | LAY | 0001 | A | 6105AK124-6264-WLAY-0001 | Q24050972-03-6264-W-LAY-0001 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Drainage, Run-off and Impoundment Design | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Drainage, Run-off and Impoundment Design |  |  |  | Pending
6105A | K124 | 6264 | W | LAY | 0002 | A | 6105AK124-6264-WLAY-0002 | Q24050972-03-6264-W-LAY-0002 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Drainage, Run-off and Impoundment Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Drainage, Run-off and Impoundment Design |  |  |  | Pending
6105A | K124 | 6264 | W | LAY | 0003 | A | 6105AK124-6264-WLAY-0003 | Q24050972-03-6264-W-LAY-0003 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Drainage, Run-off and Impoundment Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Drainage, Run-off and Impoundment Design |  |  |  | Pending
6105A | K124 | 6264 | W | LAY | 0004 | A | 6105AK124-6264-WLAY-0004 | Q24050972-03-6264-W-LAY-0004 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Drainage, Run-off and Impoundment Design | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Drainage, Run-off and Impoundment Design |  |  |  | Pending
6105A | K124 | 6264 | W | LAY | 0005 | A | 6105AK124-6264-WLAY-0005 | Q24050972-03-6264-W-LAY-0005 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Drainage, Run-off and Impoundment Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Drainage, Run-off and Impoundment Design |  |  |  | Pending
6105A | K124 | 6264 | W | LAY | 0006 | A | 6105AK124-6264-WLAY-0006 | Q24050972-03-6264-W-LAY-0006 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Drainage, Run-off and Impoundment Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Drainage, Run-off and Impoundment Design |  |  |  | Pending
6105A | K124 | 6264 | F | LST | 0001 | A | 6105AK124-6264-FLST-0001 | Q24050972-03-6264-F-LST-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Control Loop Register and Tuning Parameters | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Control Loop Register and Tuning Parameters |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control Loop Register and Tuning Parameters |  |  |  | Pending
6105A | K124 | 6264 | F | LST | 0002 | A | 6105AK124-6264-FLST-0002 | Q24050972-03-6264-F-LST-0002 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Control Loop Register and Tuning Parameters | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Control Loop Register and Tuning Parameters |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control Loop Register and Tuning Parameters |  |  |  | Pending
6105A | K124 | 6264 | F | LST | 0003 | A | 6105AK124-6264-FLST-0003 | Q24050972-03-6264-F-LST-0003 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Control Loop Register and Tuning Parameters | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Control Loop Register and Tuning Parameters |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control Loop Register and Tuning Parameters |  |  |  | Pending
6105A | K124 | 6264 | F | LST | 0004 | A | 6105AK124-6264-FLST-0004 | Q24050972-03-6264-F-LST-0004 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Control Loop Register and Tuning Parameters | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Control Loop Register and Tuning Parameters |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control Loop Register and Tuning Parameters |  |  |  | Pending
6105A | K124 | 6264 | F | LST | 0005 | A | 6105AK124-6264-FLST-0005 | Q24050972-03-6264-F-LST-0005 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Control Loop Register and Tuning Parameters | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Control Loop Register and Tuning Parameters |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control Loop Register and Tuning Parameters |  |  |  | Pending
6105A | K124 | 6264 | F | LST | 0006 | A | 6105AK124-6264-FLST-0006 | Q24050972-03-6264-F-LST-0006 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Control Loop Register and Tuning Parameters | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Control Loop Register and Tuning Parameters |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Control Loop Register and Tuning Parameters |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0001 | A | 6105AK124-6264-ILST-0001 | Q24050972-03-6264-I-LST-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Instrumentation Equipment Tag Register | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0002 | A | 6105AK124-6264-ILST-0002 | Q24050972-03-6264-I-LST-0002 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Instrumentation Equipment Tag Register | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0003 | A | 6105AK124-6264-ILST-0003 | Q24050972-03-6264-I-LST-0003 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Equipment Alarm and Trip Level Register | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0004 | A | 6105AK124-6264-ILST-0004 | Q24050972-03-6264-I-LST-0004 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Instrumentation Equipment Tag Register | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0005 | A | 6105AK124-6264-ILST-0005 | Q24050972-03-6264-I-LST-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Equipment Alarm and Trip Level Register | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0006 | A | 6105AK124-6264-ILST-0006 | Q24050972-03-6264-I-LST-0006 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Instrumentation Equipment Tag Register | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0007 | A | 6105AK124-6264-ILST-0007 | Q24050972-03-6264-I-LST-0007 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Equipment Alarm and Trip Level Register | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0008 | A | 6105AK124-6264-ILST-0008 | Q24050972-03-6264-I-LST-0008 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Instrumentation Equipment Tag Register | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0009 | A | 6105AK124-6264-ILST-0009 | Q24050972-03-6264-I-LST-0009 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Equipment Alarm and Trip Level Register | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0010 | A | 6105AK124-6264-ILST-0010 | Q24050972-03-6264-I-LST-0010 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Instrumentation Equipment Tag Register | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0011 | A | 6105AK124-6264-ILST-0011 | Q24050972-03-6264-I-LST-0011 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Instrumentation Equipment Tag Register | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0012 | A | 6105AK124-6264-ILST-0012 | Q24050972-03-6264-I-LST-0012 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Equipment Alarm and Trip Level Register | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0013 | A | 6105AK124-6264-ILST-0013 | Q24050972-03-6264-I-LST-0013 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Instrumentation Equipment Tag Register | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0014 | A | 6105AK124-6264-ILST-0014 | Q24050972-03-6264-I-LST-0014 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Equipment Alarm and Trip Level Register | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0015 | A | 6105AK124-6264-ILST-0015 | Q24050972-03-6264-I-LST-0015 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Instrumentation Equipment Tag Register | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0016 | A | 6105AK124-6264-ILST-0016 | Q24050972-03-6264-I-LST-0016 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Equipment Alarm and Trip Level Register | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0017 | A | 6105AK124-6264-ILST-0017 | Q24050972-03-6264-I-LST-0017 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Instrumentation Equipment Tag Register | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | I | LST | 0018 | A | 6105AK124-6264-ILST-0018 | Q24050972-03-6264-I-LST-0018 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Equipment Alarm and Trip Level Register | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Instrumentation Equipment Tag Register |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0001 | A | 6105AK124-6264-CMDL-0001 | Q24050972-03-6264-C-MDL-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | 3D Designs and Drawings | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0002 | A | 6105AK124-6264-CMDL-0002 | Q24050972-03-6264-C-MDL-0002 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | 3D Designs and Drawings | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0003 | A | 6105AK124-6264-CMDL-0003 | Q24050972-03-6264-C-MDL-0003 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | 3D Designs and Drawings | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0004 | A | 6105AK124-6264-CMDL-0004 | Q24050972-03-6264-C-MDL-0004 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | 3D Designs and Drawings | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0005 | A | 6105AK124-6264-CMDL-0005 | Q24050972-03-6264-C-MDL-0005 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | 3D Designs and Drawings | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0006 | A | 6105AK124-6264-CMDL-0006 | Q24050972-03-6264-C-MDL-0006 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | 3D Designs and Drawings | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0007 | A | 6105AK124-6264-CMDL-0007 | Q24050972-03-6264-C-MDL-0007 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | 3D Designs and Drawings | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0008 | A | 6105AK124-6264-CMDL-0008 | Q24050972-03-6264-C-MDL-0008 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | 3D Designs and Drawings | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0009 | A | 6105AK124-6264-CMDL-0009 | Q24050972-03-6264-C-MDL-0009 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | 3D Designs and Drawings | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0010 | A | 6105AK124-6264-CMDL-0010 | Q24050972-03-6264-C-MDL-0010 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | 3D Designs and Drawings | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0011 | A | 6105AK124-6264-CMDL-0011 | Q24050972-03-6264-C-MDL-0011 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | 3D Designs and Drawings | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0012 | A | 6105AK124-6264-CMDL-0012 | Q24050972-03-6264-C-MDL-0012 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | 3D Designs and Drawings | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0013 | A | 6105AK124-6264-CMDL-0013 | Q24050972-03-6264-C-MDL-0013 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | 3D Designs and Drawings | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 6264 | C | MDL | 0014 | A | 6105AK124-6264-CMDL-0014 | Q24050972-03-6264-C-MDL-0014 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | 3D Designs and Drawings | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | 3D Designs and Drawings |  |  |  | Pending
6105A | K124 | 0100 | Q | TMP | 0010 | A | 6105AK124-0100-QTMP-0010 | Q24050972-04-0100-Q-TMP-0010 | Sht. 1 of 2 | Project Site Wide | Non-Conformance Report (NCR) | Report | Project Site Wide - Non-Conformance Report (NCR) - Report | 2026-05-11 |  | IFR - Issued for Review | Pending | 33.33% | OC |  |  | Non-Conformance Report | Report |  |  |  | Pending
6105A | K124 | 6263 | I | HAC | 0001 | A | 6105AK124-6263-IHAC-0001 | Q24050972-04-6263-I-HAC-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Process Safety Design Review (HAZOP & LOPA) | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | HAC | 0002 | A | 6105AK124-6263-IHAC-0002 | Q24050972-04-6263-I-HAC-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Process Safety Design Review (HAZOP & LOPA) | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Process Safety Design Review (HAZOP & LOPA) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | ITD | 0001 | A | 6105AK124-6263-IITD-0001 | Q24050972-04-6263-I-ITD-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Instrument Wiring Loop Diagrams and Cable Schedule | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | ITD | 0002 | A | 6105AK124-6263-IITD-0002 | Q24050972-04-6263-I-ITD-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Instrument Wiring Loop Diagrams and Cable Schedule | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | ITD | 0003 | A | 6105AK124-6263-IITD-0003 | Q24050972-04-6263-I-ITD-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Instrument Wiring Loop Diagrams and Cable Schedule | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | ITD | 0004 | A | 6105AK124-6263-IITD-0004 | Q24050972-04-6263-I-ITD-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Instrument Wiring Loop Diagrams and Cable Schedule | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | LST | 0001 | A | 6105AK124-6263-ILST-0001 | Q24050972-04-6263-I-LST-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Instrumentation Equipment Tag Register | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | LST | 0002 | A | 6105AK124-6263-ILST-0002 | Q24050972-04-6263-I-LST-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Instrumentation Equipment Tag Register | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | LST | 0003 | A | 6105AK124-6263-ILST-0003 | Q24050972-04-6263-I-LST-0003 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Equipment Alarm and Trip Level Register | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | LST | 0004 | A | 6105AK124-6263-ILST-0004 | Q24050972-04-6263-I-LST-0004 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Instrumentation Equipment Tag Register | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | LST | 0005 | A | 6105AK124-6263-ILST-0005 | Q24050972-04-6263-I-LST-0005 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Instrumentation Equipment Tag Register | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | LST | 0006 | A | 6105AK124-6263-ILST-0006 | Q24050972-04-6263-I-LST-0006 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Equipment Alarm and Trip Level Register | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | NAR | 0001 | A | 6105AK124-6263-INAR-0001 | Q24050972-04-6263-I-NAR-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Plant Instruments Control Philosophy and Narrative | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Plant Instruments Control Philosophy and Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | NAR | 0002 | A | 6105AK124-6263-INAR-0002 | Q24050972-04-6263-I-NAR-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Plant Instruments Control Philosophy and Narrative | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Plant Instruments Control Philosophy and Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | PFD | 0001 | A | 6105AK124-6263-IPFD-0001 | Q24050972-04-6263-I-PFD-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Process Flow Diagram | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Process Flow Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | PFD | 0002 | A | 6105AK124-6263-IPFD-0002 | Q24050972-04-6263-I-PFD-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Process Flow Diagram | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Process Flow Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | PID | 0001 | A | 6105AK124-6263-IPID-0001 | Q24050972-04-6263-I-PID-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Pipe & Instrument Diagrams | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | PID | 0002 | A | 6105AK124-6263-IPID-0002 | Q24050972-04-6263-I-PID-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Pipe & Instrument Diagrams | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | PID | 0003 | A | 6105AK124-6263-IPID-0003 | Q24050972-04-6263-I-PID-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Pipe & Instrument Diagrams | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | PID | 0004 | A | 6105AK124-6263-IPID-0004 | Q24050972-04-6263-I-PID-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Pipe & Instrument Diagrams | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | QRA | 0001 | A | 6105AK124-6263-IQRA-0001 | Q24050972-04-6263-I-QRA-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Risk Assessment: Fire and Explosions | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | QRA | 0002 | A | 6105AK124-6263-IQRA-0002 | Q24050972-04-6263-I-QRA-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Risk Assessment: Hazardous Substances | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Risk Assessment: Hazardous Substances |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | QRA | 0003 | A | 6105AK124-6263-IQRA-0003 | Q24050972-04-6263-I-QRA-0003 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Risk Assessment: Fire and Explosions | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | QRA | 0004 | A | 6105AK124-6263-IQRA-0004 | Q24050972-04-6263-I-QRA-0004 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Risk Assessment: Fire and Explosions | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | QRA | 0005 | A | 6105AK124-6263-IQRA-0005 | Q24050972-04-6263-I-QRA-0005 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Risk Assessment: Hazardous Substances | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Risk Assessment: Hazardous Substances |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | QRA | 0006 | A | 6105AK124-6263-IQRA-0006 | Q24050972-04-6263-I-QRA-0006 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Risk Assessment: Fire and Explosions | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | SPC | 0001 | A | 6105AK124-6263-ISPC-0001 | Q24050972-04-6263-I-SPC-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Automated Isolation Valve Specification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | SPC | 0002 | A | 6105AK124-6263-ISPC-0002 | Q24050972-04-6263-I-SPC-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Junction Box and Interface Cabinet Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | SPC | 0003 | A | 6105AK124-6263-ISPC-0003 | Q24050972-04-6263-I-SPC-0003 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Automated Isolation Valve Specification | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | I | SPC | 0004 | A | 6105AK124-6263-ISPC-0004 | Q24050972-04-6263-I-SPC-0004 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Automated Isolation Valve Specification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | SPC | 0005 | A | 6105AK124-6263-ISPC-0005 | Q24050972-04-6263-I-SPC-0005 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Junction Box and Interface Cabinet Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | I | SPC | 0006 | A | 6105AK124-6263-ISPC-0006 | Q24050972-04-6263-I-SPC-0006 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Automated Isolation Valve Specification | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | CAL | 0001 | A | 6105AK124-6263-MCAL-0001 | Q24050972-04-6263-M-CAL-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Piping Pressure Drop Calculations | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | CAL | 0002 | A | 6105AK124-6263-MCAL-0002 | Q24050972-04-6263-M-CAL-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Vessel and Structure Design with Stress Analysis Calcs | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | CAL | 0003 | A | 6105AK124-6263-MCAL-0003 | Q24050972-04-6263-M-CAL-0003 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Piping Pressure Drop Calculations | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | CAL | 0004 | A | 6105AK124-6263-MCAL-0004 | Q24050972-04-6263-M-CAL-0004 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Piping Pressure Drop Calculations | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | CAL | 0005 | A | 6105AK124-6263-MCAL-0005 | Q24050972-04-6263-M-CAL-0005 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Vessel and Structure Design with Stress Analysis Calcs | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | CAL | 0006 | A | 6105AK124-6263-MCAL-0006 | Q24050972-04-6263-M-CAL-0006 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Piping Pressure Drop Calculations | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | DST | 0001 | A | 6105AK124-6263-MDST-0001 | Q24050972-04-6263-M-DST-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Pressure Relief Devices Design and Specification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | DST | 0002 | A | 6105AK124-6263-MDST-0002 | Q24050972-04-6263-M-DST-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Pressure Relief Devices Design and Specification | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | DST | 0003 | A | 6105AK124-6263-MDST-0003 | Q24050972-04-6263-M-DST-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Pressure Relief Devices Design and Specification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | DST | 0004 | A | 6105AK124-6263-MDST-0004 | Q24050972-04-6263-M-DST-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Pressure Relief Devices Design and Specification | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | EQL | 0001 | A | 6105AK124-6263-MEQL-0001 | Q24050972-04-6263-M-EQL-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Mechanical Equipment Register with Specifications | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | EQL | 0002 | A | 6105AK124-6263-MEQL-0002 | Q24050972-04-6263-M-EQL-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Mechanical Equipment Register with Specifications | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | EQL | 0003 | A | 6105AK124-6263-MEQL-0003 | Q24050972-04-6263-M-EQL-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Mechanical Equipment Register with Specifications | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | EQL | 0004 | A | 6105AK124-6263-MEQL-0004 | Q24050972-04-6263-M-EQL-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Mechanical Equipment Register with Specifications | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | ISO | 0001 | A | 6105AK124-6263-MISO-0001 | Q24050972-04-6263-M-ISO-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Piping Isometric Design and Layouts | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | ISO | 0002 | A | 6105AK124-6263-MISO-0002 | Q24050972-04-6263-M-ISO-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Piping Isometric Design and Layouts | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | ISO | 0003 | A | 6105AK124-6263-MISO-0003 | Q24050972-04-6263-M-ISO-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Piping Isometric Design and Layouts | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | ISO | 0004 | A | 6105AK124-6263-MISO-0004 | Q24050972-04-6263-M-ISO-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Piping Isometric Design and Layouts | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | PRC | 0001 | A | 6105AK124-6263-MPRC-0001 | Q24050972-04-6263-M-PRC-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Fastener Specification and Torque Procedures | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | PRC | 0002 | A | 6105AK124-6263-MPRC-0002 | Q24050972-04-6263-M-PRC-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Fastener Specification and Torque Procedures | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | PRC | 0003 | A | 6105AK124-6263-MPRC-0003 | Q24050972-04-6263-M-PRC-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Fastener Specification and Torque Procedures | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | PRC | 0004 | A | 6105AK124-6263-MPRC-0004 | Q24050972-04-6263-M-PRC-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Fastener Specification and Torque Procedures | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | PSP | 0001 | A | 6105AK124-6263-MPSP-0001 | Q24050972-04-6263-M-PSP-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Pipe and Cable Support Racks Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | PSP | 0002 | A | 6105AK124-6263-MPSP-0002 | Q24050972-04-6263-M-PSP-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Pipe and Cable Support Racks Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | QAD | 0001 | A | 6105AK124-6263-MQAD-0001 | Q24050972-04-6263-M-QAD-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Fabrication Inspection QC Pack (Incl. NDT) | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | QAD | 0002 | A | 6105AK124-6263-MQAD-0002 | Q24050972-04-6263-M-QAD-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Fabrication Inspection QC Pack (Incl. NDT) | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0001 | A | 6105AK124-6263-MSPC-0001 | Q24050972-04-6263-M-SPC-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Material Selection and Verification Specification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0002 | A | 6105AK124-6263-MSPC-0002 | Q24050972-04-6263-M-SPC-0002 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Gasket Schedule and Material Specification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0003 | A | 6105AK124-6263-MSPC-0003 | Q24050972-04-6263-M-SPC-0003 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Pump Design and Specifications | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Pump Design and Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0004 | A | 6105AK124-6263-MSPC-0004 | Q24050972-04-6263-M-SPC-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Lifting and Crawl Beam Design Specification | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Lifting and Crawl Beam Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0005 | A | 6105AK124-6263-MSPC-0005 | Q24050972-04-6263-M-SPC-0005 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Material Selection and Verification Specification | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0006 | A | 6105AK124-6263-MSPC-0006 | Q24050972-04-6263-M-SPC-0006 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Rotating Equipment Alignment Specifications | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Rotating Equipment Alignment Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0007 | A | 6105AK124-6263-MSPC-0007 | Q24050972-04-6263-M-SPC-0007 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Drive Coupling and Connector Design Specification | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Drive Coupling and Connector Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0008 | A | 6105AK124-6263-MSPC-0008 | Q24050972-04-6263-M-SPC-0008 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Material Selection and Verification Specification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0009 | A | 6105AK124-6263-MSPC-0009 | Q24050972-04-6263-M-SPC-0009 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Gasket Schedule and Material Specification | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0010 | A | 6105AK124-6263-MSPC-0010 | Q24050972-04-6263-M-SPC-0010 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Pump Design and Specifications | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Pump Design and Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0011 | A | 6105AK124-6263-MSPC-0011 | Q24050972-04-6263-M-SPC-0011 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Lifting and Crawl Beam Design Specification | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Lifting and Crawl Beam Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0012 | A | 6105AK124-6263-MSPC-0012 | Q24050972-04-6263-M-SPC-0012 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Material Selection and Verification Specification | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0013 | A | 6105AK124-6263-MSPC-0013 | Q24050972-04-6263-M-SPC-0013 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Rotating Equipment Alignment Specifications | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Rotating Equipment Alignment Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | SPC | 0014 | A | 6105AK124-6263-MSPC-0014 | Q24050972-04-6263-M-SPC-0014 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Drive Coupling and Connector Design Specification | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Drive Coupling and Connector Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | STD | 0001 | A | 6105AK124-6263-MSTD-0001 | Q24050972-04-6263-M-STD-0001 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Diesel Fuel Handling and Storage Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Diesel Fuel Handling and Storage Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | STD | 0002 | A | 6105AK124-6263-MSTD-0002 | Q24050972-04-6263-M-STD-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Diesel Fuel Handling and Storage Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Diesel Fuel Handling and Storage Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | M | STD | 0003 | A | 6105AK124-6263-MSTD-0003 | Q24050972-04-6263-M-STD-0003 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Diesel Fuel Handling and Storage Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Diesel Fuel Handling and Storage Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Equip | 36 MVA Power Station Fuel System Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | M | STD | 0004 | A | 6105AK124-6263-MSTD-0004 | Q24050972-04-6263-M-STD-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Diesel Fuel Handling and Storage Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Diesel Fuel Handling and Storage Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | T | RPT | 0001 | A | 6105AK124-6263-TRPT-0001 | Q24050972-04-6263-T-RPT-0001 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Site Surveying & Geotechnical Report | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | T | RPT | 0002 | A | 6105AK124-6263-TRPT-0002 | Q24050972-04-6263-T-RPT-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Site Surveying & Geotechnical Report | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | T | SPC | 0001 | A | 6105AK124-6263-TSPC-0001 | Q24050972-04-6263-T-SPC-0001 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Civil Design and Requirements | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | T | SPC | 0002 | A | 6105AK124-6263-TSPC-0002 | Q24050972-04-6263-T-SPC-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Civil Design and Requirements | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | T | SPC | 0003 | A | 6105AK124-6263-TSPC-0003 | Q24050972-04-6263-T-SPC-0003 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Civil Design and Requirements | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | T | SPC | 0004 | A | 6105AK124-6263-TSPC-0004 | Q24050972-04-6263-T-SPC-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Civil Design and Requirements | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | W | ELE | 0001 | A | 6105AK124-6263-WELE-0001 | Q24050972-04-6263-W-ELE-0001 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Bulk Earth Works Design and Report | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | W | ELE | 0002 | A | 6105AK124-6263-WELE-0002 | Q24050972-04-6263-W-ELE-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Bulk Earth Works Design and Report | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | W | ELE | 0003 | A | 6105AK124-6263-WELE-0003 | Q24050972-04-6263-W-ELE-0003 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Bulk Earth Works Design and Report | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | W | ELE | 0004 | A | 6105AK124-6263-WELE-0004 | Q24050972-04-6263-W-ELE-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Bulk Earth Works Design and Report | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | W | LAY | 0001 | A | 6105AK124-6263-WLAY-0001 | Q24050972-04-6263-W-LAY-0001 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Drainage, Run-off and Impoundment Design | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | W | LAY | 0002 | A | 6105AK124-6263-WLAY-0002 | Q24050972-04-6263-W-LAY-0002 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A | Drainage, Run-off and Impoundment Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1A - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | W | LAY | 0003 | A | 6105AK124-6263-WLAY-0003 | Q24050972-04-6263-W-LAY-0003 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Drainage, Run-off and Impoundment Design | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | W | LAY | 0004 | A | 6105AK124-6263-WLAY-0004 | Q24050972-04-6263-W-LAY-0004 |  | 36 MVA Power Station 1 | Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B | Drainage, Run-off and Impoundment Design | 36 MVA Power Station 1 - Collection Sump from Bunds for 36 MVA Power Station Gen Pad 1B - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Collection Sump from Bunds | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6263 | W | TRP | 0001 | A | 6105AK124-6263-WTRP-0001 | Q24050972-04-6263-W-TRP-0001 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1A | Soil Classification and Nomination Deliverables | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1A - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1A |  |  |  | Pending
6105A | K124 | 6263 | W | TRP | 0002 | A | 6105AK124-6263-WTRP-0002 | Q24050972-04-6263-W-TRP-0002 |  | 36 MVA Power Station 1 | Bund wall System for 36 MVA Power Station Gen Pad 1B | Soil Classification and Nomination Deliverables | 36 MVA Power Station 1 - Bund wall System for 36 MVA Power Station Gen Pad 1B - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bund wall System | 36 MVA Power Station Gen Pad 1B |  |  |  | Pending
6105A | K124 | 6264 | B | PHL | 0001 | A | 6105AK124-6264-BPHL-0001 | Q24050972-04-6264-B-PHL-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Control Philosophy | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | B | PHL | 0002 | A | 6105AK124-6264-BPHL-0002 | Q24050972-04-6264-B-PHL-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Power Management System Philosophy | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Power Management System Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | B | PHL | 0003 | A | 6105AK124-6264-BPHL-0003 | Q24050972-04-6264-B-PHL-0003 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Control Philosophy | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | B | PHL | 0004 | A | 6105AK124-6264-BPHL-0004 | Q24050972-04-6264-B-PHL-0004 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Power Management System Philosophy | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Power Management System Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | B | PHL | 0005 | A | 6105AK124-6264-BPHL-0005 | Q24050972-04-6264-B-PHL-0005 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Control Philosophy | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | B | PHL | 0006 | A | 6105AK124-6264-BPHL-0006 | Q24050972-04-6264-B-PHL-0006 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Power Management System Philosophy | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Power Management System Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | B | PHL | 0007 | A | 6105AK124-6264-BPHL-0007 | Q24050972-04-6264-B-PHL-0007 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Control Philosophy | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | B | PHL | 0008 | A | 6105AK124-6264-BPHL-0008 | Q24050972-04-6264-B-PHL-0008 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Power Management System Philosophy | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Power Management System Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | B | SPC | 0001 | A | 6105AK124-6264-BSPC-0001 | Q24050972-04-6264-B-SPC-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Functional Design Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | B | SPC | 0002 | A | 6105AK124-6264-BSPC-0002 | Q24050972-04-6264-B-SPC-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Functional Design Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | B | STD | 0001 | A | 6105AK124-6264-BSTD-0001 | Q24050972-04-6264-B-STD-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | System Detailed Engineering Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | B | STD | 0002 | A | 6105AK124-6264-BSTD-0002 | Q24050972-04-6264-B-STD-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | System Detailed Engineering Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0001 | A | 6105AK124-6264-FNAR-0001 | Q24050972-04-6264-F-NAR-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Emergency Shutdown System Control Narrative | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0002 | A | 6105AK124-6264-FNAR-0002 | Q24050972-04-6264-F-NAR-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Control System Control Narrative & Interlock Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0003 | A | 6105AK124-6264-FNAR-0003 | Q24050972-04-6264-F-NAR-0003 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Control System Control Narrative & Interlock Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0004 | A | 6105AK124-6264-FNAR-0004 | Q24050972-04-6264-F-NAR-0004 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Emergency Shutdown System Control Narrative | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0005 | A | 6105AK124-6264-FNAR-0005 | Q24050972-04-6264-F-NAR-0005 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Control System Control Narrative & Interlock Design | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0006 | A | 6105AK124-6264-FNAR-0006 | Q24050972-04-6264-F-NAR-0006 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Control System Control Narrative & Interlock Design | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0007 | A | 6105AK124-6264-FNAR-0007 | Q24050972-04-6264-F-NAR-0007 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Emergency Shutdown System Control Narrative | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0008 | A | 6105AK124-6264-FNAR-0008 | Q24050972-04-6264-F-NAR-0008 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Emergency Shutdown System Control Narrative | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0009 | A | 6105AK124-6264-FNAR-0009 | Q24050972-04-6264-F-NAR-0009 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Control System Control Narrative & Interlock Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0010 | A | 6105AK124-6264-FNAR-0010 | Q24050972-04-6264-F-NAR-0010 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Control System Control Narrative & Interlock Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0011 | A | 6105AK124-6264-FNAR-0011 | Q24050972-04-6264-F-NAR-0011 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Emergency Shutdown System Control Narrative | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0012 | A | 6105AK124-6264-FNAR-0012 | Q24050972-04-6264-F-NAR-0012 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Control System Control Narrative & Interlock Design | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0013 | A | 6105AK124-6264-FNAR-0013 | Q24050972-04-6264-F-NAR-0013 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Control System Control Narrative & Interlock Design | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Control System Control Narrative & Interlock Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | F | NAR | 0014 | A | 6105AK124-6264-FNAR-0014 | Q24050972-04-6264-F-NAR-0014 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Emergency Shutdown System Control Narrative | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Emergency Shutdown System Control Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | I | NAR | 0001 | A | 6105AK124-6264-INAR-0001 | Q24050972-04-6264-I-NAR-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Plant Instruments Control Philosophy and Narrative | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Plant Instruments Control Philosophy and Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | NAR | 0002 | A | 6105AK124-6264-INAR-0002 | Q24050972-04-6264-I-NAR-0002 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Plant Instruments Control Philosophy and Narrative | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Plant Instruments Control Philosophy and Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | NAR | 0003 | A | 6105AK124-6264-INAR-0003 | Q24050972-04-6264-I-NAR-0003 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Plant Instruments Control Philosophy and Narrative | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Plant Instruments Control Philosophy and Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | NAR | 0004 | A | 6105AK124-6264-INAR-0004 | Q24050972-04-6264-I-NAR-0004 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Plant Instruments Control Philosophy and Narrative | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Plant Instruments Control Philosophy and Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | NAR | 0005 | A | 6105AK124-6264-INAR-0005 | Q24050972-04-6264-I-NAR-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Plant Instruments Control Philosophy and Narrative | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Plant Instruments Control Philosophy and Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | NAR | 0006 | A | 6105AK124-6264-INAR-0006 | Q24050972-04-6264-I-NAR-0006 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Plant Instruments Control Philosophy and Narrative | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Plant Instruments Control Philosophy and Narrative |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 0000 | H | PLN | 0001 | A | 6105AK124-0000-HPLN-0001 | Q24050972-04-0000-H-PLN-0001 |  | General | Health & Safety | Project Sustainability Plan - Phase 1 EC&I Power Packages | General - Health & Safety - Project Sustainability Plan - Phase 1 EC&I Power Packages |  |  | RES - Reserved Placeholder | Pending | 0% | JM |  | 2026-08-05 | Health & Safety | Project Sustainability Plan |  |  |  | Pending
6105A | K124 | 6264 | I | PFD | 0001 | A | 6105AK124-6264-IPFD-0001 | Q24050972-04-6264-I-PFD-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Process Flow Diagram | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Process Flow Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | PFD | 0002 | A | 6105AK124-6264-IPFD-0002 | Q24050972-04-6264-I-PFD-0002 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Process Flow Diagram | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Process Flow Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | PFD | 0003 | A | 6105AK124-6264-IPFD-0003 | Q24050972-04-6264-I-PFD-0003 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Process Flow Diagram | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Process Flow Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | PFD | 0004 | A | 6105AK124-6264-IPFD-0004 | Q24050972-04-6264-I-PFD-0004 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Process Flow Diagram | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Process Flow Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | PFD | 0005 | A | 6105AK124-6264-IPFD-0005 | Q24050972-04-6264-I-PFD-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Process Flow Diagram | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Process Flow Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | PFD | 0006 | A | 6105AK124-6264-IPFD-0006 | Q24050972-04-6264-I-PFD-0006 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Process Flow Diagram | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Process Flow Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | F | PHL | 0001 | A | 6105AK124-6264-FPHL-0001 | Q24050972-04-6264-F-PHL-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Control System Control Philosophy | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | PHL | 0002 | A | 6105AK124-6264-FPHL-0002 | Q24050972-04-6264-F-PHL-0002 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Control System Control Philosophy | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | PHL | 0003 | A | 6105AK124-6264-FPHL-0003 | Q24050972-04-6264-F-PHL-0003 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Control System Control Philosophy | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | F | PHL | 0004 | A | 6105AK124-6264-FPHL-0004 | Q24050972-04-6264-F-PHL-0004 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Control System Control Philosophy | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | F | PHL | 0005 | A | 6105AK124-6264-FPHL-0005 | Q24050972-04-6264-F-PHL-0005 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Control System Control Philosophy | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | PHL | 0006 | A | 6105AK124-6264-FPHL-0006 | Q24050972-04-6264-F-PHL-0006 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Control System Control Philosophy | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | PHL | 0007 | A | 6105AK124-6264-FPHL-0007 | Q24050972-04-6264-F-PHL-0007 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Control System Control Philosophy | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | F | PHL | 0008 | A | 6105AK124-6264-FPHL-0008 | Q24050972-04-6264-F-PHL-0008 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Control System Control Philosophy | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Control System Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | I | PID | 0001 | A | 6105AK124-6264-IPID-0001 | Q24050972-04-6264-I-PID-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Pipe & Instrument Diagrams | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | PID | 0002 | A | 6105AK124-6264-IPID-0002 | Q24050972-04-6264-I-PID-0002 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Pipe & Instrument Diagrams | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | I | PID | 0003 | A | 6105AK124-6264-IPID-0003 | Q24050972-04-6264-I-PID-0003 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Pipe & Instrument Diagrams | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | PID | 0004 | A | 6105AK124-6264-IPID-0004 | Q24050972-04-6264-I-PID-0004 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Pipe & Instrument Diagrams | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | PID | 0005 | A | 6105AK124-6264-IPID-0005 | Q24050972-04-6264-I-PID-0005 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Pipe & Instrument Diagrams | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | I | PID | 0006 | A | 6105AK124-6264-IPID-0006 | Q24050972-04-6264-I-PID-0006 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Pipe & Instrument Diagrams | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | PID | 0007 | A | 6105AK124-6264-IPID-0007 | Q24050972-04-6264-I-PID-0007 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Pipe & Instrument Diagrams | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | I | PID | 0008 | A | 6105AK124-6264-IPID-0008 | Q24050972-04-6264-I-PID-0008 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Pipe & Instrument Diagrams | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | PID | 0009 | A | 6105AK124-6264-IPID-0009 | Q24050972-04-6264-I-PID-0009 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Pipe & Instrument Diagrams | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | PID | 0010 | A | 6105AK124-6264-IPID-0010 | Q24050972-04-6264-I-PID-0010 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Pipe & Instrument Diagrams | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Pipe & Instrument Diagrams |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | C | PLN | 0001 | A | 6105AK124-6264-CPLN-0001 | Q24050972-04-6264-C-PLN-0001 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Civil Works Execution Plan | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | C | PLN | 0002 | A | 6105AK124-6264-CPLN-0002 | Q24050972-04-6264-C-PLN-0002 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Civil Works Execution Plan | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | PLN | 0003 | A | 6105AK124-6264-CPLN-0003 | Q24050972-04-6264-C-PLN-0003 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Civil Works Execution Plan | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | PLN | 0004 | A | 6105AK124-6264-CPLN-0004 | Q24050972-04-6264-C-PLN-0004 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Civil Works Execution Plan | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | C | PLN | 0005 | A | 6105AK124-6264-CPLN-0005 | Q24050972-04-6264-C-PLN-0005 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | Civil Works Execution Plan | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | PLN | 0006 | A | 6105AK124-6264-CPLN-0006 | Q24050972-04-6264-C-PLN-0006 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Civil Works Execution Plan | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | PLN | 0007 | A | 6105AK124-6264-CPLN-0007 | Q24050972-04-6264-C-PLN-0007 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Civil Works Execution Plan | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | C | PLN | 0008 | A | 6105AK124-6264-CPLN-0008 | Q24050972-04-6264-C-PLN-0008 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Civil Works Execution Plan | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | PLN | 0009 | A | 6105AK124-6264-CPLN-0009 | Q24050972-04-6264-C-PLN-0009 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Civil Works Execution Plan | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | PLN | 0010 | A | 6105AK124-6264-CPLN-0010 | Q24050972-04-6264-C-PLN-0010 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Civil Works Execution Plan | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | C | PLN | 0011 | A | 6105AK124-6264-CPLN-0011 | Q24050972-04-6264-C-PLN-0011 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | Civil Works Execution Plan | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | PLN | 0012 | A | 6105AK124-6264-CPLN-0012 | Q24050972-04-6264-C-PLN-0012 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Civil Works Execution Plan | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | PPL | 0001 | A | 6105AK124-6264-CPPL-0001 | Q24050972-04-6264-C-PPL-0001 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Operational & Maint Access Routes Design | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | C | PPL | 0002 | A | 6105AK124-6264-CPPL-0002 | Q24050972-04-6264-C-PPL-0002 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Operational & Maint Access Routes Design | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | F | PRC | 0001 | A | 6105AK124-6264-FPRC-0001 | Q24050972-04-6264-F-PRC-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Alarm Classification Methodology | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Alarm Classification Methodology |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | PRC | 0002 | A | 6105AK124-6264-FPRC-0002 | Q24050972-04-6264-F-PRC-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Alarm Classification Methodology | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Alarm Classification Methodology |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | PRC | 0001 | A | 6105AK124-6264-MPRC-0001 | Q24050972-04-6264-M-PRC-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Fastener Specification and Torque Procedures | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | PRC | 0002 | A | 6105AK124-6264-MPRC-0002 | Q24050972-04-6264-M-PRC-0002 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Fastener Specification and Torque Procedures | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | PRC | 0003 | A | 6105AK124-6264-MPRC-0003 | Q24050972-04-6264-M-PRC-0003 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Rigging Study and Lifting Equipment Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | PRC | 0004 | A | 6105AK124-6264-MPRC-0004 | Q24050972-04-6264-M-PRC-0004 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Fastener Specification and Torque Procedures | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | PRC | 0005 | A | 6105AK124-6264-MPRC-0005 | Q24050972-04-6264-M-PRC-0005 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Fastener Specification and Torque Procedures | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | M | PRC | 0006 | A | 6105AK124-6264-MPRC-0006 | Q24050972-04-6264-M-PRC-0006 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Fastener Specification and Torque Procedures | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | PRC | 0007 | A | 6105AK124-6264-MPRC-0007 | Q24050972-04-6264-M-PRC-0007 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Fastener Specification and Torque Procedures | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | PRC | 0008 | A | 6105AK124-6264-MPRC-0008 | Q24050972-04-6264-M-PRC-0008 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Rigging Study and Lifting Equipment Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | PRC | 0009 | A | 6105AK124-6264-MPRC-0009 | Q24050972-04-6264-M-PRC-0009 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Fastener Specification and Torque Procedures | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | PRC | 0010 | A | 6105AK124-6264-MPRC-0010 | Q24050972-04-6264-M-PRC-0010 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Fastener Specification and Torque Procedures | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | M | PSP | 0001 | A | 6105AK124-6264-MPSP-0001 | Q24050972-04-6264-M-PSP-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Pipe and Cable Support Racks Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | PSP | 0002 | A | 6105AK124-6264-MPSP-0002 | Q24050972-04-6264-M-PSP-0002 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Pipe and Cable Support Racks Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | PSP | 0003 | A | 6105AK124-6264-MPSP-0003 | Q24050972-04-6264-M-PSP-0003 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Pipe and Cable Support Racks Design | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | M | PSP | 0004 | A | 6105AK124-6264-MPSP-0004 | Q24050972-04-6264-M-PSP-0004 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Pipe and Cable Support Racks Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | PSP | 0005 | A | 6105AK124-6264-MPSP-0005 | Q24050972-04-6264-M-PSP-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Pipe and Cable Support Racks Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | PSP | 0006 | A | 6105AK124-6264-MPSP-0006 | Q24050972-04-6264-M-PSP-0006 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Pipe and Cable Support Racks Design | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | M | QAD | 0001 | A | 6105AK124-6264-MQAD-0001 | Q24050972-04-6264-M-QAD-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Fabrication Inspection QC Pack (Incl. NDT) | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | QAD | 0002 | A | 6105AK124-6264-MQAD-0002 | Q24050972-04-6264-M-QAD-0002 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Fabrication Inspection QC Pack (Incl. NDT) | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | QAD | 0003 | A | 6105AK124-6264-MQAD-0003 | Q24050972-04-6264-M-QAD-0003 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Fabrication Inspection QC Pack (Incl. NDT) | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | QAD | 0004 | A | 6105AK124-6264-MQAD-0004 | Q24050972-04-6264-M-QAD-0004 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Fabrication Inspection QC Pack (Incl. NDT) | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | QRA | 0001 | A | 6105AK124-6264-EQRA-0001 | Q24050972-04-6264-E-QRA-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Lightning Protection Study and Risk Assessment | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | E | QRA | 0002 | A | 6105AK124-6264-EQRA-0002 | Q24050972-04-6264-E-QRA-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Risk Assessment: Electrical Hazards | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | E | QRA | 0003 | A | 6105AK124-6264-EQRA-0003 | Q24050972-04-6264-E-QRA-0003 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Lightning Protection Study and Risk Assessment | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | QRA | 0004 | A | 6105AK124-6264-EQRA-0004 | Q24050972-04-6264-E-QRA-0004 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Lightning Protection Study and Risk Assessment | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | E | QRA | 0005 | A | 6105AK124-6264-EQRA-0005 | Q24050972-04-6264-E-QRA-0005 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Risk Assessment: Electrical Hazards | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | E | QRA | 0006 | A | 6105AK124-6264-EQRA-0006 | Q24050972-04-6264-E-QRA-0006 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Lightning Protection Study and Risk Assessment | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0001 | A | 6105AK124-6264-IQRA-0001 | Q24050972-04-6264-I-QRA-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Risk Assessment: Fire and Explosions | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0002 | A | 6105AK124-6264-IQRA-0002 | Q24050972-04-6264-I-QRA-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Risk Assessment: Hazardous Substances | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Risk Assessment: Hazardous Substances |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0003 | A | 6105AK124-6264-IQRA-0003 | Q24050972-04-6264-I-QRA-0003 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Risk Assessment: Fire and Explosions | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0004 | A | 6105AK124-6264-IQRA-0004 | Q24050972-04-6264-I-QRA-0004 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | Risk Assessment: Fire and Explosions | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0005 | A | 6105AK124-6264-IQRA-0005 | Q24050972-04-6264-I-QRA-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Risk Assessment: Fire and Explosions | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0006 | A | 6105AK124-6264-IQRA-0006 | Q24050972-04-6264-I-QRA-0006 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Risk Assessment: Fire and Explosions | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0007 | A | 6105AK124-6264-IQRA-0007 | Q24050972-04-6264-I-QRA-0007 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Risk Assessment: Hazardous Atm. Conditions | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Risk Assessment: Hazardous Atm. Conditions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0008 | A | 6105AK124-6264-IQRA-0008 | Q24050972-04-6264-I-QRA-0008 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Risk Assessment: Fire and Explosions | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0009 | A | 6105AK124-6264-IQRA-0009 | Q24050972-04-6264-I-QRA-0009 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Risk Assessment: Hazardous Substances | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Risk Assessment: Hazardous Substances |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0010 | A | 6105AK124-6264-IQRA-0010 | Q24050972-04-6264-I-QRA-0010 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Risk Assessment: Fire and Explosions | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0011 | A | 6105AK124-6264-IQRA-0011 | Q24050972-04-6264-I-QRA-0011 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | Risk Assessment: Fire and Explosions | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0012 | A | 6105AK124-6264-IQRA-0012 | Q24050972-04-6264-I-QRA-0012 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Risk Assessment: Fire and Explosions | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0013 | A | 6105AK124-6264-IQRA-0013 | Q24050972-04-6264-I-QRA-0013 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Risk Assessment: Fire and Explosions | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | QRA | 0014 | A | 6105AK124-6264-IQRA-0014 | Q24050972-04-6264-I-QRA-0014 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Risk Assessment: Hazardous Atm. Conditions | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Risk Assessment: Hazardous Atm. Conditions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | T | RPT | 0001 | A | 6105AK124-6264-TRPT-0001 | Q24050972-04-6264-T-RPT-0001 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Site Surveying & Geotechnical Report | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | T | RPT | 0002 | A | 6105AK124-6264-TRPT-0002 | Q24050972-04-6264-T-RPT-0002 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | Site Surveying & Geotechnical Report | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | T | RPT | 0003 | A | 6105AK124-6264-TRPT-0003 | Q24050972-04-6264-T-RPT-0003 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Site Surveying & Geotechnical Report | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | T | RPT | 0004 | A | 6105AK124-6264-TRPT-0004 | Q24050972-04-6264-T-RPT-0004 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Site Surveying & Geotechnical Report | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | T | RPT | 0005 | A | 6105AK124-6264-TRPT-0005 | Q24050972-04-6264-T-RPT-0005 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | Site Surveying & Geotechnical Report | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | T | RPT | 0006 | A | 6105AK124-6264-TRPT-0006 | Q24050972-04-6264-T-RPT-0006 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Site Surveying & Geotechnical Report | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0003 | A | 6105AK124-6264-CSEC-0003 | Q24050972-04-6264-C-SEC-0003 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Corrosion Prevention and Protection Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0004 | A | 6105AK124-6264-CSEC-0004 | Q24050972-04-6264-C-SEC-0004 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Structural Earthing and Bonding Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0005 | A | 6105AK124-6264-CSEC-0005 | Q24050972-04-6264-C-SEC-0005 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Corrosion Prevention and Protection Design | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0006 | A | 6105AK124-6264-CSEC-0006 | Q24050972-04-6264-C-SEC-0006 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Structural Earthing and Bonding Design | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0007 | A | 6105AK124-6264-CSEC-0007 | Q24050972-04-6264-C-SEC-0007 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Structural Earthing and Bonding Design | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0008 | A | 6105AK124-6264-CSEC-0008 | Q24050972-04-6264-C-SEC-0008 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Structural Earthing and Bonding Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0009 | A | 6105AK124-6264-CSEC-0009 | Q24050972-04-6264-C-SEC-0009 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Corrosion Prevention and Protection Design | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0010 | A | 6105AK124-6264-CSEC-0010 | Q24050972-04-6264-C-SEC-0010 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Corrosion Prevention and Protection Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0011 | A | 6105AK124-6264-CSEC-0011 | Q24050972-04-6264-C-SEC-0011 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Structural Earthing and Bonding Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0012 | A | 6105AK124-6264-CSEC-0012 | Q24050972-04-6264-C-SEC-0012 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Corrosion Prevention and Protection Design | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0013 | A | 6105AK124-6264-CSEC-0013 | Q24050972-04-6264-C-SEC-0013 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Structural Earthing and Bonding Design | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0014 | A | 6105AK124-6264-CSEC-0014 | Q24050972-04-6264-C-SEC-0014 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Structural Earthing and Bonding Design | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0015 | A | 6105AK124-6264-CSEC-0015 | Q24050972-04-6264-C-SEC-0015 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Structural Earthing and Bonding Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SEC | 0016 | A | 6105AK124-6264-CSEC-0016 | Q24050972-04-6264-C-SEC-0016 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Corrosion Prevention and Protection Design | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | C | SHP | 0001 | A | 6105AK124-6264-CSHP-0001 | Q24050972-04-6264-C-SHP-0001 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Equipment Assembly Drawings | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SHP | 0002 | A | 6105AK124-6264-CSHP-0002 | Q24050972-04-6264-C-SHP-0002 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Equipment Assembly Drawings | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SHP | 0001 | A | 6105AK124-6264-MSHP-0001 | Q24050972-04-6264-M-SHP-0001 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Equipment Fabrication Drawings | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Equipment Fabrication Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | M | SHP | 0002 | A | 6105AK124-6264-MSHP-0002 | Q24050972-04-6264-M-SHP-0002 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Equipment Fabrication Drawings | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Equipment Fabrication Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | E | SLD | 0001 | A | 6105AK124-6264-ESLD-0001 | Q24050972-04-6264-E-SLD-0001 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Electrical Single Line Diagram | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | SLD | 0002 | A | 6105AK124-6264-ESLD-0002 | Q24050972-04-6264-E-SLD-0002 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Electrical Single Line Diagram | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0001 | A | 6105AK124-6264-CSPC-0001 | Q24050972-04-6264-C-SPC-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Steel Structures Corrosion Protection Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0002 | A | 6105AK124-6264-CSPC-0002 | Q24050972-04-6264-C-SPC-0002 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Concrete Construction Material Specifications | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0003 | A | 6105AK124-6264-CSPC-0003 | Q24050972-04-6264-C-SPC-0003 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Excavation, Trenching and Compacting Design | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0004 | A | 6105AK124-6264-CSPC-0004 | Q24050972-04-6264-C-SPC-0004 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Civil Design Requirements | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0005 | A | 6105AK124-6264-CSPC-0005 | Q24050972-04-6264-C-SPC-0005 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Excavation, Trenching and Compacting Design | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0006 | A | 6105AK124-6264-CSPC-0006 | Q24050972-04-6264-C-SPC-0006 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Concrete Construction Material Specifications | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0007 | A | 6105AK124-6264-CSPC-0007 | Q24050972-04-6264-C-SPC-0007 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Civil Design Requirements | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0008 | A | 6105AK124-6264-CSPC-0008 | Q24050972-04-6264-C-SPC-0008 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Excavation, Trenching and Compacting Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0009 | A | 6105AK124-6264-CSPC-0009 | Q24050972-04-6264-C-SPC-0009 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Concrete Construction Material Specifications | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0010 | A | 6105AK124-6264-CSPC-0010 | Q24050972-04-6264-C-SPC-0010 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Steel Structures Corrosion Protection Specification | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0011 | A | 6105AK124-6264-CSPC-0011 | Q24050972-04-6264-C-SPC-0011 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | Civil Design Requirements | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0012 | A | 6105AK124-6264-CSPC-0012 | Q24050972-04-6264-C-SPC-0012 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | Concrete Construction Material Specifications | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0013 | A | 6105AK124-6264-CSPC-0013 | Q24050972-04-6264-C-SPC-0013 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Civil Design Requirements | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0014 | A | 6105AK124-6264-CSPC-0014 | Q24050972-04-6264-C-SPC-0014 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Excavation, Trenching and Compacting Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0015 | A | 6105AK124-6264-CSPC-0015 | Q24050972-04-6264-C-SPC-0015 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Concrete Construction Material Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0016 | A | 6105AK124-6264-CSPC-0016 | Q24050972-04-6264-C-SPC-0016 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Steel Structures Corrosion Protection Specification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0017 | A | 6105AK124-6264-CSPC-0017 | Q24050972-04-6264-C-SPC-0017 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Steel Structures Corrosion Protection Specification | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0018 | A | 6105AK124-6264-CSPC-0018 | Q24050972-04-6264-C-SPC-0018 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Steel Structures Corrosion Protection Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0019 | A | 6105AK124-6264-CSPC-0019 | Q24050972-04-6264-C-SPC-0019 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Concrete Construction Material Specifications | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0020 | A | 6105AK124-6264-CSPC-0020 | Q24050972-04-6264-C-SPC-0020 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Excavation, Trenching and Compacting Design | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0021 | A | 6105AK124-6264-CSPC-0021 | Q24050972-04-6264-C-SPC-0021 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Civil Design Requirements | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0022 | A | 6105AK124-6264-CSPC-0022 | Q24050972-04-6264-C-SPC-0022 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Excavation, Trenching and Compacting Design | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0023 | A | 6105AK124-6264-CSPC-0023 | Q24050972-04-6264-C-SPC-0023 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Concrete Construction Material Specifications | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0024 | A | 6105AK124-6264-CSPC-0024 | Q24050972-04-6264-C-SPC-0024 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Civil Design Requirements | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0025 | A | 6105AK124-6264-CSPC-0025 | Q24050972-04-6264-C-SPC-0025 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Excavation, Trenching and Compacting Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0026 | A | 6105AK124-6264-CSPC-0026 | Q24050972-04-6264-C-SPC-0026 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Concrete Construction Material Specifications | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0027 | A | 6105AK124-6264-CSPC-0027 | Q24050972-04-6264-C-SPC-0027 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Steel Structures Corrosion Protection Specification | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0028 | A | 6105AK124-6264-CSPC-0028 | Q24050972-04-6264-C-SPC-0028 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | Civil Design Requirements | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0029 | A | 6105AK124-6264-CSPC-0029 | Q24050972-04-6264-C-SPC-0029 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | Concrete Construction Material Specifications | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0030 | A | 6105AK124-6264-CSPC-0030 | Q24050972-04-6264-C-SPC-0030 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Civil Design Requirements | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0031 | A | 6105AK124-6264-CSPC-0031 | Q24050972-04-6264-C-SPC-0031 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Excavation, Trenching and Compacting Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0032 | A | 6105AK124-6264-CSPC-0032 | Q24050972-04-6264-C-SPC-0032 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Concrete Construction Material Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0033 | A | 6105AK124-6264-CSPC-0033 | Q24050972-04-6264-C-SPC-0033 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Steel Structures Corrosion Protection Specification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPC | 0034 | A | 6105AK124-6264-CSPC-0034 | Q24050972-04-6264-C-SPC-0034 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Steel Structures Corrosion Protection Specification | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | E | SPC | 0001 | A | 6105AK124-6264-ESPC-0001 | Q24050972-04-6264-E-SPC-0001 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Cable and Conductor Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | SPC | 0002 | A | 6105AK124-6264-ESPC-0002 | Q24050972-04-6264-E-SPC-0002 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Cable Termination Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | SPC | 0003 | A | 6105AK124-6264-ESPC-0003 | Q24050972-04-6264-E-SPC-0003 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Generator Requirements and Specification | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Generator Requirements and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | E | SPC | 0004 | A | 6105AK124-6264-ESPC-0004 | Q24050972-04-6264-E-SPC-0004 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Cable and Conductor Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | SPC | 0005 | A | 6105AK124-6264-ESPC-0005 | Q24050972-04-6264-E-SPC-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Cable Termination Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | SPC | 0006 | A | 6105AK124-6264-ESPC-0006 | Q24050972-04-6264-E-SPC-0006 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Generator Requirements and Specification | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Generator Requirements and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | F | SPC | 0001 | A | 6105AK124-6264-FSPC-0001 | Q24050972-04-6264-F-SPC-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Control System Design Requirements | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Control System Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | SPC | 0002 | A | 6105AK124-6264-FSPC-0002 | Q24050972-04-6264-F-SPC-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Historian and Server Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | SPC | 0003 | A | 6105AK124-6264-FSPC-0003 | Q24050972-04-6264-F-SPC-0003 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Control System Design Requirements | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Control System Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | SPC | 0004 | A | 6105AK124-6264-FSPC-0004 | Q24050972-04-6264-F-SPC-0004 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Historian and Server Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | SPC | 0005 | A | 6105AK124-6264-FSPC-0005 | Q24050972-04-6264-F-SPC-0005 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Control System Design Requirements | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Control System Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | F | SPC | 0006 | A | 6105AK124-6264-FSPC-0006 | Q24050972-04-6264-F-SPC-0006 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Control System Design Requirements | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Control System Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | SPC | 0007 | A | 6105AK124-6264-FSPC-0007 | Q24050972-04-6264-F-SPC-0007 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Historian and Server Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | F | SPC | 0008 | A | 6105AK124-6264-FSPC-0008 | Q24050972-04-6264-F-SPC-0008 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Control System Design Requirements | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Control System Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | SPC | 0009 | A | 6105AK124-6264-FSPC-0009 | Q24050972-04-6264-F-SPC-0009 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Historian and Server Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | F | SPC | 0010 | A | 6105AK124-6264-FSPC-0010 | Q24050972-04-6264-F-SPC-0010 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Control System Design Requirements | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Control System Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0001 | A | 6105AK124-6264-ISPC-0001 | Q24050972-04-6264-I-SPC-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Automated Isolation Valve Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0002 | A | 6105AK124-6264-ISPC-0002 | Q24050972-04-6264-I-SPC-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Junction Box and Interface Cabinet Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0003 | A | 6105AK124-6264-ISPC-0003 | Q24050972-04-6264-I-SPC-0003 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Junction Box and Interface Cabinet Design | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0004 | A | 6105AK124-6264-ISPC-0004 | Q24050972-04-6264-I-SPC-0004 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Automated Isolation Valve Specification | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0005 | A | 6105AK124-6264-ISPC-0005 | Q24050972-04-6264-I-SPC-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Automated Isolation Valve Specification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0006 | A | 6105AK124-6264-ISPC-0006 | Q24050972-04-6264-I-SPC-0006 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Junction Box and Interface Cabinet Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0007 | A | 6105AK124-6264-ISPC-0007 | Q24050972-04-6264-I-SPC-0007 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Junction Box and Interface Cabinet Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0008 | A | 6105AK124-6264-ISPC-0008 | Q24050972-04-6264-I-SPC-0008 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Automated Isolation Valve Specification | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0009 | A | 6105AK124-6264-ISPC-0009 | Q24050972-04-6264-I-SPC-0009 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Instrument Communication Protocols Specification | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Instrument Communication Protocols Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0010 | A | 6105AK124-6264-ISPC-0010 | Q24050972-04-6264-I-SPC-0010 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1A | Junction Box and Interface Cabinet Design | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1A - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0011 | A | 6105AK124-6264-ISPC-0011 | Q24050972-04-6264-I-SPC-0011 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Automated Isolation Valve Specification | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0012 | A | 6105AK124-6264-ISPC-0012 | Q24050972-04-6264-I-SPC-0012 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Automated Isolation Valve Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0013 | A | 6105AK124-6264-ISPC-0013 | Q24050972-04-6264-I-SPC-0013 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Junction Box and Interface Cabinet Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0014 | A | 6105AK124-6264-ISPC-0014 | Q24050972-04-6264-I-SPC-0014 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Junction Box and Interface Cabinet Design | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0015 | A | 6105AK124-6264-ISPC-0015 | Q24050972-04-6264-I-SPC-0015 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Automated Isolation Valve Specification | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0016 | A | 6105AK124-6264-ISPC-0016 | Q24050972-04-6264-I-SPC-0016 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Automated Isolation Valve Specification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0017 | A | 6105AK124-6264-ISPC-0017 | Q24050972-04-6264-I-SPC-0017 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Junction Box and Interface Cabinet Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0018 | A | 6105AK124-6264-ISPC-0018 | Q24050972-04-6264-I-SPC-0018 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Junction Box and Interface Cabinet Design | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0019 | A | 6105AK124-6264-ISPC-0019 | Q24050972-04-6264-I-SPC-0019 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Automated Isolation Valve Specification | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0020 | A | 6105AK124-6264-ISPC-0020 | Q24050972-04-6264-I-SPC-0020 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Instrument Communication Protocols Specification | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Instrument Communication Protocols Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0021 | A | 6105AK124-6264-ISPC-0021 | Q24050972-04-6264-I-SPC-0021 |  | Bulk Diesel Storage 1 | Fuel Management System for Bulk Diesel Storage Yard 1B | Junction Box and Interface Cabinet Design | Bulk Diesel Storage 1 - Fuel Management System for Bulk Diesel Storage Yard 1B - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fuel Management System |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0022 | A | 6105AK124-6264-ISPC-0022 | Q24050972-04-6264-I-SPC-0022 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Automated Isolation Valve Specification | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Automated Isolation Valve Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0001 | A | 6105AK124-6264-MSPC-0001 | Q24050972-04-6264-M-SPC-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Material Selection and Verification Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0002 | A | 6105AK124-6264-MSPC-0002 | Q24050972-04-6264-M-SPC-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Gasket Schedule and Material Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0003 | A | 6105AK124-6264-MSPC-0003 | Q24050972-04-6264-M-SPC-0003 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Pump Design and Specifications | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Pump Design and Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0004 | A | 6105AK124-6264-MSPC-0004 | Q24050972-04-6264-M-SPC-0004 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Lifting and Crawl Beam Design Specification | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Lifting and Crawl Beam Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0005 | A | 6105AK124-6264-MSPC-0005 | Q24050972-04-6264-M-SPC-0005 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Material Selection and Verification Specification | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0006 | A | 6105AK124-6264-MSPC-0006 | Q24050972-04-6264-M-SPC-0006 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Rotating Equipment Alignment Specifications | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Rotating Equipment Alignment Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0007 | A | 6105AK124-6264-MSPC-0007 | Q24050972-04-6264-M-SPC-0007 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Drive Coupling and Connector Design Specification | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Drive Coupling and Connector Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0008 | A | 6105AK124-6264-MSPC-0008 | Q24050972-04-6264-M-SPC-0008 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Safety Barriers Design (Fencing, Handrails and Guards) | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Safety Barriers Design (Fencing, Handrails and Guards) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0009 | A | 6105AK124-6264-MSPC-0009 | Q24050972-04-6264-M-SPC-0009 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Material Selection and Verification Specification | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0010 | A | 6105AK124-6264-MSPC-0010 | Q24050972-04-6264-M-SPC-0010 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Manual Isolation Valve Design Specification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Manual Isolation Valve Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0011 | A | 6105AK124-6264-MSPC-0011 | Q24050972-04-6264-M-SPC-0011 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Material Selection and Verification Specification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0012 | A | 6105AK124-6264-MSPC-0012 | Q24050972-04-6264-M-SPC-0012 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Gasket Schedule and Material Specification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0013 | A | 6105AK124-6264-MSPC-0013 | Q24050972-04-6264-M-SPC-0013 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Pump Design and Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Pump Design and Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0014 | A | 6105AK124-6264-MSPC-0014 | Q24050972-04-6264-M-SPC-0014 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Rotating Equipment Alignment Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Rotating Equipment Alignment Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0015 | A | 6105AK124-6264-MSPC-0015 | Q24050972-04-6264-M-SPC-0015 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Drive Coupling and Connector Design Specification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Drive Coupling and Connector Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0016 | A | 6105AK124-6264-MSPC-0016 | Q24050972-04-6264-M-SPC-0016 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Material Selection and Verification Specification | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0017 | A | 6105AK124-6264-MSPC-0017 | Q24050972-04-6264-M-SPC-0017 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Gasket Schedule and Material Specification | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0018 | A | 6105AK124-6264-MSPC-0018 | Q24050972-04-6264-M-SPC-0018 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Material Selection and Verification Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0019 | A | 6105AK124-6264-MSPC-0019 | Q24050972-04-6264-M-SPC-0019 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Gasket Schedule and Material Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0020 | A | 6105AK124-6264-MSPC-0020 | Q24050972-04-6264-M-SPC-0020 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Pump Design and Specifications | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Pump Design and Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0021 | A | 6105AK124-6264-MSPC-0021 | Q24050972-04-6264-M-SPC-0021 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Lifting and Crawl Beam Design Specification | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Lifting and Crawl Beam Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0022 | A | 6105AK124-6264-MSPC-0022 | Q24050972-04-6264-M-SPC-0022 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Material Selection and Verification Specification | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0023 | A | 6105AK124-6264-MSPC-0023 | Q24050972-04-6264-M-SPC-0023 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Rotating Equipment Alignment Specifications | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Rotating Equipment Alignment Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0024 | A | 6105AK124-6264-MSPC-0024 | Q24050972-04-6264-M-SPC-0024 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Drive Coupling and Connector Design Specification | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Drive Coupling and Connector Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0025 | A | 6105AK124-6264-MSPC-0025 | Q24050972-04-6264-M-SPC-0025 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Safety Barriers Design (Fencing, Handrails and Guards) | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Safety Barriers Design (Fencing, Handrails and Guards) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0026 | A | 6105AK124-6264-MSPC-0026 | Q24050972-04-6264-M-SPC-0026 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Material Selection and Verification Specification | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0027 | A | 6105AK124-6264-MSPC-0027 | Q24050972-04-6264-M-SPC-0027 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Manual Isolation Valve Design Specification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Manual Isolation Valve Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0028 | A | 6105AK124-6264-MSPC-0028 | Q24050972-04-6264-M-SPC-0028 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Material Selection and Verification Specification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0029 | A | 6105AK124-6264-MSPC-0029 | Q24050972-04-6264-M-SPC-0029 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Gasket Schedule and Material Specification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0030 | A | 6105AK124-6264-MSPC-0030 | Q24050972-04-6264-M-SPC-0030 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Pump Design and Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Pump Design and Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0031 | A | 6105AK124-6264-MSPC-0031 | Q24050972-04-6264-M-SPC-0031 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Rotating Equipment Alignment Specifications | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Rotating Equipment Alignment Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0032 | A | 6105AK124-6264-MSPC-0032 | Q24050972-04-6264-M-SPC-0032 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Drive Coupling and Connector Design Specification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Drive Coupling and Connector Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0033 | A | 6105AK124-6264-MSPC-0033 | Q24050972-04-6264-M-SPC-0033 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Material Selection and Verification Specification | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | M | SPC | 0034 | A | 6105AK124-6264-MSPC-0034 | Q24050972-04-6264-M-SPC-0034 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Gasket Schedule and Material Specification | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | T | SPC | 0001 | A | 6105AK124-6264-TSPC-0001 | Q24050972-04-6264-T-SPC-0001 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Civil Design and Requirements | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | T | SPC | 0002 | A | 6105AK124-6264-TSPC-0002 | Q24050972-04-6264-T-SPC-0002 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Civil Design and Requirements | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | T | SPC | 0003 | A | 6105AK124-6264-TSPC-0003 | Q24050972-04-6264-T-SPC-0003 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Civil Design and Requirements | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | T | SPC | 0004 | A | 6105AK124-6264-TSPC-0004 | Q24050972-04-6264-T-SPC-0004 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | Civil Design and Requirements | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | T | SPC | 0005 | A | 6105AK124-6264-TSPC-0005 | Q24050972-04-6264-T-SPC-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Civil Design and Requirements | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | T | SPC | 0006 | A | 6105AK124-6264-TSPC-0006 | Q24050972-04-6264-T-SPC-0006 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Civil Design and Requirements | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | T | SPC | 0007 | A | 6105AK124-6264-TSPC-0007 | Q24050972-04-6264-T-SPC-0007 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Civil Design and Requirements | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | T | SPC | 0008 | A | 6105AK124-6264-TSPC-0008 | Q24050972-04-6264-T-SPC-0008 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Civil Design and Requirements | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | T | SPC | 0009 | A | 6105AK124-6264-TSPC-0009 | Q24050972-04-6264-T-SPC-0009 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | Civil Design and Requirements | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | T | SPC | 0010 | A | 6105AK124-6264-TSPC-0010 | Q24050972-04-6264-T-SPC-0010 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Civil Design and Requirements | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPL | 0001 | A | 6105AK124-6264-CSPL-0001 | Q24050972-04-6264-C-SPL-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Pipe Fabrication and Field Installation Inspection | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Pipe Fabrication and Field Installation Inspection |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | C | SPL | 0002 | A | 6105AK124-6264-CSPL-0002 | Q24050972-04-6264-C-SPL-0002 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Pipe Fabrication and Field Installation Inspection | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Pipe Fabrication and Field Installation Inspection |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPL | 0003 | A | 6105AK124-6264-CSPL-0003 | Q24050972-04-6264-C-SPL-0003 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Pipe Fabrication and Field Installation Inspection | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Pipe Fabrication and Field Installation Inspection |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | C | SPL | 0004 | A | 6105AK124-6264-CSPL-0004 | Q24050972-04-6264-C-SPL-0004 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Pipe Fabrication and Field Installation Inspection | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Pipe Fabrication and Field Installation Inspection |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | C | SPL | 0005 | A | 6105AK124-6264-CSPL-0005 | Q24050972-04-6264-C-SPL-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Pipe Fabrication and Field Installation Inspection | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Pipe Fabrication and Field Installation Inspection |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SPL | 0006 | A | 6105AK124-6264-CSPL-0006 | Q24050972-04-6264-C-SPL-0006 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Pipe Fabrication and Field Installation Inspection | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Pipe Fabrication and Field Installation Inspection |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | C | SSD | 0001 | A | 6105AK124-6264-CSSD-0001 | Q24050972-04-6264-C-SSD-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Steel Support Structures Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | C | SSD | 0002 | A | 6105AK124-6264-CSSD-0002 | Q24050972-04-6264-C-SSD-0002 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Steel Support Structures Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | SSD | 0003 | A | 6105AK124-6264-CSSD-0003 | Q24050972-04-6264-C-SSD-0003 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Steel Support Structures Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | C | SSD | 0004 | A | 6105AK124-6264-CSSD-0004 | Q24050972-04-6264-C-SSD-0004 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Steel Support Structures Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0001 | A | 6105AK124-6264-CSTD-0001 | Q24050972-04-6264-C-STD-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Underground Pipe Route and Cable Bedding Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0002 | A | 6105AK124-6264-CSTD-0002 | Q24050972-04-6264-C-STD-0002 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Bund-wall Requirements and Design | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0003 | A | 6105AK124-6264-CSTD-0003 | Q24050972-04-6264-C-STD-0003 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Fire Protection System Design (Civil Works) | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0004 | A | 6105AK124-6264-CSTD-0004 | Q24050972-04-6264-C-STD-0004 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Civil Construction Requirements | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0005 | A | 6105AK124-6264-CSTD-0005 | Q24050972-04-6264-C-STD-0005 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Underground Pipe Route and Cable Bedding Design | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0006 | A | 6105AK124-6264-CSTD-0006 | Q24050972-04-6264-C-STD-0006 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Bund-wall Requirements and Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0007 | A | 6105AK124-6264-CSTD-0007 | Q24050972-04-6264-C-STD-0007 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Fire Protection System Design (Civil Works) | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0008 | A | 6105AK124-6264-CSTD-0008 | Q24050972-04-6264-C-STD-0008 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Civil Construction Requirements | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0009 | A | 6105AK124-6264-CSTD-0009 | Q24050972-04-6264-C-STD-0009 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Underground Pipe Route and Cable Bedding Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0010 | A | 6105AK124-6264-CSTD-0010 | Q24050972-04-6264-C-STD-0010 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Civil Construction Requirements | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0011 | A | 6105AK124-6264-CSTD-0011 | Q24050972-04-6264-C-STD-0011 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1A | Roofing and Elevated Platforms Design | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1A - Roofing and Elevated Platforms Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0012 | A | 6105AK124-6264-CSTD-0012 | Q24050972-04-6264-C-STD-0012 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | Civil Construction Requirements | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0013 | A | 6105AK124-6264-CSTD-0013 | Q24050972-04-6264-C-STD-0013 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Fire Protection System Design (Civil Works) | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0014 | A | 6105AK124-6264-CSTD-0014 | Q24050972-04-6264-C-STD-0014 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Civil Construction Requirements | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0015 | A | 6105AK124-6264-CSTD-0015 | Q24050972-04-6264-C-STD-0015 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Underground Pipe Route and Cable Bedding Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0016 | A | 6105AK124-6264-CSTD-0016 | Q24050972-04-6264-C-STD-0016 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Underground Pipe Route and Cable Bedding Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0017 | A | 6105AK124-6264-CSTD-0017 | Q24050972-04-6264-C-STD-0017 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Bund-wall Requirements and Design | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0018 | A | 6105AK124-6264-CSTD-0018 | Q24050972-04-6264-C-STD-0018 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Fire Protection System Design (Civil Works) | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0019 | A | 6105AK124-6264-CSTD-0019 | Q24050972-04-6264-C-STD-0019 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Civil Construction Requirements | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0020 | A | 6105AK124-6264-CSTD-0020 | Q24050972-04-6264-C-STD-0020 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Underground Pipe Route and Cable Bedding Design | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0021 | A | 6105AK124-6264-CSTD-0021 | Q24050972-04-6264-C-STD-0021 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Bund-wall Requirements and Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0022 | A | 6105AK124-6264-CSTD-0022 | Q24050972-04-6264-C-STD-0022 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Fire Protection System Design (Civil Works) | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0023 | A | 6105AK124-6264-CSTD-0023 | Q24050972-04-6264-C-STD-0023 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Civil Construction Requirements | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0024 | A | 6105AK124-6264-CSTD-0024 | Q24050972-04-6264-C-STD-0024 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Underground Pipe Route and Cable Bedding Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0025 | A | 6105AK124-6264-CSTD-0025 | Q24050972-04-6264-C-STD-0025 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Civil Construction Requirements | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0026 | A | 6105AK124-6264-CSTD-0026 | Q24050972-04-6264-C-STD-0026 |  | Bulk Diesel Storage 1 | Access Staircase & Platforms for Bulk Diesel Storage Yard 1B | Roofing and Elevated Platforms Design | Bulk Diesel Storage 1 - Access Staircase & Platforms for Bulk Diesel Storage Yard 1B - Roofing and Elevated Platforms Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Access Staircase & Platforms |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0027 | A | 6105AK124-6264-CSTD-0027 | Q24050972-04-6264-C-STD-0027 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | Civil Construction Requirements | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0028 | A | 6105AK124-6264-CSTD-0028 | Q24050972-04-6264-C-STD-0028 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Fire Protection System Design (Civil Works) | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0029 | A | 6105AK124-6264-CSTD-0029 | Q24050972-04-6264-C-STD-0029 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Civil Construction Requirements | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | C | STD | 0030 | A | 6105AK124-6264-CSTD-0030 | Q24050972-04-6264-C-STD-0030 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Underground Pipe Route and Cable Bedding Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0001 | A | 6105AK124-6264-ESTD-0001 | Q24050972-04-6264-E-STD-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Earth Map and Bonding Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0002 | A | 6105AK124-6264-ESTD-0002 | Q24050972-04-6264-E-STD-0002 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Electrical Equipment Installation Requirements | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0003 | A | 6105AK124-6264-ESTD-0003 | Q24050972-04-6264-E-STD-0003 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Hazardous Area Classification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Hazardous Area Classification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0004 | A | 6105AK124-6264-ESTD-0004 | Q24050972-04-6264-E-STD-0004 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Thermal Management and Fire Prevention Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0005 | A | 6105AK124-6264-ESTD-0005 | Q24050972-04-6264-E-STD-0005 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Earth Map and Bonding Design | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0006 | A | 6105AK124-6264-ESTD-0006 | Q24050972-04-6264-E-STD-0006 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Electrical Design Standards | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0007 | A | 6105AK124-6264-ESTD-0007 | Q24050972-04-6264-E-STD-0007 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Electrical Equipment Installation Requirements | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0008 | A | 6105AK124-6264-ESTD-0008 | Q24050972-04-6264-E-STD-0008 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Hazardous Area Classification | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Hazardous Area Classification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0009 | A | 6105AK124-6264-ESTD-0009 | Q24050972-04-6264-E-STD-0009 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Thermal Management and Fire Prevention Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0010 | A | 6105AK124-6264-ESTD-0010 | Q24050972-04-6264-E-STD-0010 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Earth Map and Bonding Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0011 | A | 6105AK124-6264-ESTD-0011 | Q24050972-04-6264-E-STD-0011 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Electrical Equipment Installation Requirements | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0012 | A | 6105AK124-6264-ESTD-0012 | Q24050972-04-6264-E-STD-0012 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Hazardous Area Classification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Hazardous Area Classification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0013 | A | 6105AK124-6264-ESTD-0013 | Q24050972-04-6264-E-STD-0013 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Electrical Design Standards | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0014 | A | 6105AK124-6264-ESTD-0014 | Q24050972-04-6264-E-STD-0014 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Earth Map and Bonding Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0015 | A | 6105AK124-6264-ESTD-0015 | Q24050972-04-6264-E-STD-0015 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Electrical Equipment Installation Requirements | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0016 | A | 6105AK124-6264-ESTD-0016 | Q24050972-04-6264-E-STD-0016 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Hazardous Area Classification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Hazardous Area Classification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0017 | A | 6105AK124-6264-ESTD-0017 | Q24050972-04-6264-E-STD-0017 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Thermal Management and Fire Prevention Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0018 | A | 6105AK124-6264-ESTD-0018 | Q24050972-04-6264-E-STD-0018 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Earth Map and Bonding Design | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0019 | A | 6105AK124-6264-ESTD-0019 | Q24050972-04-6264-E-STD-0019 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Electrical Design Standards | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0020 | A | 6105AK124-6264-ESTD-0020 | Q24050972-04-6264-E-STD-0020 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Electrical Equipment Installation Requirements | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0021 | A | 6105AK124-6264-ESTD-0021 | Q24050972-04-6264-E-STD-0021 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Hazardous Area Classification | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Hazardous Area Classification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0022 | A | 6105AK124-6264-ESTD-0022 | Q24050972-04-6264-E-STD-0022 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Thermal Management and Fire Prevention Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0023 | A | 6105AK124-6264-ESTD-0023 | Q24050972-04-6264-E-STD-0023 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Earth Map and Bonding Design | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0024 | A | 6105AK124-6264-ESTD-0024 | Q24050972-04-6264-E-STD-0024 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Electrical Equipment Installation Requirements | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0025 | A | 6105AK124-6264-ESTD-0025 | Q24050972-04-6264-E-STD-0025 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Hazardous Area Classification | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Hazardous Area Classification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | E | STD | 0026 | A | 6105AK124-6264-ESTD-0026 | Q24050972-04-6264-E-STD-0026 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Electrical Design Standards | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | STD | 0001 | A | 6105AK124-6264-ISTD-0001 | Q24050972-04-6264-I-STD-0001 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Instrumentation Installation Requirements | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Instrumentation Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | STD | 0002 | A | 6105AK124-6264-ISTD-0002 | Q24050972-04-6264-I-STD-0002 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1A | Instrument Design Standards | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1A - Instrument Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | STD | 0003 | A | 6105AK124-6264-ISTD-0003 | Q24050972-04-6264-I-STD-0003 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Instrumentation Installation Requirements | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Instrumentation Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | STD | 0004 | A | 6105AK124-6264-ISTD-0004 | Q24050972-04-6264-I-STD-0004 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Instrument Design Standards | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Instrument Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | STD | 0005 | A | 6105AK124-6264-ISTD-0005 | Q24050972-04-6264-I-STD-0005 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Instrumentation Installation Requirements | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Instrumentation Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | STD | 0006 | A | 6105AK124-6264-ISTD-0006 | Q24050972-04-6264-I-STD-0006 |  | Bulk Diesel Storage 1 | Fire Protection System for Bulk Diesel Storage Yard 1B | Instrument Design Standards | Bulk Diesel Storage 1 - Fire Protection System for Bulk Diesel Storage Yard 1B - Instrument Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | STD | 0007 | A | 6105AK124-6264-ISTD-0007 | Q24050972-04-6264-I-STD-0007 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Instrumentation Installation Requirements | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Instrumentation Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | I | STD | 0008 | A | 6105AK124-6264-ISTD-0008 | Q24050972-04-6264-I-STD-0008 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Instrument Design Standards | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Instrument Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Protection System |  |  |  | Pending
6105A | K124 | 6264 | M | STD | 0001 | A | 6105AK124-6264-MSTD-0001 | Q24050972-04-6264-M-STD-0001 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Diesel Fuel Handling and Storage Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Diesel Fuel Handling and Storage Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | STD | 0002 | A | 6105AK124-6264-MSTD-0002 | Q24050972-04-6264-M-STD-0002 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1A | Diesel Fuel Handling and Storage Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1A - Diesel Fuel Handling and Storage Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | STD | 0003 | A | 6105AK124-6264-MSTD-0003 | Q24050972-04-6264-M-STD-0003 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A | Diesel Fuel Handling and Storage Design | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1A - Diesel Fuel Handling and Storage Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | M | STD | 0004 | A | 6105AK124-6264-MSTD-0004 | Q24050972-04-6264-M-STD-0004 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Diesel Fuel Handling and Storage Design | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Diesel Fuel Handling and Storage Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip |  |  |  | Pending
6105A | K124 | 6264 | M | STD | 0005 | A | 6105AK124-6264-MSTD-0005 | Q24050972-04-6264-M-STD-0005 |  | Bulk Diesel Storage 1 | Collection Sump from Bunds for Bulk Diesel Storage Yard 1B | Diesel Fuel Handling and Storage Design | Bulk Diesel Storage 1 - Collection Sump from Bunds for Bulk Diesel Storage Yard 1B - Diesel Fuel Handling and Storage Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6264 | M | STD | 0006 | A | 6105AK124-6264-MSTD-0006 | Q24050972-04-6264-M-STD-0006 |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B | Diesel Fuel Handling and Storage Design | Bulk Diesel Storage 1 - Auto ESD Shut-off Valves for Bulk Diesel Storage Yard 1B - Diesel Fuel Handling and Storage Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Auto ESD Shut-off Valves |  |  |  | Pending
6105A | K124 | 6264 | W | TRP | 0001 | A | 6105AK124-6264-WTRP-0001 | Q24050972-04-6264-W-TRP-0001 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1A | Soil Resistivity Testing Report | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1A - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | W | TRP | 0002 | A | 6105AK124-6264-WTRP-0002 | Q24050972-04-6264-W-TRP-0002 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1A | Soil Classification and Nomination Deliverables | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1A - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | W | TRP | 0003 | A | 6105AK124-6264-WTRP-0003 | Q24050972-04-6264-W-TRP-0003 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1A | Soil Classification and Nomination Deliverables | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1A - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6264 | W | TRP | 0004 | A | 6105AK124-6264-WTRP-0004 | Q24050972-04-6264-W-TRP-0004 |  | Bulk Diesel Storage 1 | Earthing System for Bulk Diesel Storage Yard 1B | Soil Resistivity Testing Report | Bulk Diesel Storage 1 - Earthing System for Bulk Diesel Storage Yard 1B - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Earthing System |  |  |  | Pending
6105A | K124 | 6264 | W | TRP | 0005 | A | 6105AK124-6264-WTRP-0005 | Q24050972-04-6264-W-TRP-0005 |  | Bulk Diesel Storage 1 | Bund wall System for Bulk Diesel Storage Yard 1B | Soil Classification and Nomination Deliverables | Bulk Diesel Storage 1 - Bund wall System for Bulk Diesel Storage Yard 1B - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Bund wall System |  |  |  | Pending
6105A | K124 | 6264 | W | TRP | 0006 | A | 6105AK124-6264-WTRP-0006 | Q24050972-04-6264-W-TRP-0006 |  | Bulk Diesel Storage 1 | Fire Wall Protection System for Bulk Diesel Storage Yard 1B | Soil Classification and Nomination Deliverables | Bulk Diesel Storage 1 - Fire Wall Protection System for Bulk Diesel Storage Yard 1B - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Wall Protection System |  |  |  | Pending
6105A | K124 | 6265 | E | CAL | 0001 | A | 6105AK124-6265-ECAL-0001 | Q24050972-04-6265-E-CAL-0001 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Cable and Conductor Sizing (incl Volt Drop Calcs) | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | E | CAL | 0002 | A | 6105AK124-6265-ECAL-0002 | Q24050972-04-6265-E-CAL-0002 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Impedance and Burn-off Calculations | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | E | CAL | 0003 | A | 6105AK124-6265-ECAL-0003 | Q24050972-04-6265-E-CAL-0003 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Cable and Conductor Sizing (incl Volt Drop Calcs) | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | E | CAL | 0004 | A | 6105AK124-6265-ECAL-0004 | Q24050972-04-6265-E-CAL-0004 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Impedance and Burn-off Calculations | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | E | DIA | 0001 | A | 6105AK124-6265-EDIA-0001 | Q24050972-04-6265-E-DIA-0001 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Electrical Circuit Diagrams (Schematics) | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | E | DIA | 0002 | A | 6105AK124-6265-EDIA-0002 | Q24050972-04-6265-E-DIA-0002 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Cable Block Diagrams and Schedules | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | E | DIA | 0003 | A | 6105AK124-6265-EDIA-0003 | Q24050972-04-6265-E-DIA-0003 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | E/I Termination Schedule | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | E | DIA | 0004 | A | 6105AK124-6265-EDIA-0004 | Q24050972-04-6265-E-DIA-0004 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Electrical Circuit Diagrams (Schematics) | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | E | DIA | 0005 | A | 6105AK124-6265-EDIA-0005 | Q24050972-04-6265-E-DIA-0005 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Cable Block Diagrams and Schedules | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | E | DIA | 0006 | A | 6105AK124-6265-EDIA-0006 | Q24050972-04-6265-E-DIA-0006 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | E/I Termination Schedule | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | F | DIA | 0001 | A | 6105AK124-6265-FDIA-0001 | Q24050972-04-6265-F-DIA-0001 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Interface Panel and I/O Schematics | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | F | DIA | 0002 | A | 6105AK124-6265-FDIA-0002 | Q24050972-04-6265-F-DIA-0002 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Interface Panel and I/O Schematics | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | E | DST | 0001 | A | 6105AK124-6265-EDST-0001 | Q24050972-04-6265-E-DST-0001 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Equipment Register and Technical Specifications | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | E | DST | 0002 | A | 6105AK124-6265-EDST-0002 | Q24050972-04-6265-E-DST-0002 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Equipment Register and Technical Specifications | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | E | DST | 0003 | A | 6105AK124-6265-EDST-0003 | Q24050972-04-6265-E-DST-0003 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Equipment Register and Technical Specifications | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | E | DST | 0004 | A | 6105AK124-6265-EDST-0004 | Q24050972-04-6265-E-DST-0004 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Equipment Register and Technical Specifications | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | W | ELE | 0001 | A | 6105AK124-6265-WELE-0001 | Q24050972-04-6265-W-ELE-0001 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Bulk Earth Works Design and Report | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | W | ELE | 0002 | A | 6105AK124-6265-WELE-0002 | Q24050972-04-6265-W-ELE-0002 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Bulk Earth Works Design and Report | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | FND | 0001 | A | 6105AK124-6265-CFND-0001 | Q24050972-04-6265-C-FND-0001 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Civil Foundation Design | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | FND | 0002 | A | 6105AK124-6265-CFND-0002 | Q24050972-04-6265-C-FND-0002 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Plinth Design and Layout | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | FND | 0003 | A | 6105AK124-6265-CFND-0003 | Q24050972-04-6265-C-FND-0003 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Civil Foundation Design | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | FND | 0004 | A | 6105AK124-6265-CFND-0004 | Q24050972-04-6265-C-FND-0004 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Plinth Design and Layout | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Plinth Design and Layout |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | GAD | 0001 | A | 6105AK124-6265-CGAD-0001 | Q24050972-04-6265-C-GAD-0001 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Buildings and Structures GA | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | GAD | 0002 | A | 6105AK124-6265-CGAD-0002 | Q24050972-04-6265-C-GAD-0002 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Terrace Equipment GA | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | GAD | 0003 | A | 6105AK124-6265-CGAD-0003 | Q24050972-04-6265-C-GAD-0003 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Stormwater and Effluent System Design | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | GAD | 0004 | A | 6105AK124-6265-CGAD-0004 | Q24050972-04-6265-C-GAD-0004 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Lighting Design and Layout GA | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | GAD | 0005 | A | 6105AK124-6265-CGAD-0005 | Q24050972-04-6265-C-GAD-0005 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Buildings and Structures GA | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | GAD | 0006 | A | 6105AK124-6265-CGAD-0006 | Q24050972-04-6265-C-GAD-0006 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Terrace Equipment GA | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | GAD | 0007 | A | 6105AK124-6265-CGAD-0007 | Q24050972-04-6265-C-GAD-0007 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Stormwater and Effluent System Design | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | GAD | 0008 | A | 6105AK124-6265-CGAD-0008 | Q24050972-04-6265-C-GAD-0008 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Lighting Design and Layout GA | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | E | LAY | 0001 | A | 6105AK124-6265-ELAY-0001 | Q24050972-04-6265-E-LAY-0001 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Control Room Power and Earthing Design | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | E | LAY | 0002 | A | 6105AK124-6265-ELAY-0002 | Q24050972-04-6265-E-LAY-0002 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Control Room Power and Earthing Design | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | W | LAY | 0001 | A | 6105AK124-6265-WLAY-0001 | Q24050972-04-6265-W-LAY-0001 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Drainage, Run-off and Impoundment Design | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | W | LAY | 0002 | A | 6105AK124-6265-WLAY-0002 | Q24050972-04-6265-W-LAY-0002 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Drainage, Run-off and Impoundment Design | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | MDL | 0001 | A | 6105AK124-6265-CMDL-0001 | Q24050972-04-6265-C-MDL-0001 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | 3D Designs and Drawings | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | MDL | 0002 | A | 6105AK124-6265-CMDL-0002 | Q24050972-04-6265-C-MDL-0002 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | 3D Designs and Drawings | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | MDL | 0003 | A | 6105AK124-6265-CMDL-0003 | Q24050972-04-6265-C-MDL-0003 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | 3D Designs and Drawings | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | MDL | 0004 | A | 6105AK124-6265-CMDL-0004 | Q24050972-04-6265-C-MDL-0004 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | 3D Designs and Drawings | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | PLN | 0001 | A | 6105AK124-6265-CPLN-0001 | Q24050972-04-6265-C-PLN-0001 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Civil Works Execution Plan | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | PLN | 0002 | A | 6105AK124-6265-CPLN-0002 | Q24050972-04-6265-C-PLN-0002 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Civil Works Execution Plan | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | PLN | 0003 | A | 6105AK124-6265-CPLN-0003 | Q24050972-04-6265-C-PLN-0003 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Civil Works Execution Plan | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | PLN | 0004 | A | 6105AK124-6265-CPLN-0004 | Q24050972-04-6265-C-PLN-0004 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Civil Works Execution Plan | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | SEC | 0001 | A | 6105AK124-6265-CSEC-0001 | Q24050972-04-6265-C-SEC-0001 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Corrosion Prevention and Protection Design | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | SEC | 0002 | A | 6105AK124-6265-CSEC-0002 | Q24050972-04-6265-C-SEC-0002 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Structural Earthing and Bonding Design | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | SEC | 0003 | A | 6105AK124-6265-CSEC-0003 | Q24050972-04-6265-C-SEC-0003 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Corrosion Prevention and Protection Design | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | SEC | 0004 | A | 6105AK124-6265-CSEC-0004 | Q24050972-04-6265-C-SEC-0004 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Structural Earthing and Bonding Design | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | SPC | 0001 | A | 6105AK124-6265-CSPC-0001 | Q24050972-04-6265-C-SPC-0001 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Civil Design Requirements | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | SPC | 0002 | A | 6105AK124-6265-CSPC-0002 | Q24050972-04-6265-C-SPC-0002 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Excavation, Trenching and Compacting Design | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | SPC | 0003 | A | 6105AK124-6265-CSPC-0003 | Q24050972-04-6265-C-SPC-0003 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Concrete Construction Material Specifications | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | SPC | 0004 | A | 6105AK124-6265-CSPC-0004 | Q24050972-04-6265-C-SPC-0004 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Concrete Construction Material Specifications | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | SPC | 0005 | A | 6105AK124-6265-CSPC-0005 | Q24050972-04-6265-C-SPC-0005 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Excavation, Trenching and Compacting Design | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | SPC | 0006 | A | 6105AK124-6265-CSPC-0006 | Q24050972-04-6265-C-SPC-0006 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Civil Design Requirements | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | SPC | 0007 | A | 6105AK124-6265-CSPC-0007 | Q24050972-04-6265-C-SPC-0007 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Excavation, Trenching and Compacting Design | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | SPC | 0008 | A | 6105AK124-6265-CSPC-0008 | Q24050972-04-6265-C-SPC-0008 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Concrete Construction Material Specifications | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | SPC | 0009 | A | 6105AK124-6265-CSPC-0009 | Q24050972-04-6265-C-SPC-0009 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Concrete Construction Material Specifications | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | SPC | 0010 | A | 6105AK124-6265-CSPC-0010 | Q24050972-04-6265-C-SPC-0010 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Excavation, Trenching and Compacting Design | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | I | SPC | 0001 | A | 6105AK124-6265-ISPC-0001 | Q24050972-04-6265-I-SPC-0001 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Junction Box and Interface Cabinet Design | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | I | SPC | 0002 | A | 6105AK124-6265-ISPC-0002 | Q24050972-04-6265-I-SPC-0002 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Junction Box and Interface Cabinet Design | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | T | SPC | 0001 | A | 6105AK124-6265-TSPC-0001 | Q24050972-04-6265-T-SPC-0001 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Civil Design and Requirements | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | T | SPC | 0002 | A | 6105AK124-6265-TSPC-0002 | Q24050972-04-6265-T-SPC-0002 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Civil Design and Requirements | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | T | SPC | 0003 | A | 6105AK124-6265-TSPC-0003 | Q24050972-04-6265-T-SPC-0003 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Civil Design and Requirements | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | T | SPC | 0004 | A | 6105AK124-6265-TSPC-0004 | Q24050972-04-6265-T-SPC-0004 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Civil Design and Requirements | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | STD | 0001 | A | 6105AK124-6265-CSTD-0001 | Q24050972-04-6265-C-STD-0001 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Bund-wall Requirements and Design | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | STD | 0002 | A | 6105AK124-6265-CSTD-0002 | Q24050972-04-6265-C-STD-0002 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Fire Protection System Design (Civil Works) | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | STD | 0003 | A | 6105AK124-6265-CSTD-0003 | Q24050972-04-6265-C-STD-0003 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Civil Construction Requirements | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | STD | 0004 | A | 6105AK124-6265-CSTD-0004 | Q24050972-04-6265-C-STD-0004 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Underground Pipe Route and Cable Bedding Design | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | C | STD | 0005 | A | 6105AK124-6265-CSTD-0005 | Q24050972-04-6265-C-STD-0005 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Bund-wall Requirements and Design | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | STD | 0006 | A | 6105AK124-6265-CSTD-0006 | Q24050972-04-6265-C-STD-0006 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Fire Protection System Design (Civil Works) | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | STD | 0007 | A | 6105AK124-6265-CSTD-0007 | Q24050972-04-6265-C-STD-0007 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Civil Construction Requirements | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | C | STD | 0008 | A | 6105AK124-6265-CSTD-0008 | Q24050972-04-6265-C-STD-0008 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Underground Pipe Route and Cable Bedding Design | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | E | STD | 0001 | A | 6105AK124-6265-ESTD-0001 | Q24050972-04-6265-E-STD-0001 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Earth Map and Bonding Design | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | E | STD | 0002 | A | 6105AK124-6265-ESTD-0002 | Q24050972-04-6265-E-STD-0002 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Electrical Design Standards | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | E | STD | 0003 | A | 6105AK124-6265-ESTD-0003 | Q24050972-04-6265-E-STD-0003 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Earth Map and Bonding Design | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | E | STD | 0004 | A | 6105AK124-6265-ESTD-0004 | Q24050972-04-6265-E-STD-0004 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Electrical Design Standards | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | W | TRP | 0001 | A | 6105AK124-6265-WTRP-0001 | Q24050972-04-6265-W-TRP-0001 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1A | Soil Classification and Nomination Deliverables | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1A - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | W | TRP | 0002 | A | 6105AK124-6265-WTRP-0002 | Q24050972-04-6265-W-TRP-0002 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1A | Soil Resistivity Testing Report | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1A - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1A |  |  |  | Pending
6105A | K124 | 6265 | W | TRP | 0003 | A | 6105AK124-6265-WTRP-0003 | Q24050972-04-6265-W-TRP-0003 |  | Truck Diesel Unloading and Power Station 1 | Drainage and Collection System for Diesel Offloading Station 1B | Soil Classification and Nomination Deliverables | Truck Diesel Unloading and Power Station 1 - Drainage and Collection System for Diesel Offloading Station 1B - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Drainage and Collection System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6265 | W | TRP | 0004 | A | 6105AK124-6265-WTRP-0004 | Q24050972-04-6265-W-TRP-0004 |  | Truck Diesel Unloading and Power Station 1 | Earthing System for Diesel Offloading Station 1B | Soil Resistivity Testing Report | Truck Diesel Unloading and Power Station 1 - Earthing System for Diesel Offloading Station 1B - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Earthing System | Diesel Offloading Station 1B |  |  |  | Pending
6105A | K124 | 6286 | E | CAL | 0001 | A | 6105AK124-6286-ECAL-0001 | Q24050972-04-6286-E-CAL-0001 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Conductor Sag and Tension Plan | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | E | CAL | 0002 | A | 6105AK124-6286-ECAL-0002 | Q24050972-04-6286-E-CAL-0002 |  | Primary Crushing | Earthing System for Mining Sub Station | Cable and Conductor Sizing (incl Volt Drop Calcs) | Primary Crushing - Earthing System for Mining Sub Station - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | E | CAL | 0003 | A | 6105AK124-6286-ECAL-0003 | Q24050972-04-6286-E-CAL-0003 |  | Primary Crushing | Earthing System for Mining Sub Station | Impedance and Burn-off Calculations | Primary Crushing - Earthing System for Mining Sub Station - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | E | CAL | 0004 | A | 6105AK124-6286-ECAL-0004 | Q24050972-04-6286-E-CAL-0004 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Cable and Conductor Sizing (incl Volt Drop Calcs) | Primary Crushing - Small Power and Lighting for Mining Sub Station - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | CAL | 0005 | A | 6105AK124-6286-ECAL-0005 | Q24050972-04-6286-E-CAL-0005 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Conductor Sag and Tension Plan | Primary Crushing - Small Power and Lighting for Mining Sub Station - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | CAL | 0006 | A | 6105AK124-6286-ECAL-0006 | Q24050972-04-6286-E-CAL-0006 |  | Primary Crushing | Lightning Protection Mining Sub Station | Impedance and Burn-off Calculations | Primary Crushing - Lightning Protection Mining Sub Station - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | M | CAL | 0001 | A | 6105AK124-6286-MCAL-0001 | Q24050972-04-6286-M-CAL-0001 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Vessel and Structure Design with Stress Analysis Calcs | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Sub Station | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | B | CAL | 0001 | A | 6105AK124-6286-BCAL-0001 | Q24050972-04-6286-B-CAL-0001 |  | Primary Crushing | Mining Substation 33/11 kV Project Package | Design Criteria / Basis of Design | Primary Crushing - Mining Substation 33/11 kV Project Package - Design Criteria / Basis of Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Sub Station | 33/11 kV Project Package |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0004 | A | 6105AK124-6286-EDIA-0004 | Q24050972-04-6286-E-DIA-0004 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Cable Block Diagrams and Schedules | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0005 | A | 6105AK124-6286-EDIA-0005 | Q24050972-04-6286-E-DIA-0005 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | E/I Termination Schedule | Primary Crushing - Cable Racks and Trays for Mining Sub Station - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0006 | A | 6105AK124-6286-EDIA-0006 | Q24050972-04-6286-E-DIA-0006 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Cable Block Diagrams and Schedules | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0007 | A | 6105AK124-6286-EDIA-0007 | Q24050972-04-6286-E-DIA-0007 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | E/I Termination Schedule | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0008 | A | 6105AK124-6286-EDIA-0008 | Q24050972-04-6286-E-DIA-0008 |  | Primary Crushing | Earthing System for Mining Sub Station | Electrical Circuit Diagrams (Schematics) | Primary Crushing - Earthing System for Mining Sub Station - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0009 | A | 6105AK124-6286-EDIA-0009 | Q24050972-04-6286-E-DIA-0009 |  | Primary Crushing | Earthing System for Mining Sub Station | Cable Block Diagrams and Schedules | Primary Crushing - Earthing System for Mining Sub Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0010 | A | 6105AK124-6286-EDIA-0010 | Q24050972-04-6286-E-DIA-0010 |  | Primary Crushing | Earthing System for Mining Sub Station | E/I Termination Schedule | Primary Crushing - Earthing System for Mining Sub Station - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0011 | A | 6105AK124-6286-EDIA-0011 | Q24050972-04-6286-E-DIA-0011 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Cable Block Diagrams and Schedules | Primary Crushing - Small Power and Lighting for Mining Sub Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0012 | A | 6105AK124-6286-EDIA-0012 | Q24050972-04-6286-E-DIA-0012 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Electrical Block Diagram | Primary Crushing - Small Power and Lighting for Mining Sub Station - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0013 | A | 6105AK124-6286-EDIA-0013 | Q24050972-04-6286-E-DIA-0013 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Electrical Circuit Diagrams (Schematics) | Primary Crushing - Small Power and Lighting for Mining Sub Station - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0014 | A | 6105AK124-6286-EDIA-0014 | Q24050972-04-6286-E-DIA-0014 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | E/I Termination Schedule | Primary Crushing - Small Power and Lighting for Mining Sub Station - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0015 | A | 6105AK124-6286-EDIA-0015 | Q24050972-04-6286-E-DIA-0015 |  | Primary Crushing | Lightning Protection Mining Sub Station | Cable Block Diagrams and Schedules | Primary Crushing - Lightning Protection Mining Sub Station - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | E | DIA | 0016 | A | 6105AK124-6286-EDIA-0016 | Q24050972-04-6286-E-DIA-0016 |  | Primary Crushing | Lightning Protection Mining Sub Station | Electrical Circuit Diagrams (Schematics) | Primary Crushing - Lightning Protection Mining Sub Station - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | F | DIA | 0001 | A | 6105AK124-6286-FDIA-0001 | Q24050972-04-6286-F-DIA-0001 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Control Network Architecture Design | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | F | DIA | 0002 | A | 6105AK124-6286-FDIA-0002 | Q24050972-04-6286-F-DIA-0002 |  | Primary Crushing | Earthing System for Mining Sub Station | Interface Panel and I/O Schematics | Primary Crushing - Earthing System for Mining Sub Station - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | I | DIA | 0001 | A | 6105AK124-6286-IDIA-0001 | Q24050972-04-6286-I-DIA-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Smoke and Fire Detection System Design | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Smoke and Fire Detection System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | I | DIA | 0002 | A | 6105AK124-6286-IDIA-0002 | Q24050972-04-6286-I-DIA-0002 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | Closed Circuit Television (CCTV) Design | Primary Crushing - Perimeter Fencing for Mining Sub Station - Closed Circuit Television (CCTV) Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | E | DST | 0008 | A | 6105AK124-6286-EDST-0008 | Q24050972-04-6286-E-DST-0008 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Equipment Register and Technical Specifications | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | E | DST | 0009 | A | 6105AK124-6286-EDST-0009 | Q24050972-04-6286-E-DST-0009 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Equipment Register and Technical Specifications | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | E | DST | 0010 | A | 6105AK124-6286-EDST-0010 | Q24050972-04-6286-E-DST-0010 |  | Primary Crushing | Earthing System for Mining Sub Station | Equipment Register and Technical Specifications | Primary Crushing - Earthing System for Mining Sub Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | E | DST | 0011 | A | 6105AK124-6286-EDST-0011 | Q24050972-04-6286-E-DST-0011 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Equipment Register and Technical Specifications | Primary Crushing - Small Power and Lighting for Mining Sub Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | DST | 0012 | A | 6105AK124-6286-EDST-0012 | Q24050972-04-6286-E-DST-0012 |  | Primary Crushing | Lightning Protection Mining Sub Station | Equipment Register and Technical Specifications | Primary Crushing - Lightning Protection Mining Sub Station - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | W | ELE | 0001 | A | 6105AK124-6286-WELE-0001 | Q24050972-04-6286-W-ELE-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Bulk Earth Works Design and Report | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | W | ELE | 0002 | A | 6105AK124-6286-WELE-0002 | Q24050972-04-6286-W-ELE-0002 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Bulk Earth Works Design and Report | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | W | ELE | 0003 | A | 6105AK124-6286-WELE-0003 | Q24050972-04-6286-W-ELE-0003 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Bulk Earth Works Design and Report | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | E | EQL | 0001 | A | 6105AK124-6286-EEQL-0001 | Q24050972-04-6286-E-EQL-0001 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Electrical Equipment Load Register | Primary Crushing - Small Power and Lighting for Mining Sub Station - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | FND | 0001 | A | 6105AK124-6286-CFND-0001 | Q24050972-04-6286-C-FND-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Civil Foundation Design | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | C | FND | 0002 | A | 6105AK124-6286-CFND-0002 | Q24050972-04-6286-C-FND-0002 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Civil Foundation Design | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | FND | 0003 | A | 6105AK124-6286-CFND-0003 | Q24050972-04-6286-C-FND-0003 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | Civil Foundation Design | Primary Crushing - Perimeter Fencing for Mining Sub Station - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | C | FND | 0004 | A | 6105AK124-6286-CFND-0004 | Q24050972-04-6286-C-FND-0004 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Civil Foundation Design | Primary Crushing - Small Power and Lighting for Mining Sub Station - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0001 | A | 6105AK124-6286-CGAD-0001 | Q24050972-04-6286-C-GAD-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Stormwater and Effluent System Design | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0002 | A | 6105AK124-6286-CGAD-0002 | Q24050972-04-6286-C-GAD-0002 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Buildings and Structures GA | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0003 | A | 6105AK124-6286-CGAD-0003 | Q24050972-04-6286-C-GAD-0003 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Cables, OHL and Fibre Route GA | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0004 | A | 6105AK124-6286-CGAD-0004 | Q24050972-04-6286-C-GAD-0004 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Terrace Equipment GA | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0005 | A | 6105AK124-6286-CGAD-0005 | Q24050972-04-6286-C-GAD-0005 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Roads, Pathways, Offloading Areas and Fences GA | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0006 | A | 6105AK124-6286-CGAD-0006 | Q24050972-04-6286-C-GAD-0006 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Buildings and Structures GA | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0007 | A | 6105AK124-6286-CGAD-0007 | Q24050972-04-6286-C-GAD-0007 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Cables, OHL and Fibre Route GA | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0008 | A | 6105AK124-6286-CGAD-0008 | Q24050972-04-6286-C-GAD-0008 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Terrace Equipment GA | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0009 | A | 6105AK124-6286-CGAD-0009 | Q24050972-04-6286-C-GAD-0009 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | Roads, Pathways, Offloading Areas and Fences GA | Primary Crushing - Perimeter Fencing for Mining Sub Station - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0010 | A | 6105AK124-6286-CGAD-0010 | Q24050972-04-6286-C-GAD-0010 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | Lighting Design and Layout GA | Primary Crushing - Perimeter Fencing for Mining Sub Station - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0011 | A | 6105AK124-6286-CGAD-0011 | Q24050972-04-6286-C-GAD-0011 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | Cables, OHL and Fibre Route GA | Primary Crushing - Perimeter Fencing for Mining Sub Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0012 | A | 6105AK124-6286-CGAD-0012 | Q24050972-04-6286-C-GAD-0012 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Buildings and Structures GA | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0013 | A | 6105AK124-6286-CGAD-0013 | Q24050972-04-6286-C-GAD-0013 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Cables, OHL and Fibre Route GA | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0014 | A | 6105AK124-6286-CGAD-0014 | Q24050972-04-6286-C-GAD-0014 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Key Emergency Points and Equipment | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0015 | A | 6105AK124-6286-CGAD-0015 | Q24050972-04-6286-C-GAD-0015 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Terrace Equipment GA | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0016 | A | 6105AK124-6286-CGAD-0016 | Q24050972-04-6286-C-GAD-0016 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Disposal Areas General Arrangement | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0017 | A | 6105AK124-6286-CGAD-0017 | Q24050972-04-6286-C-GAD-0017 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Laydown Areas and Temp Buildings GA | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0018 | A | 6105AK124-6286-CGAD-0018 | Q24050972-04-6286-C-GAD-0018 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Stormwater and Effluent System Design | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0019 | A | 6105AK124-6286-CGAD-0019 | Q24050972-04-6286-C-GAD-0019 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Lighting Design and Layout GA | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0020 | A | 6105AK124-6286-CGAD-0020 | Q24050972-04-6286-C-GAD-0020 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Roads, Pathways, Offloading Areas and Fences GA | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0021 | A | 6105AK124-6286-CGAD-0021 | Q24050972-04-6286-C-GAD-0021 |  | Primary Crushing | Earthing System for Mining Sub Station | Lighting Design and Layout GA | Primary Crushing - Earthing System for Mining Sub Station - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0022 | A | 6105AK124-6286-CGAD-0022 | Q24050972-04-6286-C-GAD-0022 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Buildings and Structures GA | Primary Crushing - Small Power and Lighting for Mining Sub Station - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0023 | A | 6105AK124-6286-CGAD-0023 | Q24050972-04-6286-C-GAD-0023 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Cables, OHL and Fibre Route GA | Primary Crushing - Small Power and Lighting for Mining Sub Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0024 | A | 6105AK124-6286-CGAD-0024 | Q24050972-04-6286-C-GAD-0024 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Terrace Equipment GA | Primary Crushing - Small Power and Lighting for Mining Sub Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0025 | A | 6105AK124-6286-CGAD-0025 | Q24050972-04-6286-C-GAD-0025 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Laydown Areas and Temp Buildings GA | Primary Crushing - Small Power and Lighting for Mining Sub Station - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0026 | A | 6105AK124-6286-CGAD-0026 | Q24050972-04-6286-C-GAD-0026 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Lighting Design and Layout GA | Primary Crushing - Small Power and Lighting for Mining Sub Station - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0027 | A | 6105AK124-6286-CGAD-0027 | Q24050972-04-6286-C-GAD-0027 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Roads, Pathways, Offloading Areas and Fences GA | Primary Crushing - Small Power and Lighting for Mining Sub Station - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0028 | A | 6105AK124-6286-CGAD-0028 | Q24050972-04-6286-C-GAD-0028 |  | Primary Crushing | Lightning Protection Mining Sub Station | Buildings and Structures GA | Primary Crushing - Lightning Protection Mining Sub Station - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0029 | A | 6105AK124-6286-CGAD-0029 | Q24050972-04-6286-C-GAD-0029 |  | Primary Crushing | Lightning Protection Mining Sub Station | Cables, OHL and Fibre Route GA | Primary Crushing - Lightning Protection Mining Sub Station - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | C | GAD | 0030 | A | 6105AK124-6286-CGAD-0030 | Q24050972-04-6286-C-GAD-0030 |  | Primary Crushing | Lightning Protection Mining Sub Station | Terrace Equipment GA | Primary Crushing - Lightning Protection Mining Sub Station - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | I | ITD | 0001 | A | 6105AK124-6286-IITD-0001 | Q24050972-04-6286-I-ITD-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Instrument Wiring Loop Diagrams and Cable Schedule | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | E | LAY | 0008 | A | 6105AK124-6286-ELAY-0008 | Q24050972-04-6286-E-LAY-0008 |  | Primary Crushing | Earthing System for Mining Sub Station | Control Room Power and Earthing Design | Primary Crushing - Earthing System for Mining Sub Station - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | E | LAY | 0009 | A | 6105AK124-6286-ELAY-0009 | Q24050972-04-6286-E-LAY-0009 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Control Room Power and Earthing Design | Primary Crushing - Small Power and Lighting for Mining Sub Station - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | LAY | 0010 | A | 6105AK124-6286-ELAY-0010 | Q24050972-04-6286-E-LAY-0010 |  | Primary Crushing | Lightning Protection Mining Sub Station | Control Room Power and Earthing Design | Primary Crushing - Lightning Protection Mining Sub Station - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | W | LAY | 0004 | A | 6105AK124-6286-WLAY-0004 | Q24050972-04-6286-W-LAY-0004 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Drainage, Run-off and Impoundment Design | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | W | LAY | 0005 | A | 6105AK124-6286-WLAY-0005 | Q24050972-04-6286-W-LAY-0005 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Drainage, Run-off and Impoundment Design | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | W | LAY | 0006 | A | 6105AK124-6286-WLAY-0006 | Q24050972-04-6286-W-LAY-0006 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Drainage, Run-off and Impoundment Design | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | I | LST | 0001 | A | 6105AK124-6286-ILST-0001 | Q24050972-04-6286-I-LST-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Equipment Alarm and Trip Level Register | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | C | MDL | 0001 | A | 6105AK124-6286-CMDL-0001 | Q24050972-04-6286-C-MDL-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | 3D Designs and Drawings | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | C | MDL | 0002 | A | 6105AK124-6286-CMDL-0002 | Q24050972-04-6286-C-MDL-0002 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | 3D Designs and Drawings | Primary Crushing - Cable Racks and Trays for Mining Sub Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | MDL | 0003 | A | 6105AK124-6286-CMDL-0003 | Q24050972-04-6286-C-MDL-0003 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | 3D Designs and Drawings | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | C | MDL | 0004 | A | 6105AK124-6286-CMDL-0004 | Q24050972-04-6286-C-MDL-0004 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | 3D Designs and Drawings | Primary Crushing - Perimeter Fencing for Mining Sub Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | C | MDL | 0005 | A | 6105AK124-6286-CMDL-0005 | Q24050972-04-6286-C-MDL-0005 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | 3D Designs and Drawings | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | MDL | 0006 | A | 6105AK124-6286-CMDL-0006 | Q24050972-04-6286-C-MDL-0006 |  | Primary Crushing | Earthing System for Mining Sub Station | 3D Designs and Drawings | Primary Crushing - Earthing System for Mining Sub Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | C | MDL | 0007 | A | 6105AK124-6286-CMDL-0007 | Q24050972-04-6286-C-MDL-0007 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | 3D Designs and Drawings | Primary Crushing - Small Power and Lighting for Mining Sub Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | MDL | 0008 | A | 6105AK124-6286-CMDL-0008 | Q24050972-04-6286-C-MDL-0008 |  | Primary Crushing | Lightning Protection Mining Sub Station | 3D Designs and Drawings | Primary Crushing - Lightning Protection Mining Sub Station - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | B | PHL | 0001 | A | 6105AK124-6286-BPHL-0001 | Q24050972-04-6286-B-PHL-0001 |  | Primary Crushing | Mining Substation 33/11 kV Project Package | Control Philosophy | Primary Crushing - Mining Substation 33/11 kV Project Package - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Sub Station | 33/11 kV Project Package |  |  |  | Pending
6105A | K124 | 6286 | B | PHL | 0002 | A | 6105AK124-6286-BPHL-0002 | Q24050972-04-6286-B-PHL-0002 |  | Primary Crushing | Mining Substation 33/11 kV Project Package | Synchronization Philosophy | Primary Crushing - Mining Substation 33/11 kV Project Package - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Sub Station | 33/11 kV Project Package |  |  |  | Pending
6105A | K124 | 6286 | C | PLN | 0001 | A | 6105AK124-6286-CPLN-0001 | Q24050972-04-6286-C-PLN-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Civil Works Execution Plan | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | C | PLN | 0002 | A | 6105AK124-6286-CPLN-0002 | Q24050972-04-6286-C-PLN-0002 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Civil Works Execution Plan | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | C | PLN | 0003 | A | 6105AK124-6286-CPLN-0003 | Q24050972-04-6286-C-PLN-0003 |  | Primary Crushing | Earthing System for Mining Sub Station | Civil Works Execution Plan | Primary Crushing - Earthing System for Mining Sub Station - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | C | PLN | 0004 | A | 6105AK124-6286-CPLN-0004 | Q24050972-04-6286-C-PLN-0004 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Civil Works Execution Plan | Primary Crushing - Small Power and Lighting for Mining Sub Station - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | PPL | 0001 | A | 6105AK124-6286-CPPL-0001 | Q24050972-04-6286-C-PPL-0001 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Operational & Maint Access Routes Design | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | PPL | 0002 | A | 6105AK124-6286-CPPL-0002 | Q24050972-04-6286-C-PPL-0002 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Operational & Maint Access Routes Design | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | C | PPL | 0003 | A | 6105AK124-6286-CPPL-0003 | Q24050972-04-6286-C-PPL-0003 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Operational & Maint Access Routes Design | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | M | PRC | 0001 | A | 6105AK124-6286-MPRC-0001 | Q24050972-04-6286-M-PRC-0001 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Rigging Study and Lifting Equipment Design | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Sub Station | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | M | PSP | 0001 | A | 6105AK124-6286-MPSP-0001 | Q24050972-04-6286-M-PSP-0001 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Pipe and Cable Support Racks Design | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Sub Station | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | E | QRA | 0001 | A | 6105AK124-6286-EQRA-0001 | Q24050972-04-6286-E-QRA-0001 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Lightning Protection Study and Risk Assessment | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | E | QRA | 0002 | A | 6105AK124-6286-EQRA-0002 | Q24050972-04-6286-E-QRA-0002 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Risk Assessment: Electrical Hazards | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | E | QRA | 0003 | A | 6105AK124-6286-EQRA-0003 | Q24050972-04-6286-E-QRA-0003 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Lightning Protection Study and Risk Assessment | Primary Crushing - Small Power and Lighting for Mining Sub Station - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | QRA | 0004 | A | 6105AK124-6286-EQRA-0004 | Q24050972-04-6286-E-QRA-0004 |  | Primary Crushing | Lightning Protection Mining Sub Station | Lightning Protection Study and Risk Assessment | Primary Crushing - Lightning Protection Mining Sub Station - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | I | QRA | 0001 | A | 6105AK124-6286-IQRA-0001 | Q24050972-04-6286-I-QRA-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Risk Assessment: Fire and Explosions | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Risk Assessment: Fire and Explosions |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | T | RPT | 0001 | A | 6105AK124-6286-TRPT-0001 | Q24050972-04-6286-T-RPT-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Site Surveying & Geotechnical Report | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | T | RPT | 0002 | A | 6105AK124-6286-TRPT-0002 | Q24050972-04-6286-T-RPT-0002 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | Site Surveying & Geotechnical Report | Primary Crushing - Perimeter Fencing for Mining Sub Station - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | T | RPT | 0003 | A | 6105AK124-6286-TRPT-0003 | Q24050972-04-6286-T-RPT-0003 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Site Surveying & Geotechnical Report | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | SEC | 0005 | A | 6105AK124-6286-CSEC-0005 | Q24050972-04-6286-C-SEC-0005 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Corrosion Prevention and Protection Design | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | SEC | 0006 | A | 6105AK124-6286-CSEC-0006 | Q24050972-04-6286-C-SEC-0006 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Structural Earthing and Bonding Design | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | SEC | 0007 | A | 6105AK124-6286-CSEC-0007 | Q24050972-04-6286-C-SEC-0007 |  | Primary Crushing | Earthing System for Mining Sub Station | Corrosion Prevention and Protection Design | Primary Crushing - Earthing System for Mining Sub Station - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | C | SEC | 0008 | A | 6105AK124-6286-CSEC-0008 | Q24050972-04-6286-C-SEC-0008 |  | Primary Crushing | Earthing System for Mining Sub Station | Structural Earthing and Bonding Design | Primary Crushing - Earthing System for Mining Sub Station - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | C | SEC | 0009 | A | 6105AK124-6286-CSEC-0009 | Q24050972-04-6286-C-SEC-0009 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Corrosion Prevention and Protection Design | Primary Crushing - Small Power and Lighting for Mining Sub Station - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | SEC | 0010 | A | 6105AK124-6286-CSEC-0010 | Q24050972-04-6286-C-SEC-0010 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Structural Earthing and Bonding Design | Primary Crushing - Small Power and Lighting for Mining Sub Station - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | SEC | 0011 | A | 6105AK124-6286-CSEC-0011 | Q24050972-04-6286-C-SEC-0011 |  | Primary Crushing | Lightning Protection Mining Sub Station | Corrosion Prevention and Protection Design | Primary Crushing - Lightning Protection Mining Sub Station - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | C | SEC | 0012 | A | 6105AK124-6286-CSEC-0012 | Q24050972-04-6286-C-SEC-0012 |  | Primary Crushing | Lightning Protection Mining Sub Station | Structural Earthing and Bonding Design | Primary Crushing - Lightning Protection Mining Sub Station - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | C | SHP | 0001 | A | 6105AK124-6286-CSHP-0001 | Q24050972-04-6286-C-SHP-0001 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Equipment Assembly Drawings | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | SHP | 0002 | A | 6105AK124-6286-CSHP-0002 | Q24050972-04-6286-C-SHP-0002 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | Equipment Assembly Drawings | Primary Crushing - Perimeter Fencing for Mining Sub Station - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | C | SHP | 0003 | A | 6105AK124-6286-CSHP-0003 | Q24050972-04-6286-C-SHP-0003 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Equipment Assembly Drawings | Primary Crushing - Small Power and Lighting for Mining Sub Station - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0012 | A | 6105AK124-6286-ESLD-0012 | Q24050972-04-6286-E-SLD-0012 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Electrical Single Line Diagram | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0013 | A | 6105AK124-6286-ESLD-0013 | Q24050972-04-6286-E-SLD-0013 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Electrical Single Line Diagram | Primary Crushing - Small Power and Lighting for Mining Sub Station - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6286 | E | SLD | 0014 | A | 6105AK124-6286-ESLD-0014 | Q24050972-04-6286-E-SLD-0014 |  | Primary Crushing | Lightning Protection Mining Sub Station | Electrical Single Line Diagram | Primary Crushing - Lightning Protection Mining Sub Station - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6286 | B | SPC | 0001 | A | 6105AK124-6286-BSPC-0001 | Q24050972-04-6286-B-SPC-0001 |  | Primary Crushing | Mining Substation 33/11 kV Project Package | Functional Design Specification | Primary Crushing - Mining Substation 33/11 kV Project Package - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Sub Station | 33/11 kV Project Package |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0002 | A | 6105AK124-6286-CSPC-0002 | Q24050972-04-6286-C-SPC-0002 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Civil Design Requirements | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0003 | A | 6105AK124-6286-CSPC-0003 | Q24050972-04-6286-C-SPC-0003 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Excavation, Trenching and Compacting Design | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0004 | A | 6105AK124-6286-CSPC-0004 | Q24050972-04-6286-C-SPC-0004 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Concrete Construction Material Specifications | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0005 | A | 6105AK124-6286-CSPC-0005 | Q24050972-04-6286-C-SPC-0005 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Civil Design Requirements | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0006 | A | 6105AK124-6286-CSPC-0006 | Q24050972-04-6286-C-SPC-0006 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Concrete Construction Material Specifications | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0007 | A | 6105AK124-6286-CSPC-0007 | Q24050972-04-6286-C-SPC-0007 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Steel Structures Corrosion Protection Specification | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0008 | A | 6105AK124-6286-CSPC-0008 | Q24050972-04-6286-C-SPC-0008 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Civil Design Requirements | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0009 | A | 6105AK124-6286-CSPC-0009 | Q24050972-04-6286-C-SPC-0009 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Excavation, Trenching and Compacting Design | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0010 | A | 6105AK124-6286-CSPC-0010 | Q24050972-04-6286-C-SPC-0010 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Concrete Construction Material Specifications | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0011 | A | 6105AK124-6286-CSPC-0011 | Q24050972-04-6286-C-SPC-0011 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | Excavation, Trenching and Compacting Design | Primary Crushing - Perimeter Fencing for Mining Sub Station - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0012 | A | 6105AK124-6286-CSPC-0012 | Q24050972-04-6286-C-SPC-0012 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | Concrete Construction Material Specifications | Primary Crushing - Perimeter Fencing for Mining Sub Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0013 | A | 6105AK124-6286-CSPC-0013 | Q24050972-04-6286-C-SPC-0013 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | Steel Structures Corrosion Protection Specification | Primary Crushing - Perimeter Fencing for Mining Sub Station - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0014 | A | 6105AK124-6286-CSPC-0014 | Q24050972-04-6286-C-SPC-0014 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Civil Design Requirements | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0015 | A | 6105AK124-6286-CSPC-0015 | Q24050972-04-6286-C-SPC-0015 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Excavation, Trenching and Compacting Design | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0016 | A | 6105AK124-6286-CSPC-0016 | Q24050972-04-6286-C-SPC-0016 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Concrete Construction Material Specifications | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0017 | A | 6105AK124-6286-CSPC-0017 | Q24050972-04-6286-C-SPC-0017 |  | Primary Crushing | Earthing System for Mining Sub Station | Concrete Construction Material Specifications | Primary Crushing - Earthing System for Mining Sub Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0018 | A | 6105AK124-6286-CSPC-0018 | Q24050972-04-6286-C-SPC-0018 |  | Primary Crushing | Earthing System for Mining Sub Station | Excavation, Trenching and Compacting Design | Primary Crushing - Earthing System for Mining Sub Station - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | C | SPC | 0019 | A | 6105AK124-6286-CSPC-0019 | Q24050972-04-6286-C-SPC-0019 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Concrete Construction Material Specifications | Primary Crushing - Small Power and Lighting for Mining Sub Station - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | SPC | 0001 | A | 6105AK124-6286-ESPC-0001 | Q24050972-04-6286-E-SPC-0001 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Cable and Conductor Specifications | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | E | SPC | 0002 | A | 6105AK124-6286-ESPC-0002 | Q24050972-04-6286-E-SPC-0002 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Cable and Conductor Specifications | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | E | SPC | 0003 | A | 6105AK124-6286-ESPC-0003 | Q24050972-04-6286-E-SPC-0003 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Lighting and Luminaire Design | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | E | SPC | 0004 | A | 6105AK124-6286-ESPC-0004 | Q24050972-04-6286-E-SPC-0004 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Cable Termination Specifications | Primary Crushing - Small Power and Lighting for Mining Sub Station - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | SPC | 0005 | A | 6105AK124-6286-ESPC-0005 | Q24050972-04-6286-E-SPC-0005 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Cable and Conductor Specifications | Primary Crushing - Small Power and Lighting for Mining Sub Station - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | SPC | 0006 | A | 6105AK124-6286-ESPC-0006 | Q24050972-04-6286-E-SPC-0006 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Lighting and Luminaire Design | Primary Crushing - Small Power and Lighting for Mining Sub Station - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | I | SPC | 0001 | A | 6105AK124-6286-ISPC-0001 | Q24050972-04-6286-I-SPC-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Junction Box and Interface Cabinet Design | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | I | SPC | 0002 | A | 6105AK124-6286-ISPC-0002 | Q24050972-04-6286-I-SPC-0002 |  | Primary Crushing | Earthing System for Mining Sub Station | Junction Box and Interface Cabinet Design | Primary Crushing - Earthing System for Mining Sub Station - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | M | SPC | 0001 | A | 6105AK124-6286-MSPC-0001 | Q24050972-04-6286-M-SPC-0001 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Material Selection and Verification Specification | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Sub Station | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | T | SPC | 0001 | A | 6105AK124-6286-TSPC-0001 | Q24050972-04-6286-T-SPC-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Civil Design and Requirements | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | T | SPC | 0002 | A | 6105AK124-6286-TSPC-0002 | Q24050972-04-6286-T-SPC-0002 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Civil Design and Requirements | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | T | SPC | 0003 | A | 6105AK124-6286-TSPC-0003 | Q24050972-04-6286-T-SPC-0003 |  | Primary Crushing | Earthing System for Mining Sub Station | Civil Design and Requirements | Primary Crushing - Earthing System for Mining Sub Station - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Substation | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | C | SSD | 0001 | A | 6105AK124-6286-CSSD-0001 | Q24050972-04-6286-C-SSD-0001 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Steel Support Structures Design | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | SSD | 0002 | A | 6105AK124-6286-CSSD-0002 | Q24050972-04-6286-C-SSD-0002 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | Steel Support Structures Design | Primary Crushing - Perimeter Fencing for Mining Sub Station - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | B | STD | 0001 | A | 6105AK124-6286-BSTD-0001 | Q24050972-04-6286-B-STD-0001 |  | Primary Crushing | Mining Substation 33/11 kV Project Package | System Detailed Engineering Design | Primary Crushing - Mining Substation 33/11 kV Project Package - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Sub Station | 33/11 kV Project Package |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0001 | A | 6105AK124-6286-CSTD-0001 | Q24050972-04-6286-C-STD-0001 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Bund-wall Requirements and Design | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0002 | A | 6105AK124-6286-CSTD-0002 | Q24050972-04-6286-C-STD-0002 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Fire Protection System Design (Civil Works) | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Fire Protection System Design (Civil Works) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0003 | A | 6105AK124-6286-CSTD-0003 | Q24050972-04-6286-C-STD-0003 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Civil Construction Requirements | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0004 | A | 6105AK124-6286-CSTD-0004 | Q24050972-04-6286-C-STD-0004 |  | Primary Crushing | Collection Sump from Bunds for Mining Sub Station | Underground Pipe Route and Cable Bedding Design | Primary Crushing - Collection Sump from Bunds for Mining Sub Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Collection Sump from Bunds |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0005 | A | 6105AK124-6286-CSTD-0005 | Q24050972-04-6286-C-STD-0005 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Underground Pipe Route and Cable Bedding Design | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0006 | A | 6105AK124-6286-CSTD-0006 | Q24050972-04-6286-C-STD-0006 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Civil Construction Requirements | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0007 | A | 6105AK124-6286-CSTD-0007 | Q24050972-04-6286-C-STD-0007 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Underground Pipe Route and Cable Bedding Design | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0008 | A | 6105AK124-6286-CSTD-0008 | Q24050972-04-6286-C-STD-0008 |  | Primary Crushing | Perimeter Fencing for Mining Sub Station | Underground Pipe Route and Cable Bedding Design | Primary Crushing - Perimeter Fencing for Mining Sub Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Perimeter Fencing |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0009 | A | 6105AK124-6286-CSTD-0009 | Q24050972-04-6286-C-STD-0009 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Bund-wall Requirements and Design | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0010 | A | 6105AK124-6286-CSTD-0010 | Q24050972-04-6286-C-STD-0010 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Civil Construction Requirements | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0011 | A | 6105AK124-6286-CSTD-0011 | Q24050972-04-6286-C-STD-0011 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Underground Pipe Route and Cable Bedding Design | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0012 | A | 6105AK124-6286-CSTD-0012 | Q24050972-04-6286-C-STD-0012 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Civil Construction Requirements | Primary Crushing - Small Power and Lighting for Mining Sub Station - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0013 | A | 6105AK124-6286-CSTD-0013 | Q24050972-04-6286-C-STD-0013 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Underground Pipe Route and Cable Bedding Design | Primary Crushing - Small Power and Lighting for Mining Sub Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0014 | A | 6105AK124-6286-CSTD-0014 | Q24050972-04-6286-C-STD-0014 |  | Primary Crushing | Lightning Protection Mining Sub Station | Civil Construction Requirements | Primary Crushing - Lightning Protection Mining Sub Station - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | C | STD | 0015 | A | 6105AK124-6286-CSTD-0015 | Q24050972-04-6286-C-STD-0015 |  | Primary Crushing | Lightning Protection Mining Sub Station | Underground Pipe Route and Cable Bedding Design | Primary Crushing - Lightning Protection Mining Sub Station - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | E | STD | 0001 | A | 6105AK124-6286-ESTD-0001 | Q24050972-04-6286-E-STD-0001 |  | Primary Crushing | Cable Racks and Trays for Mining Sub Station | Thermal Management and Fire Prevention Design | Primary Crushing - Cable Racks and Trays for Mining Sub Station - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6286 | E | STD | 0002 | A | 6105AK124-6286-ESTD-0002 | Q24050972-04-6286-E-STD-0002 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Electrical Equipment Installation Requirements | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | E | STD | 0003 | A | 6105AK124-6286-ESTD-0003 | Q24050972-04-6286-E-STD-0003 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Electrical Design Standards | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | E | STD | 0004 | A | 6105AK124-6286-ESTD-0004 | Q24050972-04-6286-E-STD-0004 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Thermal Management and Fire Prevention Design | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | E | STD | 0005 | A | 6105AK124-6286-ESTD-0005 | Q24050972-04-6286-E-STD-0005 |  | Primary Crushing | Earthing System for Mining Sub Station | Earth Map and Bonding Design | Primary Crushing - Earthing System for Mining Sub Station - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | E | STD | 0006 | A | 6105AK124-6286-ESTD-0006 | Q24050972-04-6286-E-STD-0006 |  | Primary Crushing | Earthing System for Mining Sub Station | Electrical Design Standards | Primary Crushing - Earthing System for Mining Sub Station - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | E | STD | 0007 | A | 6105AK124-6286-ESTD-0007 | Q24050972-04-6286-E-STD-0007 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Electrical Equipment Installation Requirements | Primary Crushing - Small Power and Lighting for Mining Sub Station - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | STD | 0008 | A | 6105AK124-6286-ESTD-0008 | Q24050972-04-6286-E-STD-0008 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Earth Map and Bonding Design | Primary Crushing - Small Power and Lighting for Mining Sub Station - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | STD | 0009 | A | 6105AK124-6286-ESTD-0009 | Q24050972-04-6286-E-STD-0009 |  | Primary Crushing | Small Power and Lighting for Mining Sub Station | Electrical Design Standards | Primary Crushing - Small Power and Lighting for Mining Sub Station - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6286 | E | STD | 0010 | A | 6105AK124-6286-ESTD-0010 | Q24050972-04-6286-E-STD-0010 |  | Primary Crushing | Lightning Protection Mining Sub Station | Electrical Design Standards | Primary Crushing - Lightning Protection Mining Sub Station - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | E | STD | 0011 | A | 6105AK124-6286-ESTD-0011 | Q24050972-04-6286-E-STD-0011 |  | Primary Crushing | Lightning Protection Mining Sub Station | Earth Map and Bonding Design | Primary Crushing - Lightning Protection Mining Sub Station - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | E | STD | 0012 | A | 6105AK124-6286-ESTD-0012 | Q24050972-04-6286-E-STD-0012 |  | Primary Crushing | Lightning Protection Mining Sub Station | Thermal Management and Fire Prevention Design | Primary Crushing - Lightning Protection Mining Sub Station - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | W | TRP | 0001 | A | 6105AK124-6286-WTRP-0001 | Q24050972-04-6286-W-TRP-0001 |  | Primary Crushing | Cable Trench and Tunnels for Mining Sub Station | Soil Classification and Nomination Deliverables | Primary Crushing - Cable Trench and Tunnels for Mining Sub Station - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Cable Trench and Tunnels |  |  |  | Pending
6105A | K124 | 6286 | W | TRP | 0002 | A | 6105AK124-6286-WTRP-0002 | Q24050972-04-6286-W-TRP-0002 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Soil Classification and Nomination Deliverables | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | W | TRP | 0003 | A | 6105AK124-6286-WTRP-0003 | Q24050972-04-6286-W-TRP-0003 |  | Primary Crushing | Terrace, Roads and Access-ways for Mining Sub Station | Soil Resistivity Testing Report | Primary Crushing - Terrace, Roads and Access-ways for Mining Sub Station - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6286 | W | TRP | 0004 | A | 6105AK124-6286-WTRP-0004 | Q24050972-04-6286-W-TRP-0004 |  | Primary Crushing | Earthing System for Mining Sub Station | Soil Resistivity Testing Report | Primary Crushing - Earthing System for Mining Sub Station - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Earthing System |  |  |  | Pending
6105A | K124 | 6286 | W | TRP | 0005 | A | 6105AK124-6286-WTRP-0005 | Q24050972-04-6286-W-TRP-0005 |  | Primary Crushing | Lightning Protection Mining Sub Station | Soil Classification and Nomination Deliverables | Primary Crushing - Lightning Protection Mining Sub Station - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6286 | W | TRP | 0006 | A | 6105AK124-6286-WTRP-0006 | Q24050972-04-6286-W-TRP-0006 |  | Primary Crushing | Lightning Protection Mining Sub Station | Soil Resistivity Testing Report | Primary Crushing - Lightning Protection Mining Sub Station - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Mining Open Pit | Lightning Protection |  |  |  | Pending
6105A | K124 | 6290 | B | DBD | 0001 | A | 6105AK124-6290-BDBD-0001 | Q24050972-04-6290-B-DBD-0001 |  | Renewable Energy | Solar PV Plant Project Package | Design Criteria / Basis of Design | Renewable Energy - Solar PV Plant Project Package - Design Criteria / Basis of Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Renewable Energy | Solar PV Plant Project Package |  |  |  | Pending
6105A | K124 | 6290 | B | PHL | 0001 | A | 6105AK124-6290-BPHL-0001 | Q24050972-04-6290-B-PHL-0001 |  | Renewable Energy | Solar PV Plant Project Package | Control Philosophy | Renewable Energy - Solar PV Plant Project Package - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Renewable Energy | Solar PV Plant Project Package |  |  |  | Pending
6105A | K124 | 6290 | B | PHL | 0002 | A | 6105AK124-6290-BPHL-0002 | Q24050972-04-6290-B-PHL-0002 |  | Renewable Energy | Solar PV Plant Project Package | Synchronization Philosophy | Renewable Energy - Solar PV Plant Project Package - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Renewable Energy | Solar PV Plant Project Package |  |  |  | Pending
6105A | K124 | 6290 | B | SPC | 0001 | A | 6105AK124-6290-BSPC-0001 | Q24050972-04-6290-B-SPC-0001 |  | Renewable Energy | Solar PV Plant Project Package | Functional Design Specification | Renewable Energy - Solar PV Plant Project Package - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Renewable Energy | Solar PV Plant Project Package |  |  |  | Pending
6105A | K124 | 6290 | B | STD | 0001 | A | 6105AK124-6290-BSTD-0001 | Q24050972-04-6290-B-STD-0001 |  | Renewable Energy | Solar PV Plant Project Package | System Detailed Engineering Design | Renewable Energy - Solar PV Plant Project Package - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Renewable Energy | Solar PV Plant Project Package |  |  |  | Pending
6105A | K124 | 6291 | E | CAL | 0001 | A | 6105AK124-6291-ECAL-0001 | Q24050972-04-6291-E-CAL-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Cable and Conductor Sizing (incl Volt Drop Calcs) | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | E | CAL | 0002 | A | 6105AK124-6291-ECAL-0002 | Q24050972-04-6291-E-CAL-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Cable and Conductor Sizing (incl Volt Drop Calcs) | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | M | CAL | 0001 | A | 6105AK124-6291-MCAL-0001 | Q24050972-04-6291-M-CAL-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Piping Pressure Drop Calculations | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | M | CAL | 0002 | A | 6105AK124-6291-MCAL-0002 | Q24050972-04-6291-M-CAL-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Piping Pressure Drop Calculations | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | E | DIA | 0001 | A | 6105AK124-6291-EDIA-0001 | Q24050972-04-6291-E-DIA-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Cable Block Diagrams and Schedules | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | E | DIA | 0002 | A | 6105AK124-6291-EDIA-0002 | Q24050972-04-6291-E-DIA-0002 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Electrical Circuit Diagrams (Schematics) | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | E | DIA | 0003 | A | 6105AK124-6291-EDIA-0003 | Q24050972-04-6291-E-DIA-0003 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | E/I Termination Schedule | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | E | DIA | 0004 | A | 6105AK124-6291-EDIA-0004 | Q24050972-04-6291-E-DIA-0004 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Cable Block Diagrams and Schedules | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | E | DIA | 0005 | A | 6105AK124-6291-EDIA-0005 | Q24050972-04-6291-E-DIA-0005 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Electrical Circuit Diagrams (Schematics) | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | E | DIA | 0006 | A | 6105AK124-6291-EDIA-0006 | Q24050972-04-6291-E-DIA-0006 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | E/I Termination Schedule | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | DID | 0001 | A | 6105AK124-6291-CDID-0001 | Q24050972-04-6291-C-DID-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Ventilation and Air Filtration Systems Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Ventilation and Air Filtration Systems Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | DID | 0002 | A | 6105AK124-6291-CDID-0002 | Q24050972-04-6291-C-DID-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Ventilation and Air Filtration Systems Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Ventilation and Air Filtration Systems Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | E | DST | 0001 | A | 6105AK124-6291-EDST-0001 | Q24050972-04-6291-E-DST-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Equipment Register and Technical Specifications | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | E | DST | 0002 | A | 6105AK124-6291-EDST-0002 | Q24050972-04-6291-E-DST-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Equipment Register and Technical Specifications | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | W | ELE | 0001 | A | 6105AK124-6291-WELE-0001 | Q24050972-04-6291-W-ELE-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Bulk Earth Works Design and Report | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | W | ELE | 0002 | A | 6105AK124-6291-WELE-0002 | Q24050972-04-6291-W-ELE-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Bulk Earth Works Design and Report | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | E | EQL | 0001 | A | 6105AK124-6291-EEQL-0001 | Q24050972-04-6291-E-EQL-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Electrical Equipment Load Register | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | E | EQL | 0002 | A | 6105AK124-6291-EEQL-0002 | Q24050972-04-6291-E-EQL-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Electrical Equipment Load Register | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | M | EQL | 0001 | A | 6105AK124-6291-MEQL-0001 | Q24050972-04-6291-M-EQL-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Mechanical Equipment Register with Specifications | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | M | EQL | 0002 | A | 6105AK124-6291-MEQL-0002 | Q24050972-04-6291-M-EQL-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Mechanical Equipment Register with Specifications | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0001 | A | 6105AK124-6291-CGAD-0001 | Q24050972-04-6291-C-GAD-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Buildings and Structures GA | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0002 | A | 6105AK124-6291-CGAD-0002 | Q24050972-04-6291-C-GAD-0002 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Terrace Equipment GA | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0003 | A | 6105AK124-6291-CGAD-0003 | Q24050972-04-6291-C-GAD-0003 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Pipe Routing General Arrangement | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Pipe Routing General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0004 | A | 6105AK124-6291-CGAD-0004 | Q24050972-04-6291-C-GAD-0004 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Roads, Pathways, Offloading Areas and Fences GA | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0005 | A | 6105AK124-6291-CGAD-0005 | Q24050972-04-6291-C-GAD-0005 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Water Reticulation & Sewer System Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Water Reticulation & Sewer System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0006 | A | 6105AK124-6291-CGAD-0006 | Q24050972-04-6291-C-GAD-0006 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Utilities Connections and Battery Limits GA | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Utilities Connections and Battery Limits GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0007 | A | 6105AK124-6291-CGAD-0007 | Q24050972-04-6291-C-GAD-0007 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Key Emergency Points and Equipment | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0008 | A | 6105AK124-6291-CGAD-0008 | Q24050972-04-6291-C-GAD-0008 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Laydown Areas and Temp Buildings GA | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0009 | A | 6105AK124-6291-CGAD-0009 | Q24050972-04-6291-C-GAD-0009 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Buildings and Structures GA | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0010 | A | 6105AK124-6291-CGAD-0010 | Q24050972-04-6291-C-GAD-0010 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Terrace Equipment GA | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0011 | A | 6105AK124-6291-CGAD-0011 | Q24050972-04-6291-C-GAD-0011 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Pipe Routing General Arrangement | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Pipe Routing General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0012 | A | 6105AK124-6291-CGAD-0012 | Q24050972-04-6291-C-GAD-0012 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Roads, Pathways, Offloading Areas and Fences GA | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0013 | A | 6105AK124-6291-CGAD-0013 | Q24050972-04-6291-C-GAD-0013 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Water Reticulation & Sewer System Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Water Reticulation & Sewer System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0014 | A | 6105AK124-6291-CGAD-0014 | Q24050972-04-6291-C-GAD-0014 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Utilities Connections and Battery Limits GA | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Utilities Connections and Battery Limits GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0015 | A | 6105AK124-6291-CGAD-0015 | Q24050972-04-6291-C-GAD-0015 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Key Emergency Points and Equipment | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | GAD | 0016 | A | 6105AK124-6291-CGAD-0016 | Q24050972-04-6291-C-GAD-0016 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Laydown Areas and Temp Buildings GA | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | M | ISO | 0001 | A | 6105AK124-6291-MISO-0001 | Q24050972-04-6291-M-ISO-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Piping Isometric Design and Layouts | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | M | ISO | 0002 | A | 6105AK124-6291-MISO-0002 | Q24050972-04-6291-M-ISO-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Piping Isometric Design and Layouts | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | W | LAY | 0001 | A | 6105AK124-6291-WLAY-0001 | Q24050972-04-6291-W-LAY-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Drainage, Run-off and Impoundment Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | W | LAY | 0002 | A | 6105AK124-6291-WLAY-0002 | Q24050972-04-6291-W-LAY-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Drainage, Run-off and Impoundment Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | MDL | 0001 | A | 6105AK124-6291-CMDL-0001 | Q24050972-04-6291-C-MDL-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | 3D Designs and Drawings | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | MDL | 0002 | A | 6105AK124-6291-CMDL-0002 | Q24050972-04-6291-C-MDL-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | 3D Designs and Drawings | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | PLN | 0001 | A | 6105AK124-6291-CPLN-0001 | Q24050972-04-6291-C-PLN-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Civil Works Execution Plan | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | PLN | 0002 | A | 6105AK124-6291-CPLN-0002 | Q24050972-04-6291-C-PLN-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Civil Works Execution Plan | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | PPL | 0001 | A | 6105AK124-6291-CPPL-0001 | Q24050972-04-6291-C-PPL-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Operational & Maint Access Routes Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | PPL | 0002 | A | 6105AK124-6291-CPPL-0002 | Q24050972-04-6291-C-PPL-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Operational & Maint Access Routes Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | M | PRC | 0001 | A | 6105AK124-6291-MPRC-0001 | Q24050972-04-6291-M-PRC-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Rigging Study and Lifting Equipment Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | M | PRC | 0002 | A | 6105AK124-6291-MPRC-0002 | Q24050972-04-6291-M-PRC-0002 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Fastener Specification and Torque Procedures | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | M | PRC | 0003 | A | 6105AK124-6291-MPRC-0003 | Q24050972-04-6291-M-PRC-0003 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Rigging Study and Lifting Equipment Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | M | PRC | 0004 | A | 6105AK124-6291-MPRC-0004 | Q24050972-04-6291-M-PRC-0004 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Fastener Specification and Torque Procedures | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | M | QAD | 0001 | A | 6105AK124-6291-MQAD-0001 | Q24050972-04-6291-M-QAD-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Fabrication Inspection QC Pack (Incl. NDT) | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | M | QAD | 0002 | A | 6105AK124-6291-MQAD-0002 | Q24050972-04-6291-M-QAD-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Fabrication Inspection QC Pack (Incl. NDT) | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | E | QRA | 0001 | A | 6105AK124-6291-EQRA-0001 | Q24050972-04-6291-E-QRA-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Lightning Protection Study and Risk Assessment | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | E | QRA | 0002 | A | 6105AK124-6291-EQRA-0002 | Q24050972-04-6291-E-QRA-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Lightning Protection Study and Risk Assessment | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | T | RPT | 0001 | A | 6105AK124-6291-TRPT-0001 | Q24050972-04-6291-T-RPT-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Site Surveying & Geotechnical Report | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | T | RPT | 0002 | A | 6105AK124-6291-TRPT-0002 | Q24050972-04-6291-T-RPT-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Site Surveying & Geotechnical Report | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | SEC | 0001 | A | 6105AK124-6291-CSEC-0001 | Q24050972-04-6291-C-SEC-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Structural Earthing and Bonding Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | SEC | 0002 | A | 6105AK124-6291-CSEC-0002 | Q24050972-04-6291-C-SEC-0002 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Corrosion Prevention and Protection Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | SEC | 0003 | A | 6105AK124-6291-CSEC-0003 | Q24050972-04-6291-C-SEC-0003 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Structural Earthing and Bonding Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | SEC | 0004 | A | 6105AK124-6291-CSEC-0004 | Q24050972-04-6291-C-SEC-0004 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Corrosion Prevention and Protection Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | SPC | 0001 | A | 6105AK124-6291-CSPC-0001 | Q24050972-04-6291-C-SPC-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Civil Design Requirements | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | SPC | 0002 | A | 6105AK124-6291-CSPC-0002 | Q24050972-04-6291-C-SPC-0002 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Excavation, Trenching and Compacting Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | SPC | 0003 | A | 6105AK124-6291-CSPC-0003 | Q24050972-04-6291-C-SPC-0003 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Concrete Construction Material Specifications | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | SPC | 0004 | A | 6105AK124-6291-CSPC-0004 | Q24050972-04-6291-C-SPC-0004 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Steel Structures Corrosion Protection Specification | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | SPC | 0005 | A | 6105AK124-6291-CSPC-0005 | Q24050972-04-6291-C-SPC-0005 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Civil Design Requirements | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | SPC | 0006 | A | 6105AK124-6291-CSPC-0006 | Q24050972-04-6291-C-SPC-0006 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Excavation, Trenching and Compacting Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | SPC | 0007 | A | 6105AK124-6291-CSPC-0007 | Q24050972-04-6291-C-SPC-0007 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Concrete Construction Material Specifications | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | SPC | 0008 | A | 6105AK124-6291-CSPC-0008 | Q24050972-04-6291-C-SPC-0008 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Steel Structures Corrosion Protection Specification | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | E | SPC | 0001 | A | 6105AK124-6291-ESPC-0001 | Q24050972-04-6291-E-SPC-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Cable Termination Specifications | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | E | SPC | 0002 | A | 6105AK124-6291-ESPC-0002 | Q24050972-04-6291-E-SPC-0002 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Lighting and Luminaire Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | E | SPC | 0003 | A | 6105AK124-6291-ESPC-0003 | Q24050972-04-6291-E-SPC-0003 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Cable Termination Specifications | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | E | SPC | 0004 | A | 6105AK124-6291-ESPC-0004 | Q24050972-04-6291-E-SPC-0004 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Lighting and Luminaire Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | M | SPC | 0001 | A | 6105AK124-6291-MSPC-0001 | Q24050972-04-6291-M-SPC-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Manual Isolation Valve Design Specification | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Manual Isolation Valve Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | M | SPC | 0002 | A | 6105AK124-6291-MSPC-0002 | Q24050972-04-6291-M-SPC-0002 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Material Selection and Verification Specification | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | M | SPC | 0003 | A | 6105AK124-6291-MSPC-0003 | Q24050972-04-6291-M-SPC-0003 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Gasket Schedule and Material Specification | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | M | SPC | 0004 | A | 6105AK124-6291-MSPC-0004 | Q24050972-04-6291-M-SPC-0004 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Manual Isolation Valve Design Specification | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Manual Isolation Valve Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | M | SPC | 0005 | A | 6105AK124-6291-MSPC-0005 | Q24050972-04-6291-M-SPC-0005 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Material Selection and Verification Specification | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | M | SPC | 0006 | A | 6105AK124-6291-MSPC-0006 | Q24050972-04-6291-M-SPC-0006 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Gasket Schedule and Material Specification | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | T | SPC | 0001 | A | 6105AK124-6291-TSPC-0001 | Q24050972-04-6291-T-SPC-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Civil Design and Requirements | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | T | SPC | 0002 | A | 6105AK124-6291-TSPC-0002 | Q24050972-04-6291-T-SPC-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Civil Design and Requirements | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | SPL | 0001 | A | 6105AK124-6291-CSPL-0001 | Q24050972-04-6291-C-SPL-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Pipe Fabrication and Field Installation Inspection | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Pipe Fabrication and Field Installation Inspection |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | SPL | 0002 | A | 6105AK124-6291-CSPL-0002 | Q24050972-04-6291-C-SPL-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Pipe Fabrication and Field Installation Inspection | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Pipe Fabrication and Field Installation Inspection |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | A | STD | 0001 | A | 6105AK124-6291-ASTD-0001 | Q24050972-04-6291-A-STD-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Building Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Building Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | A | STD | 0002 | A | 6105AK124-6291-ASTD-0002 | Q24050972-04-6291-A-STD-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Building Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Building Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | STD | 0001 | A | 6105AK124-6291-CSTD-0001 | Q24050972-04-6291-C-STD-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Civil Construction Requirements | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | STD | 0002 | A | 6105AK124-6291-CSTD-0002 | Q24050972-04-6291-C-STD-0002 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Roofing and Elevated Platforms Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Roofing and Elevated Platforms Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | STD | 0003 | A | 6105AK124-6291-CSTD-0003 | Q24050972-04-6291-C-STD-0003 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Underground Pipe Route and Cable Bedding Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | C | STD | 0004 | A | 6105AK124-6291-CSTD-0004 | Q24050972-04-6291-C-STD-0004 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Civil Construction Requirements | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | STD | 0005 | A | 6105AK124-6291-CSTD-0005 | Q24050972-04-6291-C-STD-0005 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Roofing and Elevated Platforms Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Roofing and Elevated Platforms Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | C | STD | 0006 | A | 6105AK124-6291-CSTD-0006 | Q24050972-04-6291-C-STD-0006 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Underground Pipe Route and Cable Bedding Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | E | STD | 0001 | A | 6105AK124-6291-ESTD-0001 | Q24050972-04-6291-E-STD-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Earth Map and Bonding Design | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | E | STD | 0002 | A | 6105AK124-6291-ESTD-0002 | Q24050972-04-6291-E-STD-0002 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Electrical Design Standards | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | E | STD | 0003 | A | 6105AK124-6291-ESTD-0003 | Q24050972-04-6291-E-STD-0003 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Earth Map and Bonding Design | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | E | STD | 0004 | A | 6105AK124-6291-ESTD-0004 | Q24050972-04-6291-E-STD-0004 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Electrical Design Standards | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6291 | W | TRP | 0001 | A | 6105AK124-6291-WTRP-0001 | Q24050972-04-6291-W-TRP-0001 |  | Administration and General Buildings | Control Room & Equip Offloading Storage Building for Solar PV Plant | Soil Classification and Nomination Deliverables | Administration and General Buildings - Control Room & Equip Offloading Storage Building for Solar PV Plant - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Control Room & Equip Offloading Storage Building |  |  |  | Pending
6105A | K124 | 6291 | W | TRP | 0002 | A | 6105AK124-6291-WTRP-0002 | Q24050972-04-6291-W-TRP-0002 |  | Administration and General Buildings | Solar PV Plant Yard Ablution Facilities | Soil Classification and Nomination Deliverables | Administration and General Buildings - Solar PV Plant Yard Ablution Facilities - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | RE Administration and General Buildings | Solar PV Plant Yard |  |  |  | Pending
6105A | K124 | 6293 | E | CAL | 0001 | A | 6105AK124-6293-ECAL-0001 | Q24050972-04-6293-E-CAL-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Cable and Conductor Sizing (incl Volt Drop Calcs) | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | CAL | 0002 | A | 6105AK124-6293-ECAL-0002 | Q24050972-04-6293-E-CAL-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Conductor Sag and Tension Plan | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | CAL | 0003 | A | 6105AK124-6293-ECAL-0003 | Q24050972-04-6293-E-CAL-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Cable and Conductor Sizing (incl Volt Drop Calcs) | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | E | CAL | 0004 | A | 6105AK124-6293-ECAL-0004 | Q24050972-04-6293-E-CAL-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Impedance and Burn-off Calculations | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | E | CAL | 0005 | A | 6105AK124-6293-ECAL-0005 | Q24050972-04-6293-E-CAL-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Cable and Conductor Sizing (incl Volt Drop Calcs) | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | E | CAL | 0006 | A | 6105AK124-6293-ECAL-0006 | Q24050972-04-6293-E-CAL-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Impedance and Burn-off Calculations | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | E | CAL | 0007 | A | 6105AK124-6293-ECAL-0007 | Q24050972-04-6293-E-CAL-0007 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Impedance and Burn-off Calculations | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | E | CAL | 0008 | A | 6105AK124-6293-ECAL-0008 | Q24050972-04-6293-E-CAL-0008 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Cable and Conductor Sizing (incl Volt Drop Calcs) | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Cable and Conductor Sizing (incl Volt Drop Calcs) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | E | CAL | 0009 | A | 6105AK124-6293-ECAL-0009 | Q24050972-04-6293-E-CAL-0009 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Impedance and Burn-off Calculations | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Impedance and Burn-off Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | E | CAL | 0010 | A | 6105AK124-6293-ECAL-0010 | Q24050972-04-6293-E-CAL-0010 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Conductor Sag and Tension Plan | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Conductor Sag and Tension Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | E | CAL | 0011 | A | 6105AK124-6293-ECAL-0011 | Q24050972-04-6293-E-CAL-0011 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Solar Resource Performance Ratio Calculations | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Solar Resource Performance Ratio Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | E | CAL | 0012 | A | 6105AK124-6293-ECAL-0012 | Q24050972-04-6293-E-CAL-0012 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Solar Resource Performance Ratio Calculations | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Solar Resource Performance Ratio Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | I | CAL | 0001 | A | 6105AK124-6293-ICAL-0001 | Q24050972-04-6293-I-CAL-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Instrument Sizing and Specification Sheets | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Instrument Sizing and Specification Sheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | M | CAL | 0001 | A | 6105AK124-6293-MCAL-0001 | Q24050972-04-6293-M-CAL-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Vessel and Structure Design with Stress Analysis Calcs | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | M | CAL | 0002 | A | 6105AK124-6293-MCAL-0002 | Q24050972-04-6293-M-CAL-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Piping Pressure Drop Calculations | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Piping Pressure Drop Calculations |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | E | DBD | 0001 | A | 6105AK124-6293-EDBD-0001 | Q24050972-04-6293-E-DBD-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Solar Plant Control System Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Solar Plant Control System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | I | DBD | 0002 | A | 6105AK124-6293-IDBD-0002 | Q24050972-04-6293-I-DBD-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Security System and Access Control Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Security System and Access Control Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | I | DBD | 0003 | A | 6105AK124-6293-IDBD-0003 | Q24050972-04-6293-I-DBD-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Security System and Access Control Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Security System and Access Control Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0001 | A | 6105AK124-6293-EDIA-0001 | Q24050972-04-6293-E-DIA-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Cable Block Diagrams and Schedules | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0002 | A | 6105AK124-6293-EDIA-0002 | Q24050972-04-6293-E-DIA-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Electrical Circuit Diagrams (Schematics) | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0003 | A | 6105AK124-6293-EDIA-0003 | Q24050972-04-6293-E-DIA-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Cable Block Diagrams and Schedules | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0004 | A | 6105AK124-6293-EDIA-0004 | Q24050972-04-6293-E-DIA-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Electrical Block Diagram | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0005 | A | 6105AK124-6293-EDIA-0005 | Q24050972-04-6293-E-DIA-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Electrical Circuit Diagrams (Schematics) | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0006 | A | 6105AK124-6293-EDIA-0006 | Q24050972-04-6293-E-DIA-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | E/I Termination Schedule | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0007 | A | 6105AK124-6293-EDIA-0007 | Q24050972-04-6293-E-DIA-0007 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Cable Block Diagrams and Schedules | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0008 | A | 6105AK124-6293-EDIA-0008 | Q24050972-04-6293-E-DIA-0008 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Electrical Circuit Diagrams (Schematics) | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0009 | A | 6105AK124-6293-EDIA-0009 | Q24050972-04-6293-E-DIA-0009 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Electrical Block Diagram | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0010 | A | 6105AK124-6293-EDIA-0010 | Q24050972-04-6293-E-DIA-0010 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | E/I Termination Schedule | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0011 | A | 6105AK124-6293-EDIA-0011 | Q24050972-04-6293-E-DIA-0011 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Cable Block Diagrams and Schedules | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0012 | A | 6105AK124-6293-EDIA-0012 | Q24050972-04-6293-E-DIA-0012 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Electrical Circuit Diagrams (Schematics) | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0013 | A | 6105AK124-6293-EDIA-0013 | Q24050972-04-6293-E-DIA-0013 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Electrical Block Diagram | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0014 | A | 6105AK124-6293-EDIA-0014 | Q24050972-04-6293-E-DIA-0014 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | E/I Termination Schedule | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0015 | A | 6105AK124-6293-EDIA-0015 | Q24050972-04-6293-E-DIA-0015 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Cable Block Diagrams and Schedules | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0016 | A | 6105AK124-6293-EDIA-0016 | Q24050972-04-6293-E-DIA-0016 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | E/I Termination Schedule | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0017 | A | 6105AK124-6293-EDIA-0017 | Q24050972-04-6293-E-DIA-0017 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Cable Block Diagrams and Schedules | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0018 | A | 6105AK124-6293-EDIA-0018 | Q24050972-04-6293-E-DIA-0018 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | E/I Termination Schedule | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0019 | A | 6105AK124-6293-EDIA-0019 | Q24050972-04-6293-E-DIA-0019 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Cable Block Diagrams and Schedules | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0020 | A | 6105AK124-6293-EDIA-0020 | Q24050972-04-6293-E-DIA-0020 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Electrical Circuit Diagrams (Schematics) | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0021 | A | 6105AK124-6293-EDIA-0021 | Q24050972-04-6293-E-DIA-0021 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Electrical Circuit Diagrams (Schematics) | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0022 | A | 6105AK124-6293-EDIA-0022 | Q24050972-04-6293-E-DIA-0022 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Cable Block Diagrams and Schedules | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0023 | A | 6105AK124-6293-EDIA-0023 | Q24050972-04-6293-E-DIA-0023 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | E/I Termination Schedule | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - E/I Termination Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0024 | A | 6105AK124-6293-EDIA-0024 | Q24050972-04-6293-E-DIA-0024 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Cable Block Diagrams and Schedules | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Cable Block Diagrams and Schedules |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0025 | A | 6105AK124-6293-EDIA-0025 | Q24050972-04-6293-E-DIA-0025 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Electrical Circuit Diagrams (Schematics) | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Electrical Circuit Diagrams (Schematics) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0026 | A | 6105AK124-6293-EDIA-0026 | Q24050972-04-6293-E-DIA-0026 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Electrical Block Diagram | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Electrical Block Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0027 | A | 6105AK124-6293-EDIA-0027 | Q24050972-04-6293-E-DIA-0027 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Solar Plant Efficiency Control Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Solar Plant Efficiency Control Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | E | DIA | 0028 | A | 6105AK124-6293-EDIA-0028 | Q24050972-04-6293-E-DIA-0028 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Solar Plant Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Solar Plant Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | F | DIA | 0001 | A | 6105AK124-6293-FDIA-0001 | Q24050972-04-6293-F-DIA-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Control Network Architecture Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | F | DIA | 0002 | A | 6105AK124-6293-FDIA-0002 | Q24050972-04-6293-F-DIA-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Control Network Communication Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Control Network Communication Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | F | DIA | 0003 | A | 6105AK124-6293-FDIA-0003 | Q24050972-04-6293-F-DIA-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Control System UPS & Back-up Systems Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Control System UPS & Back-up Systems Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | F | DIA | 0004 | A | 6105AK124-6293-FDIA-0004 | Q24050972-04-6293-F-DIA-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Control Network Architecture Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Control Network Architecture Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | F | DIA | 0005 | A | 6105AK124-6293-FDIA-0005 | Q24050972-04-6293-F-DIA-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Interface Panel and I/O Schematics | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Interface Panel and I/O Schematics |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | I | DIA | 0001 | A | 6105AK124-6293-IDIA-0001 | Q24050972-04-6293-I-DIA-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Closed Circuit Television (CCTV) Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Closed Circuit Television (CCTV) Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | I | DIA | 0002 | A | 6105AK124-6293-IDIA-0002 | Q24050972-04-6293-I-DIA-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Closed Circuit Television (CCTV) Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Closed Circuit Television (CCTV) Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | E | DST | 0001 | A | 6105AK124-6293-EDST-0001 | Q24050972-04-6293-E-DST-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Equipment Register and Technical Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | E | DST | 0002 | A | 6105AK124-6293-EDST-0002 | Q24050972-04-6293-E-DST-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Equipment Register and Technical Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | DST | 0003 | A | 6105AK124-6293-EDST-0003 | Q24050972-04-6293-E-DST-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Equipment Register and Technical Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | E | DST | 0004 | A | 6105AK124-6293-EDST-0004 | Q24050972-04-6293-E-DST-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Equipment Register and Technical Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | E | DST | 0005 | A | 6105AK124-6293-EDST-0005 | Q24050972-04-6293-E-DST-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Equipment Register and Technical Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | E | DST | 0006 | A | 6105AK124-6293-EDST-0006 | Q24050972-04-6293-E-DST-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Equipment Register and Technical Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | E | DST | 0007 | A | 6105AK124-6293-EDST-0007 | Q24050972-04-6293-E-DST-0007 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Equipment Register and Technical Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | E | DST | 0008 | A | 6105AK124-6293-EDST-0008 | Q24050972-04-6293-E-DST-0008 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Equipment Register and Technical Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | E | DST | 0009 | A | 6105AK124-6293-EDST-0009 | Q24050972-04-6293-E-DST-0009 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | CT and PT Datasheets | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - CT and PT Datasheets |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | E | DST | 0010 | A | 6105AK124-6293-EDST-0010 | Q24050972-04-6293-E-DST-0010 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Equipment Register and Technical Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | E | DST | 0011 | A | 6105AK124-6293-EDST-0011 | Q24050972-04-6293-E-DST-0011 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Equipment Register and Technical Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Equipment Register and Technical Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | W | ELE | 0001 | A | 6105AK124-6293-WELE-0001 | Q24050972-04-6293-W-ELE-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Bulk Earth Works Design and Report | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | W | ELE | 0002 | A | 6105AK124-6293-WELE-0002 | Q24050972-04-6293-W-ELE-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Bulk Earth Works Design and Report | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Bulk Earth Works Design and Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | E | EQL | 0001 | A | 6105AK124-6293-EEQL-0001 | Q24050972-04-6293-E-EQL-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Electrical Equipment Load Register | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | E | EQL | 0002 | A | 6105AK124-6293-EEQL-0002 | Q24050972-04-6293-E-EQL-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Electrical Equipment Load Register | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | EQL | 0003 | A | 6105AK124-6293-EEQL-0003 | Q24050972-04-6293-E-EQL-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Electrical Equipment Load Register | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | E | EQL | 0004 | A | 6105AK124-6293-EEQL-0004 | Q24050972-04-6293-E-EQL-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Electrical Equipment Load Register | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Electrical Equipment Load Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | M | EQL | 0001 | A | 6105AK124-6293-MEQL-0001 | Q24050972-04-6293-M-EQL-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Mechanical Equipment Register with Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | C | FND | 0001 | A | 6105AK124-6293-CFND-0001 | Q24050972-04-6293-C-FND-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Civil Foundation Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | C | FND | 0002 | A | 6105AK124-6293-CFND-0002 | Q24050972-04-6293-C-FND-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Civil Foundation Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | FND | 0003 | A | 6105AK124-6293-CFND-0003 | Q24050972-04-6293-C-FND-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Civil Foundation Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Civil Foundation Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0001 | A | 6105AK124-6293-CGAD-0001 | Q24050972-04-6293-C-GAD-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Roads, Pathways, Offloading Areas and Fences GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0002 | A | 6105AK124-6293-CGAD-0002 | Q24050972-04-6293-C-GAD-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Lighting Design and Layout GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0003 | A | 6105AK124-6293-CGAD-0003 | Q24050972-04-6293-C-GAD-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Cables, OHL and Fibre Route GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0004 | A | 6105AK124-6293-CGAD-0004 | Q24050972-04-6293-C-GAD-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Buildings and Structures GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0005 | A | 6105AK124-6293-CGAD-0005 | Q24050972-04-6293-C-GAD-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Cables, OHL and Fibre Route GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0006 | A | 6105AK124-6293-CGAD-0006 | Q24050972-04-6293-C-GAD-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Terrace Equipment GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0007 | A | 6105AK124-6293-CGAD-0007 | Q24050972-04-6293-C-GAD-0007 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Lighting Design and Layout GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0008 | A | 6105AK124-6293-CGAD-0008 | Q24050972-04-6293-C-GAD-0008 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Buildings and Structures GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0009 | A | 6105AK124-6293-CGAD-0009 | Q24050972-04-6293-C-GAD-0009 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Cables, OHL and Fibre Route GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0010 | A | 6105AK124-6293-CGAD-0010 | Q24050972-04-6293-C-GAD-0010 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Terrace Equipment GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0011 | A | 6105AK124-6293-CGAD-0011 | Q24050972-04-6293-C-GAD-0011 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Laydown Areas and Temp Buildings GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0012 | A | 6105AK124-6293-CGAD-0012 | Q24050972-04-6293-C-GAD-0012 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Lighting Design and Layout GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0013 | A | 6105AK124-6293-CGAD-0013 | Q24050972-04-6293-C-GAD-0013 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Roads, Pathways, Offloading Areas and Fences GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0014 | A | 6105AK124-6293-CGAD-0014 | Q24050972-04-6293-C-GAD-0014 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Cables, OHL and Fibre Route GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0015 | A | 6105AK124-6293-CGAD-0015 | Q24050972-04-6293-C-GAD-0015 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Terrace Equipment GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0016 | A | 6105AK124-6293-CGAD-0016 | Q24050972-04-6293-C-GAD-0016 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Cables, OHL and Fibre Route GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0017 | A | 6105AK124-6293-CGAD-0017 | Q24050972-04-6293-C-GAD-0017 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Terrace Equipment GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0018 | A | 6105AK124-6293-CGAD-0018 | Q24050972-04-6293-C-GAD-0018 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Buildings and Structures GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0019 | A | 6105AK124-6293-CGAD-0019 | Q24050972-04-6293-C-GAD-0019 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Cables, OHL and Fibre Route GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0020 | A | 6105AK124-6293-CGAD-0020 | Q24050972-04-6293-C-GAD-0020 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Terrace Equipment GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0021 | A | 6105AK124-6293-CGAD-0021 | Q24050972-04-6293-C-GAD-0021 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Roads, Pathways, Offloading Areas and Fences GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0022 | A | 6105AK124-6293-CGAD-0022 | Q24050972-04-6293-C-GAD-0022 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Buildings and Structures GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0023 | A | 6105AK124-6293-CGAD-0023 | Q24050972-04-6293-C-GAD-0023 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Cables, OHL and Fibre Route GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0024 | A | 6105AK124-6293-CGAD-0024 | Q24050972-04-6293-C-GAD-0024 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Terrace Equipment GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0025 | A | 6105AK124-6293-CGAD-0025 | Q24050972-04-6293-C-GAD-0025 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Buildings and Structures GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0026 | A | 6105AK124-6293-CGAD-0026 | Q24050972-04-6293-C-GAD-0026 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Cables, OHL and Fibre Route GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0027 | A | 6105AK124-6293-CGAD-0027 | Q24050972-04-6293-C-GAD-0027 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Terrace Equipment GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0028 | A | 6105AK124-6293-CGAD-0028 | Q24050972-04-6293-C-GAD-0028 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Lighting Design and Layout GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0029 | A | 6105AK124-6293-CGAD-0029 | Q24050972-04-6293-C-GAD-0029 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Buildings and Structures GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0030 | A | 6105AK124-6293-CGAD-0030 | Q24050972-04-6293-C-GAD-0030 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Cables, OHL and Fibre Route GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0031 | A | 6105AK124-6293-CGAD-0031 | Q24050972-04-6293-C-GAD-0031 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Key Emergency Points and Equipment | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Key Emergency Points and Equipment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0032 | A | 6105AK124-6293-CGAD-0032 | Q24050972-04-6293-C-GAD-0032 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Terrace Equipment GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0033 | A | 6105AK124-6293-CGAD-0033 | Q24050972-04-6293-C-GAD-0033 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Disposal Areas General Arrangement | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Disposal Areas General Arrangement |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0034 | A | 6105AK124-6293-CGAD-0034 | Q24050972-04-6293-C-GAD-0034 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Laydown Areas and Temp Buildings GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Laydown Areas and Temp Buildings GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0035 | A | 6105AK124-6293-CGAD-0035 | Q24050972-04-6293-C-GAD-0035 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Stormwater and Effluent System Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0036 | A | 6105AK124-6293-CGAD-0036 | Q24050972-04-6293-C-GAD-0036 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Lighting Design and Layout GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0037 | A | 6105AK124-6293-CGAD-0037 | Q24050972-04-6293-C-GAD-0037 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Roads, Pathways, Offloading Areas and Fences GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0038 | A | 6105AK124-6293-CGAD-0038 | Q24050972-04-6293-C-GAD-0038 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Terrace Equipment GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0039 | A | 6105AK124-6293-CGAD-0039 | Q24050972-04-6293-C-GAD-0039 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Buildings and Structures GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0040 | A | 6105AK124-6293-CGAD-0040 | Q24050972-04-6293-C-GAD-0040 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Cables, OHL and Fibre Route GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0041 | A | 6105AK124-6293-CGAD-0041 | Q24050972-04-6293-C-GAD-0041 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Terrace Equipment GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0042 | A | 6105AK124-6293-CGAD-0042 | Q24050972-04-6293-C-GAD-0042 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Stormwater and Effluent System Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0043 | A | 6105AK124-6293-CGAD-0043 | Q24050972-04-6293-C-GAD-0043 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Utilities Connections and Battery Limits GA | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Utilities Connections and Battery Limits GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | C | GAD | 0044 | A | 6105AK124-6293-CGAD-0044 | Q24050972-04-6293-C-GAD-0044 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Water Reticulation & Sewer System Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Water Reticulation & Sewer System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | M | ISO | 0001 | A | 6105AK124-6293-MISO-0001 | Q24050972-04-6293-M-ISO-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Piping Isometric Design and Layouts | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Piping Isometric Design and Layouts |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | I | ITD | 0001 | A | 6105AK124-6293-IITD-0001 | Q24050972-04-6293-I-ITD-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Instrument Wiring Loop Diagrams and Cable Schedule | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | I | ITD | 0002 | A | 6105AK124-6293-IITD-0002 | Q24050972-04-6293-I-ITD-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Instrument Wiring Loop Diagrams and Cable Schedule | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Instrument Wiring Loop Diagrams and Cable Schedule |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | E | LAY | 0001 | A | 6105AK124-6293-ELAY-0001 | Q24050972-04-6293-E-LAY-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Control Room Power and Earthing Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | LAY | 0002 | A | 6105AK124-6293-ELAY-0002 | Q24050972-04-6293-E-LAY-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Control Room Power and Earthing Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | E | LAY | 0003 | A | 6105AK124-6293-ELAY-0003 | Q24050972-04-6293-E-LAY-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Control Room Power and Earthing Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Control Room Power and Earthing Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | E | LAY | 0004 | A | 6105AK124-6293-ELAY-0004 | Q24050972-04-6293-E-LAY-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Switch Room (PCC and MCC) Detail Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Switch Room (PCC and MCC) Detail Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | W | LAY | 0001 | A | 6105AK124-6293-WLAY-0001 | Q24050972-04-6293-W-LAY-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Drainage, Run-off and Impoundment Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | W | LAY | 0002 | A | 6105AK124-6293-WLAY-0002 | Q24050972-04-6293-W-LAY-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Drainage, Run-off and Impoundment Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | W | LAY | 0003 | A | 6105AK124-6293-WLAY-0003 | Q24050972-04-6293-W-LAY-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Drainage, Run-off and Impoundment Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Drainage, Run-off and Impoundment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | I | LST | 0001 | A | 6105AK124-6293-ILST-0001 | Q24050972-04-6293-I-LST-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Instrumentation Equipment Tag Register | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | I | LST | 0002 | A | 6105AK124-6293-ILST-0002 | Q24050972-04-6293-I-LST-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Instrumentation Equipment Tag Register | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Instrumentation Equipment Tag Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | I | LST | 0003 | A | 6105AK124-6293-ILST-0003 | Q24050972-04-6293-I-LST-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Equipment Alarm and Trip Level Register | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Equipment Alarm and Trip Level Register |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | C | MDL | 0001 | A | 6105AK124-6293-CMDL-0001 | Q24050972-04-6293-C-MDL-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | 3D Designs and Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | C | MDL | 0002 | A | 6105AK124-6293-CMDL-0002 | Q24050972-04-6293-C-MDL-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | 3D Designs and Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | MDL | 0003 | A | 6105AK124-6293-CMDL-0003 | Q24050972-04-6293-C-MDL-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | 3D Designs and Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | MDL | 0004 | A | 6105AK124-6293-CMDL-0004 | Q24050972-04-6293-C-MDL-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | 3D Designs and Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | C | MDL | 0005 | A | 6105AK124-6293-CMDL-0005 | Q24050972-04-6293-C-MDL-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | 3D Designs and Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | C | MDL | 0006 | A | 6105AK124-6293-CMDL-0006 | Q24050972-04-6293-C-MDL-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | 3D Designs and Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | C | MDL | 0007 | A | 6105AK124-6293-CMDL-0007 | Q24050972-04-6293-C-MDL-0007 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | 3D Designs and Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | MDL | 0008 | A | 6105AK124-6293-CMDL-0008 | Q24050972-04-6293-C-MDL-0008 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | 3D Designs and Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | C | PLN | 0001 | A | 6105AK124-6293-CPLN-0001 | Q24050972-04-6293-C-PLN-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Civil Works Execution Plan | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | PLN | 0002 | A | 6105AK124-6293-CPLN-0002 | Q24050972-04-6293-C-PLN-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Civil Works Execution Plan | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | C | PLN | 0003 | A | 6105AK124-6293-CPLN-0003 | Q24050972-04-6293-C-PLN-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Civil Works Execution Plan | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | C | PLN | 0004 | A | 6105AK124-6293-CPLN-0004 | Q24050972-04-6293-C-PLN-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Civil Works Execution Plan | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | C | PLN | 0005 | A | 6105AK124-6293-CPLN-0005 | Q24050972-04-6293-C-PLN-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Civil Works Execution Plan | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | C | PPL | 0001 | A | 6105AK124-6293-CPPL-0001 | Q24050972-04-6293-C-PPL-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Operational & Maint Access Routes Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | PPL | 0002 | A | 6105AK124-6293-CPPL-0002 | Q24050972-04-6293-C-PPL-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Operational & Maint Access Routes Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | C | PPL | 0003 | A | 6105AK124-6293-CPPL-0003 | Q24050972-04-6293-C-PPL-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Operational & Maint Access Routes Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | PPL | 0004 | A | 6105AK124-6293-CPPL-0004 | Q24050972-04-6293-C-PPL-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Operational & Maint Access Routes Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | M | PRC | 0001 | A | 6105AK124-6293-MPRC-0001 | Q24050972-04-6293-M-PRC-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Rigging Study and Lifting Equipment Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | M | PRC | 0002 | A | 6105AK124-6293-MPRC-0002 | Q24050972-04-6293-M-PRC-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Rigging Study and Lifting Equipment Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Rigging Study and Lifting Equipment Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | M | PRC | 0003 | A | 6105AK124-6293-MPRC-0003 | Q24050972-04-6293-M-PRC-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Fastener Specification and Torque Procedures | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Fastener Specification and Torque Procedures |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | M | PSP | 0001 | A | 6105AK124-6293-MPSP-0001 | Q24050972-04-6293-M-PSP-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Pipe and Cable Support Racks Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | M | PSP | 0002 | A | 6105AK124-6293-MPSP-0002 | Q24050972-04-6293-M-PSP-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Pipe and Cable Support Racks Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | M | PSP | 0003 | A | 6105AK124-6293-MPSP-0003 | Q24050972-04-6293-M-PSP-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Pipe and Cable Support Racks Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Pipe and Cable Support Racks Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | M | QAD | 0001 | A | 6105AK124-6293-MQAD-0001 | Q24050972-04-6293-M-QAD-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Fabrication Inspection QC Pack (Incl. NDT) | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Fabrication Inspection QC Pack (Incl. NDT) |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | E | QRA | 0001 | A | 6105AK124-6293-EQRA-0001 | Q24050972-04-6293-E-QRA-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Lightning Protection Study and Risk Assessment | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | E | QRA | 0002 | A | 6105AK124-6293-EQRA-0002 | Q24050972-04-6293-E-QRA-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Lightning Protection Study and Risk Assessment | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | QRA | 0003 | A | 6105AK124-6293-EQRA-0003 | Q24050972-04-6293-E-QRA-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Lightning Protection Study and Risk Assessment | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | E | QRA | 0004 | A | 6105AK124-6293-EQRA-0004 | Q24050972-04-6293-E-QRA-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Risk Assessment: Electrical Hazards | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Risk Assessment: Electrical Hazards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | E | QRA | 0005 | A | 6105AK124-6293-EQRA-0005 | Q24050972-04-6293-E-QRA-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Lightning Protection Study and Risk Assessment | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Lightning Protection Study and Risk Assessment |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | I | QRA | 0001 | A | 6105AK124-6293-IQRA-0001 | Q24050972-04-6293-I-QRA-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Risk Assessment: Hazardous Substances | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Risk Assessment: Hazardous Substances |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | T | RPT | 0001 | A | 6105AK124-6293-TRPT-0001 | Q24050972-04-6293-T-RPT-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Site Surveying & Geotechnical Report | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | T | RPT | 0002 | A | 6105AK124-6293-TRPT-0002 | Q24050972-04-6293-T-RPT-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Site Surveying & Geotechnical Report | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | SEC | 0001 | A | 6105AK124-6293-CSEC-0001 | Q24050972-04-6293-C-SEC-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Corrosion Prevention and Protection Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System for Solar |  |  |  | Pending
6105A | K124 | 6293 | C | SEC | 0002 | A | 6105AK124-6293-CSEC-0002 | Q24050972-04-6293-C-SEC-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Corrosion Prevention and Protection Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | SEC | 0003 | A | 6105AK124-6293-CSEC-0003 | Q24050972-04-6293-C-SEC-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Structural Earthing and Bonding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | SEC | 0004 | A | 6105AK124-6293-CSEC-0004 | Q24050972-04-6293-C-SEC-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Corrosion Prevention and Protection Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | SEC | 0005 | A | 6105AK124-6293-CSEC-0005 | Q24050972-04-6293-C-SEC-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Structural Earthing and Bonding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | SEC | 0006 | A | 6105AK124-6293-CSEC-0006 | Q24050972-04-6293-C-SEC-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Corrosion Prevention and Protection Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | C | SEC | 0007 | A | 6105AK124-6293-CSEC-0007 | Q24050972-04-6293-C-SEC-0007 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Structural Earthing and Bonding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | C | SEC | 0008 | A | 6105AK124-6293-CSEC-0008 | Q24050972-04-6293-C-SEC-0008 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Corrosion Prevention and Protection Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Corrosion Prevention and Protection Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | C | SEC | 0009 | A | 6105AK124-6293-CSEC-0009 | Q24050972-04-6293-C-SEC-0009 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Structural Earthing and Bonding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Structural Earthing and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | C | SHP | 0001 | A | 6105AK124-6293-CSHP-0001 | Q24050972-04-6293-C-SHP-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Equipment Assembly Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | C | SHP | 0002 | A | 6105AK124-6293-CSHP-0002 | Q24050972-04-6293-C-SHP-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Equipment Assembly Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | C | SHP | 0003 | A | 6105AK124-6293-CSHP-0003 | Q24050972-04-6293-C-SHP-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Equipment Assembly Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | SHP | 0004 | A | 6105AK124-6293-CSHP-0004 | Q24050972-04-6293-C-SHP-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Equipment Assembly Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | SHP | 0005 | A | 6105AK124-6293-CSHP-0005 | Q24050972-04-6293-C-SHP-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Equipment Assembly Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | C | SHP | 0006 | A | 6105AK124-6293-CSHP-0006 | Q24050972-04-6293-C-SHP-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Equipment Assembly Drawings | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | E | SLD | 0001 | A | 6105AK124-6293-ESLD-0001 | Q24050972-04-6293-E-SLD-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Electrical Single Line Diagram | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | E | SLD | 0002 | A | 6105AK124-6293-ESLD-0002 | Q24050972-04-6293-E-SLD-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Electrical Single Line Diagram | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | SLD | 0003 | A | 6105AK124-6293-ESLD-0003 | Q24050972-04-6293-E-SLD-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Electrical Single Line Diagram | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | E | SLD | 0004 | A | 6105AK124-6293-ESLD-0004 | Q24050972-04-6293-E-SLD-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Electrical Single Line Diagram | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | E | SLD | 0005 | A | 6105AK124-6293-ESLD-0005 | Q24050972-04-6293-E-SLD-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Electrical Single Line Diagram | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | E | SLD | 0006 | A | 6105AK124-6293-ESLD-0006 | Q24050972-04-6293-E-SLD-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Electrical Single Line Diagram | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Electrical Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0001 | A | 6105AK124-6293-CSPC-0001 | Q24050972-04-6293-C-SPC-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Excavation, Trenching and Compacting Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0002 | A | 6105AK124-6293-CSPC-0002 | Q24050972-04-6293-C-SPC-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Concrete Construction Material Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0003 | A | 6105AK124-6293-CSPC-0003 | Q24050972-04-6293-C-SPC-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Steel Structures Corrosion Protection Specification | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0004 | A | 6105AK124-6293-CSPC-0004 | Q24050972-04-6293-C-SPC-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Concrete Construction Material Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0005 | A | 6105AK124-6293-CSPC-0005 | Q24050972-04-6293-C-SPC-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Excavation, Trenching and Compacting Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0006 | A | 6105AK124-6293-CSPC-0006 | Q24050972-04-6293-C-SPC-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Concrete Construction Material Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0007 | A | 6105AK124-6293-CSPC-0007 | Q24050972-04-6293-C-SPC-0007 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Excavation, Trenching and Compacting Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0008 | A | 6105AK124-6293-CSPC-0008 | Q24050972-04-6293-C-SPC-0008 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Concrete Construction Material Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0009 | A | 6105AK124-6293-CSPC-0009 | Q24050972-04-6293-C-SPC-0009 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Civil Design Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0010 | A | 6105AK124-6293-CSPC-0010 | Q24050972-04-6293-C-SPC-0010 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Concrete Construction Material Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0011 | A | 6105AK124-6293-CSPC-0011 | Q24050972-04-6293-C-SPC-0011 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Steel Structures Corrosion Protection Specification | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0012 | A | 6105AK124-6293-CSPC-0012 | Q24050972-04-6293-C-SPC-0012 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Civil Design Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0013 | A | 6105AK124-6293-CSPC-0013 | Q24050972-04-6293-C-SPC-0013 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Excavation, Trenching and Compacting Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0014 | A | 6105AK124-6293-CSPC-0014 | Q24050972-04-6293-C-SPC-0014 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Concrete Construction Material Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0015 | A | 6105AK124-6293-CSPC-0015 | Q24050972-04-6293-C-SPC-0015 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Concrete Construction Material Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0016 | A | 6105AK124-6293-CSPC-0016 | Q24050972-04-6293-C-SPC-0016 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Excavation, Trenching and Compacting Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0017 | A | 6105AK124-6293-CSPC-0017 | Q24050972-04-6293-C-SPC-0017 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Civil Design Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0018 | A | 6105AK124-6293-CSPC-0018 | Q24050972-04-6293-C-SPC-0018 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Excavation, Trenching and Compacting Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0019 | A | 6105AK124-6293-CSPC-0019 | Q24050972-04-6293-C-SPC-0019 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Concrete Construction Material Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0020 | A | 6105AK124-6293-CSPC-0020 | Q24050972-04-6293-C-SPC-0020 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Civil Design Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Civil Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | C | SPC | 0021 | A | 6105AK124-6293-CSPC-0021 | Q24050972-04-6293-C-SPC-0021 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Steel Structures Corrosion Protection Specification | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Steel Structures Corrosion Protection Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | E | SPC | 0001 | A | 6105AK124-6293-ESPC-0001 | Q24050972-04-6293-E-SPC-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Cable and Conductor Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | E | SPC | 0002 | A | 6105AK124-6293-ESPC-0002 | Q24050972-04-6293-E-SPC-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Cable Termination Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | E | SPC | 0003 | A | 6105AK124-6293-ESPC-0003 | Q24050972-04-6293-E-SPC-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Electrical Equipment Communication Specification | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Electrical Equipment Communication Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | E | SPC | 0004 | A | 6105AK124-6293-ESPC-0004 | Q24050972-04-6293-E-SPC-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Cable Termination Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | SPC | 0005 | A | 6105AK124-6293-ESPC-0005 | Q24050972-04-6293-E-SPC-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Cable and Conductor Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | SPC | 0006 | A | 6105AK124-6293-ESPC-0006 | Q24050972-04-6293-E-SPC-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Lighting and Luminaire Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | SPC | 0007 | A | 6105AK124-6293-ESPC-0007 | Q24050972-04-6293-E-SPC-0007 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Cable Termination Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | E | SPC | 0008 | A | 6105AK124-6293-ESPC-0008 | Q24050972-04-6293-E-SPC-0008 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Cable Termination Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | E | SPC | 0009 | A | 6105AK124-6293-ESPC-0009 | Q24050972-04-6293-E-SPC-0009 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Cable and Conductor Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | E | SPC | 0010 | A | 6105AK124-6293-ESPC-0010 | Q24050972-04-6293-E-SPC-0010 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Cable and Conductor Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Cable and Conductor Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | E | SPC | 0011 | A | 6105AK124-6293-ESPC-0011 | Q24050972-04-6293-E-SPC-0011 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Lighting and Luminaire Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Lighting and Luminaire Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | E | SPC | 0012 | A | 6105AK124-6293-ESPC-0012 | Q24050972-04-6293-E-SPC-0012 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Cable Termination Specifications | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Cable Termination Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | F | SPC | 0001 | A | 6105AK124-6293-FSPC-0001 | Q24050972-04-6293-F-SPC-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Control System Design Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Control System Design Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | F | SPC | 0002 | A | 6105AK124-6293-FSPC-0002 | Q24050972-04-6293-F-SPC-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Historian and Server Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Historian and Server Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | I | SPC | 0001 | A | 6105AK124-6293-ISPC-0001 | Q24050972-04-6293-I-SPC-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Instrument Communication Protocols Specification | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Instrument Communication Protocols Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | I | SPC | 0002 | A | 6105AK124-6293-ISPC-0002 | Q24050972-04-6293-I-SPC-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Junction Box and Interface Cabinet Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | I | SPC | 0003 | A | 6105AK124-6293-ISPC-0003 | Q24050972-04-6293-I-SPC-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Junction Box and Interface Cabinet Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Junction Box and Interface Cabinet Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | M | SPC | 0001 | A | 6105AK124-6293-MSPC-0001 | Q24050972-04-6293-M-SPC-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Material Selection and Verification Specification | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | M | SPC | 0002 | A | 6105AK124-6293-MSPC-0002 | Q24050972-04-6293-M-SPC-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Material Selection and Verification Specification | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | M | SPC | 0003 | A | 6105AK124-6293-MSPC-0003 | Q24050972-04-6293-M-SPC-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Gasket Schedule and Material Specification | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Gasket Schedule and Material Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | M | SPC | 0004 | A | 6105AK124-6293-MSPC-0004 | Q24050972-04-6293-M-SPC-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Manual Isolation Valve Design Specification | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Manual Isolation Valve Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | T | SPC | 0001 | A | 6105AK124-6293-TSPC-0001 | Q24050972-04-6293-T-SPC-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Civil Design and Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | T | SPC | 0002 | A | 6105AK124-6293-TSPC-0002 | Q24050972-04-6293-T-SPC-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Civil Design and Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | T | SPC | 0003 | A | 6105AK124-6293-TSPC-0003 | Q24050972-04-6293-T-SPC-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Civil Design and Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Civil Design and Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | C | SSD | 0001 | A | 6105AK124-6293-CSSD-0001 | Q24050972-04-6293-C-SSD-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Steel Support Structures Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | C | SSD | 0002 | A | 6105AK124-6293-CSSD-0002 | Q24050972-04-6293-C-SSD-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Steel Support Structures Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | SSD | 0003 | A | 6105AK124-6293-CSSD-0003 | Q24050972-04-6293-C-SSD-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Steel Support Structures Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Steel Support Structures Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | E | SSD | 0001 | A | 6105AK124-6293-ESSD-0001 | Q24050972-04-6293-E-SSD-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Solar PV Array Layout & Mounting Structure Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Solar PV Array Layout & Mounting Structure Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0001 | A | 6105AK124-6293-CSTD-0001 | Q24050972-04-6293-C-STD-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Perimeter Fencing and Access Gates for Solar PV Yard | Underground Pipe Route and Cable Bedding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Perimeter Fencing and Access Gates for Solar PV Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Perimeter Fencing and Access Gates |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0002 | A | 6105AK124-6293-CSTD-0002 | Q24050972-04-6293-C-STD-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Civil Construction Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0003 | A | 6105AK124-6293-CSTD-0003 | Q24050972-04-6293-C-STD-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Underground Pipe Route and Cable Bedding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0004 | A | 6105AK124-6293-CSTD-0004 | Q24050972-04-6293-C-STD-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Civil Construction Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0005 | A | 6105AK124-6293-CSTD-0005 | Q24050972-04-6293-C-STD-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Underground Pipe Route and Cable Bedding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0006 | A | 6105AK124-6293-CSTD-0006 | Q24050972-04-6293-C-STD-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Civil Construction Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0007 | A | 6105AK124-6293-CSTD-0007 | Q24050972-04-6293-C-STD-0007 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Underground Pipe Route and Cable Bedding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0008 | A | 6105AK124-6293-CSTD-0008 | Q24050972-04-6293-C-STD-0008 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Underground Pipe Route and Cable Bedding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0009 | A | 6105AK124-6293-CSTD-0009 | Q24050972-04-6293-C-STD-0009 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Civil Construction Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0010 | A | 6105AK124-6293-CSTD-0010 | Q24050972-04-6293-C-STD-0010 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Underground Pipe Route and Cable Bedding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0011 | A | 6105AK124-6293-CSTD-0011 | Q24050972-04-6293-C-STD-0011 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Civil Construction Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0012 | A | 6105AK124-6293-CSTD-0012 | Q24050972-04-6293-C-STD-0012 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Underground Pipe Route and Cable Bedding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0013 | A | 6105AK124-6293-CSTD-0013 | Q24050972-04-6293-C-STD-0013 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Bund-wall Requirements and Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Bund-wall Requirements and Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0014 | A | 6105AK124-6293-CSTD-0014 | Q24050972-04-6293-C-STD-0014 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Civil Construction Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Civil Construction Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0015 | A | 6105AK124-6293-CSTD-0015 | Q24050972-04-6293-C-STD-0015 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Underground Pipe Route and Cable Bedding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | C | STD | 0016 | A | 6105AK124-6293-CSTD-0016 | Q24050972-04-6293-C-STD-0016 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Panel Cleaning Systems Infrastructure | Underground Pipe Route and Cable Bedding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Panel Cleaning Systems Infrastructure - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Panel Cleaning Systems Infrastructure |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0001 | A | 6105AK124-6293-ESTD-0001 | Q24050972-04-6293-E-STD-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | CCTV & Security System for Solar PV Yard and Buildings | Electrical Equipment Installation Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - CCTV & Security System for Solar PV Yard and Buildings - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | CCTV & Security System |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0002 | A | 6105AK124-6293-ESTD-0002 | Q24050972-04-6293-E-STD-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Electrical Equipment Installation Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0003 | A | 6105AK124-6293-ESTD-0003 | Q24050972-04-6293-E-STD-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Earth Map and Bonding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0004 | A | 6105AK124-6293-ESTD-0004 | Q24050972-04-6293-E-STD-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | Small Power and Lighting for Solar PV Yard | Electrical Design Standards | Power Station 1 Photovoltaic Array, Inverters, and Transformers - Small Power and Lighting for Solar PV Yard - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Small Power and Lighting |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0005 | A | 6105AK124-6293-ESTD-0005 | Q24050972-04-6293-E-STD-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Electrical Equipment Installation Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0006 | A | 6105AK124-6293-ESTD-0006 | Q24050972-04-6293-E-STD-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Electrical Equipment Installation Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0007 | A | 6105AK124-6293-ESTD-0007 | Q24050972-04-6293-E-STD-0007 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Racks and Trays for Solar yard | Thermal Management and Fire Prevention Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Racks and Trays for Solar yard - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Racks and Trays |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0008 | A | 6105AK124-6293-ESTD-0008 | Q24050972-04-6293-E-STD-0008 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Electrical Equipment Installation Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0009 | A | 6105AK124-6293-ESTD-0009 | Q24050972-04-6293-E-STD-0009 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Electrical Design Standards | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0010 | A | 6105AK124-6293-ESTD-0010 | Q24050972-04-6293-E-STD-0010 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Thermal Management and Fire Prevention Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0011 | A | 6105AK124-6293-ESTD-0011 | Q24050972-04-6293-E-STD-0011 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Electrical Design Standards | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0012 | A | 6105AK124-6293-ESTD-0012 | Q24050972-04-6293-E-STD-0012 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Earth Map and Bonding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0013 | A | 6105AK124-6293-ESTD-0013 | Q24050972-04-6293-E-STD-0013 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Thermal Management and Fire Prevention Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Thermal Management and Fire Prevention Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0014 | A | 6105AK124-6293-ESTD-0014 | Q24050972-04-6293-E-STD-0014 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Earth Map and Bonding Design | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Earth Map and Bonding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0015 | A | 6105AK124-6293-ESTD-0015 | Q24050972-04-6293-E-STD-0015 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Electrical Design Standards | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Electrical Design Standards |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | E | STD | 0016 | A | 6105AK124-6293-ESTD-0016 | Q24050972-04-6293-E-STD-0016 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) | Electrical Equipment Installation Requirements | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Metering Instr. & Weather Station (Incl. PV Performance Man. System) - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Metering Instr. & Weather Station |  |  |  | Pending
6105A | K124 | 6293 | W | TRP | 0001 | A | 6105AK124-6293-WTRP-0001 | Q24050972-04-6293-W-TRP-0001 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | MV Cables for Solar PV Yard | Soil Classification and Nomination Deliverables | Power Station 1 Photovoltaic Array, Inverters, and Transformers - MV Cables for Solar PV Yard - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | MV Cables |  |  |  | Pending
6105A | K124 | 6293 | W | TRP | 0002 | A | 6105AK124-6293-WTRP-0002 | Q24050972-04-6293-W-TRP-0002 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard | Soil Classification and Nomination Deliverables | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - LV, Control and Signal Cables (Incl. Gland/Lugs) for Solar Yard - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | LV, Control and Signal Cables |  |  |  | Pending
6105A | K124 | 6293 | W | TRP | 0003 | A | 6105AK124-6293-WTRP-0003 | Q24050972-04-6293-W-TRP-0003 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Cable Trench / Tunnels for Solar yard | Soil Classification and Nomination Deliverables | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Cable Trench / Tunnels for Solar yard - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Cable Trench / Tunnels |  |  |  | Pending
6105A | K124 | 6293 | W | TRP | 0004 | A | 6105AK124-6293-WTRP-0004 | Q24050972-04-6293-W-TRP-0004 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Soil Classification and Nomination Deliverables | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | W | TRP | 0005 | A | 6105AK124-6293-WTRP-0005 | Q24050972-04-6293-W-TRP-0005 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Lightning Protection System for Solar PV Panels and Yard | Soil Resistivity Testing Report | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Lightning Protection System for Solar PV Panels and Yard - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Lightning Protection System |  |  |  | Pending
6105A | K124 | 6293 | W | TRP | 0006 | A | 6105AK124-6293-WTRP-0006 | Q24050972-04-6293-W-TRP-0006 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Earthing System for Solar Yard | Soil Resistivity Testing Report | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Earthing System for Solar Yard - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Earthing System |  |  |  | Pending
6105A | K124 | 6293 | W | TRP | 0007 | A | 6105AK124-6293-WTRP-0007 | Q24050972-04-6293-W-TRP-0007 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Soil Classification and Nomination Deliverables | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Soil Classification and Nomination Deliverables |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6293 | W | TRP | 0008 | A | 6105AK124-6293-WTRP-0008 | Q24050972-04-6293-W-TRP-0008 |  | Power Station 1 Photovoltaic Array, Inverters, and Transformers | K110 (6291) - Terrace, Roads and Access-ways for Solar Yard | Soil Resistivity Testing Report | Power Station 1 Photovoltaic Array, Inverters, and Transformers - K110 (6291) - Terrace, Roads and Access-ways for Solar Yard - Soil Resistivity Testing Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Power Station 1 Photovoltaic Array | Terrace, Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6200 | C | PLN | 0001 | A | 6105AK124-6200-CPLN-0001 | Q24050972-04-6200-C-PLN-0001 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Civil Works Execution Plan | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Civil Works Execution Plan | Main Consumer Substation |  |  |  | Pending
6105A | K124 | 6200 | C | PLN | 0002 | A | 6105AK124-6200-CPLN-0002 | Q24050972-04-6200-C-PLN-0002 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Civil Works Execution Plan | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Civil Works Execution Plan | Main Consumer Substation |  |  |  | Pending
6105A | K124 | 6200 | C | PLN | 0003 | A | 6105AK124-6200-CPLN-0003 | Q24050972-04-6200-C-PLN-0003 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Civil Works Execution Plan | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Civil Works Execution Plan | Main Consumer Substation |  |  |  | Pending
6105A | K124 | 6200 | C | PLN | 0004 | A | 6105AK124-6200-CPLN-0004 | Q24050972-04-6200-C-PLN-0004 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Civil Works Execution Plan | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Civil Works Execution Plan | Main Consumer Substation |  |  |  | Pending
6105A | K124 | 6200 | C | PLN | 0005 | A | 6105AK124-6200-CPLN-0005 | Q24050972-04-6200-C-PLN-0005 |  | On-Site Power Supply and Transmission | Pipe Racks and Supports for Main Consumer Sub Station Yard | Civil Works Execution Plan | On-Site Power Supply and Transmission - Pipe Racks and Supports for Main Consumer Sub Station Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Civil Works Execution Plan | Main Consumer Substation |  |  |  | Pending
6105A | K124 | 6200 | C | PLN | 0006 | A | 6105AK124-6200-CPLN-0006 | Q24050972-04-6200-C-PLN-0006 |  | On-Site Power Supply and Transmission | Earthing Systems for Main Consumer Sub Station Yard | Civil Works Execution Plan | On-Site Power Supply and Transmission - Earthing Systems for Main Consumer Sub Station Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Civil Works Execution Plan | Main Consumer Substation |  |  |  | Pending
6105A | K124 | 6200 | C | PLN | 0007 | A | 6105AK124-6200-CPLN-0007 | Q24050972-04-6200-C-PLN-0007 |  | On-Site Power Supply and Transmission | Small Power and Lighting for Main Consumer Sub Station Yard | Civil Works Execution Plan | On-Site Power Supply and Transmission - Small Power and Lighting for Main Consumer Sub Station Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Civil Works Execution Plan | Main Consumer Substation |  |  |  | Pending
6105A | K124 | 6200 | C | PLN | 0008 | A | 6105AK124-6200-CPLN-0008 | Q24050972-04-6200-C-PLN-0008 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Civil Works Execution Plan | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Civil Works Execution Plan | Main Consumer Substation |  |  |  | Pending
6105A | K124 | 6260 | B | DBD | 0001 | A | 6105AK124-6260-BDBD-0001 | Q24050972-03-6260-B-DBD-0001 |  | Emergency Power Generation (Main Plant) | Emergency Power Generation Project Package | Design Criteria / Basis of Design | Emergency Power Generation (Main Plant) - Emergency Power Generation Project Package - Design Criteria / Basis of Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Power Generation | Basis of Design |  |  |  | Pending
6105A | K124 | 6260 | B | PHL | 0001 | A | 6105AK124-6260-BPHL-0001 | Q24050972-03-6260-B-PHL-0001 |  | Emergency Power Generation (Main Plant) | Emergency Power Generation Project Package | Control Philosophy | Emergency Power Generation (Main Plant) - Emergency Power Generation Project Package - Control Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Power Generation | Project Package |  |  |  | Pending
6105A | K124 | 6260 | B | PHL | 0002 | A | 6105AK124-6260-BPHL-0002 | Q24050972-03-6260-B-PHL-0002 |  | Emergency Power Generation (Main Plant) | Emergency Power Generation Project Package | Synchronization Philosophy | Emergency Power Generation (Main Plant) - Emergency Power Generation Project Package - Synchronization Philosophy |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Power Generation | Project Package |  |  |  | Pending
6105A | K124 | 6260 | B | SPC | 0001 | A | 6105AK124-6260-BSPC-0001 | Q24050972-03-6260-B-SPC-0001 |  | Emergency Power Generation (Main Plant) | Emergency Power Generation Project Package | Functional Design Specification | Emergency Power Generation (Main Plant) - Emergency Power Generation Project Package - Functional Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Power Generation | Project Package |  |  |  | Pending
6105A | K124 | 6260 | B | STD | 0001 | A | 6105AK124-6260-BSTD-0001 | Q24050972-03-6260-B-STD-0001 |  | Emergency Power Generation (Main Plant) | Emergency Power Generation Project Package | System Detailed Engineering Design | Emergency Power Generation (Main Plant) - Emergency Power Generation Project Package - System Detailed Engineering Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Emergency Power Generation | Project Package |  |  |  | Pending
6105A | K124 | 6241 | C | PLN | 0001 | A | 6105AK124-6241-CPLN-0001 | Q24050972-03-6241-C-PLN-0001 |  | 33/220 kV Solar PV Substation | 33kV Interconnect Cables between Solar S/Room and Solar PV Substation | Civil Works Execution Plan | 33/220 kV Solar PV Substation - 33kV Interconnect Cables between Solar S/Room and Solar PV Substation - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | 33kV Interconnect Cables |  |  |  | Pending
6105A | K124 | 6241 | C | PLN | 0002 | A | 6105AK124-6241-CPLN-0002 | Q24050972-03-6241-C-PLN-0002 |  | 33/220 kV Solar PV Substation | Oil Collection Sump from Bunds for Solar PV Substation | Civil Works Execution Plan | 33/220 kV Solar PV Substation - Oil Collection Sump from Bunds for Solar PV Substation - Civil Works Execution Plan |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Solar PV Substation | Oil Collection Sump |  |  |  | Pending
6105A | K124 | 6200 | E | TDM | 0001 | A | 6105AK124-6200-ETDM-0001 | Q24050972-05-6200-E-TDM-0001 |  | On-Site Power Supply and Transmission | Study Report - Potential Load Increase and Impact on Electrical Network | Electrical | On-Site Power Supply and Transmission - Study Report - Potential Load Increase and Impact on Electrical Network - Electrical |  |  | RES - Reserved Placeholder | Pending | 0% | MM |  | 2026-06-31 | On-Site Power Supply and Transmission | Study Report |  |  |  | Pending
6105A | K124 | 6200 | G | CAL | 0001 | A | 6105AK124-6200-GCAL-0001 | Q24050972-05-6200-G-CAL-0001 |  | On-Site Power Supply and Transmission | Plant Main SS EPG Diesel Consumption Calculations | Calculation | On-Site Power Supply and Transmission - Plant Main SS EPG Diesel Consumption Calculations - Calculation | 2026-05-29 |  | IFR - Issued for Review | Pending | 33.33% | VV |  |  | Diesel Consumption Calculations | Calculation |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0001 | A | 6105AK124-9134-CTMP-0001 | Q24050972-05-9134-C-TMP-0001 |  | Survey, Inspection, and Quality Control | Base / Fill Layer Inspection Record | Inspection Record | Survey, Inspection, and Quality Control - Base / Fill Layer Inspection Record - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Fill Layer Inspection Record | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0002 | A | 6105AK124-9134-CTMP-0002 | Q24050972-05-9134-C-TMP-0002 |  | Survey, Inspection, and Quality Control | Light Mast Footings and service ducts | Inspection Record | Survey, Inspection, and Quality Control - Light Mast Footings and service ducts - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Light Mast Footings and service ducts | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0003 | A | 6105AK124-9134-CTMP-0003 | Q24050972-05-9134-C-TMP-0003 |  | Survey, Inspection, and Quality Control | Layerworks | Inspection Record | Survey, Inspection, and Quality Control - Layerworks - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Layerworks | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0004 | A | 6105AK124-9134-CTMP-0004 | Q24050972-05-9134-C-TMP-0004 |  | Survey, Inspection, and Quality Control | QAQC Laboratory Test Request | Inspection Record | Survey, Inspection, and Quality Control - QAQC Laboratory Test Request - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Laboratory Test Request | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0005 | A | 6105AK124-9134-CTMP-0005 | Q24050972-05-9134-C-TMP-0005 |  | Survey, Inspection, and Quality Control | QAQC Layerworks Level Control Sheet | Inspection Record | Survey, Inspection, and Quality Control - QAQC Layerworks Level Control Sheet - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Layerworks Level Control Sheet | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0006 | A | 6105AK124-9134-CTMP-0006 | Q24050972-05-9134-C-TMP-0006 |  | Survey, Inspection, and Quality Control | Materials Design and Submission Schedule | Inspection Record | Survey, Inspection, and Quality Control - Materials Design and Submission Schedule - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Materials Design and Submission Schedule | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0007 | A | 6105AK124-9134-CTMP-0007 | Q24050972-05-9134-C-TMP-0007 |  | Survey, Inspection, and Quality Control | Cement Stabilisation Spacing Calculation | Inspection Record | Survey, Inspection, and Quality Control - Cement Stabilisation Spacing Calculation - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Cement Stabilisation Spacing Calculation | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0008 | A | 6105AK124-9134-CTMP-0008 | Q24050972-05-9134-C-TMP-0008 |  | Survey, Inspection, and Quality Control | Quality Work Inspection Record | Inspection Record | Survey, Inspection, and Quality Control - Quality Work Inspection Record - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Quality Work Inspection Record | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0009 | A | 6105AK124-9134-CTMP-0009 | Q24050972-05-9134-C-TMP-0009 |  | Survey, Inspection, and Quality Control | QAQC Test Summary | Inspection Record | Survey, Inspection, and Quality Control - QAQC Test Summary - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Test Summary | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0010 | A | 6105AK124-9134-CTMP-0010 | Q24050972-05-9134-C-TMP-0010 |  | Survey, Inspection, and Quality Control | Time for completion of Laboratory Testing | Inspection Record | Survey, Inspection, and Quality Control - Time for completion of Laboratory Testing - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Laboratory Testing | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0011 | A | 6105AK124-9134-CTMP-0011 | Q24050972-05-9134-C-TMP-0011 |  | Survey, Inspection, and Quality Control | QAQC Trace Sheet | Inspection Record | Survey, Inspection, and Quality Control - QAQC Trace Sheet - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Trace Sheet | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0012 | A | 6105AK124-9134-CTMP-0012 | Q24050972-05-9134-C-TMP-0012 |  | Survey, Inspection, and Quality Control | Fill Layer Depth Control Sheet | Inspection Record | Survey, Inspection, and Quality Control - Fill Layer Depth Control Sheet - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Fill Layer Depth Control Sheet | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0013 | A | 6105AK124-9134-CTMP-0013 | Q24050972-05-9134-C-TMP-0013 |  | Survey, Inspection, and Quality Control | Cement Stabilised Layer Inspection Record | Inspection Record | Survey, Inspection, and Quality Control - Cement Stabilised Layer Inspection Record - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Inspection Record | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0014 | A | 6105AK124-9134-CTMP-0014 | Q24050972-05-9134-C-TMP-0014 |  | Survey, Inspection, and Quality Control | Post Concrete Inspection | Inspection Record | Survey, Inspection, and Quality Control - Post Concrete Inspection - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Post Concrete Inspection | Inspection Record |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0015 | A | 6105AK124-9134-CTMP-0015 | Q24050972-05-9134-C-TMP-0015 |  | Survey, Inspection, and Quality Control | Pre Concrete Inspection | Inspection Record | Survey, Inspection, and Quality Control - Pre Concrete Inspection - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-15 | Pre Concrete Inspection | Inspection Record |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0030 | A | 6105AK124-6200-ESLD-0030 | Q24050972-05-6200-E-SLD-0030 |  | On-Site Power Supply and Transmission | Solar Plant PV Substation-220kV/33kV Panel H02, H07, H12 Mains Incomers | Single Line Diagram | On-Site Power Supply and Transmission - Solar Plant PV Substation-220kV/33kV Panel H02, H07, H12 Mains Incomers - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-29 | Solar Plant PV Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0031 | A | 6105AK124-6200-ESLD-0031 | Q24050972-05-6200-E-SLD-0031 |  | On-Site Power Supply and Transmission | Solar Plant PV Substation-Panel H04-H10 - Bus Couplers | Single Line Diagram | On-Site Power Supply and Transmission - Solar Plant PV Substation-Panel H04-H10 - Bus Couplers - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-29 | Solar Plant PV Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0032 | A | 6105AK124-6200-ESLD-0032 | Q24050972-05-6200-E-SLD-0032 |  | On-Site Power Supply and Transmission | Solar Plant PV Substation-Panel H00, H15- Feeders | Single Line Diagram | On-Site Power Supply and Transmission - Solar Plant PV Substation-Panel H00, H15- Feeders - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-29 | Solar Plant PV Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 9134 | C | TMP | 0016 | A | 6105AK124-9134-CTMP-0016 | Q24050972-05-9134-C-TMP-0016 |  | Survey, Inspection, and Quality Control | Concrete Slump Cone Test | Inspection Record | Survey, Inspection, and Quality Control - Concrete Slump Cone Test - Inspection Record |  |  | RES - Reserved Placeholder | Pending | 0% | QV |  | 2026-05-19 | Concrete Slump Cone Test | Inspection Record |  |  |  | Pending
6105A | K124 | 0000 | H | RPT | 0001 | A | 6105AK124-0000-HRPT-0001 | Q24050972-05-0000-H-RPT-0001 |  | General | Fire Fighting system | Fire Fighting system | General - Fire Fighting system - Fire Fighting system |  |  | RES - Reserved Placeholder | Pending | 0% | PN |  | 2026-12-05 | Health & Safety | Fire Fighting system |  |  |  | Pending
6105A | K124 | 0100 | E | GDL | 0001 | A | 6105AK124-0100-EGDL-0001 | Q24050972-05-0100-E-GDL-0001 |  | Project Site Wide | Site Acceptance Test (SAT) | 400Vac Aux Supply Gensets | Project Site Wide - Site Acceptance Test (SAT) - 400Vac Aux Supply Gensets |  |  | RES - Reserved Placeholder | Pending | 0% | IS |  | 2026-05-22 | Site Acceptance Test (SAT) | 400Vac Aux Supply Gensets |  |  |  | Pending
6105A | K124 | 6251 | C | LAY | 0002 | A | 6105AK124-6251-CLAY-0002 | Q24050972-05-6251-C-LAY-0002 |  | Load Bank | Wartsila Power Plant 1 | Transformer - Layout | Load Bank - Wartsila Power Plant 1 - Transformer - Layout |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-30 | Wartsila Power Plant 1 | Transformer - Layout |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0024 | A | 6105AK124-6251-CSEC-0024 | Q24050972-05-6251-C-SEC-0024 |  | Load Bank | Wartsila Power Plant 1 | Transformer - section views | Load Bank - Wartsila Power Plant 1 - Transformer - section views |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-30 | Wartsila Power Plant 1 | Transformer - section views |  |  |  | Pending
6105A | K124 | 6251 | C | DTL | 0002 | A | 6105AK124-6251-CDTL-0002 | Q24050972-03-6251-C-DTL-0002 |  | Load Bank | Wartsila Power Plant 1 | Transformer - Rebar bending schedule | Load Bank - Wartsila Power Plant 1 - Transformer - Rebar bending schedule |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-30 | Wartsila Power Plant 1 | Rebar bending schedule |  |  |  | Pending
6105A | K124 | 6251 | C | LAY | 0003 | A | 6105AK124-6251-CLAY-0003 | Q24050972-05-6251-C-LAY-0003 |  | Load Bank | Wartsila Power Plant 1 | Load bank - Layout | Load Bank - Wartsila Power Plant 1 - Load bank - Layout |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-30 | Wartsila Power Plant 1 | Layout |  |  |  | Pending
6105A | K124 | 6251 | C | SEC | 0025 | A | 6105AK124-6251-CSEC-0025 | Q24050972-05-6251-C-SEC-0025 |  | Load Bank | Wartsila Power Plant 1 | Load bank - section views | Load Bank - Wartsila Power Plant 1 - Load bank - section views |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-30 | Wartsila Power Plant 1 | section views |  |  |  | Pending
6105A | K124 | 6251 | C | LAY | 0026 | A | 6105AK124-6251-CLAY-0026 | Q24050972-05-6251-C-LAY-0026 |  | Load Bank | Wartsila Power Plant 1 | Gen Bund - Civil Layout | Load Bank - Wartsila Power Plant 1 - Gen Bund - Civil Layout |  |  | No Placeholder Yet | No Placeholder Yet | 0% | CLR |  | 2026-05-30 | Wartsila Power Plant 1 | Civil Layout |  |  |  | Pending
6105A | K124 | 6251 | C | DTL | 0003 | A | 6105AK124-6251-CDTL-0003 | Q24050972-03-6251-C-DTL-0003 |  | Load Bank | Wartsila Power Plant 1 | Load bank - Rebar bending schedule | Load Bank - Wartsila Power Plant 1 - Load bank - Rebar bending schedule |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-30 | Wartsila Power Plant 1 | Rebar bending schedule |  |  |  | Pending
6105A | K124 | 6251 | C | DTL | 0004 | A | 6105AK124-6251-CDTL-0004 | Q24050972-03-6251-C-DTL-0004 |  | Load Bank | Wartsila Power Plant 1 | Gen Bund - Rebar bending schedule | Load Bank - Wartsila Power Plant 1 - Gen Bund - Rebar bending schedule |  |  | RES - Reserved Placeholder | Pending | 0% | CLR |  | 2026-05-30 | Wartsila Power Plant 1 | Rebar bending schedule |  |  |  | Pending
6105A | K124 | 6200 | E | SLD | 0033 | A | 6105AK124-6200-ESLD-0033 | Q24050972-05-6200-E-SLD-0033 |  | On-Site Power Supply and Transmission | Solar Plant PV Substation-Panel H01,H03,H06,H08,H09,H11,H13- Feeders | Single Line Diagram | On-Site Power Supply and Transmission - Solar Plant PV Substation-Panel H01,H03,H06,H08,H09,H11,H13- Feeders - Single Line Diagram |  |  | RES - Reserved Placeholder | Pending | 0% | LG |  | 2026-05-29 | Solar Plant PV Substation | Single Line Diagram |  |  |  | Pending
6105A | K124 | 6264 | M | DST | 0006 | A | 6105AK124-6264-MDST-0006 | Q24050972-05-6264-M-DST-0006 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Pressure Relief Devices Design and Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Pressure Relief Devices Design and Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Pressure Relief Devices
6105A | K124 | 6200 | M | SPC | 0017 | A | 6105AK124-6200-MSPC-0017 | Q24050972-05-6200-M-SPC-0017 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Material Selection and Verification Specification | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Underground Utility Piping
6105A | K124 | 6200 | M | SPC | 0018 | A | 6105AK124-6200-MSPC-0018 | Q24050972-05-6200-M-SPC-0018 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Material Selection and Verification Specification | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Ablution Facilities
6105A | K124 | 6200 | M | EQL | 0006 | A | 6105AK124-6200-MEQL-0006 | Q24050972-05-6200-M-EQL-0006 |  | On-Site Power Supply and Transmission | Collection Sump from Bunds for Main Consumer Sub Station Yard | Mechanical Equipment Register with Specifications | On-Site Power Supply and Transmission - Collection Sump from Bunds for Main Consumer Sub Station Yard - Mechanical Equipment Register with Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Main Consumer Sub Station Yard | Mechanical Equipment Register with Specifications
6105A | K124 | 6251 | C | GAD | 0083 | A | 6105AK124-6251-CGAD-0083 | Q24050972-05-6251-C-GAD-0083 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Buildings and Structures GA | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station Mobile | Buildings and Structures
6105A | K124 | 6251 | C | GAD | 0084 | A | 6105AK124-6251-CGAD-0084 | Q24050972-05-6251-C-GAD-0084 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Cables, OHL and Fibre Route GA | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station Mobile | Cables, OHL and Fibre Route
6105A | K124 | 6251 | C | GAD | 0085 | A | 6105AK124-6251-CGAD-0085 | Q24050972-05-6251-C-GAD-0085 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Terrace Equipment GA | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station Mobile | Terrace Equipment
6105A | K124 | 6251 | C | GAD | 0086 | A | 6105AK124-6251-CGAD-0086 | Q24050972-05-6251-C-GAD-0086 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Lighting Design and Layout GA | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station Mobile | Lighting Design and Layout
6105A | K124 | 6251 | C | GAD | 0087 | A | 6105AK124-6251-CGAD-0087 | Q24050972-05-6251-C-GAD-0087 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Roads, Pathways, Offloading Areas and Fences GA | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station Mobile | Roads, Pathways, Offloading Areas and Fences
6105A | K124 | 6251 | C | GAD | 0088 | A | 6105AK124-6251-CGAD-0088 | Q24050972-05-6251-C-GAD-0088 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Stormwater and Effluent System Design | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Stormwater and Effluent System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station Mobile | Stormwater and Effluent System Design
6105A | K124 | 6251 | C | GAD | 0089 | A | 6105AK124-6251-CGAD-0089 | Q24050972-05-6251-C-GAD-0089 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Buildings and Structures GA | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Buildings and Structures GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station Mobile | Buildings and Structures
6105A | K124 | 6251 | C | GAD | 0090 | A | 6105AK124-6251-CGAD-0090 | Q24050972-05-6251-C-GAD-0090 |  | Load Bank | Perimeter Fencing for for Wartsila Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Perimeter Fencing for for Wartsila Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Cables, OHL and Fibre Route
6105A | K124 | 6251 | C | GAD | 0091 | A | 6105AK124-6251-CGAD-0091 | Q24050972-05-6251-C-GAD-0091 |  | Load Bank | Terrace Roads and Access-ways for Wartsila Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Terrace Roads and Access-ways for Wartsila Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Terrace Roads and Access-ways | Terrace Equipment
6105A | K124 | 6251 | C | GAD | 0092 | A | 6105AK124-6251-CGAD-0092 | Q24050972-05-6251-C-GAD-0092 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Cables, OHL and Fibre Route GA | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Lighting Design and Layout
6105A | K124 | 6251 | C | GAD | 0093 | A | 6105AK124-6251-CGAD-0093 | Q24050972-05-6251-C-GAD-0093 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Lighting Design and Layout GA | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Lighting Design and Layout GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Roads, Pathways, Offloading Areas and Fences
6105A | K124 | 6251 | C | GAD | 0094 | A | 6105AK124-6251-CGAD-0094 | Q24050972-05-6251-C-GAD-0094 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Roads, Pathways, Offloading Areas and Fences GA | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Roads, Pathways, Offloading Areas and Fences GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Stormwater and Effluent System Design
6105A | K124 | 6251 | C | MDL | 0018 | A | 6105AK124-6251-CMDL-0018 | Q24050972-05-6251-C-MDL-0018 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | 3D Designs and Drawings | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | PPL | 0009 | A | 6105AK124-6251-CPPL-0009 | Q24050972-05-6251-C-PPL-0009 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Concrete Pad | Operational & Maint Access Routes Design | Load Bank - 36 MVA Power Station Mobile Load Bank Concrete Pad - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Mobile Load Bank Concrete Pad
6105A | K124 | 6251 | C | PPL | 0010 | A | 6105AK124-6251-CPPL-0010 | Q24050972-05-6251-C-PPL-0010 |  | Load Bank | Platform and Foundations for Wartsila Load Bank | Operational & Maint Access Routes Design | Load Bank - Platform and Foundations for Wartsila Load Bank - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Platform and Foundations | Wartsila Load Bank
6105A | K124 | 6251 | C | PPL | 0011 | A | 6105AK124-6251-CPPL-0011 | Q24050972-05-6251-C-PPL-0011 |  | Load Bank | Pad Platform and Foundations for Emergency Gen Load Bank | Operational & Maint Access Routes Design | Load Bank - Pad Platform and Foundations for Emergency Gen Load Bank - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Pad Platform and Foundations | Emergency Gen Load Bank
6105A | K124 | 6251 | C | SPC | 0047 | A | 6105AK124-6251-CSPC-0047 | Q24050972-05-6251-C-SPC-0047 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Excavation, Trenching and Compacting Design | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Excavation, Trenching and Compacting Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | SPC | 0048 | A | 6105AK124-6251-CSPC-0048 | Q24050972-05-6251-C-SPC-0048 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Concrete Construction Material Specifications | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Concrete Construction Material Specifications |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | C | STD | 0037 | A | 6105AK124-6251-CSTD-0037 | Q24050972-05-6251-C-STD-0037 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Underground Pipe Route and Cable Bedding Design | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Underground Pipe Route and Cable Bedding Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6251 | T | RPT | 0006 | A | 6105AK124-6251-TRPT-0006 | Q24050972-05-6251-T-RPT-0006 |  | Load Bank | Perimeter Fencing for Emergency Gen Load Bank | Site Surveying & Geotechnical Report | Load Bank - Perimeter Fencing for Emergency Gen Load Bank - Site Surveying & Geotechnical Report |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Perimeter Fencing | Emergency Gen Load Bank |  |  |  | Pending
6105A | K124 | 6253 | C | MDL | 0007 | A | 6105AK124-6253-CMDL-0007 | Q24050972-05-6253-C-MDL-0007 |  | Synchronous Condenser 1 | Offloading Equipment and Spreader Beam for Synchronous Condensers | 3D Designs and Drawings | Synchronous Condenser 1 - Offloading Equipment and Spreader Beam for Synchronous Condensers - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Synchronous Condensers |  |  |  | Pending
6105A | K124 | 6261 | C | GAD | 0038 | A | 6105AK124-6261-CGAD-0038 | Q24050972-05-6261-C-GAD-0038 |  | Administration and General Buildings | Offloading Equipment and Spreader Beam for Generators | Terrace Equipment GA | Administration and General Buildings - Offloading Equipment and Spreader Beam for Generators - Terrace Equipment GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Generators |  |  |  | Pending
6105A | K124 | 6261 | C | MDL | 0007 | A | 6105AK124-6261-CMDL-0007 | Q24050972-05-6261-C-MDL-0007 |  | Administration and General Buildings | Offloading Equipment and Spreader Beam for Generators | 3D Designs and Drawings | Administration and General Buildings - Offloading Equipment and Spreader Beam for Generators - 3D Designs and Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Generators |  |  |  | Pending
6105A | K124 | 6261 | C | PPL | 0006 | A | 6105AK124-6261-CPPL-0006 | Q24050972-05-6261-C-PPL-0006 |  | Administration and General Buildings | Offloading Equipment and Spreader Beam for Generators | Operational & Maint Access Routes Design | Administration and General Buildings - Offloading Equipment and Spreader Beam for Generators - Operational & Maint Access Routes Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Generators |  |  |  | Pending
6105A | K124 | 6261 | C | SHP | 0004 | A | 6105AK124-6261-CSHP-0004 | Q24050972-05-6261-C-SHP-0004 |  | Administration and General Buildings | Offloading Equipment and Spreader Beam for Generators | Equipment Assembly Drawings | Administration and General Buildings - Offloading Equipment and Spreader Beam for Generators - Equipment Assembly Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Generators |  |  |  | Pending
6105A | K124 | 6261 | C | SSD | 0002 | A | 6105AK124-6261-CSSD-0002 | Q24050972-05-6261-C-SSD-0002 |  | Administration and General Buildings | Offloading Equipment and Spreader Beam for Generators | Steel Support Structures Design | Administration and General Buildings - Offloading Equipment and Spreader Beam for Generators - Steel Support Structures Design |  |  | No Placeholder Yet | No Placeholder Yet | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Generators |  |  |  | Pending
6105A | K124 | 6261 | M | CAL | 0002 | A | 6105AK124-6261-MCAL-0002 | Q24050972-05-6261-M-CAL-0002 |  | Administration and General Buildings | Offloading Equipment and Spreader Beam for Generators | Vessel and Structure Design with Stress Analysis Calcs | Administration and General Buildings - Offloading Equipment and Spreader Beam for Generators - Vessel and Structure Design with Stress Analysis Calcs |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Generators |  |  |  | Pending
6105A | K124 | 6261 | M | SHP | 0001 | A | 6105AK124-6261-MSHP-0001 | Q24050972-05-6261-M-SHP-0001 |  | Administration and General Buildings | Offloading Equipment and Spreader Beam for Generators | Equipment Fabrication Drawings | Administration and General Buildings - Offloading Equipment and Spreader Beam for Generators - Equipment Fabrication Drawings |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Generators |  |  |  | Pending
6105A | K124 | 6261 | M | SPC | 0002 | A | 6105AK124-6261-MSPC-0002 | Q24050972-05-6261-M-SPC-0002 |  | Administration and General Buildings | Offloading Equipment and Spreader Beam for Generators | Lifting and Crawl Beam Design Specification | Administration and General Buildings - Offloading Equipment and Spreader Beam for Generators - Lifting and Crawl Beam Design Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Generators |  |  |  | Pending
6105A | K124 | 6261 | M | SPC | 0003 | A | 6105AK124-6261-MSPC-0003 | Q24050972-05-6261-M-SPC-0003 |  | Administration and General Buildings | Offloading Equipment and Spreader Beam for Generators | Material Selection and Verification Specification | Administration and General Buildings - Offloading Equipment and Spreader Beam for Generators - Material Selection and Verification Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Offloading Equipment and Spreader Beam | Generators |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0013 | A | 6105AK124-6263-ESTD-0013 | Q24050972-05-6263-E-STD-0013 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Electrical Equipment Installation Requirements | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station Fuel System Pad 1A | Electrical Equipment Installation Requirements |  |  |  | Pending
6105A | K124 | 6263 | E | STD | 0014 | A | 6105AK124-6263-ESTD-0014 | Q24050972-05-6263-E-STD-0014 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Electrical Equipment Installation Requirements | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Electrical Equipment Installation Requirements |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station Fuel System Pad 1B | Electrical Equipment Installation Requirements |  |  |  | Pending
6105A | K124 | 6264 | I | SPC | 0023 | A | 6105AK124-6264-ISPC-0023 | Q24050972-05-6264-I-SPC-0023 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Yard 1A | Emergency Shutdown System Design - Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Yard 1A - Emergency Shutdown System Design - Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip
6105A | K124 | 6264 | I | SPC | 0024 | A | 6105AK124-6264-ISPC-0024 | Q24050972-05-6264-I-SPC-0024 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1A | Emergency Shutdown System Design - Specification | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1A - Emergency Shutdown System Design - Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System
6105A | K124 | 6264 | I | SPC | 0025 | A | 6105AK124-6264-ISPC-0025 | Q24050972-05-6264-I-SPC-0025 |  | Bulk Diesel Storage 1 | Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B | Emergency Shutdown System Design - Specification | Bulk Diesel Storage 1 - Emergency Equip for Bulk Diesel Storage Fuel System Yard 1B - Emergency Shutdown System Design - Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Emergency Equip
6105A | K124 | 6264 | I | SPC | 0026 | A | 6105AK124-6264-ISPC-0026 | Q24050972-05-6264-I-SPC-0026 |  | Bulk Diesel Storage 1 | Fire Detection System for Bulk Diesel Storage Yard 1B | Emergency Shutdown System Design - Specification | Bulk Diesel Storage 1 - Fire Detection System for Bulk Diesel Storage Yard 1B - Emergency Shutdown System Design - Specification |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | Bulk Diesel Storage 1 | Fire Detection System
6105A | K124 | 6251 | C | GAD | 0095 | A | 6105AK124-6251-CGAD-0095 | Q24050972-05-6251-C-GAD-0095 |  | Load Bank | 36 MVA Power Station Mobile Load Bank Cable Racks | Cables, OHL and Fibre Route GA | Load Bank - 36 MVA Power Station Mobile Load Bank Cable Racks - Cables, OHL and Fibre Route GA |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Cables, OHL and Fibre Route GA
6105A | K124 | 6263 | I | SPC | 0007 | A | 6105AK124-6263-ISPC-0007 | Q24050972-05-6263-I-SPC-0007 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A | Emergency Shutdown System Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1A - Emergency Shutdown System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Emergency Equip
6105A | K124 | 6263 | I | SPC | 0008 | A | 6105AK124-6263-ISPC-0008 | Q24050972-05-6263-I-SPC-0008 |  | 36 MVA Power Station 1 | Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B | Emergency Shutdown System Design | 36 MVA Power Station 1 - Emergency Equip. for 36 MVA Power Station Fuel System Pad 1B - Emergency Shutdown System Design |  |  | RES - Reserved Placeholder | Pending | 0% | VV |  |  | 36 MVA Power Station | Emergency Equip
6105A | K124 | 6200 | E | LAY | 0007 | A | 6105AK124-6200-ELAY-0007 | Q24050972-05-6200-E-LAY-0007 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Underground Services Servitude Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Underground Services Servitude Layout |  |  | No Placeholder Yet | No Placeholder Yet | 0% | TDK |  | 2026-06-15 | Main Consumer Substation | Layout |  |  |  | Pending
6105A | K124 | 6200 | E | LAY | 0008 | A | 6105AK124-6200-ELAY-0008 | Q24050972-05-6200-E-LAY-0008 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Control Room Facility and Workshop Layout | On-Site Power Supply and Transmission - Main Consumer Substation - Control Room Facility and Workshop Layout |  |  | No Placeholder Yet | No Placeholder Yet | 0% | TDK |  | 2026-06-15 | Main Consumer Substation | Layout |  |  |  | Pending
6105A | K124 | 6200 | E | LAY | 0009 | A | 6105AK124-6200-ELAY-0009 | Q24050972-05-6200-E-LAY-0009 |  | On-Site Power Supply and Transmission | Main Consumer Substation | Pseudo-Color Illuminance Distribution Map | On-Site Power Supply and Transmission - Main Consumer Substation - Pseudo-Color Illuminance Distribution Map |  |  | No Placeholder Yet | No Placeholder Yet | 0% | TDK |  | 2026-06-15 | Main Consumer Substation | Layout |  |  |  | Pending
6105A | K124 | 6262 | C | LAY | 0001 | A | 6105AK124-6262-CLAY-0001 | Q24050972-06-6262-C-LAY-0001 |  | Emergency Power Substation 1 and Control Room 1 | Main Consumer Substation | Transformer Layout | Emergency Power Substation 1 and Control Room 1 - Main Consumer Substation - Transformer Layout |  |  | No Placeholder Yet | No Placeholder Yet | 0% | YB |  | 2026-06-30 | Main Consumer Substation | Transformer Layout |  |  |  | Pending
6105A | K124 | 6262 | C | LAY | 0002 | A | 6105AK124-6262-CLAY-0002 | Q24050972-06-6262-C-LAY-0002 |  | Emergency Power Substation 1 and Control Room 1 | Main Consumer Substation | 11kV E-house Layout | Emergency Power Substation 1 and Control Room 1 - Main Consumer Substation - 11kV E-house Layout |  |  | No Placeholder Yet | No Placeholder Yet | 0% | YB |  | 2026-06-30 | Main Consumer Substation | E-house Layout |  |  |  | Pending
6105A | K124 | 6262 | C | SEC | 0001 | A | 6105AK124-6262-CSEC-0001 | Q24050972-06-6262-C-SEC-0001 |  | Emergency Power Substation 1 and Control Room 1 | Main Consumer Substation | Transformer Section | Emergency Power Substation 1 and Control Room 1 - Main Consumer Substation - Transformer Section |  |  | No Placeholder Yet | No Placeholder Yet | 0% | YB |  | 2026-06-30 | Main Consumer Substation | Transformer Section |  |  |  | Pending
6105A | K124 | 6262 | C | SEC | 0002 | A | 6105AK124-6262-CSEC-0002 | Q24050972-06-6262-C-SEC-0002 |  | Emergency Power Substation 1 and Control Room 1 | Main Consumer Substation | 11kV E-house Section | Emergency Power Substation 1 and Control Room 1 - Main Consumer Substation - 11kV E-house Section |  |  | No Placeholder Yet | No Placeholder Yet | 0% | YB |  | 2026-06-30 | Main Consumer Substation | E-house Section |  |  |  | Pending
6105A | K124 | 6262 | C | DTL | 0001 | A | 6105AK124-6262-CDTL-0001 | Q24050972-06-6262-C-DTL-0001 |  | Emergency Power Substation 1 and Control Room 1 | Main Consumer Substation | Transformer Rebar Bending Schedule | Emergency Power Substation 1 and Control Room 1 - Main Consumer Substation - Transformer Rebar Bending Schedule |  |  | No Placeholder Yet | No Placeholder Yet | 0% | YB |  | 2026-06-30 | Main Consumer Substation | Transformer Detail |  |  |  | Pending
6105A | K124 | 6262 | C | DTL | 0002 | A | 6105AK124-6262-CDTL-0002 | Q24050972-06-6262-C-DTL-0002 |  | Emergency Power Substation 1 and Control Room 1 | Main Consumer Substation | 11kV E-house Detail | Emergency Power Substation 1 and Control Room 1 - Main Consumer Substation - 11kV E-house Detail |  |  | No Placeholder Yet | No Placeholder Yet | 0% | YB |  | 2026-06-30 | Main Consumer Substation | E-house Detail |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0057 | A | 6105AK124-6200-CGAD-0057 | Q24050972-06-6200-C-GAD-0057 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Stormwater Drainage | Stormwater and Effluent System Design | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Stormwater Drainage - Stormwater and Effluent System Design |  |  | No Placeholder Yet | No Placeholder Yet | 0% | VV |  |  | Main Consumer Sub Station | Stormwater Drainage |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0058 | A | 6105AK124-6200-CGAD-0058 | Q24050972-06-6200-C-GAD-0058 |  | On-Site Power Supply and Transmission | Main Consumer Sub Station Yard Underground Utility Piping | Pipe Routing General Arrangement | On-Site Power Supply and Transmission - Main Consumer Sub Station Yard Underground Utility Piping - Pipe Routing General Arrangement |  |  | No Placeholder Yet | No Placeholder Yet | 0% | VV |  |  | Main Consumer Sub Station | Underground Utility Piping |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0059 | A | 6105AK124-6200-CGAD-0059 | Q24050972-06-6200-C-GAD-0059 |  | On-Site Power Supply and Transmission | Perimeter Fencing and Access Control for Main Consumer Sub Station Yard | Roads, Pathways, Offloading Areas and Fences GA | On-Site Power Supply and Transmission - Perimeter Fencing and Access Control for Main Consumer Sub Station Yard - Roads, Pathways, Offloading Areas and Fences GA |  |  | No Placeholder Yet | No Placeholder Yet | 0% | VV |  |  | Main Consumer Sub Station | Perimeter Fencing and Access Control |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0060 | A | 6105AK124-6200-CGAD-0060 | Q24050972-06-6200-C-GAD-0060 |  | On-Site Power Supply and Transmission | Terrace Roads and Access-ways for Main Consumer SS | Roads, Pathways, Offloading Areas and Fences GA | On-Site Power Supply and Transmission - Terrace Roads and Access-ways for Main Consumer SS - Roads, Pathways, Offloading Areas and Fences GA |  |  | No Placeholder Yet | No Placeholder Yet | 0% | VV |  |  | Main Consumer SS | Terrace Roads and Access-ways |  |  |  | Pending
6105A | K124 | 6260 | E | PHL | 0001 | A | 6105AK124-6260-EPHL-0001 | Q24050972-06-6260-E-PHL-0001 |  | Emergency Power Generation (Main Plant) | Operating Philosophy of 11kV Emergency Diesel Generators | Primary Electrical Reticulation Network | Emergency Power Generation (Main Plant) - Operating Philosophy of 11kV Emergency Diesel Generators - Primary Electrical Reticulation Network |  |  | No Placeholder Yet | No Placeholder Yet | 0% | JC |  | 2026-06-30 | Operating Philosophy | 11kV Emergency Diesel Generators |  |  |  | Pending
6105A | K124 | 0100 | M | GAD | 0001 | A | 6105AK124-0100-MGAD-0001 | Q24050972-06-0100-M-GAD-0001 |  | Project Site Wide | Data Center | General Mechanical | Project Site Wide - Data Center - General Mechanical |  |  | No Placeholder Yet | No Placeholder Yet | 0% | LS |  | 2026-08-06 | Data Center | General Mechanical |  |  |  | Pending
6105A | K124 | 0100 | M | GAD | 0002 | A | 6105AK124-0100-MGAD-0002 | Q24050972-06-0100-M-GAD-0002 |  | Project Site Wide | Data Center | General Electrical | Project Site Wide - Data Center - General Electrical |  |  | No Placeholder Yet | No Placeholder Yet | 0% | LS |  | 2026-08-06 | Data Center | General Electrical |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0061 | A | 6105AK124-6200-CGAD-0061 | Q24050972-06-6200-C-GAD-0061 |  | On-Site Power Supply and Transmission | Control Room and Ablution Facilities for Main Consumer Sub Station Yard | Buildings and Structures GA | On-Site Power Supply and Transmission - Control Room and Ablution Facilities for Main Consumer Sub Station Yard - Buildings and Structures GA |  |  | No Placeholder Yet | No Placeholder Yet | 0% | VV |  |  | Main Consumer Sub Station Yard | Buildings and Structures |  |  |  | Pending
6105A | K124 | 6200 | B | PHL | 0003 | A | 6105AK124-6200-BPHL-0003 | Q24050972-06-6200-B-PHL-0003 |  | On-Site Power Supply and Transmission | Concentrator 33 kV Main Consumer SS Project Package | Control Philosophy | On-Site Power Supply and Transmission - Concentrator 33 kV Main Consumer SS Project Package - Control Philosophy |  |  | No Placeholder Yet | No Placeholder Yet | 0% | VV |  |  | Concentrator 33 kV Main Consumer | Control Philosophy |  |  |  | Pending
6105A | K124 | 6200 | B | PHL | 0004 | A | 6105AK124-6200-BPHL-0004 | Q24050972-06-6200-B-PHL-0004 |  | On-Site Power Supply and Transmission | Concentrator 33 kV Main Consumer SS Project Package | Synchronization Philosophy | On-Site Power Supply and Transmission - Concentrator 33 kV Main Consumer SS Project Package - Synchronization Philosophy |  |  | No Placeholder Yet | No Placeholder Yet | 0% | VV |  |  | Concentrator 33 kV Main Consumer | Synchronization Philosophy |  |  |  | Pending
6105A | K124 | 6200 | C | GAD | 0062 | A | 6105AK124-6200-CGAD-0062 | Q24050972-06-6200-C-GAD-0062 |  | On-Site Power Supply and Transmission | Cable Trench and Tunnels for Main Consumer Sub Station Yard | Cables, OHL and Fibre Route GA | On-Site Power Supply and Transmission - Cable Trench and Tunnels for Main Consumer Sub Station Yard - Cables, OHL and Fibre Route GA |  |  | No Placeholder Yet | No Placeholder Yet | 0% | VV |  |  | Main Consumer Sub Station Yard | Cables, OHL and Fibre Route GA |  |  |  | Pending
6105A | K124 | 0000 | G | RPT | 0026 | 0 | 6105AK124-0000-GRPT-0026 | Q24050972-04-0000-G-RPT-0026 |  | General | Cost Flow Forecast - June 2026 | Report | General - Cost Flow Forecast - June 2026 - Report |  |  | No Placeholder Yet | No Placeholder Yet | 0% | LC |  | 2026-06-29 | Cost Forecast Basis | General |  |  |  | Pending

## PPE WBS Codes
L1 | L2 | L3 | L4 | Code | Reko Diq Copper - Gold Project Facility Name
0 | 0 | 0 | 0 | 0000 | General | 0000 - General
0 | 1 | 0 | 0 | 0100 | Project Site Wide | 0100 - Project Site Wide
5 | 3 | 5 | 0 | 5350 | Process Water Dams | 5350 - Process Water Dams
5 | 3 | 6 | 0 | 5360 | Raw Water Dams | 5360 - Raw Water Dams
5 | 3 | 7 | 0 | 5370 | Turkey Nests | 5370 - Turkey Nests
5 | 5 | 3 | 0 | 5530 | Village Sewage | 5530 - Village Sewage
5 | 6 | 3 | 0 | 5630 | Potable Water Treatment | 5630 - Potable Water Treatment
6 | 1 | 8 | 0 | 6180 | Village | 6180 - Village
6 | 1 | 8 | 1 | 6181 | Accommodation | 6181 - Accommodation
6 | 1 | 8 | 2 | 6182 | Mess Hall and Food Storage | 6182 - Mess Hall and Food Storage
6 | 1 | 8 | 3 | 6183 | Leisure Amenities | 6183 - Leisure Amenities
6 | 1 | 8 | 4 | 6184 | Laundry Facilities | 6184 - Laundry Facilities
6 | 1 | 8 | 5 | 6185 | Potable Water and Water Treatment | 6185 - Potable Water and Water Treatment
6 | 1 | 8 | 6 | 6186 | Firewater - Tank & Fire Fighting System | 6186 - Firewater - Tank & Fire Fighting System
6 | 1 | 8 | 7 | 6187 | Support Facilities - Diesel Generators | 6187 - Support Facilities - Diesel Generators
6 | 1 | 8 | 8 | 6188 | Underground Services - Sewage Treatment | 6188 - Underground Services - Sewage Treatment
6 | 1 | 8 | 9 | 6189 | Common Facilities and Services | 6189 - Common Facilities and Services
6 | 2 | 0 | 0 | 6200 | On-Site Power Supply and Transmission | 6200 - On-Site Power Supply and Transmission
6 | 2 | 1 | 0 | 6210 | Power Stations | 6210 - Power Stations
6 | 2 | 1 | 2 | 6212 | Power Station 1 | 6212 - Power Station 1
6 | 2 | 3 | 0 | 6230 | High Voltage (220 kV) Transmission Lines | 6230 - High Voltage (220 kV) Transmission Lines
6 | 2 | 4 | 0 | 6240 | High Voltage Substations | 6240 - High Voltage Substations
6 | 2 | 4 | 1 | 6241 | 33/220 kV Solar PV Substation | 6241 - 33/220 kV Solar PV Substation
6 | 2 | 4 | 2 | 6242 | 33/220 kV Power Station Substation | 6242 - 33/220 kV Power Station Substation
6 | 2 | 4 | 3 | 6243 | 220/33 kV Plant Main Substation | 6243 - 220/33 kV Plant Main Substation
6 | 2 | 5 | 0 | 6250 | Power Conditioning Equipment | 6250 - Power Conditioning Equipment
6 | 2 | 5 | 1 | 6251 | Load Bank | 6251 - Load Bank
6 | 2 | 5 | 2 | 6252 | Harmonic Filters 1 | 6252 - Harmonic Filters 1
6 | 2 | 5 | 3 | 6253 | Synchronous Condenser 1 | 6253 - Synchronous Condenser 1
6 | 2 | 5 | 4 | 6254 | Battery Energy Storage System 1 | 6254 - Battery Energy Storage System 1
6 | 2 | 5 | 5 | 6255 | Harmonic Filters 2 | 6255 - Harmonic Filters 2
6 | 2 | 5 | 6 | 6256 | Synchronous Condenser 2 | 6256 - Synchronous Condenser 2
6 | 2 | 5 | 7 | 6257 | Battery Energy Storage System 2 | 6257 - Battery Energy Storage System 2
6 | 2 | 6 | 0 | 6260 | Emergency Power Generation (Main Plant) | 6260 - Emergency Power Generation (Main Plant)
6 | 2 | 6 | 1 | 6261 | Administration and General Buildings | 6261 - Administration and General Buildings
6 | 2 | 6 | 2 | 6262 | Emergency Power Substation 1 and Control Room 1 | 6262 - Emergency Power Substation 1 and Control Room 1
6 | 2 | 6 | 3 | 6263 | 36 MVA Power Station 1 | 6263 - 36 MVA Power Station 1
6 | 2 | 6 | 4 | 6264 | Bulk Diesel Storage 1 | 6264 - Bulk Diesel Storage 1
6 | 2 | 6 | 5 | 6265 | Truck Diesel Unloading and Power Station 1 | 6265 - Truck Diesel Unloading and Power Station 1
6 | 2 | 6 | 6 | 6266 | Emergency Power Substation 2 and Control Room 2 | 6266 - Emergency Power Substation 2 and Control Room 2
6 | 2 | 6 | 7 | 6267 | 36 MVA Power Station 2 | 6267 - 36 MVA Power Station 2
6 | 2 | 6 | 8 | 6268 | Bulk Diesel Storage 2 | 6268 - Bulk Diesel Storage 2
6 | 2 | 6 | 9 | 6269 | Truck Diesel Unloading and Power Station 2 | 6269 - Truck Diesel Unloading and Power Station 2
6 | 2 | 8 | 0 | 6280 | Medium Voltage (33 kV) Overhead Powerlines | 6280 - Medium Voltage (33 kV) Overhead Powerlines
6 | 2 | 8 | 1 | 6281 | Booster Pump Station and Borefields | 6281 - Booster Pump Station and Borefields
6 | 2 | 8 | 2 | 6282 | Potable Water Treatment Plant | 6282 - Potable Water Treatment Plant
6 | 2 | 8 | 3 | 6283 | Sewage Treatment Plant | 6283 - Sewage Treatment Plant
6 | 2 | 8 | 4 | 6284 | Village | 6284 - Village
6 | 2 | 8 | 5 | 6285 | Mining Open Pit | 6285 - Mining Open Pit
6 | 2 | 8 | 6 | 6286 | Primary Crushing | 6286 - Primary Crushing
6 | 2 | 8 | 7 | 6287 | Tailings Storage Facility | 6287 - Tailings Storage Facility
6 | 2 | 8 | 8 | 6288 | Rail Offloading Facility | 6288 - Rail Offloading Facility
6 | 2 | 8 | 9 | 6289 | Explosive Magazine / Emulsion Facility | 6289 - Explosive Magazine / Emulsion Facility
6 | 2 | 9 | 0 | 6290 | Renewable Energy | 6290 - Renewable Energy
6 | 2 | 9 | 1 | 6291 | Administration and General Buildings | 6291 - Administration and General Buildings
6 | 2 | 9 | 2 | 6292 | 11/33 kV Solar PV Substation 1 and Control Room 1 | 6292 - 11/33 kV Solar PV Substation 1 and Control Room 1
6 | 2 | 9 | 3 | 6293 | Power Station 1 Photovoltaic Array, Inverters, and Transformers | 6293 - Power Station 1 Photovoltaic Array, Inverters, and Transformers
7 | 1 | 7 | 7 | 7177 | Off-Site Fan Sediments Bore Field 13 | 7177 - Off-Site Fan Sediments Bore Field 13
7 | 1 | 7 | 7 | 7177 | Off-Site Fan Sediments Bore Field 41 | 7177 - Off-Site Fan Sediments Bore Field 41
7 | 1 | 7 | 9 | 7179 | Off-Site Borehole Fieldwater Pipeline - Fan Sediments Construction Line | 7179 - Off-Site Borehole Fieldwater Pipeline - Fan Sediments Construction Line
9 | 1 | 2 | 0 | 9120 | Temporary Facilities | 9120 - Temporary Facilities
9 | 1 | 2 | 1 | 9121 | Offices and Support Buildings | 9121 - Offices and Support Buildings
9 | 1 | 2 | 2 | 9122 | Warehouse and Yards | 9122 - Warehouse and Yards
9 | 1 | 2 | 3 | 9123 | Shelters | 9123 - Shelters
9 | 1 | 2 | 4 | 9124 | Power Generation | 9124 - Power Generation
9 | 1 | 2 | 5 | 9125 | Aggregate and Concrete | 9125 - Aggregate and Concrete
9 | 1 | 2 | 6 | 9126 | Water System | 9126 - Water System
9 | 1 | 2 | 7 | 9127 | Fuel Stations | 9127 - Fuel Stations
9 | 1 | 3 | 0 | 9130 | Temporary Services | 9130 - Temporary Services
9 | 1 | 3 | 1 | 9131 | Power | 9131 - Power
9 | 1 | 3 | 2 | 9132 | Maintenance and Cleanup | 9132 - Maintenance and Cleanup
9 | 1 | 3 | 3 | 9133 | Personnel Transportation | 9133 - Personnel Transportation
9 | 1 | 3 | 4 | 9134 | Survey, Inspection, and Quality Control | 9134 - Survey, Inspection, and Quality Control
9 | 1 | 3 | 5 | 9135 | Medical and Security | 9135 - Medical and Security
9 | 1 | 3 | 6 | 9136 | Heating | 9136 - Heating
9 | 1 | 3 | 7 | 9137 | Fuel Supply | 9137 - Fuel Supply
9 | 1 | 3 | 8 | 9138 | Water, Sewage, and Waste Disposal | 9138 - Water, Sewage, and Waste Disposal
7 | 3 | 3 | 7 | 7337 | Port Qasim PIBT Control Room | 7337 - Port Qasim PIBT Control Room

## Rev10 RDMC WBS Areas
| Facility Level ID |  |  | Facility Code | Reko Diq Project Facility Name | Engineering | Procurement | Contracts | Construction Management
L1 | L2 | L3 | L4
0 | 0 | 0 | 0 | 0 | General | - | - | - | -
0 | 1 | 0 | 0 | 100 | Project Site Wide | - | - | - | -
1 | 0 | 0 | 0 | 1000 | Mining - OP | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
1 | 1 | 0 | 0 | 1100 | Open Pit Mine | RDMC/Fluo r | RDMC/Fluo r | RDMC/Fluo r | RDMC/Fluo r
1 | 1 | 1 | 0 | 1110 | Open Pit Mine Development | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 1 | 1111 | Pre-Stripping | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 2 | 1112 | Stockpiling | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 3 | 1113 | Waste Dumps | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 4 | 1114 | Run-of-Mine Pad | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 5 | 1115 | Clearing, Grubbing and Topsoil Stockpiling | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 9 | 1119 | Common Facilities and Services | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 0 | 1120 | Open Pit Mining Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 1 | 1121 | Drilling Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 2 | 1122 | Loading Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 3 | 1123 | Hauling Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 4 | 1124 | Support Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 5 | 1125 | Maintenance Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 3 | 0 | 1130 | Infrastructure | RDMC/Fluor/PPE | RDMC/Fluor/PPE | RDMC/Fluor/PPE | RDMC/Fluor/PPE
1 | 1 | 3 | 1 | 1131 | Haul Roads | RDMC | RDMC | RDMC | RDMC
1 | 1 | 3 | 2 | 1132 | Pioneering | RDMC | RDMC | RDMC | RDMC
1 | 1 | 3 | 3 | 1133 | Dewatering | Fluor | Fluor | Fluor | Fluor
1 | 1 | 3 | 4 | 1134 | Trailing Cables and Shovel Reticulation | PPE | PPE | PPE | PPE
1 | 1 | 3 | 7 | 1137 | Planning and Exploration | RDMC | RDMC | RDMC | RDMC
1 | 1 | 3 | 9 | 1139 | Common Facilities and Services | Fluor/PPE | Fluor/PPE | Fluor/PPE | Fluor/PPE
1 | 1 | 8 | 0 | 1180 | Explosives Plant, Magazine and Storage | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 1 | 1181 | Explosives and Detonator Magazines | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 2 | 1182 | Manufacturing Plant | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 3 | 1183 | Raw Materials Warehouse | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 4 | 1184 | Ammonium Nitrate Warehouse | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 5 | 1185 | Office and Dry Mess | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 6 | 1186 | Change Room and Ablutions | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 7 | 1187 | Workshop | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 8 | 1188 | Washdown Facility | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 9 | 1189 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 0 | 0 | 1200 | Mine Infrastructure Area and Services | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
1 | 2 | 1 | 0 | 1210 | Site Preparation | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
1 | 2 | 1 | 1 | 1211 | Bulk Earthworks | Fluor | Fluor | Fluor | Fluor
1 | 2 | 1 | 2 | 1212 | Drainage and Culverts | Fluor | Fluor | Fluor | Fluor
1 | 2 | 1 | 3 | 1213 | Improvements | Fluor | Fluor | Fluor | Fluor
1 | 2 | 1 | 4 | 1214 | Security Fencing | RDMC | RDMC | RDMC | RDMC
1 | 2 | 2 | 0 | 1220 | Roads and Paving | Fluor | Fluor | Fluor | Fluor
1 | 2 | 2 | 1 | 1221 | In-Plant Roads | Fluor | Fluor | Fluor | Fluor
1 | 2 | 2 | 2 | 1222 | Carparks and Hardstand Areas | Fluor | Fluor | Fluor | Fluor
1 | 2 | 3 | 0 | 1230 | Central Facilities | Fluor | Fluor | Fluor | Fluor
1 | 2 | 3 | 1 | 1231 | Administration Buildings | Fluor | Fluor | Fluor | Fluor
1 | 2 | 3 | 2 | 1232 | Change Rooms and Ablution Blocks | Fluor | Fluor | Fluor | Fluor
1 | 2 | 3 | 9 | 1239 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 0 | 1240 | Heavy Equipment Maintenance Facilities | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 1 | 1241 | Preventive Maintenance Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 2 | 1242 | Utilities Area | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 3 | 1243 | Repair Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 4 | 1244 | Tyre Storage and Change | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 5 | 1245 | Washdown Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 6 | 1246 | Warehouse | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 7 | 1247 | Fabrication Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 8 | 1248 | Assembly Area | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 9 | 1249 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 0 | 1250 | Light Vehicle Equipment Maintenance Facilities | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 1 | 1251 | Preventive Maintenance Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 2 | 1252 | Hydraulics and Electrical Repair Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 3 | 1253 | Repair/Rebuild Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 4 | 1254 | Tyre Storage and Change | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 5 | 1255 | Washdown Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 6 | 1256 | Warehouse | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 8 | 1258 | Laydown Area | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 9 | 1259 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 0 | 1260 | Water and Waste Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 1 | 1261 | Raw Water Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 2 | 1262 | Fire Water Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 3 | 1263 | Potable Water Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 4 | 1264 | Waste Water Disposal | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 5 | 1265 | Sewage Effluent Disposal | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 6 | 1266 | Raw Water Distribution | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 7 | 1267 | Firewater Distribution | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 8 | 1268 | Potable Water Distribution | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 9 | 1269 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 7 | 0 | 1270 | Power, Communications and Security Systems | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
1 | 2 | 7 | 1 | 1271 | Light Vehicle Power Supply and Distribution | Fluor | Fluor | Fluor | Fluor
1 | 2 | 7 | 2 | 1272 | Communication | Fluor | Fluor | Fluor | Fluor
1 | 2 | 7 | 3 | 1273 | Mine Dispatch | RDMC | RDMC | RDMC | RDMC
1 | 2 | 7 | 4 | 1274 | Security | RDMC | RDMC | RDMC | RDMC
1 | 2 | 7 | 9 | 1279 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 0 | 1280 | Compressed Air Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 1 | 1281 | Compression | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 2 | 1282 | Wet Receiving | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 3 | 1283 | Drying | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 4 | 1284 | Dry Receiving | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 5 | 1285 | Distribution | - | - | - | -
1 | 2 | 8 | 9 | 1289 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 0 | 1290 | Fuel and Lubrication Storage and Reticulation | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 1 | 1291 | Diesel Bulk Storage Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 2 | 1292 | Central Refuelling Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 3 | 1293 | Remote Refuelling Bay 1 | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 4 | 1294 | Remote Refuelling Bay 2 | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 5 | 1295 | Remote Refuelling Bay 3 | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 6 | 1296 | Heavy Vehicle Lube Unloading and Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 7 | 1297 | Light Vehicle Refuelling Area | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 8 | 1298 | Light Vehicle Lube Unloading and Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 9 | 1299 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
2 | 0 | 0 | 0 | 2000 | Mining - Underground | - | - | - | -
2 | 1 | 0 | 0 | 2100 | Underground Mine | - | - | - | -
2 | 1 | 1 | 0 | 2110 | Mine Development | - | - | - | -
2 | 1 | 1 | 1 | 2111 | Access Development | - | - | - | -
2 | 1 | 1 | 2 | 2112 | Mine Stockpiling | - | - | - | -
2 | 1 | 1 | 3 | 2113 | Waste Dumps | - | - | - | -
2 | 1 | 1 | 4 | 2114 | Level Access Development | - | - | - | -
2 | 1 | 1 | 5 | 2115 | Haulage Development | - | - | - | -
2 | 1 | 1 | 6 | 2116 | Reef Development | - | - | - | -
2 | 1 | 1 | 7 | 2117 | Raw | - | - | - | -
2 | 1 | 2 | 0 | 2120 | Underground Mining Equipment | - | - | - | -
2 | 1 | 2 | 1 | 2121 | Drilling Equipment | - | - | - | -
2 | 1 | 2 | 2 | 2122 | Loading Equipment | - | - | - | -
2 | 1 | 2 | 3 | 2123 | Hauling Equipment | - | - | - | -
2 | 1 | 2 | 4 | 2124 | Support Equipment | - | - | - | -
2 | 1 | 2 | 5 | 2125 | Mine Maintenance Equipment | - | - | - | -
2 | 1 | 2 | 6 | 2126 | Underground Communication | - | - | - | -
2 | 1 | 2 | 7 | 2127 | Reinforcements | - | - | - | -
2 | 1 | 2 | 8 | 2128 | Control and Instrumentation | - | - | - | -
2 | 1 | 3 | 0 | 2130 | Underground Mine Infrastructure | - | - | - | -
2 | 1 | 3 | 1 | 2131 | Mine Roads | - | - | - | -
2 | 1 | 3 | 2 | 2132 | Development | - | - | - | -
2 | 1 | 3 | 3 | 2133 | Dewatering | - | - | - | -
2 | 1 | 3 | 4 | 2134 | Truck Shop | - | - | - | -
2 | 1 | 3 | 5 | 2135 | Explosive Magazine | - | - | - | -
2 | 1 | 3 | 6 | 2136 | Mine Stockpiling Platforms | - | - | - | -
2 | 1 | 3 | 7 | 2137 | Timber Preparation Facilities | - | - | - | -
2 | 1 | 3 | 8 | 2138 | Mine Facilities and Services | - | - | - | -
2 | 1 | 3 | 9 | 2139 | Planning and Exploration | - | - | - | -
2 | 1 | 4 | 0 | 2140 | Underground Mine Shaft | - | - | - | -
2 | 1 | 4 | 1 | 2141 | Shaft Development | - | - | - | -
2 | 1 | 4 | 2 | 2142 | Head Frame | - | - | - | -
2 | 1 | 4 | 3 | 2143 | Hoisting | - | - | - | -
2 | 1 | 5 | 0 | 2150 | Ventilation and Services | - | - | - | -
2 | 1 | 5 | 1 | 2151 | Ventilation Shafts | - | - | - | -
2 | 1 | 5 | 2 | 2152 | Ventilation Fans and Equipment | - | - | - | -
2 | 1 | 5 | 3 | 2153 | Refrigeration | - | - | - | -
2 | 1 | 5 | 4 | 2154 | Compressed Air Plant | - | - | - | -
2 | 1 | 6 | 0 | 2160 | Underground Material Handling | - | - | - | -
2 | 1 | 6 | 1 | 2161 | Ore and Waste Passes | - | - | - | -
2 | 1 | 6 | 2 | 2162 | Underground Crushing | - | - | - | -
2 | 1 | 6 | 3 | 2163 | Underground Conveying | - | - | - | -
3 | 0 | 0 | 0 | 3000 | Dry Plant | Fluor | Fluor | Fluor | Fluor
3 | 1 | 0 | 0 | 3100 | Primary Crushing | Fluor | Fluor | Fluor | Fluor
3 | 1 | 1 | 0 | 3110 | Crushers | Fluor | Fluor | Fluor | Fluor
3 | 1 | 1 | 1 | 3111 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 1 | 2 | 3112 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 2 | 0 | 3120 | Truck Dump Pad | Fluor | Fluor | Fluor | Fluor
3 | 1 | 2 | 1 | 3121 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 2 | 2 | 3122 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 3 | 0 | 3130 | Chamber | Fluor | Fluor | Fluor | Fluor
3 | 1 | 3 | 1 | 3131 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 3 | 2 | 3132 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 4 | 0 | 3140 | Tunnel | Fluor | Fluor | Fluor | Fluor
3 | 1 | 4 | 1 | 3141 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 4 | 2 | 3142 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 5 | 0 | 3150 | Crusher Discharge Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 1 | 5 | 1 | 3151 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 5 | 2 | 3152 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 6 | 0 | 3160 | Transfer Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 1 | 6 | 2 | 3162 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 9 | 0 | 3190 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 1 | 9 | 7 | 3197 | Dust Control | Fluor | Fluor | Fluor | Fluor
3 | 1 | 9 | 8 | 3198 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 1 | 9 | 9 | 3199 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 2 | 0 | 0 | 3200 | Coarse Ore Transport | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 0 | 3210 | Stockpile Feed | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 1 | 3211 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 2 | 3212 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 3 | 3213 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 4 | 3214 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 5 | 3215 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 2 | 9 | 0 | 3290 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 2 | 9 | 7 | 3297 | Dust Control | Fluor | Fluor | Fluor | Fluor
3 | 2 | 9 | 8 | 3298 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 2 | 9 | 9 | 3299 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 3 | 0 | 0 | 3300 | Coarse Ore Storage & Reclaim | Fluor | Fluor | Fluor | Fluor
3 | 3 | 1 | 0 | 3310 | Base Pad | Fluor | Fluor | Fluor | Fluor
3 | 3 | 2 | 0 | 3320 | Chamber | Fluor | Fluor | Fluor | Fluor
3 | 3 | 3 | 0 | 3330 | Tunnel | Fluor | Fluor | Fluor | Fluor
3 | 3 | 3 | 1 | 3331 | Reclaim | Fluor | Fluor | Fluor | Fluor
3 | 3 | 3 | 2 | 3332 | Escape | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 0 | 3340 | Coarse Ore Reclaim | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 1 | 3341 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 2 | 3342 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 3 | 3343 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 4 | 3344 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 5 | 3345 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 3 | 9 | 0 | 3390 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 3 | 9 | 7 | 3397 | Dust Control | Fluor | Fluor | Fluor | Fluor
3 | 3 | 9 | 8 | 3398 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 3 | 9 | 9 | 3399 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 4 | 0 | 0 | 3400 | Coarse Ore Screening and Transport | Fluor | Fluor | Fluor | Fluor
3 | 4 | 1 | 0 | 3410 | Screening | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 0 | 3420 | Coarse Ore Screen Oversize | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 1 | 3421 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 2 | 3422 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 3 | 3423 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 4 | 3424 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 5 | 3425 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 0 | 3430 | Coarse Ore Screen Undersize | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 1 | 3431 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 2 | 3432 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 3 | 3433 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 4 | 3434 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 5 | 3435 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 0 | 3440 | HPGR Feed | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 1 | 3441 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 2 | 3442 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 3 | 3443 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 4 | 3444 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 5 | 3445 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 9 | 0 | 3490 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 4 | 9 | 7 | 3497 | Dust Control | Fluor | Fluor | Fluor | Fluor
3 | 4 | 9 | 8 | 3498 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 4 | 9 | 9 | 3499 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 5 | 0 | 0 | 3500 | Secondary Crushing | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 0 | 3520 | Secondary Crushing | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 1 | 3521 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 2 | 3522 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 3 | 3523 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 4 | 3524 | Train 4 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 5 | 3525 | Train 5 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 9 | 0 | 3590 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 5 | 9 | 7 | 3597 | Dust collection | Fluor | Fluor | Fluor | Fluor
3 | 5 | 9 | 8 | 3598 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 5 | 9 | 9 | 3599 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 6 | 0 | 0 | 3600 | Tertiary Crushing | Fluor | Fluor | Fluor | Fluor
3 | 6 | 1 | 0 | 3610 | High Pressure Grinding | Fluor | Fluor | Fluor | Fluor
3 | 6 | 1 | 1 | 3611 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 6 | 1 | 2 | 3612 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 6 | 1 | 3 | 3613 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 0 | 3620 | Fine Ore Storage Feed | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 1 | 3621 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 2 | 3622 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 3 | 3623 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 4 | 3624 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 5 | 3625 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 6 | 9 | 0 | 3690 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 6 | 9 | 7 | 3697 | Dust Collection | Fluor | Fluor | Fluor | Fluor
3 | 6 | 9 | 8 | 3698 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 6 | 9 | 9 | 3699 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 7 | 0 | 0 | 3700 | Fine Ore | Fluor | Fluor | Fluor | Fluor
3 | 7 | 1 | 0 | 3710 | Storage Bins | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 0 | 3720 | Reclaim Feeders | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 1 | 3721 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 2 | 3722 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 3 | 3723 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 4 | 3724 | Train 4 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 5 | 3725 | Train 5 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 6 | 3726 | Train 6 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 0 | 3730 | Screen Conveyors | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 1 | 3731 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 2 | 3732 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 3 | 3733 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 4 | 3734 | Train 4 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 5 | 3735 | Train 5 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 6 | 3736 | Train 6 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 0 | 3740 | Screens | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 1 | 3741 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 2 | 3742 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 3 | 3743 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 4 | 3744 | Train 4 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 5 | 3745 | Train 5 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 6 | 3746 | Train 6 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 0 | 3750 | Screen Oversize | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 1 | 3751 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 2 | 3752 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 3 | 3753 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 4 | 3754 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 5 | 3755 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 7 | 9 | 0 | 3790 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 7 | 9 | 7 | 3797 | Dust Collection | Fluor | Fluor | Fluor | Fluor
3 | 7 | 9 | 8 | 3798 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 7 | 9 | 9 | 3799 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 8 | 0 | 0 | 3800 | HPGR Oversize | Fluor | Fluor | Fluor | Fluor
3 | 8 | 1 | 0 | 3810 | Surge Bin | Fluor | Fluor | Fluor | Fluor
3 | 8 | 2 | 0 | 3820 | Reclaim Feeder | Fluor | Fluor | Fluor | Fluor
3 | 8 | 3 | 0 | 3830 | Reclaim Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 0 | 3840 | Surge Bin Overflow | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 1 | 3841 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 2 | 3842 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 3 | 3843 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 4 | 3844 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 5 | 3845 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 8 | 5 | 0 | 3850 | Dead Stockpile | Fluor | Fluor | Fluor | Fluor
3 | 8 | 9 | 0 | 3890 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 8 | 9 | 8 | 3898 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 8 | 9 | 9 | 3899 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 0 | 0 | 0 | 4000 | Wet Plant | Fluor | Fluor | Fluor | Fluor
4 | 1 | 0 | 0 | 4100 | Grinding and Classification | Fluor | Fluor | Fluor | Fluor
4 | 1 | 1 | 0 | 4110 | Grinding | Fluor | Fluor | Fluor | Fluor
4 | 1 | 1 | 1 | 4111 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 1 | 2 | 4112 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 1 | 3 | 4113 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 3 | 0 | 4130 | Classification | Fluor | Fluor | Fluor | Fluor
4 | 1 | 3 | 1 | 4131 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 3 | 2 | 4132 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 3 | 3 | 4133 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 4 | 0 | 4140 | Flash Flotation (future) | Future | Future | Future | Future
4 | 1 | 5 | 0 | 4150 | Gravity Gold Recovery (future) | Future | Future | Future | Future
4 | 1 | 6 | 0 | 4160 | Gold Room (future) | Future | Future | Future | Future
4 | 1 | 7 | 0 | 4170 | Reagent Distribution | Fluor | Fluor | Fluor | Fluor
4 | 1 | 8 | 0 | 4180 | Media Handling | Fluor | Fluor | Fluor | Fluor
4 | 1 | 8 | 1 | 4181 | Ball Unloading | Fluor | Fluor | Fluor | Fluor
4 | 1 | 8 | 2 | 4182 | Ball Storage | Fluor | Fluor | Fluor | Fluor
4 | 1 | 8 | 3 | 4183 | Ball Conveying | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 0 | 4190 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 1 | 4191 | Grinding Train 1 Cooling Water | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 2 | 4192 | Grinding Train 2 Cooling Water | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 3 | 4193 | Grinding Train 3 Cooling Water | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 8 | 4198 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 9 | 4199 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 2 | 0 | 0 | 4200 | Copper Rougher Processing | Fluor | Fluor | Fluor | Fluor
4 | 2 | 1 | 0 | 4210 | Surge and Conditioning | Fluor | Fluor | Fluor | Fluor
4 | 2 | 1 | 1 | 4211 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 1 | 2 | 4212 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 1 | 3 | 4213 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 3 | 0 | 4230 | Flotation | Fluor | Fluor | Fluor | Fluor
4 | 2 | 3 | 1 | 4231 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 3 | 2 | 4232 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 3 | 3 | 4233 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 0 | 4240 | Concentrate Regrinding | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 1 | 4241 | Stage 1 Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 2 | 4242 | Stage 1 Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 3 | 4243 | Stage 1 Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 4 | 4244 | Stage 1 Train 4 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 5 | 4245 | Stage 2 Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 6 | 4246 | Stage 2 Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 7 | 4247 | Stage 2 Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 8 | 4248 | Stage 2 Train 4 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 5 | 0 | 4250 | Concentrate Regrind Media Handling | Fluor | Fluor | Fluor | Fluor
4 | 2 | 5 | 5 | 4255 | Stage 2 Header | Fluor | Fluor | Fluor | Fluor
4 | 2 | 5 | 6 | 4256 | Stage 2 Dewatering | Fluor | Fluor | Fluor | Fluor
4 | 2 | 5 | 7 | 4257 | Stage 2 Recirculation | Fluor | Fluor | Fluor | Fluor
4 | 2 | 6 | 0 | 4260 | Tailings Collection | Fluor | Fluor | Fluor | Fluor
4 | 2 | 6 | 1 | 4261 | Tank | Fluor | Fluor | Fluor | Fluor
4 | 2 | 6 | 2 | 4262 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 2 | 7 | 0 | 4270 | Reagent Distribution (not used) | Fluor | Fluor | Fluor | Fluor
4 | 2 | 8 | 0 | 4280 | Sampling and Analysis | Fluor | Fluor | Fluor | Fluor
4 | 2 | 8 | 1 | 4281 | On-Stream Analyser 1 | - | - | - | -
4 | 2 | 8 | 2 | 4282 | On-Stream Analyser 2 | - | - | - | -
4 | 2 | 8 | 3 | 4283 | Stage 1 Train 1/2 Mill Product | - | - | - | -
4 | 2 | 8 | 4 | 4284 | Stage 1 Train 3/4 Mill Product | - | - | - | -
4 | 2 | 8 | 5 | 4285 | Stage 2 Train 1/2 Cyclone Overflow | - | - | - | -
4 | 2 | 8 | 6 | 4286 | Stage 2 train 1/2 Cyclone Overflow | - | - | - | -
4 | 2 | 8 | 7 | 4287 | Stage 2 Train 1/2 Mill Product | - | - | - | -
4 | 2 | 8 | 8 | 4288 | Stage 2 Train 3/4 Mill Product | - | - | - | -
4 | 2 | 9 | 0 | 4290 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 2 | 9 | 8 | 4298 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 2 | 9 | 9 | 4299 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 3 | 0 | 0 | 4300 | Copper Cleaner Processing | Fluor | Fluor | Fluor | Fluor
4 | 3 | 2 | 0 | 4320 | Aeration | Fluor | Fluor | Fluor | Fluor
4 | 3 | 2 | 1 | 4321 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 2 | 2 | 4322 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 2 | 3 | 4323 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 3 | 0 | 4330 | Conditioning | Fluor | Fluor | Fluor | Fluor
4 | 3 | 3 | 1 | 4331 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 3 | 2 | 4332 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 3 | 3 | 4333 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 4 | 0 | 4340 | First Cleaner Flotation - Scalper Flotation | Fluor | Fluor | Fluor | Fluor
4 | 3 | 4 | 1 | 4341 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 4 | 2 | 4342 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 4 | 3 | 4343 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 5 | 0 | 4350 | Second Cleaner Flotation - Scavenger Conditioning and Flotation | Fluor | Fluor | Fluor | Fluor
4 | 3 | 5 | 1 | 4351 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 5 | 2 | 4352 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 5 | 3 | 4353 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 6 | 0 | 4360 | Third Cleaner Flotation - Recleaner Conditioning and Flotation | Fluor | Fluor | Fluor | Fluor
4 | 3 | 6 | 1 | 4361 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 6 | 2 | 4362 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 6 | 3 | 4363 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 8 | 0 | 4380 | Sampling and Analysis | Fluor | Fluor | Fluor | Fluor
4 | 3 | 8 | 1 | 4381 | On-Stream Analyser 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 8 | 2 | 4382 | On-Stream Analyser 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 8 | 3 | 4383 | On-Stream Analyser 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 9 | 0 | 4390 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 3 | 9 | 8 | 4398 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 3 | 9 | 9 | 4399 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 4 | 0 | 0 | 4400 | Coarse Particle Processing (future) | Future | Future | Future | Future
4 | 4 | 1 | 0 | 4410 | Feed Classification (future) | Future | Future | Future | Future
4 | 4 | 1 | 1 | 4411 | Train 1 (future) | Future | Future | Future | Future
4 | 4 | 1 | 2 | 4412 | Train 2 (future) | Future | Future | Future | Future
4 | 4 | 1 | 3 | 4413 | Train 3 (future) | Future | Future | Future | Future
4 | 4 | 2 | 0 | 4420 | Conditioning (future) | Future | Future | Future | Future
4 | 4 | 2 | 1 | 4421 | Train 1 (future) | Future | Future | Future | Future
4 | 4 | 2 | 2 | 4422 | Train 2 (future) | Future | Future | Future | Future
4 | 4 | 2 | 3 | 4423 | Train 3 (future) | Future | Future | Future | Future
4 | 4 | 3 | 0 | 4430 | Flotation (future) | Future | Future | Future | Future
4 | 4 | 3 | 1 | 4431 | Train 1 (future) | Future | Future | Future | Future
4 | 4 | 3 | 2 | 4432 | Train 2 (future) | Future | Future | Future | Future
4 | 4 | 3 | 3 | 4433 | Train 3 (future) | Future | Future | Future | Future
4 | 4 | 4 | 0 | 4440 | Concentrate Regrind (future) | Future | Future | Future | Future
4 | 4 | 4 | 1 | 4441 | Train 1 (future) | Future | Future | Future | Future
4 | 4 | 4 | 2 | 4442 | Train 2 (future) | Future | Future | Future | Future
4 | 4 | 4 | 3 | 4443 | Train 3 (future) | Future | Future | Future | Future
4 | 4 | 5 | 0 | 4450 | Regrind Media Handling (future) | Future | Future | Future | Future
4 | 4 | 8 | 0 | 4480 | Sampling and Analysis (future) | Future | Future | Future | Future
4 | 4 | 9 | 0 | 4490 | Facilities and Services (future) | Future | Future | Future | Future
4 | 4 | 9 | 8 | 4498 | Building or Structure (future) | Future | Future | Future | Future
4 | 4 | 9 | 9 | 4499 | Electrical (future) | Future | Future | Future | Future
4 | 5 | 0 | 0 | 4500 | Molybdenum Processing (future) | Future | Future | Future | Future
4 | 5 | 1 | 0 | 4510 | Bulk Concentrate Thickening (future) | Future | Future | Future | Future
4 | 5 | 2 | 0 | 4520 | Rougher Conditioning (future) | Future | Future | Future | Future
4 | 5 | 3 | 0 | 4530 | Rougher Flotation (future) | Future | Future | Future | Future
4 | 5 | 4 | 0 | 4540 | Cleaner Flotation (future) | Future | Future | Future | Future
4 | 5 | 8 | 0 | 4580 | Sampling and Analysis (future) | Future | Future | Future | Future
4 | 5 | 9 | 0 | 4590 | Common Facilities and Services (future) | Future | Future | Future | Future
4 | 6 | 0 | 0 | 4600 | Concentrate Handling | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 0 | 4610 | Copper Concentrate Thickening | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 1 | 4611 | Feed | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 2 | 4612 | Thickener | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 3 | 4613 | Overflow | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 4 | 4614 | Underflow | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 0 | 4620 | Copper Concentrate Filtration and Storage | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 1 | 4621 | Train 1 (filter 1) | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 2 | 4622 | Train 2 (filter 2) | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 3 | 4623 | Train 3 (filter 3) | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 4 | 4624 | Train 4 (filter 4) | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 5 | 4625 | Filtrate Transfer Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 6 | 4626 | Storage Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 7 | 4627 | Sampler Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 0 | 4630 | Copper Concentrate Reclaim and Loadout | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 1 | 4631 | Reclaim | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 2 | 4632 | Loadout Storage Reclaim Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 4 | 4634 | Product Sampler Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 6 | 4636 | Loadout Conveyor | - | - | - | -
4 | 6 | 5 | 0 | 4650 | Molybdenum Concentrate Thickening (future) | Future | Future | Future | Future
4 | 6 | 6 | 0 | 4660 | Molybdenum Concentrate Filtration and Storage (future) | Future | Future | Future | Future
4 | 6 | 7 | 0 | 4670 | Molybdenum Concentrate Bagging (future) | Future | Future | Future | Future
4 | 6 | 9 | 0 | 4690 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 6 | 9 | 7 | 4697 | Truck Wash | Fluor | Fluor | Fluor | Fluor
4 | 6 | 9 | 8 | 4698 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 6 | 9 | 9 | 4699 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 7 | 0 | 0 | 4700 | Tailings Handling | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 0 | 4710 | Rougher Thickening | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 1 | 4711 | Feed Distribution | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 2 | 4712 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 3 | 4713 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 4 | 4714 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 5 | 4715 | Overflow | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 6 | 4716 | Underflow | Fluor | Fluor | Fluor | Fluor
4 | 7 | 2 | 0 | 4720 | Rougher Disposal Pumping | Fluor | Fluor | Fluor | Fluor
4 | 7 | 2 | 1 | 4721 | Line 1 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 2 | 2 | 4722 | Line 2 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 2 | 3 | 4723 | Line 3 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 3 | 0 | 4730 | Filtration (future) | Future | Future | Future | Future
4 | 7 | 4 | 0 | 4740 | CPF Sands De-Watering (future) | Future | Future | Future | Future
4 | 7 | 4 | 1 | 4741 | Train 1 (future) | Future | Future | Future | Future
4 | 7 | 4 | 2 | 4742 | Train 2 (future) | Future | Future | Future | Future
4 | 7 | 4 | 3 | 4743 | Train 3 (future) | Future | Future | Future | Future
4 | 7 | 5 | 0 | 4750 | Cleaner Thickening | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 1 | 4751 | Feed Distribution | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 2 | 4752 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 6 | 4756 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 4 | 4754 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 5 | 4755 | Overflow | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 6 | 4756 | Underflow | Fluor | Fluor | Fluor | Fluor
4 | 7 | 6 | 0 | 4760 | Cleaner Disposal Pumping | Fluor | Fluor | Fluor | Fluor
4 | 7 | 6 | 1 | 4761 | Line 1 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 6 | 2 | 4762 | Line 2 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 7 | 0 | 4770 | Tailings Overland Conveying (future) | Future | Future | Future | Future
4 | 7 | 9 | 0 | 4790 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 7 | 9 | 8 | 4798 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 7 | 9 | 9 | 4799 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 8 | 0 | 0 | 4800 | Reagents | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 0 | 4810 | General | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 1 | 4811 | Exterior Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 2 | 4812 | Interior Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 3 | 4813 | Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 4 | 4814 | Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 5 | 4815 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 2 | 0 | 4820 | Collector | Fluor | Fluor | Fluor | Fluor
4 | 8 | 2 | 1 | 4821 | Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 2 | 2 | 4822 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 0 | 4830 | Promoter | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 1 | 4831 | Promoter 1 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 2 | 4832 | Promoter 1 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 3 | 4833 | Promoter 2 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 4 | 4834 | Promoter 2 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 5 | 4835 | Promoter 3 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 6 | 4836 | Promoter 3 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 0 | 4840 | Frother | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 1 | 4841 | Frother 1 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 2 | 4842 | Frother 1 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 3 | 4843 | Frother 2 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 4 | 4844 | Frother 2 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 0 | 4850 | SMBS | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 1 | 4851 | SMBS 1 Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 2 | 4852 | SMBS 1 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 3 | 4853 | SMBS 1 Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 4 | 4854 | SMBS 1 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 5 | 4855 | SMBS 2 Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 6 | 4856 | SMBS 2 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 7 | 4857 | SMBS 2 Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 8 | 4858 | SMBS 2 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 0 | 4860 | Flocculant | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 1 | 4861 | Flocculant 1 Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 2 | 4862 | Flocculant 1 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 3 | 4863 | Flocculant 1 Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 4 | 4864 | Flocculant 1 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 5 | 4865 | Flocculant 2 Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 6 | 4866 | Flocculant 2 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 7 | 4867 | Flocculant 2 Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 8 | 4868 | Flocculant 2 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 7 | 0 | 4870 | Spare Reagent Systems | Fluor | Fluor | Fluor | Fluor
4 | 8 | 7 | 1 | 4871 | Spare Reagent 1 | Fluor | Fluor | Fluor | Fluor
4 | 8 | 7 | 2 | 4872 | Spare Reagent 2 | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 0 | 4880 | Dosing | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 1 | 4881 | General | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 2 | 4882 | Collector | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 3 | 4883 | Promoter | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 4 | 4884 | Frother | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 5 | 4885 | SMBS | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 6 | 4886 | Flocculant | Fluor | Fluor | Fluor | Fluor
4 | 8 | 9 | 0 | 4890 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 8 | 9 | 8 | 4898 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 8 | 9 | 9 | 4899 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 9 | 0 | 0 | 4900 | Plant Services | Fluor | Fluor | Fluor | Fluor
4 | 9 | 1 | 0 | 4910 | Raw Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 1 | 1 | 4911 | Storage | Fluor | Fluor | Fluor | Fluor
4 | 9 | 1 | 2 | 4912 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 1 | 3 | 4913 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 2 | 0 | 4920 | Process Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 2 | 2 | 4922 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 2 | 3 | 4923 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 3 | 0 | 4930 | Gland Seal Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 3 | 1 | 4931 | Storage | Fluor | Fluor | Fluor | Fluor
4 | 9 | 3 | 2 | 4932 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 3 | 3 | 4933 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 4 | 0 | 4940 | Cooling Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 4 | 1 | 4941 | Storage | Fluor | Fluor | Fluor | Fluor
4 | 9 | 4 | 2 | 4942 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 4 | 3 | 4943 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 0 | 4950 | Treated Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 1 | 4951 | Plant | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 2 | 4952 | Storage | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 3 | 4953 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 4 | 4954 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 0 | 4960 | Plant Air | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 1 | 4961 | Processing Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 2 | 4962 | CPF Hydrofloat Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 3 | 4963 | CPF Tailings Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 4 | 4964 | Concentrate Filtration Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 5 | 4965 | Concentrate Drying Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 0 | 4970 | Instrument Air | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 1 | 4971 | Processing Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 2 | 4972 | CPF Hydrofloat Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 3 | 4973 | CPF Tailings Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 4 | 4974 | Concentrate Filtration Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 5 | 4975 | Concentrate Drying Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 0 | 4980 | Flotation Blower Air | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 1 | 4981 | Rougher Flotation | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 2 | 4982 | Cleaner Aeration Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 3 | 4983 | Cleaner Flotation | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 4 | 4984 | Cleaner Scavenger Flotation | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 5 | 4985 | SMBS Neutralisation | Fluor | Fluor | Fluor | Fluor
4 | 9 | 9 | 0 | 4990 | Nitrogen (future) | Future | Future | Future | Future
5 | 0 | 0 | 0 | 5000 | Tailings and Water Management | Fluor/KP | IPMT | IPMT/Fluor | IPMT/Fluor/RDMC
5 | 1 | 0 | 0 | 5100 | Tailings Management | KP/Fluor | IPMT | IPMT/Fluor | IMPT/Fluor
5 | 1 | 1 | 0 | 5110 | Rougher Dams | KP | IPMT | IPMT | RDMC/IPMT
5 | 1 | 1 | 1 | 5111 | Compartment 1 | KP | IPMT | IPMT | RDMC
5 | 1 | 1 | 2 | 5112 | Compartment 2 | KP | IPMT | IPMT | IPMT
5 | 1 | 1 | 3 | 5113 | Compartment 3 | KP | IPMT | IPMT | IPMT
5 | 1 | 1 | 5 | 5115 | Monitoring Wells | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 0 | 5120 | Cleaner Dams | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 1 | 5121 | Compartment 1 | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 2 | 5122 | Compartment 2 | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 3 | 5123 | Compartment 3 | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 5 | 5125 | Monitoring Wells | KP | IPMT | IPMT | IPMT
5 | 1 | 3 | 0 | 5130 | Seepage System and Return | Fluor | Fluor | Fluor | Fluor
5 | 1 | 3 | 1 | 5131 | Rougher Collection | Fluor | Fluor | Fluor | Fluor
5 | 1 | 3 | 2 | 5132 | Rougher Return | Fluor | Fluor | Fluor | Fluor
5 | 1 | 3 | 5 | 5135 | Cleaner Collection | Fluor | Fluor | Fluor | Fluor
5 | 1 | 3 | 6 | 5136 | Cleaner Return | Fluor | Fluor | Fluor | Fluor
5 | 1 | 4 | 0 | 5140 | Sand Deposition (future) | Future | Future | Future | Future
5 | 1 | 5 | 0 | 5150 | Transport and Deposition | Fluor/KP | Fluor/IPMT | Fluor/IPMT | Fluor/IPMT
5 | 1 | 5 | 1 | 5151 | Rougher Pipeline 1 | Fluor | Fluor | Fluor | Fluor
5 | 1 | 5 | 2 | 5152 | Rougher Pipeline 2 | Fluor | Fluor | Fluor | Fluor
5 | 1 | 5 | 3 | 5153 | Rougher Pipeline 3 | Fluor | Fluor | Fluor | Fluor
5 | 1 | 5 | 4 | 5154 | Rougher Deposition | KP | IMPT | IMPT | IPMT
5 | 1 | 5 | 5 | 5155 | Cleaner Transport | Fluor | Fluor | Fluor | Fluor
5 | 1 | 5 | 6 | 5156 | Cleaner Deposition | KP | IMPT | IMPT | IPMT
5 | 1 | 9 | 0 | 5190 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
5 | 1 | 9 | 8 | 5198 | Building or Structure | Fluor | Fluor | Fluor | Fluor
5 | 1 | 9 | 9 | 5199 | Electrical | Fluor | Fluor | Fluor | Fluor
5 | 2 | 0 | 0 | 5200 | Reclaim Water | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 0 | 5210 | Rougher TSF | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 1 | 5211 | Pontoons | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 2 | 5212 | Return Pumping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 3 | 5213 | Return Piping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 4 | 5214 | Transfer Pumping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 5 | 5215 | Transfer Piping | - | - | - | -
5 | 2 | 2 | 0 | 5220 | Cleaner TSF | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 1 | 5211 | Pontoons | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 2 | 5212 | Return Pumping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 3 | 5213 | Return Piping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 4 | 5214 | Transfer Pumping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 5 | 5215 | Transfer Piping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 9 | 0 | 5290 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
5 | 2 | 9 | 8 | 5298 | Building or Structure | Fluor | Fluor | Fluor | Fluor
5 | 2 | 9 | 9 | 5299 | Electrical | Fluor | Fluor | Fluor | Fluor
5 | 3 | 0 | 0 | 5300 | Water Management | Fluor/KP | Fluor/IPMT/RDMC | Fluor/IPMT/RDMC | Fluor/IPMT/RDMC
5 | 3 | 1 | 0 | 5310 | Surface Water Diversion | Fluor/KP | Fluor/IPMT | RDMC/Fluor/IPMT | RDMC/Fluor/IPMT
5 | 3 | 1 | 1 | 5311 | Mining | KP | IPMT | RDMC | RDMC
5 | 3 | 1 | 2 | 5312 | Dry Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 1 | 3 | 5313 | Wet Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 1 | 4 | 5314 | TSF | KP | IPMT | IPMT | IPMT
5 | 3 | 1 | 5 | 5315 | Infrastructure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 2 | 0 | 5320 | Surface Water Collection and Storage | Fluor/KP | Fluor/IPMT | Fluor/IMPT/ RDMC | Fluor/IPMT/RDMC
5 | 3 | 2 | 1 | 5321 | Mining | KP | IPMT | RDMC | RDMC
5 | 3 | 2 | 2 | 5322 | Dry Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 2 | 3 | 5323 | Wet Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 2 | 4 | 5324 | TSF | KP | IPMT | IPMT | IPMT
5 | 3 | 2 | 5 | 5325 | Infrastructure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 3 | 0 | 5330 | Surface Water Pumping and Distribution | Fluor | Fluor | Fluor | Fluor
5 | 3 | 3 | 1 | 5331 | Mining | KP | IPMT | RDMC | RDMC
5 | 3 | 3 | 2 | 5332 | Dry Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 3 | 3 | 5333 | Wet Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 3 | 4 | 5334 | TSF | KP | IPMT | IPMT | IPMT
5 | 3 | 3 | 5 | 5335 | Infrastructure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 4 | 0 | 5340 | Surface Water Sediment and Erosion Control | Fluor | Fluor | Fluor | Fluor
5 | 3 | 4 | 1 | 5341 | Mining | KP | IPMT | RDMC | RDMC
5 | 3 | 4 | 2 | 5342 | Dry Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 4 | 3 | 5343 | Wet Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 4 | 4 | 5344 | TSF | KP | IPMT | IPMT | IPMT
5 | 3 | 4 | 5 | 5345 | Infrastructure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 5 | 0 | 5350 | Process Water Dams | KP | IPMT | IPMT | IPMT
5 | 3 | 6 | 0 | 5360 | Raw Water Dams | KP | IPMT | IPMT | IPMT
5 | 3 | 7 | 0 | 5370 | Turkey Nests | RDMC | RDMC | RDMC | RDMC
5 | 3 | 8 | 0 | 5380 | Rejects Pond | KP | IPMT | IPMT | IPMT
5 | 3 | 8 | 1 | 5381 | Earthworks | KP | IPMT | IPMT | IPMT
5 | 3 | 8 | 2 | 5382 | Transfer Pumping | KP | IPMT | IPMT | IPMT
5 | 3 | 8 | 3 | 5383 | Transfer Piping | KP | IPMT | IPMT | IPMT
5 | 3 | 8 | 4 | 5384 | Sprayfield | KP | IPMT | IPMT | IPMT
5 | 3 | 9 | 0 | 5390 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
5 | 3 | 9 | 8 | 5398 | Building or Structure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 9 | 9 | 5399 | Electrical | Fluor | Fluor | Fluor | Fluor
5 | 4 | 0 | 0 | 5400 | Acid Rock Drainage Treatment | - | - | - | -
5 | 4 | 1 | 0 | 5410 | Dams | - | - | - | -
5 | 4 | 2 | 0 | 5420 | Pumps and Pipelines | - | - | - | -
5 | 4 | 3 | 0 | 5430 | Seepage Control | - | - | - | -
5 | 4 | 9 | 0 | 5490 | Common Facilities and Services | - | - | - | -
5 | 5 | 0 | 0 | 5500 | Effluent Treatment | Fluor | Fluor | Fluor | Fluor
5 | 5 | 1 | 0 | 5510 | Industrial | - | - | - | -
5 | 5 | 2 | 0 | 5520 | Plant Sewage | Fluor | Fluor | Fluor | Fluor
5 | 5 | 2 | 1 | 5521 | Collection | Fluor | Fluor | Fluor | Fluor
5 | 5 | 2 | 2 | 5522 | Pumping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 2 | 3 | 5523 | Piping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 0 | 5530 | Village Sewage | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 1 | 5531 | Collection | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 2 | 5532 | Pumping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 3 | 5533 | Plant 1 | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 4 | 5534 | Plant 2 | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 5 | 5535 | Treated Effluent Storage | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 6 | 5536 | Treated Effluent Pumping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 7 | 5537 | Treated Effluent Piping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 4 | 0 | 5540 | Agricultural | - | - | - | -
5 | 5 | 9 | 0 | 5590 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
5 | 5 | 9 | 8 | 5598 | Building or Structure | Fluor | Fluor | Fluor | Fluor
5 | 5 | 9 | 9 | 5599 | Electrical | Fluor | Fluor | Fluor | Fluor
5 | 6 | 0 | 0 | 5600 | Water Services | Fluor | Fluor | Fluor | Fluor
5 | 6 | 1 | 0 | 5610 | Firewater Storage | Fluor | Fluor | Fluor | Fluor
5 | 6 | 2 | 0 | 5620 | Firewater Pumping and Distribution | Fluor | Fluor | Fluor | Fluor
5 | 6 | 3 | 0 | 5630 | Potable Water Treatment | Fluor | Fluor | Fluor | Fluor
5 | 6 | 3 | 2 | 5632 | Plant 1 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 3 | 3 | 5633 | Plant 2 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 0 | 5640 | Potable Water Storage | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 1 | 5641 | Common | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 2 | 5642 | System 1 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 3 | 5643 | System 2 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 4 | 5644 | Plant | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 0 | 5650 | Potable Water Pumping and Distribution | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 1 | 5651 | Common | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 2 | 5652 | System 1 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 3 | 5653 | System 2 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 4 | 5654 | Plant | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 5 | 5655 | Safety Shower | Fluor | Fluor | Fluor | Fluor
6 | 0 | 0 | 0 | 6000 | Internal Infrastructure | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 0 | 0 | 6100 | On-Site Infrastructure | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 1 | 0 | 6110 | Site Preparation, Earthworks and Fencing | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 1 | 3 | 6113 | Site Security Fencing | RDMC | RDMC | RDMC | RDMC
6 | 1 | 1 | 4 | 6114 | Bulk Earthworks | Fluor | Fluor | Fluor | Fluor
6 | 1 | 1 | 5 | 6115 | Detailed Earthworks | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 0 | 6120 | Roads and Platforms | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 2 | 1 | 6121 | Processing Plant Roads | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 2 | 6122 | Crushing Plant Roads | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 3 | 6123 | Exploration Roads | RDMC | RDMC | RDMC | RDMC
6 | 1 | 2 | 4 | 6124 | Parking Areas and Hardstand Areas | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 5 | 6125 | Exploration Platforms | RDMC | RDMC | RDMC | RDMC
6 | 1 | 2 | 6 | 6126 | On-Site Helipad and Airstrip | RDMC | RDMC | RDMC | RDMC
6 | 1 | 2 | 8 | 6128 | Permanent Village Road | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 9 | 6129 | Mine Site Access Road | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 0 | 6130 | Non-Process Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 1 | 6131 | Fire, Ambulance, and Emergency Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 2 | 6132 | Security and Medical Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 3 | 6133 | Main Administration Building | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 4 | 6134 | Laboratories | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 5 | 6135 | Plant Warehouse and Maintenance Shop | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 6 | 6136 | Change House and Dry Building | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 7 | 6137 | Training Building and Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 8 | 6138 | Stores and Warehouse | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 9 | 6139 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 4 | 0 | 6140 | Mobile Equipment | RDMC | RDMC | RDMC | RDMC
6 | 1 | 4 | 1 | 6141 | Maintenance | RDMC | RDMC | RDMC | RDMC
6 | 1 | 4 | 2 | 6142 | General and Administration | RDMC | RDMC | RDMC | RDMC
6 | 1 | 5 | 0 | 6150 | Bulk Storage (NB Storage of Utilities) | Fluor/PPE | Fluor/PPE | Fluor/PPE | Fluor/PPE
6 | 1 | 5 | 5 | 6155 | Diesel | Fluor | Fluor | Fluor | Fluor
6 | 1 | 5 | 7 | 6157 | Reagents Receival and Storage | Fluor | Fluor | Fluor | Fluor
6 | 1 | 5 | 8 | 6158 | Container Receival and Storage | Fluor | Fluor | Fluor | Fluor
6 | 1 | 5 | 9 | 6159 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 6 | 0 | 6160 | Services and Utilities (NB Distribution of Utilities) | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 6 | 5 | 6165 | Environmental Monitoring | RDMC | RDMC | RDMC | RDMC
6 | 1 | 6 | 6 | 6166 | Compressed Air | Fluor | Fluor | Fluor | Fluor
6 | 1 | 6 | 8 | 6168 | Diesel Fuel Distribution and Refuelling | Fluor | Fluor | Fluor | Fluor
6 | 1 | 6 | 9 | 6169 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 7 | 0 | 6170 | Communications | Fluor | Fluor | Fluor | Fluor
6 | 1 | 7 | 1 | 6171 | Distributed Control System | Fluor | Fluor | Fluor | Fluor
6 | 1 | 7 | 2 | 6172 | Communications and Networks | Fluor | Fluor | Fluor | Fluor
6 | 1 | 7 | 9 | 6179 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 0 | 6180 | Village | Fluor/PPE | Fluor/PPE | Fluor/PPE | Fluor/PPE
6 | 1 | 8 | 1 | 6181 | Accommodation | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 2 | 6182 | Mess Hall and Food Storage | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 3 | 6183 | Leisure Amenities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 4 | 6184 | Laundry Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 5 | 6185 | Potable Water | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 6 | 6186 | Firewater | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 7 | 6187 | Support Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 8 | 6188 | Underground Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 9 | 6189 | Common Facilities and Services | Fluor/PPE | Fluor/PPE | Fluor/PPE | Fluor/PPE
6 | 1 | 9 | 0 | 6190 | Rail | Vec | Vec | Vec | Vec
6 | 2 | 0 | 0 | 6200 | On-Site Power Supply and Transmission | PPE/WAR | PPE/WAR | PPE/WAR | PPE/WAR
6 | 2 | 1 | 0 | 6210 | Power Stations | WAR | WAR | WAR | WAR
6 | 2 | 1 | 1 | 6211 | Administration and General Buildings | WAR | WAR | WAR | WAR
6 | 2 | 1 | 2 | 6212 | Power Station 1 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 3 | 6213 | HFO Storage Power Station 1 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 4 | 6214 | Truck Unloading and Pumping Power Station 1 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 5 | 6215 | Power Station 2 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 6 | 6216 | HFO Storage Power Station 2 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 7 | 6217 | Truck Unloading and Pumping Power Station 2 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 8 | 6218 | Rail Unloading | WAR | WAR | WAR | WAR
6 | 2 | 1 | 9 | 6219 | Common Facilities and Services | WAR | WAR | WAR | WAR
6 | 2 | 3 | 0 | 6230 | High Voltage (220 kV) Transmission Lines | PPE | PPE | PPE | PPE
6 | 2 | 3 | 1 | 6231 | Solar PV Substation to Power Station Substation | PPE | PPE | PPE | PPE
6 | 2 | 3 | 2 | 6232 | Power Station Substation to Plant Main Substation | PPE | PPE | PPE | PPE
6 | 2 | 3 | 3 | 6233 | NDTC (Pakistan Grid Operator) Power Supply (future) | PPE | PPE | PPE | PPE
6 | 2 | 4 | 0 | 6240 | High Voltage Substations | PPE | PPE | PPE | PPE
6 | 2 | 4 | 1 | 6241 | 33/220 kV Solar PV Substation | PPE | PPE | PPE | PPE
6 | 2 | 4 | 2 | 6242 | 33/220 kV Power Station Substation | PPE | PPE | PPE | PPE
6 | 2 | 4 | 3 | 6243 | 220/33 kV Plant Main Substation | PPE | PPE | PPE | PPE
6 | 2 | 5 | 0 | 6250 | Power Conditioning Equipment | PPE | PPE | PPE | PPE
6 | 2 | 5 | 1 | 6251 | Load Bank | PPE | PPE | PPE | PPE
6 | 2 | 5 | 2 | 6252 | Harmonic Filters 1 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 3 | 6253 | Synchronous Condenser 1 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 4 | 6254 | Battery Energy Storage System 1 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 5 | 6255 | Harmonic Filters 2 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 6 | 6256 | Synchronous Condenser 2 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 7 | 6257 | Battery Energy Storage System 2 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 0 | 6260 | Emergency Power Generation | PPE | PPE | PPE | PPE
6 | 2 | 6 | 1 | 6261 | Administration and General Buildings | PPE | PPE | PPE | PPE
6 | 2 | 6 | 2 | 6262 | Emergency Power Substation 1 and Control Room 1 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 3 | 6263 | 36 MVA Power Station 1 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 4 | 6264 | Bulk Diesel Storage 1 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 5 | 6265 | Truck Diesel Unloading and Power Station 1 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 6 | 6266 | Emergency Power Substation 2 and Control Room 2 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 7 | 6267 | 36 MVA Power Station 2 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 8 | 6268 | Bulk Diesel Storage 2 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 9 | 6269 | Truck Diesel Unloading and Power Station 2 | PPE | PPE | PPE | PPE
6 | 2 | 8 | 0 | 6280 | Medium Voltage (33 kV) Overhead Powerlines | PPE | PPE | PPE | PPE
6 | 2 | 8 | 1 | 6281 | Booster Pump Station | PPE | PPE | PPE | PPE
6 | 2 | 8 | 2 | 6282 | Borefields | PPE | PPE | PPE | PPE
6 | 2 | 8 | 3 | 6283 | Potable Water Treatment Plant | PPE | PPE | PPE | PPE
6 | 2 | 8 | 4 | 6284 | Sewage Treatment Plant | PPE | PPE | PPE | PPE
6 | 2 | 8 | 5 | 6285 | Village | PPE | PPE | PPE | PPE
6 | 2 | 8 | 6 | 6286 | Mining Open Pit | PPE | PPE | PPE | PPE
6 | 2 | 8 | 7 | 6287 | Primary Crushing | PPE | PPE | PPE | PPE
6 | 2 | 8 | 8 | 6288 | Tailings Storage Facility | PPE | PPE | PPE | PPE
6 | 2 | 8 | 9 | 6289 | Rail Offloading Facility | PPE | PPE | PPE | PPE
6 | 2 | 9 | 0 | 6290 | Renewable Energy | PPE | PPE | PPE | PPE
6 | 2 | 9 | 1 | 6291 | Administration and General Buildings | PPE | PPE | PPE | PPE
6 | 2 | 9 | 2 | 6292 | 11/33 kV Solar PV Substation 1 and Control Room 1 | PPE | PPE | PPE | PPE
6 | 2 | 9 | 3 | 6293 | Power Station 1 Photovoltaic Array, Inverters, and Transformers | PPE | PPE | PPE | PPE
6 | 2 | 9 | 4 | 6294 | 11/33 kV Solar PV Substation 2 and Control Room 2 (future) | Future | Future | Future | Future
6 | 2 | 9 | 5 | 6295 | Power Station 2 Photovoltaic Array, Inverters, and Transformers (future) | Future | Future | Future | Future
6 | 3 | 0 | 0 | 6300 | On-Site Rail | - | - | - | -
6 | 3 | 1 | 0 | 6310 | Site Preparation | - | - | - | -
6 | 3 | 1 | 1 | 6311 | Embankment & Cuttings | - | - | - | -
6 | 3 | 1 | 2 | 6312 | Drainage & Culverts | - | - | - | -
6 | 3 | 1 | 3 | 6313 | Site Security Fencing | - | - | - | -
6 | 3 | 1 | 4 | 6314 | Bulk Site Earthworks | - | - | - | -
6 | 3 | 1 | 5 | 6315 | Detailed Site Earthworks | - | - | - | -
6 | 3 | 1 | 6 | 6316 | Roads | - | - | - | -
6 | 3 | 1 | 7 | 6317 | Signaling | - | - | - | -
6 | 3 | 2 | 0 | 6320 | Site Utilities and Services | - | - | - | -
6 | 3 | 2 | 2 | 6322 | Fire Water Storage | - | - | - | -
6 | 3 | 2 | 3 | 6323 | Fire Water Pump House & Reticulation | - | - | - | -
6 | 3 | 2 | 4 | 6324 | Fuel Storage | - | - | - | -
6 | 3 | 2 | 5 | 6325 | Potable Water System | - | - | - | -
6 | 3 | 2 | 6 | 6326 | Sewage Collection & Distribution | - | - | - | -
6 | 3 | 2 | 7 | 6327 | Waste Sorting Facility | - | - | - | -
6 | 3 | 4 | 0 | 6340 | Rail Facilities | - | - | - | -
6 | 3 | 4 | 1 | 6341 | Incoming Train Covered Inspection Shed | - | - | - | -
6 | 3 | 4 | 2 | 6342 | Operation Staff Building | - | - | - | -
6 | 3 | 4 | 3 | 6343 | CuCon Filling Point | - | - | - | -
6 | 3 | 4 | 4 | 6344 | In-Motion Weighing Bridge + Office | - | - | - | -
6 | 3 | 4 | 5 | 6345 | Washing Station | - | - | - | -
6 | 3 | 4 | 6 | 6346 | Wagons and Locomotives Running Shed and Refueling Station | - | - | - | -
6 | 3 | 4 | 7 | 6347 | Rotainers and Containers Handling and Repairing Platform | - | - | - | -
6 | 3 | 6 | 0 | 6360 | Comms, IT and Controls | - | - | - | -
6 | 3 | 6 | 1 | 6361 | Telecommunications | - | - | - | -
6 | 3 | 6 | 2 | 6362 | CCTV System | - | - | - | -
6 | 3 | 6 | 3 | 6363 | IT and Systems | - | - | - | -
6 | 3 | 6 | 4 | 6364 | Control System | - | - | - | -
6 | 3 | 9 | 0 | 6390 | Rail Electrical | - | - | - | -
6 | 3 | 9 | 1 | 6391 | Sub-Station | - | - | - | -
6 | 3 | 9 | 2 | 6392 | Site Wide Area Lighting | - | - | - | -
7 | 0 | 0 | 0 | 7000 | External Infrastructure | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW
7 | 1 | 0 | 0 | 7100 | Off-Site Infrastructure | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW
7 | 1 | 1 | 0 | 7110 | Off-Site Roads / Water Diversions | Fluor | Fluor | Fluor | Fluor
7 | 1 | 1 | 1 | 7111 | Site Access Road (45km) | Fluor | Fluor | Fluor | Fluor
7 | 1 | 2 | 0 | 7120 | Off-Site Facilities | RDMC/Fluor/Vec | RDMC/Fluor/Vec | RDMC/Fluor/Vec | RDMC/Fluor/Vec
7 | 1 | 2 | 1 | 7121 | Off-Site Permanent Buildings (Not Accomodation) | - | - | - | -
7 | 1 | 2 | 2 | 7122 | Off-Site Railways | - | - | - | -
7 | 1 | 2 | 3 | 7123 | Off-Site Accommodation | RDMC | RDMC | RDMC | RDMC
7 | 1 | 2 | 4 | 7124 | Off-Site Solid Waste Storage | Fluor | Fluor | Fluor | Fluor
7 | 1 | 2 | 5 | 7125 | Off-Site Hazardous Waste Storage | Fluor | Fluor | Fluor | Fluor
7 | 1 | 2 | 6 | 7126 | Site Bulk Road & Bulk Rail Loading | Vec | Vec | Vec | Vec
7 | 1 | 2 | 7 | 7127 | Port Qasim Bulk Road & Bulk Rail Unloading | - | - | - | -
7 | 1 | 3 | 0 | 7130 | Off-Site Mobile Maintenance Equipment | RDMC | RDMC | RDMC | RDMC
7 | 1 | 4 | 0 | 7140 | Off-Site Utilities Pipelines & Bulk Storage (exclude water) | Vecturis/PRDW | Vecturis/PRDW | Vecturis/PRDW | Vecturis/PRDW
7 | 1 | 4 | 2 | 7142 | Off-Site Fuel Pipeline | - | - | - | -
7 | 1 | 4 | 3 | 7143 | Off-Site Concentrate Pipeline | Future | Future | Future | Future
7 | 1 | 4 | 5 | 7145 | Off-Site Fuel Bulk Storage | Vecturis/PR DW | Vecturis/PR DW | Vecturis/PR DW | Vecturis/PR DW
7 | 1 | 4 | 6 | 7146 | Off-Site Concentrate Bulk Storage | PRDW | PRDW | PRDW | PRDW
7 | 1 | 4 | 7 | 7147 | Off-Site Effluent Utilities | Vecturis/PR DW | Vecturis/PR DW | Vecturis/PR DW | Vecturis/PR DW
7 | 1 | 4 | 9 | 7149 | Natural Gas Pipeline & Associated Equipment (K&T) | - | - | - | -
7 | 1 | 6 | 0 | 7160 | Off-Site Airport Facilities | - | - | - | -
7 | 1 | 6 | 1 | 7161 | Airport Runways | - | - | - | -
7 | 1 | 6 | 2 | 7162 | Airport Taxiways | - | - | - | -
7 | 1 | 6 | 3 | 7163 | Airport Aprons | - | - | - | -
7 | 1 | 6 | 4 | 7164 | Airport Passenger Terminal Buildings | - | - | - | -
7 | 1 | 6 | 5 | 7165 | Airport Freight Handling Facilities | - | - | - | -
7 | 1 | 6 | 9 | 7169 | Airport Facilities & Services | - | - | - | -
7 | 1 | 7 | 0 | 7170 | Off-Site Water Pipelines & Bulk Storage | Fluor | Fluor | Fluor | Fluor
7 | 1 | 7 | 1 | 7171 | Off-Site Desalinated Water Pipeline | Future | Future | Future | Future
7 | 1 | 7 | 4 | 7174 | Off-Site Water Bulk Storage
7 | 1 | 7 | 5 | 7175 | Off-Site Hamun-i-Mashkel (HIM) Bore Field | Future | Future | Future | Future
7 | 1 | 7 | 6 | 7176 | Off-Site Borehole Fieldwater Pipeline - Hamun-i-Mashkel (HIM) | Future | Future | Future | Future
7 | 1 | 7 | 7 | 7177 | Off-Site Fan Sediments Bore Field | Fluor | Fluor | Fluor | Fluor
7 | 1 | 7 | 8 | 7178 | Off-Site Borehole Fieldwater Pipeline - Fan Sediments Main Line | Fluor | Fluor | Fluor | Fluor
7 | 1 | 7 | 9 | 7179 | Off-Site Borehole Fieldwater Pipeline - Fan Sediments Construction Line | RDMC | RDMC | Fluor | Fluor
7 | 1 | 8 | 0 | 7180 | Off-Site Services/Utilities | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 1 | 7181 | Off-Site Fresh Water Distribution | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 2 | 7182 | Off-Site Potable Water Distribution | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 3 | 7183 | Off-Site Acid Rock Drainage (ARD) Water Distribution
7 | 1 | 8 | 4 | 7184 | Off-Site Fire Water Distribution | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 5 | 7185 | Off-Site Environmental Monitoring | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 6 | 7186 | Off-Site Communications | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 7 | 7187 | Off-Site Effluent Utilities | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 8 | 7188 | Off-Site Other Utilities (Compressed Air & Propane, etc.) | RDMC | RDMC | RDMC | RDMC
7 | 1 | 9 | 0 | 7190 | Off-Site Power Supply & Transmission
7 | 1 | 9 | 1 | 7191 | Switchyard
7 | 1 | 9 | 2 | 7192 | Off-Site Transmission
7 | 1 | 9 | 3 | 7193 | Main Substation
7 | 1 | 9 | 4 | 7194 | Power Generation
7 | 1 | 9 | 9 | 7199 | Off-Site Power Facilities & Services
7 | 2 | 0 | 0 | 7200 | Off-Site Port (Qasim & Gwadar) - (Not in Scope) | - | - | - | -
7 | 2 | 1 | 0 | 7210 | Port Concentrate Handling | - | - | - | -
7 | 2 | 1 | 1 | 7211 | Port Copper Concentrate Thickening | - | - | - | -
7 | 2 | 1 | 2 | 7212 | Port Concentrate Filtration | - | - | - | -
7 | 2 | 1 | 3 | 7213 | Port Concentrate Conveyor & Handling | - | - | - | -
7 | 2 | 1 | 4 | 7214 | Port Concentrate Stacking Conveyor | - | - | - | -
7 | 2 | 1 | 5 | 7215 | Port Concentrate Storage | - | - | - | -
7 | 2 | 1 | 6 | 7216 | Port Concentrate Emergencg Dump Pond | - | - | - | -
7 | 2 | 1 | 7 | 7217 | Process Water Treatment | - | - | - | -
7 | 2 | 1 | 8 | 7218 | Sampling Plant | - | - | - | -
7 | 2 | 1 | 9 | 7219 | Utilities & Services | - | - | - | -
7 | 2 | 2 | 0 | 7220 | Port Site Utilities & Services | - | - | - | -
7 | 2 | 2 | 1 | 7221 | Reagents Handling Facility | - | - | - | -
7 | 2 | 2 | 2 | 7222 | Utilities Services For Port Conveying Onshore | - | - | - | -
7 | 2 | 2 | 3 | 7223 | Fuel offloading & Refuelling | - | - | - | -
7 | 2 | 2 | 4 | 7224 | Fuel Storage & Dispensing | - | - | - | -
7 | 2 | 2 | 5 | 7225 | Fuel Pipeline | - | - | - | -
7 | 2 | 2 | 6 | 7226 | Potable Water System | - | - | - | -
7 | 2 | 2 | 7 | 7227 | Sewage Collection & Treatment | - | - | - | -
7 | 2 | 2 | 8 | 7228 | Waste Sorting Facility | - | - | - | -
7 | 2 | 2 | 9 | 7229 | Fresh & Fire Water System | - | - | - | -
7 | 2 | 3 | 0 | 7230 | Port Facilities | - | - | - | -
7 | 2 | 3 | 1 | 7231 | Port Gwadar Gatehouse | - | - | - | -
7 | 2 | 3 | 2 | 7232 | Port Gwadar Maintenance Shop | - | - | - | -
7 | 2 | 3 | 3 | 7233 | Port Gwadar Security Building | - | - | - | -
7 | 2 | 3 | 4 | 7234 | Port Gwadar Electrical Switchrooms | - | - | - | -
7 | 2 | 3 | 5 | 7235 | Guardhouse & Security Gate | - | - | - | -
7 | 2 | 3 | 6 | 7236 | Mobile Equipment | - | - | - | -
7 | 2 | 3 | 9 | 7239 | Utilities & Services | - | - | - | -
7 | 2 | 4 | 0 | 7240 | Port Earthworks & Drainage | - | - | - | -
7 | 2 | 4 | 1 | 7241 | Bulk Site Earthworks | - | - | - | -
7 | 2 | 4 | 2 | 7242 | Detailed Site Earthworks | - | - | - | -
7 | 2 | 4 | 3 | 7243 | Site Drainage & Culverts | - | - | - | -
7 | 2 | 4 | 4 | 7244 | In-Plant Roads | - | - | - | -
7 | 2 | 4 | 5 | 7245 | Carparks & Hardstand Areas | - | - | - | -
7 | 2 | 4 | 6 | 7246 | Site Improvements | - | - | - | -
7 | 2 | 4 | 7 | 7247 | Site Security Fencing | - | - | - | -
7 | 2 | 4 | 8 | 7248 | Underground Services | - | - | - | -
7 | 2 | 4 | 9 | 7249 | Utilities & Services | - | - | - | -
7 | 2 | 5 | 0 | 7250 | Concentrate Port offshore | - | - | - | -
7 | 2 | 5 | 1 | 7251 | Navigation & Dredging | - | - | - | -
7 | 2 | 5 | 2 | 7252 | Berth Structure | - | - | - | -
7 | 2 | 5 | 3 | 7253 | Shiploading | - | - | - | -
7 | 2 | 5 | 4 | 7254 | Marine Services | - | - | - | -
7 | 2 | 5 | 5 | 7255 | Coastal Structures | - | - | - | -
7 | 2 | 5 | 6 | 7256 | Navigation Aids | - | - | - | -
7 | 2 | 5 | 7 | 7257 | Mooring Systems | - | - | - | -
7 | 2 | 5 | 9 | 7259 | Utilities & Services | - | - | - | -
7 | 2 | 6 | 0 | 7260 | LNG Import Terminal | - | - | - | -
7 | 2 | 6 | 1 | 7261 | Navigation & Dredging | - | - | - | -
7 | 2 | 6 | 2 | 7262 | Berth Structure | - | - | - | -
7 | 2 | 6 | 3 | 7263 | Unloading System | - | - | - | -
7 | 2 | 6 | 4 | 7264 | Marine Services | - | - | - | -
7 | 2 | 6 | 5 | 7265 | Coastal Structures | - | - | - | -
7 | 2 | 6 | 6 | 7266 | Navigation Aids | - | - | - | -
7 | 2 | 6 | 7 | 7267 | Mooring Systems | - | - | - | -
7 | 2 | 6 | 9 | 7269 | Utilities & Services | - | - | - | -
7 | 2 | 8 | 0 | 7280 | SWRO Plant | - | - | - | -
7 | 2 | 8 | 1 | 7281 | Intake System | - | - | - | -
7 | 2 | 8 | 2 | 7282 | Ro Plant | - | - | - | -
7 | 2 | 8 | 3 | 7283 | Brine Discharge System | - | - | - | -
7 | 2 | 8 | 4 | 7284 | Coastal Structures | - | - | - | -
7 | 2 | 8 | 5 | 7285 | Bulk Earthworks | - | - | - | -
7 | 2 | 8 | 6 | 7286 | Roads & Paving | - | - | - | -
7 | 2 | 8 | 9 | 7289 | Utilities & Services | - | - | - | -
7 | 3 | 0 | 0 | 7300 | Off-Site Port Qasim - PIBT | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 0 | 7310 | Port Earthworks & Drainage | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 1 | 7311 | Bulk Site Earthworks | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 3 | 7313 | Site Drainage & Culverts | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 4 | 7314 | In-Plant Roads | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 5 | 7315 | Carparks & Hardstand Areas | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 6 | 7316 | Site and Soil Improvements | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 7 | 7317 | Site Security Fencing | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 8 | 7318 | Underground Services | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 0 | 7320 | Port Site Utilities & Services | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 1 | 7321 | Stormwater Piping | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 2 | 7322 | Fire Water Storage | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 3 | 7323 | Fire Water Pump House & Reticulation | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 4 | 7324 | Fuel Storage & Dispensing | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 6 | 7326 | Potable Water System | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 7 | 7327 | Sewage Collection & Treatment | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 8 | 7328 | Waste Sorting Facility | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 9 | 7329 | Services Building | - | - | - | -
7 | 3 | 3 | 0 | 7330 | Port Facilities | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 1 | 7331 | Port Qasim PIBT Gatehouse | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 2 | 7332 | Port Qasim PIBT Workshop & Engineering Offices | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 3 | 7333 | Port Qasim PIBT Security Building | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 4 | 7334 | Port Qasim PIBT Weighbridge | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 5 | 7335 | Port Qasim PIBT Security & Weighbridge Office | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 6 | 7336 | Port Qasim PIBT Administration Building | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 7 | 7337 | Port Qasim PIBT Control Room | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 8 | 7338 | Port Qasim PIBT Sampling & Laboratory | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 9 | 7339 | Port Qasim PIBT Washdown Facility | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 0 | 7340 | Port Concentrate Handling | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 1 | 7341 | Truck Discharge Station | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 2 | 7342 | Port Concentrate Conveyor CV-101 & TR-101 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 3 | 7343 | Port Concentrate Conveyor CV-102 & TR-102 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 4 | 7344 | Port Concentrate Port Storage Shed | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 5 | 7345 | Port Concentrate Conveyor CV-103 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 6 | 7346 | Port Concentrate Conveyor CV-104 & TR-103 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 7 | 7347 | Port Concentrate Conveyor CV-105 & TR-104 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 8 | 7348 | PIBT Port Handling Upgrade | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 9 | 7349 | Conveyor Galleries & Structures | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 0 | 7350 | Port Concentrate Offshore | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 1 | 7351 | Navigation & Dredging | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 2 | 7352 | Berth Structure | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 3 | 7353 | Shiploading | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 4 | 7354 | Marine Services | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 5 | 7355 | Coastal Structures | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 6 | 7356 | Navigation Aids | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 7 | 7357 | Mooring Systems | PRDW | PRDW | PRDW | PRDW
7 | 3 | 6 | 0 | 7360 | Port Comms, IT and Controls | PRDW | PRDW | PRDW | PRDW
7 | 3 | 6 | 1 | 7361 | CCTV and Security System | PRDW | PRDW | PRDW | PRDW
7 | 3 | 6 | 2 | 7362 | Port Handling Control System | PRDW | PRDW | PRDW | PRDW
7 | 3 | 6 | 3 | 7363 | IT | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 0 | 7390 | Port Electrical | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 1 | 7391 | Sub Station 1 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 2 | 7392 | Sub Station 2 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 3 | 7393 | Sub Station 3 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 4 | 7394 | PIBT Karachi Electric Substation | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 5 | 7395 | Site Wide Area Lighting | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 6 | 7396 | HV Reticulation | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 7 | 7397 | PIBT Port Generator | - | - | - | -
7 | 4 | 0 | 0 | 7400 | Off-Site Rail Facilities
7 | 4 | 1 | 0 | 7410 | Earthworks & Drainage
7 | 4 | 1 | 1 | 7411 | Bulk Site Earthworks
7 | 4 | 1 | 3 | 7413 | Site Drainage & Culverts
7 | 4 | 1 | 4 | 7414 | In-Plant Roads
7 | 4 | 1 | 5 | 7415 | Carparks & Hardstand Areas
7 | 4 | 1 | 6 | 7416 | Site and Soil Improvements
7 | 4 | 1 | 7 | 7417 | Site Security Fencing
7 | 4 | 1 | 8 | 7418 | Underground Services
7 | 4 | 2 | 0 | 7420 | Site Utilities and Services
7 | 4 | 2 | 1 | 7421 | Stormwater Piping
7 | 4 | 2 | 2 | 7422 | Fire Water Storage
7 | 4 | 2 | 3 | 7423 | Fire Water Pump House & Reticulation
7 | 4 | 2 | 4 | 7424 | Fuel Storage & Dispensing
7 | 4 | 2 | 5 | 7425 | Potable Water System
7 | 4 | 2 | 6 | 7426 | Sewage Collection & Treatment
7 | 4 | 2 | 7 | 7427 | Waste Sorting Facility
7 | 4 | 2 | 8 | 7428 | Telecommunications
7 | 4 | 2 | 9 | 7429 | Signaling
7 | 4 | 3 | 0 | 7430 | Infrastructure and Systems
7 | 4 | 3 | 1 | 7431 | Maintenance Yard Sidings
7 | 4 | 3 | 2 | 7432 | Operation Sidings
7 | 4 | 3 | 3 | 7433 | Telecommunications
7 | 4 | 3 | 4 | 7434 | CCTV System
7 | 4 | 3 | 5 | 7435 | IT and Systems
7 | 4 | 3 | 6 | 7436 | Control System
7 | 4 | 3 | 7 | 7437 | ML-3 Upgrade Works
7 | 4 | 3 | 8 | 7438 | Rolling Stock Maintenance Facility
7 | 4 | 3 | 9 | 7439 | Rolling Stock Refueling Station
7 | 4 | 4 | 0 | 7440 | Operational Facilities Port
7 | 4 | 4 | 1 | 7441 | Incoming Train Covered Inspection Shed
7 | 4 | 4 | 2 | 7442 | Operation Staff Building
7 | 4 | 4 | 3 | 7443 | In-Motion Weighing Bridge + Weight Bridge Office
7 | 4 | 4 | 4 | 7444 | Reagents FIBC Management Platform
7 | 4 | 4 | 5 | 7445 | Rotainers Management Platform
7 | 4 | 4 | 6 | 7446 | Tank Containers, Containers and IBC Management Platform
7 | 4 | 4 | 7 | 7447 | Canteen, Drivers’ Dorm and Training Rooms Building
7 | 4 | 4 | 8 | 7448 | CuCon Security + Weight Bridge Office
7 | 4 | 4 | 9 | 7449 | Truck Access Gate + Truck Weight Bridge
7 | 4 | 5 | 0 | 7450 | Maintenance Facilities Port
7 | 4 | 5 | 1 | 7451 | Shunting Locomotives Parking Garage
7 | 4 | 5 | 2 | 7452 | Locomotives & Wagons Wash Station
7 | 4 | 5 | 3 | 7453 | Wagons And Locomotives Paint Booth
7 | 4 | 5 | 4 | 7454 | Underfloor Wheel Lathe
7 | 4 | 5 | 5 | 7455 | Fuel Storage
7 | 4 | 5 | 6 | 7456 | Pre-inpection and Refuelling shed
7 | 4 | 5 | 7 | 7457 | Major Assemblies and Spare Parts Store
7 | 4 | 5 | 8 | 7458 | Main Maintenance Workshop
7 | 4 | 6 | 0 | 7460 | Spur Line & Main line
7 | 4 | 6 | 1 | 7461 | Permanent Way
7 | 4 | 6 | 2 | 7462 | Koh-i-Dalil Station
7 | 4 | 6 | 3 | 7463 | Reko Diq Terminal Station
7 | 4 | 6 | 4 | 7464 | Engineering Structures
7 | 4 | 6 | 5 | 7465 | Level Crossings
7 | 4 | 6 | 6 | 7466 | Electrical and Power
7 | 4 | 6 | 7 | 7467 | Signaling
7 | 4 | 6 | 8 | 7468 | Telecommunications
7 | 4 | 7 | 0 | 7470 | Temporary Loading Facility
7 | 4 | 7 | 1 | 7471 | Incoming Train Covered Inspection Shed
7 | 4 | 7 | 2 | 7472 | Operation Staff Building
7 | 4 | 7 | 3 | 7473 | In-motion Weighing Bridge + Office
7 | 4 | 7 | 4 | 7474 | Washing Station
7 | 4 | 7 | 5 | 7475 | Wagons and Locomotives Running Shed + Refueling Station
7 | 4 | 7 | 6 | 7476 | Rotainers and Containers Handling and Repairing Platform
7 | 4 | 7 | 7 | 7477 | Fencing and Gates
7 | 4 | 7 | 8 | 7478 | CCTV System
7 | 4 | 7 | 9 | 7479 | Power Supply and Distribution
7 | 4 | 8 | 0 | 7480 | Rolling Stock
7 | 4 | 8 | 1 | 7481 | Main Line ocomotives
7 | 4 | 8 | 2 | 7482 | Shunting Locomotives
7 | 4 | 8 | 3 | 7483 | Wagons
7 | 4 | 8 | 4 | 7484 | Rotainers
7 | 4 | 8 | 5 | 7485 | Tanktainers
7 | 4 | 8 | 6 | 7486 | Shipping Containers
7 | 4 | 8 | 7 | 7487 | Mobile Equipment
7 | 4 | 9 | 0 | 7490 | Electrical Port
7 | 4 | 9 | 1 | 7491 | Sub-station
7 | 4 | 9 | 2 | 7492 | Site Wide Area Lighting
8 | 0 | 0 | 0 | 8000 | Indirect Costs (Owner)
8 | 1 | 0 | 0 | 8100 | Owner's Costs (Common Construction Facilities and Services)
8 | 1 | 0 | 0 | 8100 | Project Costs
8 | 1 | 1 | 1 | 8111 | Project Management | - | - | - | -
8 | 1 | 1 | 2 | 8112 | Project Controls
8 | 1 | 1 | 3 | 8113 | Engineering and Procurement
8 | 1 | 1 | 4 | 8114 | Construction Management
8 | 1 | 1 | 5 | 8115 | Legal and Permitting
8 | 1 | 1 | 6 | 8116 | Public Relations
8 | 1 | 1 | 8 | 8118 | Community Engagement
8 | 1 | 1 | 9 | 8119 | General and Administration
8 | 1 | 2 | 0 | 8120 | Spares and Inventory | RDMC | RDMC | RDMC | RDMC
8 | 1 | 2 | 1 | 8121 | Spares
8 | 1 | 2 | 2 | 8122 | First Fills
8 | 1 | 3 | 0 | 8130 | Pre-Production Operations
8 | 1 | 3 | 1 | 8131 | Recruitment and Training of Operation and Maintenance Staff
8 | 1 | 3 | 2 | 8132 | Mobile Fleet Supporting Operations
8 | 1 | 3 | 3 | 8133 | Wet Commissioning
8 | 1 | 3 | 4 | 8134 | Post-Commissioning Modifications
8 | 1 | 3 | 5 | 8135 | Ramp-Up
8 | 1 | 3 | 6 | 8136 | Working Capital
8 | 1 | 4 | 0 | 8140 | Studies
8 | 1 | 5 | 0 | 8150 | Closure and Rehabilitation
8 | 1 | 6 | 0 | 8160 | Health Security and Safety
8 | 1 | 6 | 1 | 8161 | Clinic
8 | 1 | 6 | 2 | 8162 | Emergency Response
8 | 1 | 6 | 3 | 8163 | Security
8 | 1 | 6 | 4 | 8164 | Safety
8 | 1 | 7 | 0 | 8170 | Operational Readiness | - | - | - | -
8 | 1 | 8 | 0 | 8180 | Owner’s Management
8 | 1 | 8 | 1 | 8181 | Team
8 | 1 | 8 | 2 | 8182 | Nonmanual Labour Expenses
8 | 1 | 8 | 3 | 8183 | Home Office Expenses
8 | 1 | 8 | 4 | 8184 | Project Office Expenses
8 | 1 | 8 | 5 | 8185 | Site Office Expenses
8 | 8 | 1 | 0 | 8810 | Allowance (Early Works)
8 | 9 | 0 | 0 | 8900 | Contingency and Reserve
8 | 9 | 1 | 0 | 8910 | Cost Contingency
8 | 9 | 2 | 0 | 8920 | Schedule Contingency
8 | 9 | 3 | 0 | 8930 | Owner Cost Reserve
9 | 0 | 0 | 0 | 9000 | Indirect Costs (Other Parties)
9 | 1 | 0 | 0 | 9100 | Indirect Costs (Implementation Contractors, EPCM)
9 | 1 | 1 | 0 | 9110 | EPCM Cost | - | - | - | -
9 | 1 | 1 | 1 | 9111 | EP Cost | - | - | - | -
9 | 1 | 1 | 2 | 9112 | CM Cost | - | - | - | -
9 | 1 | 1 | 6 | 9116 | Vendor Field Representatives | - | - | - | -
9 | 1 | 1 | 9 | 9119 | Miscellaneous Engineering, Construction Management Services Costs | - | - | - | -
9 | 1 | 2 | 0 | 9120 | Temporary Facilities
9 | 1 | 2 | 1 | 9121 | Offices and Support Buildings
9 | 1 | 2 | 2 | 9122 | Warehouse and Yards
9 | 1 | 2 | 3 | 9123 | Shelters
9 | 1 | 2 | 4 | 9124 | Power Generation
9 | 1 | 2 | 5 | 9125 | Aggregate and Concrete
9 | 1 | 2 | 6 | 9126 | Water System
9 | 1 | 2 | 7 | 9127 | Fuel Stations
9 | 1 | 3 | 0 | 9130 | Temporary Services
9 | 1 | 3 | 1 | 9131 | Power
9 | 1 | 3 | 2 | 9132 | Maintenance and Cleanup
9 | 1 | 3 | 3 | 9133 | Personnel Transportation
9 | 1 | 3 | 4 | 9134 | Survey, Inspection, and Quality Control
9 | 1 | 3 | 5 | 9135 | Medical and Security
9 | 1 | 3 | 6 | 9136 | Heating
9 | 1 | 3 | 7 | 9137 | Fuel Supply
9 | 1 | 3 | 8 | 9138 | Water, Sewage, and Waste Disposal
9 | 1 | 3 | 9 | 9139 | Other Functions
9 | 1 | 4 | 0 | 9140 | Construction Equipment
9 | 1 | 4 | 1 | 9141 | Cranes
9 | 1 | 4 | 2 | 9142 | Vehicles
9 | 1 | 4 | 3 | 9143 | Mobile Equipment
9 | 1 | 4 | 4 | 9144 | Specialty Equipment
9 | 1 | 5 | 0 | 9150 | Environmental, Safety, and Health
9 | 1 | 5 | 1 | 9151 | Environmental
9 | 1 | 5 | 2 | 9152 | Safety
9 | 1 | 5 | 3 | 9153 | Health
9 | 1 | 6 | 0 | 9160 | Temporary Camp and Catering
9 | 1 | 6 | 1 | 9161 | Facilities
9 | 1 | 6 | 2 | 9162 | Catering
9 | 1 | 7 | 0 | 9170 | Freight / Traffic Warehouse Services and Logistics
9 | 1 | 7 | 1 | 9171 | Offshore Inland Freight
9 | 1 | 7 | 2 | 9172 | Marine Transportation
9 | 1 | 7 | 3 | 9173 | Onshore Inland Freight
9 | 1 | 7 | 4 | 9174 | Air Freight
9 | 1 | 7 | 5 | 9175 | Brokerage and Agent Fees
9 | 1 | 7 | 6 | 9176 | Import Duties
9 | 1 | 7 | 7 | 9177 | Warehousing Service
9 | 1 | 8 | 0 | 9180 | Commissioning
9 | 1 | 8 | 1 | 9181 | Owners Team
9 | 1 | 8 | 2 | 9182 | EPCM
9 | 1 | 8 | 3 | 9183 | Contractor Support

## Discipline Codes
DISCIPLINE CODES
Code | Discipline/Function Identifier
A | Architectural | Pending
B | Project Controls | Updated
C | Civil/Concrete
D | Supply Chain
E | Electrical
F | Process
G | General
H | Health & Safety / Security
I | Instrumentation
J | Environmental / Social Impact
L | Human Resources
M | Mechanical
N | Mining
P | Piping
Q | Quality & Control / HAZOP / HAZID / Risk
S | Structural
T | Geotechnical
U | Pipeline
W | Earthworks / Drainage / Fencing / Roads / Water

## Document and Drawing Type
Document and Drawing Types
Code | Document Type identifier | Description
GENERAL
AUT | Authority | - Permitting - Authority Implementation Plan - Authority Approval Packages - Regulatory Compliance - Environmental Permitting Compliance Requirements | AUT
BLT | Battery Limit | - Battery Limit Table | BLT
BOE | Basis of Estimate |  | BOE
BOS | Basis of Schedule |  | BOS
BOM | Bill of Material |  | BOM
CAL | Calculation |  | CAL
CHR | Chart | Organization Chart, Department Chart | CHR
CON | Contract | Any contract documentation | CON
DBD | Design Basis and Criteria | Design Criteria of the Project | DBD
DBK | Project Data Book | - Manufacturer Data Records | DBK
DDR | Document and Data Register | Master Data and Document Register for Supplier, Sub-Contractors | DDR
DEM | Demolition | Demolition Documents | DEM
DST | Datasheet |  | DST
DTA | Data (Digital Record) | Any data e.g. Survey Data | DTA
EQL | Equipment List | Specific list for equipments | EQL
EST | Estimates |  | EST
EXE | Execution | Can be used for Supplier Data - if not specify on the list | EXE
FRM | Forms |  | FRM
GDL | Guideline | - Guideline - Protocols | GDL
HAC | Hazard Classification | HAZOP, Hazard Analysis, Hazard identification | HAC
HMB | Heat Material Balance |  | HMB
IDX | Index | Technical and Non-technical | IDX
INS | Instructions | e.g. operation instructions, installation instructions | INS
IOM | Installation Operation and Maintenance Manual |  | IOM
ITP | Inspection Test Plan |  | ITP
IWP | Installation Work Package |  | IWP
LST | List/Matrix | Technical List: Valve List, Motor List, Instrument List, Spare Part List Non-Technical List: Distribution Matrix, Communication Matrix | LST
LTR | Letter |  | LTR
MAN | Manual |  | MAN
MDL | Models | - 3Models | MDL
MDR | Master Document Register | Document Register for Engineering - Documentation System Description - Document Filing Index - Transmittal Log - Gate Review Completed | MDR
MEM | Memorandum |  | MEM
MOM | Minutes of Meeting |  | MOM
MTO | Material Take Off |  | MTO
NAR | Narrative | - Process Control Narrative - Safeguarding Narrative | NAR
NCR | Non-Conformance Report |  | NCR
PCN | Project Change Notice |  | PCN
PDR | Procedure Deviation Request |  | PDR
PHL | Philosophy |  | PHL
DOCUMENTS
PLN | Plan | Used for non-technical plan i.e. Engineering Plan, Risk Plan, HSE Plan, Contract & Procurement Plan, HR plan, Project Execution Plan, Study Plan. etc. | PLN
PLC | Policy |  | PLC
PRC | Procedure | Document represents the procedure as prescribed by the various departments. The practices generally relate to the way in which work is to be done within or for the department and also the approved way in which the Company deals with Contractors, and other organizations | PRC
PRO | Procurement | Any procurement documentation | PRO
QAD | Quality Assurance Documents | Any quality assurance documents. Except Quality Management Plan can use PLN | QAD
QRA | Quantitive Risk Assessment | Structured approach to measuring and analyzing risk using numerical data | QRA
REQ | Request | - Travel request - Any requests | REQ
RFA | Recommendation for Award |  | RFA
RFI | Request for Information |  | RFI
RPT | Report | Technical Report: Geotechnical Investigation Report, , etc. Non-technical Report: Safety Monthly report | RPT
SCH | Schedule |  | SCH
SMP | Sample | - Interior Design and Furniture Sample - Finish Boards | SMP
SOP | Standard Operating Procedure |  | SOP
SOW | Scope of Work | Document outlines the extent of work to be performed by others. The SOW may include functional specifications when a functional specification is not written which typically occurs when the contents of a functional specification is minimal (2 pages). | SOW
SPC | Specification | Document represents the design and performance requirements for materials, parts, plant and equipment | SPC
SPL | Piping Specialty Item List |  | SPL
STD | Standards | For any standards, codes, and regulation documents, are generally controlled | STD
STR | Strategy |  | STR
SUM | Summary |  | SUM
TDM | Technical Decision Memorandum |  | TDM
TDN | Trends | Project Controls Trends | TDN
TMP | Templates |  | TMP
TOR | Terms of Reference |  | TOR
TRP | Test Report | - Concrete test report - Any test report - Soil test report - Non-Destruction Examination Test Report - Any Test Report | TRP
TVR | Turnover Dossier |  | TVR
VIS | Visualisation | - Drone Video | VIS
WLD | Welding | Any welding documents | WLD
DRAWINGS
BLT | Battery Limit | - Battery Limit Drawings | BLT
CAE | Cause and Effect Drawing | - Cause and Effect Drawing, etc. | CAE
CRV | Curves |  | CRV
DEM | Demolition | Demolition Drawings | DEM
DIA | Diagram | - Traffic Diagram - Schematic Diagram - Block Diagram | DIA
DID | Ducting and Instrument Diagram | HVAC Utility Piping Ducting and Instrumentation Diagram | DID
DTL | Details | Any drawings details | DTL
EHT | Electrical Heat Tracing Isometric |  | EHT
ELE | Elevation | Any drawings elevation | ELE
FND | Foundation Drawings | Any foundation drawings | FND
GAD | General Arrangement | Any general arrangements drawings | GAD
ITD | Instrumentation Drawing |  | ITD
ISO | Isometrics | Drawing provides a three-dimensional layout of the equipment and piping. | ISO
LAY | Layout | Any drawings layout | LAY
MSD | Material Selection Diagram |  | MSD
PFD | Process Flow Diagram |  | PFD
PID | Piping and Instrumentation Diagram |  | PID
PLN | Plan | Any drawings plan | PLN
PPL | Plot Plan | Site Plot Plan | PPL
PSP | Piping Support | Drawing piping support. | PSP
SEC | Section | Any drawings section | SEC
SHP | Shop Drawings | Supplier Shop Drawings - Fabrication Drawings - Fabrication Steel Drawings - Erection Drawings - Plate Schedule - Spool Drawings - etc. | SHP
SKT | Sketch | Any drawings sketch | SKT
SLD | Single Line Diagram | Drawing provides a representation of an electrical system. | SLD
SSD | Structural Steel Drawings | Engineering (Design) | SSD
STD | Standard Drawings | Drawing shows the materials, set out standard construction details and provide general design data. | STD
TIE | Tie-In |  | TIE