## Register
REKO DIQ MINING PROJECT - E516B - Supplier Document & Drawing Register (SDDR)
Project Number | Package Number | Area/ WBS No. | Discipline | Document Type | Sequential Number | Revision | Document Number | Sht. # of # | Area / Facility | Column1 | Broad Type | Full Title | Due Date | Doc Owner | IFR Transmittal Date | IFC/IFU Transmittal Date | PPE Doc Status | % Complete | As Built Required (Y/N) | Certified Final Required (Y/N) | Tag Number (if any) | Comments | ABB Document ID | Sub-supplier | issued For
6105A | E516B | 0000 | G | DDR | 0001 | A | 6105AE516B-0000-GDDR-0001 |  | General | Project Document List | Document and Data Register | General - Project Document List - Document and Data Register | 06.03.2026 | Mario Reitze |  |  |  | 0% |  |  | General |  | 4HCH017794 | ABB | For Information
6105A | E516B | 0000 | G | CHR | 0001 | A | 6105AE516B-0000-GCHR-0001 |  | General | ABB Organization | Chart | General - ABB Organization - Chart | 06.03.2026 | Thomas Krueger |  |  |  | 0% |  |  | General |  | 4HCH017795 | ABB | For Information
6105A | E516B | 0000 | G | PLN | 0001 | A | 6105AE516B-0000-GPLN-0001 |  | General | Project Communication | Plan | General - Project Communication - Plan | 06.03.2026 | Thomas Krueger |  |  |  | 0% |  |  | General |  | 4HCH017796 | ABB | For Information
6105A | E516B | 0000 | G | SCH | 0001 | A | 6105AE516B-0000-GSCH-0001 |  | General | Project Baseline | Schedule | General - Project Baseline - Schedule | 06.03.2026 | Milan Vucelic |  |  |  | 0% |  |  | General |  | 4HCH017797 | ABB | For Approval
6105A | E516B | 0000 | G | SCH | 0002 | M | 6105AE516B-0000-GSCH-0002 |  | General | Project Weekly Update | Schedule | General - Project Weekly Update - Schedule | 26.02.2026 | Milan Vucelic | 2026-05-28 |  |  | 33% |  |  | General |  | 4HCH017798 | ABB | For Information
6105A | E516B | 0000 | G | PLN | 0002 | A | 6105AE516B-0000-GPLN-0002 |  | General | Project Quality | Plan | General - Project Quality - Plan | 29.05.2026 | Thomas Krueger |  |  |  | 0% |  |  | General |  | 4HCH017799 | ABB | For Information
6105A | E516B | 6200 | E | TRP | 0001 | A | 6105AE516B-6200-ETRP-0001 |  | On-Site Power Supply and Transmission | E-House - 6200-SR-051 | Test Report | On-Site Power Supply and Transmission - E-House - 6200-SR-051 - Test Report | 08.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6200-SR-051 |  | 4HCH017800 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | CAL | 0001 | A | 6105AE516B-6286-ECAL-0001 |  | Mining Open Pit | E-House Design Fire Protection System - 6286-SR-002 | Calculation | Mining Open Pit - E-House Design Fire Protection System - 6286-SR-002 - Calculation | 15.05.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-002 |  | 4HCH017801 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | CAL | 0004 | A | 6105AE516B-6286-ECAL-0004 |  | Mining Open Pit | E-House Design HVAC - 6286-SR-002 | Calculation | Mining Open Pit - E-House Design HVAC - 6286-SR-002 - Calculation | 17.04.2026 | Lazar Kobiljski | 2026-04-28 |  | Approved | 100% |  |  | 6286-SR-002 |  | 4HCH017802 | Alex Sistemi | For Approval
6105A | E516B | 6200 | E | GAD | 0001 | A | 6105AE516B-6200-EGAD-0001 |  | On-Site Power Supply and Transmission | E-House Assembly Drawing - 6200-SR-051 | General Arrangement | On-Site Power Supply and Transmission - E-House Assembly Drawing - 6200-SR-051 - General Arrangement | 08.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6200-SR-051 |  | 4HCH017803 | Alex Sistemi | For Information
6105A | E516B | 6200 | E | DIA | 0001 | A | 6105AE516B-6200-EDIA-0001 |  | On-Site Power Supply and Transmission | E-House Detail Design Drawing Auxiliaries - 6200-SR-051 | Diagram | On-Site Power Supply and Transmission - E-House Detail Design Drawing Auxiliaries - 6200-SR-051 - Diagram | 20.03.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6200-SR-051 |  | 4HCH017804 | Alex Sistemi | For Approval
6105A | E516B | 6200 | E | DIA | 0002 | A | 6105AE516B-6200-EDIA-0002 |  | On-Site Power Supply and Transmission | E-House Internal Interconnections - 6200-SR-051 | Diagram | On-Site Power Supply and Transmission - E-House Internal Interconnections - 6200-SR-051 - Diagram | 12.06.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6200-SR-051 |  | 4HCH017805 | Alex Sistemi | For Information
6105A | E516B | 6262 | E | TRP | 0001 | A | 6105AE516B-6262-ETRP-0001 |  | Emergency Power Substation 1 and Control Room 1 | E-House - 6262-SR-001 | Test Report | Emergency Power Substation 1 and Control Room 1 - E-House - 6262-SR-001 - Test Report | 08.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6262-SR-001 |  | 4HCH017806 | Alex Sistemi | For Information
6105A | E516B | 6292 | E | TRP | 0001 | A | 6105AE516B-6292-ETRP-0001 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House - 6292-SR-001 | Test Report | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House - 6292-SR-001 - Test Report | 12.02.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6292-SR-001 |  | 4HCH017807 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | TRP | 0001 | A | 6105AE516B-6286-ETRP-0001 |  | Mining Open Pit | E-House - 6286-SR-001 | Test Report | Mining Open Pit - E-House - 6286-SR-001 - Test Report | 08.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-001 |  | 4HCH017808 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | TRP | 0002 | A | 6105AE516B-6286-ETRP-0002 |  | Mining Open Pit | E-House - 6286-SR-002 | Test Report | Mining Open Pit - E-House - 6286-SR-002 - Test Report | 08.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-002 |  | 4HCH017809 | Alex Sistemi | For Information
6105A | E516B | 6200 | E | DIA | 0003 | A | 6105AE516B-6200-EDIA-0003 |  | On-Site Power Supply and Transmission | E-House Wiring Auxiliary Panels - 6200-SR-051 | Diagram | On-Site Power Supply and Transmission - E-House Wiring Auxiliary Panels - 6200-SR-051 - Diagram | 12.06.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6200-SR-051 |  | 4HCH017810 | Alex Sistemi | For Approval
6105A | E516B | 6200 | E | CAL | 0001 | A | 6105AE516B-6200-ECAL-0001 |  | On-Site Power Supply and Transmission | E-House Design Fire Protection System - 6200-SR-051 | Calculation | On-Site Power Supply and Transmission - E-House Design Fire Protection System - 6200-SR-051 - Calculation | 15.05.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6200-SR-051 |  | 4HCH017811 | Alex Sistemi | For Approval
6105A | E516B | 6262 | E | CAL | 0002 | A | 6105AE516B-6262-ECAL-0002 |  | Emergency Power Substation 1 and Control Room 1 | E-House Design Fire Protection System - 6262-SR-001 | Calculation | Emergency Power Substation 1 and Control Room 1 - E-House Design Fire Protection System - 6262-SR-001 - Calculation | 17.04.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6262-SR-001 |  | 4HCH017812 | Alex Sistemi | For Approval
6105A | E516B | 6292 | E | CAL | 0001 | A | 6105AE516B-6292-ECAL-0001 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Design Fire Protection System - 6292-SR-001 | Calculation | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Design Fire Protection System - 6292-SR-001 - Calculation | 22.05.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6292-SR-001 |  | 4HCH017813 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | CAL | 0002 | A | 6105AE516B-6286-ECAL-0002 |  | Mining Open Pit | E-House Design Fire Protection System - 6286-SR-001 | Calculation | Mining Open Pit - E-House Design Fire Protection System - 6286-SR-001 - Calculation | 15.05.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-001 |  | 4HCH017814 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | GAD | 0001 | D | 6105AE516B-6286-EGAD-0001 |  | Mining Open Pit | E-House Drawing - 6286-SR-002 | General Arrangement | Mining Open Pit - E-House Drawing - 6286-SR-002 - General Arrangement | 20.02.2026 | Lazar Kobiljski | 2026-04-09 |  | Reviewed | 33% |  |  | 6286-SR-002 |  | 4HCH017815 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | CAL | 0003 | A | 6105AE516B-6286-ECAL-0003 |  | Mining Open Pit | E-House Design HVAC - 6286-SR-001 | Calculation | Mining Open Pit - E-House Design HVAC - 6286-SR-001 - Calculation | 17.04.2026 | Lazar Kobiljski | 2026-04-28 |  | Approved | 100% |  |  | 6286-SR-001 |  | 4HCH017816 | Alex Sistemi | For Approval
6105A | E516B | 6200 | E | CAL | 0003 | A | 6105AE516B-6200-ECAL-0003 |  | On-Site Power Supply and Transmission | E-House Design HVAC - 6200-SR-051 | Calculation | On-Site Power Supply and Transmission - E-House Design HVAC - 6200-SR-051 - Calculation |  | Lazar Kobiljski | 2026-04-28 |  | Approved | 100% |  |  | 6200-SR-051 |  | 4HCH017817 | Alex Sistemi | For Approval
6105A | E516B | 6262 | E | CAL | 0004 | A | 6105AE516B-6262-ECAL-0004 |  | Emergency Power Substation 1 and Control Room 1 | E-House Design HVAC - 6262-SR-001 | Calculation | Emergency Power Substation 1 and Control Room 1 - E-House Design HVAC - 6262-SR-001 - Calculation |  | Lazar Kobiljski | 2026-04-28 |  | Approved | 100% |  |  | 6262-SR-001 |  | 4HCH017818 | Alex Sistemi | For Approval
6105A | E516B | 6292 | E | CAL | 0002 | A | 6105AE516B-6292-ECAL-0002 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Design HVAC - 6292-SR-001 | Calculation | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Design HVAC - 6292-SR-001 - Calculation | 24.04.2026 | Lazar Kobiljski | 2026-04-28 |  | Approved | 100% |  |  | 6292-SR-001 |  | 4HCH017819 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | SSD | 0001 | A | 6105AE516B-6286-ESSD-0001 |  | Mining Open Pit | E-House Detail - 6286-SR-001 | Structural Steel Drawings | Mining Open Pit - E-House Detail - 6286-SR-001 - Structural Steel Drawings | 08.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Approved | 100% |  |  | 6286-SR-001 |  | 4HCH017820 | Alex Sistemi | For Approval
6105A | E516B | 6262 | E | CAL | 0005 | A | 6105AE516B-6262-ECAL-0005 |  | Mining Open Pit | E-House Design Lighting - 6286-SR-002 | Calculation | Mining Open Pit - E-House Design Lighting - 6286-SR-002 - Calculation | 20.03.2026 | Lazar Kobiljski | 2026-06-04 |  |  | 33% |  |  | 6286-SR-002 |  | 4HCH017821 | Alex Sistemi | For Information
6105A | E516B | 6200 | E | CAL | 0004 | A | 6105AE516B-6200-ECAL-0004 |  | On-Site Power Supply and Transmission | E-House Design Lighting - 6200-SR-051 | Calculation | On-Site Power Supply and Transmission - E-House Design Lighting - 6200-SR-051 - Calculation | 20.02.2026 | Lazar Kobiljski | 2026-06-04 |  |  | 33% |  |  | 6200-SR-051 |  | 4HCH017822 | Alex Sistemi | For Information
6105A | E516B | 6262 | E | CAL | 0006 | A | 6105AE516B-6262-ECAL-0006 |  | Emergency Power Substation 1 and Control Room 1 | E-House Design Lighting - 6262-SR-001 | Calculation | Emergency Power Substation 1 and Control Room 1 - E-House Design Lighting - 6262-SR-001 - Calculation | 08.01.2027 | Lazar Kobiljski | 2026-06-04 |  |  | 33% |  |  | 6262-SR-001 |  | 4HCH017823 | Alex Sistemi | For Information
6105A | E516B | 6292 | E | CAL | 0003 | A | 6105AE516B-6292-ECAL-0003 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Design Lighting - 6292-SR-001 | Calculation | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Design Lighting - 6292-SR-001 - Calculation | 22.05.2026 | Lazar Kobiljski | 2026-06-04 |  |  | 33% |  |  | 6292-SR-001 |  | 4HCH017824 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | FND | 0001 | A | 6105AE516B-6286-EFND-0001 |  | Mining Open Pit | E-House Foundation Plan - 6286-SR-001 | Foundation Drawings | Mining Open Pit - E-House Foundation Plan - 6286-SR-001 - Foundation Drawings | 08.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Reviewed | 33% |  |  | 6286-SR-001 |  | 4HCH017825 | Alex Sistemi | For Approval
6105A | E516B | 6200 | E | CAL | 0005 | A | 6105AE516B-6200-ECAL-0005 |  | On-Site Power Supply and Transmission | E-House Structural Static - 6200-SR-051 | Calculation | On-Site Power Supply and Transmission - E-House Structural Static - 6200-SR-051 - Calculation | 20.02.2026 | Lazar Kobiljski | 2026-05-28 |  | Reviewed | 33% |  |  | 6200-SR-051 |  | 4HCH017826 | Alex Sistemi | For Approval
6105A | E516B | 6200 | E | LST | 0001 | A | 6105AE516B-6200-ELST-0001 |  | On-Site Power Supply and Transmission | E-House Electrical Load - 6200-SR-051 | List/Matrix | On-Site Power Supply and Transmission - E-House Electrical Load - 6200-SR-051 - List/Matrix | 26.06.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6200-SR-051 |  | 4HCH017827 | Alex Sistemi | For Information
6105A | E516B | 6262 | E | GAD | 0001 | A | 6105AE516B-6262-EGAD-0001 |  | Emergency Power Substation 1 and Control Room 1 | E-House Assembly Drawing - 6262-SR-001 | General Arrangement | Emergency Power Substation 1 and Control Room 1 - E-House Assembly Drawing - 6262-SR-001 - General Arrangement | 08.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6262-SR-001 |  | 4HCH017828 | Alex Sistemi | For Information
6105A | E516B | 6292 | E | GAD | 0001 | A | 6105AE516B-6292-EGAD-0001 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Assembly Drawing - 6292-SR-001 | General Arrangement | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Assembly Drawing - 6292-SR-001 - General Arrangement | 12.02.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6292-SR-001 |  | 4HCH017829 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | GAD | 0002 | A | 6105AE516B-6286-EGAD-0002 |  | Mining Open Pit | E-House Assembly Drawing - 6286-SR-001 | General Arrangement | Mining Open Pit - E-House Assembly Drawing - 6286-SR-001 - General Arrangement | 08.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-001 |  | 4HCH017830 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | GAD | 0003 | A | 6105AE516B-6286-EGAD-0003 |  | Mining Open Pit | E-House Assembly Drawing - 6286-SR-002 | General Arrangement | Mining Open Pit - E-House Assembly Drawing - 6286-SR-002 - General Arrangement | 08.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-002 |  | 4HCH017831 | Alex Sistemi | For Information
6105A | E516B | 6200 | E | LST | 0002 | A | 6105AE516B-6200-ELST-0002 |  | On-Site Power Supply and Transmission | E-House Packing - 6200-SR-051 | List/Matrix | On-Site Power Supply and Transmission - E-House Packing - 6200-SR-051 - List/Matrix | 15.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6200-SR-051 |  | 4HCH017832 | Alex Sistemi | For Information
6105A | E516B | 6262 | E | DIA | 0002 | A | 6105AE516B-6262-EDIA-0002 |  | Emergency Power Substation 1 and Control Room 1 | E-House Detail Design Drawing Auxiliaries - 6262-SR-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - E-House Detail Design Drawing Auxiliaries - 6262-SR-001 - Diagram | 12.06.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6262-SR-001 |  | 4HCH017833 | Alex Sistemi | For Approval
6105A | E516B | 6292 | E | DIA | 0015 | A | 6105AE516B-6292-EDIA-0015 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Detail Design Drawing Auxiliaries - 6292-SR-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Detail Design Drawing Auxiliaries - 6292-SR-001 - Diagram | 27.03.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6292-SR-001 |  | 4HCH017834 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | DIA | 0003 | A | 6105AE516B-6286-EDIA-0003 |  | Mining Open Pit | E-House Detail Design Drawing Auxiliaries - 6286-SR-001 | Diagram | Mining Open Pit - E-House Detail Design Drawing Auxiliaries - 6286-SR-001 - Diagram | 12.06.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-001 |  | 4HCH017835 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | DIA | 0004 | A | 6105AE516B-6286-EDIA-0004 |  | Mining Open Pit | E-House Detail Design Drawing Auxiliaries - 6286-SR-002 | Diagram | Mining Open Pit - E-House Detail Design Drawing Auxiliaries - 6286-SR-002 - Diagram | 12.06.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-002 |  | 4HCH017836 | Alex Sistemi | For Approval
6105A | E516B | 6200 | E | GAD | 0005 | A | 6105AE516B-6200-EGAD-0005 |  | On-Site Power Supply and Transmission | E-House Shipping Weights and Dimensions - 6200-SR-051 | General Arrangement | On-Site Power Supply and Transmission - E-House Shipping Weights and Dimensions - 6200-SR-051 - General Arrangement | 15.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6200-SR-051 |  | 4HCH017837 | Alex Sistemi | For Information
6105A | E516B | 6292 | E | DIA | 0014 | A | 6105AE516B-6292-EDIA-0014 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Internal Interconnection s - 6292-SR-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Internal Interconnection s - 6292-SR-001 - Diagram | 19.06.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6292-SR-001 |  | 4HCH017838 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | DIA | 0005 | A | 6105AE516B-6286-EDIA-0005 |  | Mining Open Pit | E-House Internal Interconnection s - 6286-SR-001 | Diagram | Mining Open Pit - E-House Internal Interconnection s - 6286-SR-001 - Diagram | 12.06.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-001 |  | 4HCH017839 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | DIA | 0006 | A | 6105AE516B-6286-EDIA-0006 |  | Mining Open Pit | E-House Internal Interconnection s - 6286-SR-002 | Diagram | Mining Open Pit - E-House Internal Interconnection s - 6286-SR-002 - Diagram | 12.06.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-002 |  | 4HCH017840 | Alex Sistemi | For Information
6105A | E516B | 6262 | E | DIA | 0001 | A | 6105AE516B-6262-EDIA-0001 |  | Emergency Power Substation 1 and Control Room 1 | E-House Internal Interconnection s - 6262-SR-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - E-House Internal Interconnection s - 6262-SR-001 - Diagram | 20.03.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6262-SR-001 |  | 4HCH017841 | Alex Sistemi | For Information
6105A | E516B | 6262 | E | DIA | 0003 | A | 6105AE516B-6262-EDIA-0003 |  | Emergency Power Substation 1 and Control Room 1 | E-House Wiring Auxiliary Panels - 6262-SR-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - E-House Wiring Auxiliary Panels - 6262-SR-001 - Diagram | 12.06.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6262-SR-001 |  | 4HCH017842 | Alex Sistemi | For Approval
6105A | E516B | 6292 | E | DIA | 0001 | A | 6105AE516B-6292-EDIA-0001 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Wiring Auxiliary Panels - 6292-SR-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Wiring Auxiliary Panels - 6292-SR-001 - Diagram | 19.06.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6292-SR-001 |  | 4HCH017843 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | DIA | 0007 | A | 6105AE516B-6286-EDIA-0007 |  | Mining Open Pit | E-House Wiring Auxiliary Panels - 6286-SR-001 | Diagram | Mining Open Pit - E-House Wiring Auxiliary Panels - 6286-SR-001 - Diagram | 30.01.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-001 |  | 4HCH017844 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | DIA | 0008 | A | 6105AE516B-6286-EDIA-0008 |  | Mining Open Pit | E-House Wiring Auxiliary Panels - 6286-SR-002 | Diagram | Mining Open Pit - E-House Wiring Auxiliary Panels - 6286-SR-002 - Diagram | 30.01.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-002 |  | 4HCH017845 | Alex Sistemi | For Approval
6105A | E516B | 6200 | E | GAD | 0007 | D | 6105AE516B-6200-EGAD-0007 |  | On-Site Power Supply and Transmission | E-House Drawing - 6200-SR-051 | General Arrangement | On-Site Power Supply and Transmission - E-House Drawing - 6200-SR-051 - General Arrangement | 20.02.2026 | Lazar Kobiljski | 2026-04-09 |  | Reviewed | 33% |  |  | 6200-SR-051 |  | 4HCH017846 | Alex Sistemi | For Approval
6105A | E516B | 6262 | E | GAD | 0004 | D | 6105AE516B-6262-EGAD-0004 |  | Emergency Power Substation 1 and Control Room 1 | E-House Drawing - 6262-SR-001 | General Arrangement | Emergency Power Substation 1 and Control Room 1 - E-House Drawing - 6262-SR-001 - General Arrangement | 20.02.2026 | Lazar Kobiljski | 2026-04-09 |  | Reviewed | 33% |  |  | 6262-SR-001 |  | 4HCH017847 | Alex Sistemi | For Approval
6105A | E516B | 6292 | E | GAD | 0002 | D | 6105AE516B-6292-EGAD-0002 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Drawing - 6292-SR-001 | General Arrangement | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Drawing - 6292-SR-001 - General Arrangement | 27.02.2026 | Lazar Kobiljski | 2026-04-09 |  | Reviewed | 33% |  |  | 6292-SR-001 |  | 4HCH017848 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | GAD | 0004 | D | 6105AE516B-6286-EGAD-0004 |  | Mining Open Pit | E-House Drawing - 6286-SR-001 | General Arrangement | Mining Open Pit - E-House Drawing - 6286-SR-001 - General Arrangement | 20.02.2026 | Lazar Kobiljski | 2026-04-09 |  | Reviewed | 33% |  |  | 6286-SR-001 |  | 4HCH017849 | Alex Sistemi | For Approval
6105A | E516B | 0000 | E | PRC | 0001 | A | 6105AE516B-0000-EPRC-0001 |  | General | E-House Factory Acceptance Test | Procedure | General - E-House Factory Acceptance Test - Procedure | 25.02.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | General |  | 4HCH017850 | Alex Sistemi | For Information
6105A | E516B | 6200 | E | SSD | 0001 | A | 6105AE516B-6200-ESSD-0001 |  | On-Site Power Supply and Transmission | E-House Detail - 6200-SR051 | Structural Steel Drawings | On-Site Power Supply and Transmission - E-House Detail - 6200-SR051 - Structural Steel Drawings | 08.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Reviewed | 33% |  |  | 6200-SR-051 |  | 4HCH017851 | Alex Sistemi | For Approval
6105A | E516B | 6262 | E | SSD | 0001 | A | 6105AE516B-6262-ESSD-0001 |  | Emergency Power Substation 1 and Control Room 1 | E-House Detail - 6262-SR-001 | Structural Steel Drawings | Emergency Power Substation 1 and Control Room 1 - E-House Detail - 6262-SR-001 - Structural Steel Drawings | 08.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Approved | 100% |  |  | 6262-SR-001 |  | 4HCH017852 | Alex Sistemi | For Approval
6105A | E516B | 6292 | E | SSD | 0001 | A | 6105AE516B-6292-ESSD-0001 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Detail - 6292-SR-001 | Structural Steel Drawings | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Detail - 6292-SR-001 - Structural Steel Drawings | 15.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Approved | 100% |  |  | 6292-SR-001 |  | 4HCH017853 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | SSD | 0002 | A | 6105AE516B-6286-ESSD-0002 |  | Mining Open Pit | E-House Detail - 6286-SR-002 | Structural Steel Drawings | Mining Open Pit - E-House Detail - 6286-SR-002 - Structural Steel Drawings | 08.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Approved | 100% |  |  | 6286-SR-002 |  | 4HCH017854 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | FND | 0002 | A | 6105AE516B-6286-EFND-0002 |  | Mining Open Pit | E-House Foundation Plan - 6286-SR-002 | Foundation Drawings | Mining Open Pit - E-House Foundation Plan - 6286-SR-002 - Foundation Drawings | 08.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Reviewed | 33% |  |  | 6286-SR-002 |  | 4HCH017855 | Alex Sistemi | For Approval
6105A | E516B | 6200 | E | FND | 0001 | A | 6105AE516B-6200-EFND-0001 |  | On-Site Power Supply and Transmission | E-House Foundation Plan - 6200-SR-051 | Foundation Drawings | On-Site Power Supply and Transmission - E-House Foundation Plan - 6200-SR-051 - Foundation Drawings | 08.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Reviewed | 33% |  |  | 6200-SR-051 |  | 4HCH017856 | Alex Sistemi | For Approval
6105A | E516B | 6262 | E | FND | 0001 | A | 6105AE516B-6262-EFND-0001 |  | Emergency Power Substation 1 and Control Room 1 | E-House Foundation Plan - 6262-SR-001 | Foundation Drawings | Emergency Power Substation 1 and Control Room 1 - E-House Foundation Plan - 6262-SR-001 - Foundation Drawings | 08.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Reviewed | 33% |  |  | 6262-SR-001 |  | 4HCH017857 | Alex Sistemi | For Approval
6105A | E516B | 6292 | E | FND | 0001 | A | 6105AE516B-6292-EFND-0001 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Foundation Plan - 6292-SR-001 | Foundation Drawings | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Foundation Plan - 6292-SR-001 - Foundation Drawings | 15.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Reviewed | 33% |  |  | 6292-SR-001 |  | 4HCH017858 | Alex Sistemi | For Approval
6105A | E516B | 0000 | E | ITP | 0001 | A | 6105AE516B-0000-EITP-0001 |  | General | E-House (ITP) | Inspection Test Plan | General - E-House (ITP) - Inspection Test Plan | 28.01.2026 | Lazar Kobiljski | 2026-04-17 |  | Approved | 100% |  |  | General |  | 4HCH017859 | Alex Sistemi | For Approval
6105A | E516B | 6262 | E | CAL | 0007 | A | 6105AE516B-6262-ECAL-0007 |  | Emergency Power Substation 1 and Control Room 1 | E-House Structural Static - 6262-SR-001 | Calculation | Emergency Power Substation 1 and Control Room 1 - E-House Structural Static - 6262-SR-001 - Calculation | 06.03.2026 | Lazar Kobiljski | 2026-05-28 |  | Reviewed | 33% |  |  | 6262-SR-001 |  | 4HCH017860 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | CAL | 0005 | A | 6105AE516B-6286-ECAL-0005 |  | Mining Open Pit | E-House Structural Static - 6286-SR-001 | Calculation | Mining Open Pit - E-House Structural Static - 6286-SR-001 - Calculation | 08.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Reviewed | 33% |  |  | 6286-SR-001 |  | 4HCH017861 | Alex Sistemi | For Approval
6105A | E516B | 6286 | E | CAL | 0008 | A | 6105AE516B-6286-ECAL-0008 |  | Mining Open Pit | E-House Structural Static - 6286-SR-002 | Calculation | Mining Open Pit - E-House Structural Static - 6286-SR-002 - Calculation | 08.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Reviewed | 33% |  |  | 6286-SR-002 |  | 4HCH017862 | Alex Sistemi | For Approval
6105A | E516B | 6292 | E | CAL | 0005 | A | 6105AE516B-6292-ECAL-0005 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Structural Static - 6292-SR-001 | Calculation | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Structural Static - 6292-SR-001 - Calculation | 15.05.2026 | Lazar Kobiljski | 2026-05-28 |  | Reviewed | 33% |  |  | 6292-SR-001 |  | 4HCH017863 | Alex Sistemi | For Approval
6105A | E516B | 6262 | E | LST | 0001 | A | 6105AE516B-6262-ELST-0001 |  | Emergency Power Substation 1 and Control Room 1 | E-House Electrical Load - 6286-SR-001 | List/Matrix | Emergency Power Substation 1 and Control Room 1 - E-House Electrical Load - 6286-SR-001 - List/Matrix | 03.04.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-001 |  | 4HCH017864 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | LST | 0001 | A | 6105AE516B-6286-ELST-0001 |  | Mining Open Pit | E-House Electrical Load - 6286-SR-002 | List/Matrix | Mining Open Pit - E-House Electrical Load - 6286-SR-002 - List/Matrix | 03.04.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-002 |  | 4HCH017865 | Alex Sistemi | For Information
6105A | E516B | 6262 | E | LST | 0002 | A | 6105AE516B-6262-ELST-0002 |  | Emergency Power Substation 1 and Control Room 1 | E-House Electrical Load - 6262-SR-001 | List/Matrix | Emergency Power Substation 1 and Control Room 1 - E-House Electrical Load - 6262-SR-001 - List/Matrix | 26.06.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6262-SR-001 |  | 4HCH017866 | Alex Sistemi | For Information
6105A | E516B | 6292 | E | LST | 0001 | A | 6105AE516B-6292-ELST-0001 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Electrical Load - 6292-SR-001 | List/Matrix | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Electrical Load - 6292-SR-001 - List/Matrix | 03.07.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6292-SR-001 |  | 4HCH017867 | Alex Sistemi | For Information
6105A | E516B | 0000 | E | SPC | 0001 | B | 6105AE516B-0000-ESPC-0001 |  | General | E-House Technical | Specification | General - E-House Technical - Specification | 28.01.2026 | Lazar Kobiljski | 2026-05-05 |  | Approved | 100% |  |  | General |  | 4HCH017868 | Alex Sistemi | For Approval
6105A | E516B | 0000 | E | PRC | 0002 | C | 6105AE516B-0000-EPRC-0002 |  | General | E-House Manufacturer Standard Painting | Procedure | General - E-House Manufacturer Standard Painting - Procedure | 04.02.2026 | Lazar Kobiljski | 2026-06-04 |  | Reviewed | 33% |  |  | General |  | 4HCH017869 | Alex Sistemi | For Information
6105A | E516B | 6200 | E | IOM | 0001 | A | 6105AE516B-6200-EIOM-0001 |  | On-Site Power Supply and Transmission | E-House (IOM) - 6200-SR-051 | Installation Operation and Maintenance Manual | On-Site Power Supply and Transmission - E-House (IOM) - 6200-SR-051 - Installation Operation and Maintenance Manual | 08.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6200-SR-051 |  | 4HCH017870 | Alex Sistemi | For Information
6105A | E516B | 6262 | E | IOM | 0001 | A | 6105AE516B-6262-EIOM-0001 |  | Emergency Power Substation 1 and Control Room 1 | E-House (IOM) - 6262-SR-001 | Installation Operation and Maintenance Manual | Emergency Power Substation 1 and Control Room 1 - E-House (IOM) - 6262-SR-001 - Installation Operation and Maintenance Manual | 08.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6262-SR-001 |  | 4HCH017871 | Alex Sistemi | For Information
6105A | E516B | 6292 | E | IOM | 0001 | A | 6105AE516B-6292-EIOM-0001 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House (IOM) - 6292-SR-001 | Installation Operation and Maintenance Manual | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House (IOM) - 6292-SR-001 - Installation Operation and Maintenance Manual | 12.02.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6292-SR-001 |  | 4HCH017872 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | IOM | 0001 | A | 6105AE516B-6286-EIOM-0001 |  | Mining Open Pit | E-House (IOM) - 6286-SR-001 | Installation Operation and Maintenance Manual | Mining Open Pit - E-House (IOM) - 6286-SR-001 - Installation Operation and Maintenance Manual | 08.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-001 |  | 4HCH017873 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | IOM | 0002 | A | 6105AE516B-6286-EIOM-0002 |  | Mining Open Pit | E-House (IOM) - 6286-SR-002 | Installation Operation and Maintenance Manual | Mining Open Pit - E-House (IOM) - 6286-SR-002 - Installation Operation and Maintenance Manual | 08.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-002 |  | 4HCH017874 | Alex Sistemi | For Information
6105A | E516B | 6262 | E | LST | 0003 | A | 6105AE516B-6262-ELST-0003 |  | Emergency Power Substation 1 and Control Room 1 | E-House Packing - 6262-SR-001 | List/Matrix | Emergency Power Substation 1 and Control Room 1 - E-House Packing - 6262-SR-001 - List/Matrix | 15.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6262-SR-001 |  | 4HCH017875 | Alex Sistemi | For Information
6105A | E516B | 6292 | E | LST | 0002 | A | 6105AE516B-6292-ELST-0002 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Packing - 6292-SR-001 | List/Matrix | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Packing - 6292-SR-001 - List/Matrix | 19.02.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6292-SR-001 |  | 4HCH017876 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | LST | 0002 | A | 6105AE516B-6286-ELST-0002 |  | Mining Open Pit | E-House Packing - 6286-SR-001 | List/Matrix | Mining Open Pit - E-House Packing - 6286-SR-001 - List/Matrix | 15.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-001 |  | 4HCH017877 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | LST | 0003 | A | 6105AE516B-6286-ELST-0003 |  | Mining Open Pit | E-House Packing - 6286-SR-002 | List/Matrix | Mining Open Pit - E-House Packing - 6286-SR-002 - List/Matrix | 15.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-002 |  | 4HCH017878 | Alex Sistemi | For Information
6105A | E516B | 6262 | E | GAD | 0005 | A | 6105AE516B-6262-EGAD-0005 |  | Emergency Power Substation 1 and Control Room 1 | E-House Shipping Weights and Dimensions - 6262-SR-001 | General Arrangement | Emergency Power Substation 1 and Control Room 1 - E-House Shipping Weights and Dimensions - 6262-SR-001 - General Arrangement | 15.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6262-SR-001 |  | 4HCH017879 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | GAD | 0012 | A | 6105AE516B-6286-EGAD-0012 |  | Mining Open Pit | E-House Shipping Weights and Dimensions - 6286-SR-001 | General Arrangement | Mining Open Pit - E-House Shipping Weights and Dimensions - 6286-SR-001 - General Arrangement | 27.03.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-001 |  | 4HCH017880 | Alex Sistemi | For Information
6105A | E516B | 6286 | E | GAD | 0013 | A | 6105AE516B-6286-EGAD-0013 |  | Mining Open Pit | E-House Shipping Weights and Dimensions - 6286-SR-002 | General Arrangement | Mining Open Pit - E-House Shipping Weights and Dimensions - 6286-SR-002 - General Arrangement | 15.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6286-SR-002 |  | 4HCH017881 | Alex Sistemi | For Information
6105A | E516B | 6292 | E | GAD | 0004 | A | 6105AE516B-6292-EGAD-0004 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | E-House Shipping Weights and Dimensions - 6292-SR-001 | General Arrangement | 11/33kV Solar PV Substation 1 and Control Room 1 - E-House Shipping Weights and Dimensions - 6292-SR-001 - General Arrangement | 15.01.2027 | Lazar Kobiljski |  |  |  | 0% |  |  | 6292-SR-001 |  | 4HCH017882 | Alex Sistemi | For Information
6105A | E516B | 0000 | E | INS | 0001 | A | 6105AE516B-0000-EINS-0001 |  | General | E-House Transport, Handling and Storage | Instructions | General - E-House Transport, Handling and Storage - Instructions | 11.12.2026 | Lazar Kobiljski |  |  |  | 0% |  |  | General |  | 4HCH017883 | Alex Sistemi | For Information
6105A | E516B | 0000 | E | ITP | 0002 | A | 6105AE516B-0000-EITP-0002 |  | General | MV AIS (ITP) | Inspection Test Plan | General - MV AIS (ITP) - Inspection Test Plan | 07.04.2026 | Sanja Todoran | 2026-05-18 |  | Approved | 100% |  |  | General |  | 4HCH017884 | ABB CZ | For Approval
6105A | E516B | 0000 | E | PRC | 0003 | A | 6105AE516B-0000-EPRC-0003 |  | General | MV AIS Test | Procedure | General - MV AIS Test - Procedure | 05.05.2026 | Sanja Todoran | 2026-05-18 |  |  | 33% |  |  | General |  | 4HCH017885 | ABB CZ | For Information
6105A | E516B | 6262 | E | TRP | 0002 | A | 6105AE516B-6262-ETRP-0002 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS - 6262-SB-001 | Test Report | Emergency Power Substation 1 and Control Room 1 - MV AIS - 6262-SB-001 - Test Report | 18.09.2026 | Sanja Todoran |  |  |  | 0% |  |  | 6262-SB-001 |  | 4HCH017886 | ABB CZ | For Information
6105A | E516B | 6262 | E | CAL | 0008 | 0 | 6105AE516B-6262-ECAL-0008 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS CT - 6262-SB-001 | Calculation | Emergency Power Substation 1 and Control Room 1 - MV AIS CT - 6262-SB-001 - Calculation | 06.03.2026 | Sanja Todoran | 2026-04-23 | 2026-05-12 | Approved | 100% |  |  | 6262-SB-001 |  | 4HCH017887 | ABB CZ | For Approval
6105A | E516B | 0000 | E | IOM | 0001 | A | 6105AE516B-0000-EIOM-0001 |  | General | MV AIS (IOM) | Installation Operation and Maintenance Manual | General - MV AIS (IOM) - Installation Operation and Maintenance Manual | 18.09.2026 | Sanja Todoran | 2026-05-18 |  |  | 33% |  |  | General |  | 4HCH017888 | ABB CZ | For Information
6105A | E516B | 6262 | E | GAD | 0002 | B | 6105AE516B-6262-EGAD-0002 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS - 6262-SB-001 | General Arrangement | Emergency Power Substation 1 and Control Room 1 - MV AIS - 6262-SB-001 - General Arrangement | 30.01.2026 | Sanja Todoran | 2026-05-20 |  | Approved | 100% |  |  | 6262-SB-001 |  | 4HCH017889 | ABB CZ | For Approval
6105A | E516B | 6262 | E | DIA | 0004 | A | 6105AE516B-6262-EDIA-0004 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS Single Line - 6262-SB-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - MV AIS Single Line - 6262-SB-001 - Diagram | 30.01.2026 | Sanja Todoran | 2026-03-12 |  | Reviewed | 33% |  |  | 6262-SB-001 |  | 4HCH017890 | ABB CZ | For Approval
6105A | E516B | 6262 | E | DIA | 0005 | D | 6105AE516B-6262-EDIA-0005 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS Typical Wiring s Bus Coupler - 6262-SB-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - MV AIS Typical Wiring s Bus Coupler - 6262-SB-001 - Diagram | 24.03.2026 | Sanja Todoran | 2026-05-26 |  | Reviewed | 33% |  |  | 6262-SB-001 |  | 4HCH017891 | ABB CZ | For Approval
6105A | E516B | 6262 | E | DIA | 0006 | 1 | 6105AE516B-6262-EDIA-0006 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS Typical Wiring s Bus Riser - 6262-SB-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - MV AIS Typical Wiring s Bus Riser - 6262-SB-001 - Diagram | 24.03.2026 | Sanja Todoran | 2026-04-17 | 2026-05-26 | Approved | 100% |  |  | 6262-SB-001 |  | 4HCH017892 | ABB CZ | For Approval
6105A | E516B | 6262 | E | DIA | 0007 | D | 6105AE516B-6262-EDIA-0007 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS Typical Wiring s Generator Feeder - 6262-SB-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - MV AIS Typical Wiring s Generator Feeder - 6262-SB-001 - Diagram | 24.03.2026 | Sanja Todoran | 2026-05-26 |  | Reviewed | 33% |  |  | 6262-SB-001 |  | 4HCH017893 | ABB CZ | For Approval
6105A | E516B | 6262 | E | DIA | 0008 | D | 6105AE516B-6262-EDIA-0008 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS Typical Wiring s Load Bank Feeder - 6262-SB-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - MV AIS Typical Wiring s Load Bank Feeder - 6262-SB-001 - Diagram | 24.03.2026 | Sanja Todoran | 2026-05-26 |  | Approved | 100% |  |  | 6262-SB-001 |  | 4HCH017894 | ABB CZ | For Approval
6105A | E516B | 6262 | E | DIA | 0009 | D | 6105AE516B-6262-EDIA-0009 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS Typical Wiring Feeder - 6262-SB-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - MV AIS Typical Wiring Feeder - 6262-SB-001 - Diagram | 24.03.2026 | Sanja Todoran | 2026-05-26 |  | Approved | 100% |  |  | 6262-SB-001 |  | 4HCH017895 | ABB CZ | For Approval
6105A | E516B | 6262 | E | DIA | 0010 | 1 | 6105AE516B-6262-EDIA-0010 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS Typical Wiring Busbar VT - 6262-SB-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - MV AIS Typical Wiring Busbar VT - 6262-SB-001 - Diagram | 24.03.2026 | Sanja Todoran | 2026-04-17 | 2026-05-26 | Approved | 100% |  |  | 6262-SB-001 |  | 4HCH017896 | ABB CZ | For Approval
6105A | E516B | 6262 | E | DIA | 0011 | D | 6105AE516B-6262-EDIA-0011 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS Typical Wiring s Oil Transformer Feeder - 6262-SB-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - MV AIS Typical Wiring s Oil Transformer Feeder - 6262-SB-001 - Diagram | 24.03.2026 | Sanja Todoran | 2026-05-26 |  | Reviewed | 33% |  |  | 6262-SB-001 |  | 4HCH017897 | ABB CZ | For Approval
6105A | E516B | 0000 | E | ITP | 0003 | A | 6105AE516B-0000-EITP-0003 |  | General | 33kV MV GIS (ITP) | Inspection Test Plan | General - 33kV MV GIS (ITP) - Inspection Test Plan | 07.04.2026 | Milan Djurdjevic | 2026-05-19 |  | Approved | 100% |  |  | General |  | 4HCH017898 | ABB CZ | For Approval
6105A | E516B | 0000 | E | PRC | 0004 | A | 6105AE516B-0000-EPRC-0004 |  | General | 33kV MV GIS Test | Procedure | General - 33kV MV GIS Test - Procedure | 05.05.2026 | Milan Djurdjevic | 2026-05-19 |  |  | 33% |  |  | General |  | 4HCH017899 | ABB CZ | For Information
6105A | E516B | 6200 | E | TRP | 0002 | A | 6105AE516B-6200-ETRP-0002 |  | On-Site Power Supply and Transmission | 33kV MV GIS - 6200-SB-051 | Test Report | On-Site Power Supply and Transmission - 33kV MV GIS - 6200-SB-051 - Test Report | 09.10.2026 | Milan Djurdjevic |  |  |  | 0% |  |  | 6200-SB-051 |  | 4HCH017900 | ABB CZ | For Information
6105A | E516B | 6286 | E | TRP | 0003 | A | 6105AE516B-6286-ETRP-0003 |  | Mining Open Pit | 33kV MV GIS - 6286-SB-001 | Test Report | Mining Open Pit - 33kV MV GIS - 6286-SB-001 - Test Report | 09.10.2026 | Milan Djurdjevic |  |  |  | 0% |  |  | 6286-SB-001 |  | 4HCH017901 | ABB CZ | For Information
6105A | E516B | 6286 | E | TRP | 0004 | A | 6105AE516B-6286-ETRP-0004 |  | Mining Open Pit | MV AIS - 6286-SB-002 | Test Report | Mining Open Pit - MV AIS - 6286-SB-002 - Test Report | 18.09.2026 | Sanja Todoran |  |  |  | 0% |  |  | 6286-SB-002 |  | 4HCH017902 | ABB CZ | For Information
6105A | E516B | 6200 | E | CAL | 0007 | 0 | 6105AE516B-6200-ECAL-0007 |  | On-Site Power Supply and Transmission | 33kV MV GIS CT - 6200-SB-051 | Calculation | On-Site Power Supply and Transmission - 33kV MV GIS CT - 6200-SB-051 - Calculation | 06.03.2026 | Milan Djurdjevic | 2026-04-23 | 2026-05-12 | Approved | 100% |  |  | 6200-SB-051 |  | 4HCH017903 | ABB CZ | For Approval
6105A | E516B | 0000 | E | IOM | 0002 | A | 6105AE516B-0000-EIOM-0002 |  | General | MV GIS ZX2 (IOM) | Installation Operation and Maintenance Manual | General - MV GIS ZX2 (IOM) - Installation Operation and Maintenance Manual | 09.10.2026 | Milan Djurdjevic | 2026-05-19 |  |  | 33% |  |  | General |  | 4HCH017904 | ABB CZ | For Information
6105A | E516B | 6200 | E | GAD | 0002 | B | 6105AE516B-6200-EGAD-0002 |  | On-Site Power Supply and Transmission | 33kV MV GIS - 6200-SB-051 | General Arrangement | On-Site Power Supply and Transmission - 33kV MV GIS - 6200-SB-051 - General Arrangement | 30.01.2026 | Milan Djurdjevic | 2026-05-22 |  | Approved | 100% |  |  | 6200-SB-051 |  | 4HCH017905 | ABB CZ | For Approval
6105A | E516B | 6286 | E | GAD | 0005 | B | 6105AE516B-6286-EGAD-0005 |  | Mining Open Pit | 33kV MV GIS - 6286-SB-001 | General Arrangement | Mining Open Pit - 33kV MV GIS - 6286-SB-001 - General Arrangement | 30.01.2026 | Milan Djurdjevic | 2026-05-22 |  | Reviewed | 33% |  |  | 6286-SB-001 |  | 4HCH017906 | ABB CZ | For Approval
6105A | E516B | 6286 | E | GAD | 0006 | B | 6105AE516B-6286-EGAD-0006 |  | Mining Open Pit | MV AIS - 6286-SB-002 | General Arrangement | Mining Open Pit - MV AIS - 6286-SB-002 - General Arrangement | 30.01.2026 | Sanja Todoran | 2026-05-20 |  | Approved | 100% |  |  | 6286-SB-002 |  | 4HCH017907 | ABB CZ | For Approval
6105A | E516B | 6200 | E | DIA | 0006 | B | 6105AE516B-6200-EDIA-0006 |  | On-Site Power Supply and Transmission | 33kV MV GIS Single Line - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Single Line - 6200-SB-051 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-06-04 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH017908 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0009 | B | 6105AE516B-6286-EDIA-0009 |  | Mining Open Pit | 33kV MV GIS Single Line - 6286-SB-001 | Diagram | Mining Open Pit - 33kV MV GIS Single Line - 6286-SB-001 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-06-04 |  | Reviewed | 33% |  |  | 6286-SB-001 |  | 4HCH017909 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0010 | A | 6105AE516B-6286-EDIA-0010 |  | Mining Open Pit | MV AIS Single Line - 6286-SB-002 | Diagram | Mining Open Pit - MV AIS Single Line - 6286-SB-002 - Diagram | 24.03.2026 | Sanja Todoran | 2026-03-12 |  | Reviewed | 33% |  |  | 6286-SB-002 |  | 4HCH017910 | ABB CZ | For Approval
6105A | E516B | 6200 | E | DIA | 0007 | B | 6105AE516B-6200-EDIA-0007 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Bus Coupler Bus A & Bus B- 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Bus Coupler Bus A & Bus B- 6200-SB-051 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH017911 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0011 | C | 6105AE516B-6286-EDIA-0011 |  | Mining Open Pit | MV AIS Typical Wiring s Bus Coupler - 6286-SB-002 | Diagram | Mining Open Pit - MV AIS Typical Wiring s Bus Coupler - 6286-SB-002 - Diagram | 24.03.2026 | Sanja Todoran | 2026-05-26 |  | Approved | 100% |  |  | 6286-SB-002 |  | 4HCH017912 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0012 | 0 | 6105AE516B-6286-EDIA-0012 |  | Mining Open Pit | 33kV MV GIS Typical Wiring Bus Sectionaliser - 6286-SB-001 | Diagram | Mining Open Pit - 33kV MV GIS Typical Wiring Bus Sectionaliser - 6286-SB-001 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-05-18 | 2026-06-04 | Approved | 100% |  |  | 6286-SB-001 |  | 4HCH017913 | ABB CZ | For Approval
6105A | E516B | 6200 | E | DIA | 0008 | B | 6105AE516B-6200-EDIA-0008 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Bus Coupler Bus B & Bus C- 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Bus Coupler Bus B & Bus C- 6200-SB-051 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH017914 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0013 | 0 | 6105AE516B-6286-EDIA-0013 |  | Mining Open Pit | MV AIS Typical Wiring Bus Riser - 6286-SB-002 | Diagram | Mining Open Pit - MV AIS Typical Wiring Bus Riser - 6286-SB-002 - Diagram | 24.03.2026 | Sanja Todoran | 2026-05-04 | 2026-05-26 | Approved | 100% |  |  | 6286-SB-002 |  | 4HCH017915 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0014 | 1 | 6105AE516B-6286-EDIA-0014 |  | Mining Open Pit | 33kV MV GIS Typical Wiring Bus Riser - 6286-SB-001 | Diagram | Mining Open Pit - 33kV MV GIS Typical Wiring Bus Riser - 6286-SB-001 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-04-28 | 2026-06-04 | Approved | 100% |  |  | 6286-SB-001 |  | 4HCH017916 | ABB CZ | For Approval
6105A | E516B | 6200 | E | DIA | 0009 | B | 6105AE516B-6200-EDIA-0009 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Incomer Bus A & Bus C - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Incomer Bus A & Bus C - 6200-SB-051 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-06-05 |  |  | 33% |  |  | 6200-SB-051 |  | 4HCH017917 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0015 | 0 | 6105AE516B-6286-EDIA-0015 |  | Mining Open Pit | 33kV MV GIS Typical Wiring s Incomer - 6286-SB-001 | Diagram | Mining Open Pit - 33kV MV GIS Typical Wiring s Incomer - 6286-SB-001 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-05-18 | 2026-06-04 | Approved | 100% |  |  | 6286-SB-001 |  | 4HCH017918 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0016 | C | 6105AE516B-6286-EDIA-0016 |  | Mining Open Pit | MV AIS Typical Wiring s Incomer - 6286-SB-002 | Diagram | Mining Open Pit - MV AIS Typical Wiring s Incomer - 6286-SB-002 - Diagram | 24.03.2026 | Sanja Todoran | 2026-05-26 |  | Approved | 100% |  |  | 6286-SB-002 |  | 4HCH017919 | ABB CZ | For Approval
6105A | E516B | 6200 | E | DIA | 0010 | B | 6105AE516B-6200-EDIA-0010 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Metering Bus A & Bus B - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Metering Bus A & Bus B - 6200-SB-051 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-06-05 |  | Approved | 100% |  |  | 6200-SB-051 |  | 4HCH017920 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0017 | 0 | 6105AE516B-6286-EDIA-0017 |  | Mining Open Pit | 33kV MV GIS Typical Wiring Spare Feeder H01 - 6286-SB-001 | Diagram | Mining Open Pit - 33kV MV GIS Typical Wiring Spare Feeder H01 - 6286-SB-001 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-05-18 | 2026-06-04 | Approved | 100% |  |  | 6286-SB-001 |  | 4HCH017921 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0018 | C | 6105AE516B-6286-EDIA-0018 |  | Mining Open Pit | MV AIS Typical Wiring Busbar VT - 6286-SB-002 | Diagram | Mining Open Pit - MV AIS Typical Wiring Busbar VT - 6286-SB-002 - Diagram | 24.03.2026 | Sanja Todoran | 2026-05-26 |  | Approved | 100% |  |  | 6286-SB-002 |  | 4HCH017922 | ABB CZ | For Approval
6105A | E516B | 6200 | E | DIA | 0011 | B | 6105AE516B-6200-EDIA-0011 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Syncon TX Bus A and Bus C Feeder - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Syncon TX Bus A and Bus C Feeder - 6200-SB-051 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH017923 | ABB CZ | For Approval
6105A | E516B | 6200 | E | DIA | 0012 | B | 6105AE516B-6200-EDIA-0012 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Outgoing Feeder - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Outgoing Feeder - 6200-SB-051 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH017924 | ABB CZ | For Approval
6105A | E516B | 6200 | E | DIA | 0013 | B | 6105AE516B-6200-EDIA-0013 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring OHL Feeder Bus A and Bus C - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring OHL Feeder Bus A and Bus C - 6200-SB-051 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH017925 | ABB CZ | For Approval
6105A | E516B | 6200 | E | DIA | 0014 | B | 6105AE516B-6200-EDIA-0014 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Bus Tie from Phase 2 - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Bus Tie from Phase 2 - 6200-SB-051 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH017926 | ABB CZ | For Approval
6105A | E516B | 6200 | E | DIA | 0015 | B | 6105AE516B-6200-EDIA-0015 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Spare Feeder H01 - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Spare Feeder H01 - 6200-SB-051 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH017927 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0019 | 1 | 6105AE516B-6286-EDIA-0019 |  | Mining Open Pit | 33kV MV GIS Typical Wiring Transformer Feeder - 6286-SB-001 | Diagram | Mining Open Pit - 33kV MV GIS Typical Wiring Transformer Feeder - 6286-SB-001 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-04-28 | 2026-06-04 | Approved | 100% |  |  | 6286-SB-001 |  | 4HCH017928 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0020 | B | 6105AE516B-6286-EDIA-0020 |  | Mining Open Pit | MV AIS Typical Wiring Common - 6286-SB-002 | Diagram | Mining Open Pit - MV AIS Typical Wiring Common - 6286-SB-002 - Diagram | 24.03.2026 | Sanja Todoran | 2026-05-04 |  | Reviewed | 33% |  |  | 6286-SB-002 |  | 4HCH017929 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0021 | C | 6105AE516B-6286-EDIA-0021 |  | Mining Open Pit | MV AIS Typical Wiring Feeder - 6286-SB-002 | Diagram | Mining Open Pit - MV AIS Typical Wiring Feeder - 6286-SB-002 - Diagram | 24.03.2026 | Sanja Todoran | 2026-05-26 |  | Approved | 100% |  |  | 6286-SB-002 |  | 4HCH017930 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0022 | B | 6105AE516B-6286-EDIA-0022 |  | Mining Open Pit | MV AIS Typical Wiring Arc protection - 6286-SB-002 | Diagram | Mining Open Pit - MV AIS Typical Wiring Arc protection - 6286-SB-002 - Diagram | 06.02.2026 | Sanja Todoran | 2026-05-04 |  | Approved | 100% |  |  | 6286-SB-002 |  | 4HCH017931 | ABB CZ | For Approval
6105A | E516B | 6200 | E | DIA | 0016 | B | 6105AE516B-6200-EDIA-0016 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Capacitor Feeder - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Capacitor Feeder - 6200-SB-051 - Diagram | 20.02.2026 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH017932 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0023 | C | 6105AE516B-6286-EDIA-0023 |  | Mining Open Pit | MV AIS Typical Wiring s PFC Feeder - 6286-SB-002 | Diagram | Mining Open Pit - MV AIS Typical Wiring s PFC Feeder - 6286-SB-002 - Diagram | 06.02.2026 | Sanja Todoran | 2026-05-26 |  | Approved | 100% |  |  | 6286-SB-002 |  | 4HCH017933 | ABB CZ | For Approval
6105A | E516B | 0000 | E | ITP | 0004 | A | 6105AE516B-0000-EITP-0004 |  | General | DC Power Supply System (ITP) | Inspection Test Plan | General - DC Power Supply System (ITP) - Inspection Test Plan | 27.03.2026 | Maurizio Brescia |  |  |  | 0% |  |  | General |  | 4HCH017934 | ABB CH | For Approval
6105A | E516B | 6200 | E | TRP | 0003 | A | 6105AE516B-6200-ETRP-0003 |  | On-Site Power Supply and Transmission | DC Power Supply System - 6200-DBD-051 | Test Report | On-Site Power Supply and Transmission - DC Power Supply System - 6200-DBD-051 - Test Report | 04.09.2026 | Maurizio Brescia |  |  |  | 0% |  |  | 6200-DBD-051 |  | 4HCH017935 | ABB CH | For Information
6105A | E516B | 6262 | E | TRP | 0003 | A | 6105AE516B-6262-ETRP-0003 |  | Emergency Power Substation 1 and Control Room 1 | DC Power Supply System - 6262-DBD-001 | Test Report | Emergency Power Substation 1 and Control Room 1 - DC Power Supply System - 6262-DBD-001 - Test Report | 04.09.2026 | Maurizio Brescia |  |  |  | 0% |  |  | 6262-DBD-001 |  | 4HCH017936 | ABB CH | For Information
6105A | E516B | 6292 | E | TRP | 0002 | A | 6105AE516B-6292-ETRP-0002 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | DC Power Supply System - 6292-DBD-001 | Test Report | 11/33kV Solar PV Substation 1 and Control Room 1 - DC Power Supply System - 6292-DBD-001 - Test Report | 04.09.2026 | Maurizio Brescia |  |  |  | 0% |  |  | 6292-DBD-001 |  | 4HCH017937 | ABB CH | For Information
6105A | E516B | 6286 | E | TRP | 0005 | A | 6105AE516B-6286-ETRP-0005 |  | Mining Open Pit | DC Power Supply System - 6286-DBD-002 | Test Report | Mining Open Pit - DC Power Supply System - 6286-DBD-002 - Test Report | 04.09.2026 | Maurizio Brescia |  |  |  | 0% |  |  | 6286-DBD-002 |  | 4HCH017938 | ABB CH | For Information
6105A | E516B | 6286 | E | TRP | 0006 | A | 6105AE516B-6286-ETRP-0006 |  | Mining Open Pit | DC Power Supply System - 6286-DBD-001 | Test Report | Mining Open Pit - DC Power Supply System - 6286-DBD-001 - Test Report | 04.09.2026 | Maurizio Brescia |  |  |  | 0% |  |  | 6286-DBD-001 |  | 4HCH017939 | ABB CH | For Information
6105A | E516B | 0000 | E | DST | 0001 | A | 6105AE516B-0000-EDST-0001 |  | General | DC Power Supply System Material Safety | Datasheet | General - DC Power Supply System Material Safety - Datasheet | 04.09.2026 | Maurizio Brescia |  |  |  | 0% |  |  | General |  | 4HCH017940 | ABB CH | For Information
6105A | E516B | 6200 | E | CAL | 0002 | 0 | 6105AE516B-6200-ECAL-0002 |  | On-Site Power Supply and Transmission | DC Power Supply System Battery Sizing - 6200-DBD-051 | Calculation | On-Site Power Supply and Transmission - DC Power Supply System Battery Sizing - 6200-DBD-051 - Calculation | 17.04.2026 | Maurizio Brescia | 2026-03-23 | 2026-03-31 | Approved | 100% |  |  | 6200-DBD-051 |  | 4HCH017941 | ABB CH | For Approval
6105A | E516B | 6262 | E | CAL | 0001 | 0 | 6105AE516B-6262-ECAL-0001 |  | Emergency Power Substation 1 and Control Room 1 | DC Power Supply System Battery Sizing - 6262-DBD-001 | Calculation | Emergency Power Substation 1 and Control Room 1 - DC Power Supply System Battery Sizing - 6262-DBD-001 - Calculation | 15.05.2026 | Maurizio Brescia | 2026-03-23 | 2026-03-31 | Approved | 100% |  |  | 6262-DBD-001 |  | 4HCH017942 | ABB CH | For Approval
6105A | E516B | 6292 | E | CAL | 0006 | 0 | 6105AE516B-6292-ECAL-0006 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | DC Power Supply System Battery Sizing - 6292-DBD-001 | Calculation | 11/33kV Solar PV Substation 1 and Control Room 1 - DC Power Supply System Battery Sizing - 6292-DBD-001 - Calculation | 06.03.2026 | Maurizio Brescia | 2026-03-23 | 2026-03-31 | Approved | 100% |  |  | 6292-DBD-001 |  | 4HCH017943 | ABB CH | For Approval
6105A | E516B | 6286 | E | CAL | 0006 | 0 | 6105AE516B-6286-ECAL-0006 |  | Mining Open Pit | DC Power Supply System Battery Sizing - 6286-DBD-002 | Calculation | Mining Open Pit - DC Power Supply System Battery Sizing - 6286-DBD-002 - Calculation | 06.03.2026 | Maurizio Brescia | 2026-03-23 | 2026-03-31 | Approved | 100% |  |  | 6286-DBD-002 |  | 4HCH017944 | ABB CH | For Approval
6105A | E516B | 6286 | E | CAL | 0007 | 0 | 6105AE516B-6286-ECAL-0007 |  | Mining Open Pit | DC Power Supply System Battery Sizing - 6286-DBD-001 | Calculation | Mining Open Pit - DC Power Supply System Battery Sizing - 6286-DBD-001 - Calculation | 06.03.2026 | Maurizio Brescia | 2026-03-23 | 2026-03-31 | Approved | 100% |  |  | 6286-DBD-001 |  | 4HCH017945 | ABB CH | For Approval
6105A | E516B | 0000 | E | IOM | 0003 | A | 6105AE516B-0000-EIOM-0003 |  | General | DC Power Supply System (IOM) | Installation Operation and Maintenance Manual | General - DC Power Supply System (IOM) - Installation Operation and Maintenance Manual | 04.09.2026 | Maurizio Brescia | 2026-05-20 |  |  | 33% |  |  | General |  | 4HCH017946 | ABB CH | For Information
6105A | E516B | 6200 | E | GAD | 0003 | A | 6105AE516B-6200-EGAD-0003 |  | On-Site Power Supply and Transmission | DC Power Supply System - 6200-DBD-051 | General Arrangement | On-Site Power Supply and Transmission - DC Power Supply System - 6200-DBD-051 - General Arrangement | 06.02.2026 | Maurizio Brescia | 2026-03-25 |  | Reviewed | 33% |  |  | 6200-DBD-051 |  | 4HCH017947 | ABB CH | For Approval
6105A | E516B | 6262 | E | GAD | 0003 | A | 6105AE516B-6262-EGAD-0003 |  | Emergency Power Substation 1 and Control Room 1 | DC Power Supply System - 6262-DBD-001 | General Arrangement | Emergency Power Substation 1 and Control Room 1 - DC Power Supply System - 6262-DBD-001 - General Arrangement | 06.02.2026 | Maurizio Brescia | 2026-03-25 |  | Reviewed | 33% |  |  | 6262-DBD-001 |  | 4HCH017948 | ABB CH | For Approval
6105A | E516B | 6292 | E | GAD | 0005 | A | 6105AE516B-6292-EGAD-0005 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | DC Power Supply System - 6292-DBD-001 | General Arrangement | 11/33kV Solar PV Substation 1 and Control Room 1 - DC Power Supply System - 6292-DBD-001 - General Arrangement | 06.02.2026 | Maurizio Brescia | 2026-03-25 |  | Reviewed | 33% |  |  | 6292-DBD-001 |  | 4HCH017949 | ABB CH | For Approval
6105A | E516B | 6286 | E | GAD | 0007 | A | 6105AE516B-6286-EGAD-0007 |  | Mining Open Pit | DC Power Supply System - 6286-DBD-002 | General Arrangement | Mining Open Pit - DC Power Supply System - 6286-DBD-002 - General Arrangement | 06.02.2026 | Maurizio Brescia | 2026-03-25 |  | Reviewed | 33% |  |  | 6286-DBD-002 |  | 4HCH017950 | ABB CH | For Approval
6105A | E516B | 6286 | E | GAD | 0008 | A | 6105AE516B-6286-EGAD-0008 |  | Mining Open Pit | DC Power Supply System - 6286-DBD-001 | General Arrangement | Mining Open Pit - DC Power Supply System - 6286-DBD-001 - General Arrangement | 06.02.2026 | Maurizio Brescia | 2026-03-25 |  | Reviewed | 33% |  |  | 6286-DBD-001 |  | 4HCH017951 | ABB CH | For Approval
6105A | E516B | 6200 | E | DIA | 0017 | A | 6105AE516B-6200-EDIA-0017 |  | On-Site Power Supply and Transmission | DC Power Supply System Single Line - 6200-DBD-051 | Diagram | On-Site Power Supply and Transmission - DC Power Supply System Single Line - 6200-DBD-051 - Diagram | 06.02.2026 | Maurizio Brescia | 2026-03-25 |  | Reviewed | 33% |  |  | 6200-DBD-051 |  | 4HCH017952 | ABB CH | For Approval
6105A | E516B | 6262 | E | DIA | 0012 | A | 6105AE516B-6262-EDIA-0012 |  | Emergency Power Substation 1 and Control Room 1 | DC Power Supply System Single Line - 6262-DBD-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - DC Power Supply System Single Line - 6262-DBD-001 - Diagram | 06.02.2026 | Maurizio Brescia | 2026-03-25 |  | Reviewed | 33% |  |  | 6262-DBD-001 |  | 4HCH017953 | ABB CH | For Approval
6105A | E516B | 6292 | E | DIA | 0002 | A | 6105AE516B-6292-EDIA-0002 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | DC Power Supply System Single Line - 6292-DBD-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - DC Power Supply System Single Line - 6292-DBD-001 - Diagram | 06.02.2026 | Maurizio Brescia | 2026-03-25 |  | Reviewed | 33% |  |  | 6292-DBD-001 |  | 4HCH017954 | ABB CH | For Approval
6105A | E516B | 6286 | E | DIA | 0024 | A | 6105AE516B-6286-EDIA-0024 |  | Mining Open Pit | DC Power Supply System Single Line - 6286-DBD-002 | Diagram | Mining Open Pit - DC Power Supply System Single Line - 6286-DBD-002 - Diagram | 20.02.2026 | Maurizio Brescia | 2026-03-25 |  | Reviewed | 33% |  |  | 6286-DBD-002 |  | 4HCH017955 | ABB CH | For Approval
6105A | E516B | 6286 | E | DIA | 0025 | A | 6105AE516B-6286-EDIA-0025 |  | Mining Open Pit | DC Power Supply System Single Line - 6286-DBD-001 | Diagram | Mining Open Pit - DC Power Supply System Single Line - 6286-DBD-001 - Diagram | 20.02.2026 | Maurizio Brescia | 2026-03-25 |  | Reviewed | 33% |  |  | 6286-DBD-001 |  | 4HCH017956 | ABB CH | For Approval
6105A | E516B | 6200 | E | DIA | 0018 | A | 6105AE516B-6200-EDIA-0018 |  | On-Site Power Supply and Transmission | DC Power Supply System Wiring - 6200-DBD-051 | Diagram | On-Site Power Supply and Transmission - DC Power Supply System Wiring - 6200-DBD-051 - Diagram | 20.02.2026 | Maurizio Brescia | 2026-04-13 |  | Approved | 100% |  |  | 6200-DBD-051 |  | 4HCH017957 | ABB CH | For Approval
6105A | E516B | 6262 | E | DIA | 0013 | A | 6105AE516B-6262-EDIA-0013 |  | Emergency Power Substation 1 and Control Room 1 | DC Power Supply System Wiring - 6262-DBD-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - DC Power Supply System Wiring - 6262-DBD-001 - Diagram | 20.02.2026 | Maurizio Brescia | 2026-04-13 |  | Approved | 100% |  |  | 6262-DBD-001 |  | 4HCH017958 | ABB CH | For Approval
6105A | E516B | 6292 | E | DIA | 0003 | A | 6105AE516B-6292-EDIA-0003 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | DC Power Supply System Wiring - 6292-DBD-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - DC Power Supply System Wiring - 6292-DBD-001 - Diagram | 20.02.2026 | Maurizio Brescia | 2026-04-13 |  | Approved | 100% |  |  | 6292-DBD-001 |  | 4HCH017959 | ABB CH | For Approval
6105A | E516B | 6286 | E | DIA | 0026 | A | 6105AE516B-6286-EDIA-0026 |  | Mining Open Pit | DC Power Supply System Wiring - 6286-DBD-002 | Diagram | Mining Open Pit - DC Power Supply System Wiring - 6286-DBD-002 - Diagram | 06.02.2026 | Maurizio Brescia | 2026-04-13 |  | Approved | 100% |  |  | 6286-DBD-002 |  | 4HCH017960 | ABB CH | For Approval
6105A | E516B | 6286 | E | DIA | 0027 | A | 6105AE516B-6286-EDIA-0027 |  | Mining Open Pit | DC Power Supply System Wiring - 6286-DBD-001 | Diagram | Mining Open Pit - DC Power Supply System Wiring - 6286-DBD-001 - Diagram | 06.02.2026 | Maurizio Brescia | 2026-04-13 |  | Approved | 100% |  |  | 6286-DBD-001 |  | 4HCH017961 | ABB CH | For Approval
6105A | E516B | 0000 | E | ITP | 0005 | A | 6105AE516B-0000-EITP-0005 |  | General | LV Main Distribution Panel (ITP) | Inspection Test Plan | General - LV Main Distribution Panel (ITP) - Inspection Test Plan | 20.03.2026 | Belen Garcia-San-Miguel |  |  |  | 0% |  |  | General |  | 4HCH017962 | Kurita | For Approval
6105A | E516B | 0000 | E | PRC | 0005 | A | 6105AE516B-0000-EPRC-0005 |  | General | LV Main Distribution Panel Test | Procedure | General - LV Main Distribution Panel Test - Procedure | 17.04.2026 | Belen Garcia-San-Miguel |  |  |  | 0% |  |  | General |  | 4HCH017963 | Kurita | For Information
6105A | E516B | 6200 | E | TRP | 0004 | A | 6105AE516B-6200-ETRP-0004 |  | On-Site Power Supply and Transmission | LV Main Distribution Panel - 6200-MC-051 | Test Report | On-Site Power Supply and Transmission - LV Main Distribution Panel - 6200-MC-051 - Test Report | 04.09.2026 | Belen Garcia-San-Miguel |  |  |  | 0% |  |  | 6200-MC-051 |  | 4HCH017964 | Kurita | For Information
6105A | E516B | 6262 | E | TRP | 0004 | A | 6105AE516B-6262-ETRP-0004 |  | Emergency Power Substation 1 and Control Room 1 | LV Main Distribution Panel - 6262-MC-001 | Test Report | Emergency Power Substation 1 and Control Room 1 - LV Main Distribution Panel - 6262-MC-001 - Test Report | 04.09.2026 | Belen Garcia-San-Miguel |  |  |  | 0% |  |  | 6262-MC-001 |  | 4HCH017965 | Kurita | For Information
6105A | E516B | 6292 | E | TRP | 0003 | A | 6105AE516B-6292-ETRP-0003 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | LV Main Distribution Panel - 6292-MC-001 | Test Report | 11/33kV Solar PV Substation 1 and Control Room 1 - LV Main Distribution Panel - 6292-MC-001 - Test Report | 04.09.2026 | Belen Garcia-San-Miguel |  |  |  | 0% |  |  | 6292-MC-001 |  | 4HCH017966 | Kurita | For Information
6105A | E516B | 6286 | E | TRP | 0007 | A | 6105AE516B-6286-ETRP-0007 |  | Mining Open Pit | LV Main Distribution Panel - 6286-MC-001 | Test Report | Mining Open Pit - LV Main Distribution Panel - 6286-MC-001 - Test Report | 04.09.2026 | Belen Garcia-San-Miguel |  |  |  | 0% |  |  | 6286-MC-001 |  | 4HCH017967 | Kurita | For Information
6105A | E516B | 6286 | E | TRP | 0008 | A | 6105AE516B-6286-ETRP-0008 |  | Mining Open Pit | LV Main Distribution Panel - 6286-MC-002 | Test Report | Mining Open Pit - LV Main Distribution Panel - 6286-MC-002 - Test Report | 04.09.2026 | Belen Garcia-San-Miguel |  |  |  | 0% |  |  | 6286-MC-002 |  | 4HCH017968 | Kurita | For Information
6105A | E516B | 6200 | E | DIA | 0019 | A | 6105AE516B-6200-EDIA-0019 |  | On-Site Power Supply and Transmission | LV Main Distribution Panel Drawing - 6200-MC-051 | Diagram | On-Site Power Supply and Transmission - LV Main Distribution Panel Drawing - 6200-MC-051 - Diagram | 06.02.2026 | Belen Garcia-San-Miguel | 2026-06-04 |  |  | 33% |  |  | 6200-MC-051 |  | 4HCH017969 | Kurita | For Approval
6105A | E516B | 6262 | E | DIA | 0014 | A | 6105AE516B-6262-EDIA-0014 |  | Emergency Power Substation 1 and Control Room 1 | LV Main Distribution Panel Drawing - 6262-MC-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - LV Main Distribution Panel Drawing - 6262-MC-001 - Diagram | 06.02.2026 | Belen Garcia-San-Miguel | 2026-06-04 |  |  | 33% |  |  | 6262-MC-001 |  | 4HCH017970 | Kurita | For Approval
6105A | E516B | 6292 | E | DIA | 0004 | A | 6105AE516B-6292-EDIA-0004 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | LV Main Distribution Panel Drawing - 6292-MC-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - LV Main Distribution Panel Drawing - 6292-MC-001 - Diagram | 06.02.2026 | Belen Garcia-San-Miguel | 2026-06-04 |  |  | 33% |  |  | 6292-MC-001 |  | 4HCH017971 | Kurita | For Approval
6105A | E516B | 6286 | E | DIA | 0028 | A | 6105AE516B-6286-EDIA-0028 |  | Mining Open Pit | LV Main Distribution Panel Drawing - 6286-MC-001 | Diagram | Mining Open Pit - LV Main Distribution Panel Drawing - 6286-MC-001 - Diagram | 20.02.2026 | Belen Garcia-San-Miguel | 2026-06-04 |  |  | 33% |  |  | 6286-MC-001 |  | 4HCH017972 | Kurita | For Approval
6105A | E516B | 6286 | E | DIA | 0029 | A | 6105AE516B-6286-EDIA-0029 |  | Mining Open Pit | LV Main Distribution Panel Drawing - 6286-MC-002 | Diagram | Mining Open Pit - LV Main Distribution Panel Drawing - 6286-MC-002 - Diagram | 06.02.2026 | Belen Garcia-San-Miguel | 2026-06-04 |  |  | 33% |  |  | 6286-MC-002 |  | 4HCH017973 | Kurita | For Approval
6105A | E516B | 0000 | E | ITP | 0006 | A | 6105AE516B-0000-EITP-0006 |  | General | UPS (ITP) | Inspection Test Plan | General - UPS (ITP) - Inspection Test Plan | 06.03.2026 | Alvaro Martin | 2026-05-13 |  | Approved | 100% |  |  | General |  | 4HCH017974 | ABB CH | For Approval
6105A | E516B | 6200 | E | TRP | 0005 | A | 6105AE516B-6200-ETRP-0005 |  | On-Site Power Supply and Transmission | UPS - 6200-UPS-051A | Test Report | On-Site Power Supply and Transmission - UPS - 6200-UPS-051A - Test Report | 04.09.2026 | Alvaro Martin |  |  |  | 0% |  |  | 6200-UPS-051A |  | 4HCH017975 | ABB CH | For Information
6105A | E516B | 6262 | E | TRP | 0005 | A | 6105AE516B-6262-ETRP-0005 |  | Emergency Power Substation 1 and Control Room 1 | UPS - 6262-UPS-001 | Test Report | Emergency Power Substation 1 and Control Room 1 - UPS - 6262-UPS-001 - Test Report | 04.09.2026 | Alvaro Martin |  |  |  | 0% |  |  | 6262-UPS-001 | Check the Tag Number in Name | 4HCH017977 | ABB CH | For Information
6105A | E516B | 6292 | E | TRP | 0004 | A | 6105AE516B-6292-ETRP-0004 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | UPS - 6292-UPS-001 | Test Report | 11/33kV Solar PV Substation 1 and Control Room 1 - UPS - 6292-UPS-001 - Test Report | 04.09.2026 | Alvaro Martin |  |  |  | 0% |  |  | 6292-UPS-001 |  | 4HCH017979 | ABB CH | For Information
6105A | E516B | 6286 | E | TRP | 0009 | A | 6105AE516B-6286-ETRP-0009 |  | Mining Open Pit | UPS - 6286-UPS-004 | Test Report | Mining Open Pit - UPS - 6286-UPS-004 - Test Report | 04.09.2026 | Alvaro Martin |  |  |  | 0% |  |  | 6286-UPS-004 | 11kv Open Pit | 4HCH017980 | ABB CH | For Information
6105A | E516B | 6286 | E | TRP | 0010 | A | 6105AE516B-6286-ETRP-0010 |  | Mining Open Pit | UPS - 6286-UPS-002 | Test Report | Mining Open Pit - UPS - 6286-UPS-002 - Test Report | 04.09.2026 | Alvaro Martin |  |  |  | 0% |  |  | 6286-UPS-002 |  | 4HCH017981 | ABB CH | For Information
6105A | E516B | 0000 | E | DST | 0002 | A | 6105AE516B-0000-EDST-0002 |  | General | UPS Material Safety | Datasheet | General - UPS Material Safety - Datasheet | 04.09.2026 | Alvaro Martin |  |  |  | 0% |  |  | General |  | 4HCH017982 | ABB CH | For Information
6105A | E516B | 0000 | E | IOM | 0004 | 0 | 6105AE516B-0000-EIOM-0004 |  | General | UPS (IOM) | Installation Operation and Maintenance Manual | General - UPS (IOM) - Installation Operation and Maintenance Manual | 04.09.2026 | Alvaro Martin | 2026-05-13 | 2026-05-18 | Approved | 100% |  |  | General |  | 4HCH017983 | ABB CH | For Information
6105A | E516B | 6200 | E | GAD | 0004 | 0 | 6105AE516B-6200-EGAD-0004 |  | On-Site Power Supply and Transmission | UPS - 6200-UPS-051A | General Arrangement | On-Site Power Supply and Transmission - UPS - 6200-UPS-051A - General Arrangement | 06.02.2026 | Alvaro Martin | 2026-05-07 | 2026-05-13 | Approved | 100% |  |  | 6200-UPS-051A |  | 4HCH017984 | ABB CH | For Approval
6105A | E516B | 6292 | E | GAD | 0006 | 0 | 6105AE516B-6292-EGAD-0006 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | UPS - 6292-UPS-001 | General Arrangement | 11/33kV Solar PV Substation 1 and Control Room 1 - UPS - 6292-UPS-001 - General Arrangement | 06.02.2026 | Alvaro Martin | 2026-05-07 | 2026-05-13 | Approved | 100% |  |  | 6292-UPS-001 |  | 4HCH017988 | ABB CH | For Approval
6105A | E516B | 6286 | E | GAD | 0009 | 0 | 6105AE516B-6286-EGAD-0009 |  | Mining Open Pit | UPS- 6286-UPS-004 | General Arrangement | Mining Open Pit - UPS- 6286-UPS-004 - General Arrangement | 06.02.2026 | Alvaro Martin | 2026-05-07 | 2026-05-13 | Approved | 100% |  |  | 6286-UPS-004 | 11kv Open Pit | 4HCH017989 | ABB CH | For Approval
6105A | E516B | 6286 | E | GAD | 0010 | 0 | 6105AE516B-6286-EGAD-0010 |  | Mining Open Pit | UPS - 6286-UPS-002 | General Arrangement | Mining Open Pit - UPS - 6286-UPS-002 - General Arrangement | 06.02.2026 | Alvaro Martin | 2026-05-07 | 2026-05-13 | Approved | 100% |  |  | 6286-UPS-002 |  | 4HCH017990 | ABB CH | For Approval
6105A | E516B | 6200 | E | DIA | 0020 | 0 | 6105AE516B-6200-EDIA-0020 |  | On-Site Power Supply and Transmission | UPS Single Line - 6200-UPS-051A | Diagram | On-Site Power Supply and Transmission - UPS Single Line - 6200-UPS-051A - Diagram | 06.02.2026 | Alvaro Martin | 2026-05-07 | 2026-05-13 | Approved | 100% |  |  | 6200-UPS-051A |  | 4HCH017991 | ABB CH | For Approval
6105A | E516B | 6262 | E | DIA | 0015 | 0 | 6105AE516B-6262-EDIA-0015 |  | Emergency Power Substation 1 and Control Room 1 | UPS Single Line - 6262-UPS-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - UPS Single Line - 6262-UPS-001 - Diagram | 06.02.2026 | Alvaro Martin | 2026-05-07 | 2026-05-13 | Approved | 100% |  |  | 6262-UPS-001 | Check the Tag Number in Name | 4HCH017993 | ABB CH | For Approval
6105A | E516B | 6292 | E | DIA | 0005 | 0 | 6105AE516B-6292-EDIA-0005 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | UPS Single Line - 6292-UPS-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - UPS Single Line - 6292-UPS-001 - Diagram | 06.02.2026 | Alvaro Martin | 2026-05-07 | 2026-05-13 | Approved | 100% |  |  | 6292-UPS-001 |  | 4HCH017995 | ABB CH | For Approval
6105A | E516B | 6286 | E | DIA | 0030 | 0 | 6105AE516B-6286-EDIA-0030 |  | Mining Open Pit | UPS Single Line - 6286-UPS-004 | Diagram | Mining Open Pit - UPS Single Line - 6286-UPS-004 - Diagram | 06.02.2026 | Alvaro Martin | 2026-05-07 | 2026-05-13 | Approved | 100% |  |  | 6286-UPS-004 | 11kv Open Pit | 4HCH017996 | ABB CH | For Approval
6105A | E516B | 6286 | E | DIA | 0031 | 0 | 6105AE516B-6286-EDIA-0031 |  | Mining Open Pit | UPS Single Line - 6286-UPS-002 | Diagram | Mining Open Pit - UPS Single Line - 6286-UPS-002 - Diagram | 24.04.2026 | Alvaro Martin | 2026-05-07 | 2026-05-13 | Approved | 100% |  |  | 6286-UPS-002 |  | 4HCH017997 | ABB CH | For Approval
6105A | E516B | 6200 | E | DIA | 0004 | B | 6105AE516B-6200-EDIA-0004 |  | On-Site Power Supply and Transmission | UPS Wiring - 6200-UPS-051A | Diagram | On-Site Power Supply and Transmission - UPS Wiring - 6200-UPS-051A - Diagram | 30.01.2026 | Alvaro Martin | 2026-05-07 |  | Reviewed | 33% |  |  | 6200-UPS-051A |  | 4HCH017998 | ABB CH | For Approval
6105A | E516B | 6262 | E | DIA | 0016 | B | 6105AE516B-6262-EDIA-0016 |  | Emergency Power Substation 1 and Control Room 1 | UPS Wiring s - 6262-UPS-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - UPS Wiring s - 6262-UPS-001 - Diagram | 20.02.2026 | Alvaro Martin | 2026-05-07 |  | Reviewed | 33% |  |  | 6262-UPS-001 | Check the Tag Number in Name | 4HCH018000 | ABB CH | For Approval
6105A | E516B | 6292 | E | DIA | 0006 | B | 6105AE516B-6292-EDIA-0006 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | UPS Wiring s - 6292-UPS-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - UPS Wiring s - 6292-UPS-001 - Diagram | 20.02.2026 | Alvaro Martin | 2026-05-07 |  | Reviewed | 33% |  |  | 6292-UPS-001 |  | 4HCH018002 | ABB CH | For Approval
6105A | E516B | 6286 | E | DIA | 0032 | B | 6105AE516B-6286-EDIA-0032 |  | Mining Open Pit | UPS Wiring s - 6286-UPS-004 | Diagram | Mining Open Pit - UPS Wiring s - 6286-UPS-004 - Diagram | 20.02.2026 | Alvaro Martin | 2026-05-07 |  | Reviewed | 33% |  |  | 6286-UPS-004 | 11kv Open Pit | 4HCH018003 | ABB CH | For Approval
6105A | E516B | 6286 | E | DIA | 0001 | B | 6105AE516B-6286-EDIA-0001 |  | Mining Open Pit | UPS Wiring s - 6286-UPS-002 | Diagram | Mining Open Pit - UPS Wiring s - 6286-UPS-002 - Diagram | 20.03.2026 | Alvaro Martin | 2026-05-07 |  | Reviewed | 33% |  |  | 6286-UPS-002 |  | 4HCH018004 | ABB CH | For Approval
6105A | E516B | 6200 | E | CAL | 0006 | 0 | 6105AE516B-6200-ECAL-0006 |  | On-Site Power Supply and Transmission | UPS Battery Sizing - 6200-UPS-051A | Calculation | On-Site Power Supply and Transmission - UPS Battery Sizing - 6200-UPS-051A - Calculation | 06.03.2026 | Alvaro Martin | 2026-04-15 | 2026-05-12 | Approved | 100% |  |  | 6200-UPS-051A |  | 4HCH018005 | ABB CH | For Approval
6105A | E516B | 6262 | E | CAL | 0003 | 0 | 6105AE516B-6262-ECAL-0003 |  | Emergency Power Substation 1 and Control Room 1 | UPS Battery Sizing - 6262-UPS-001 | Calculation | Emergency Power Substation 1 and Control Room 1 - UPS Battery Sizing - 6262-UPS-001 - Calculation |  | Alvaro Martin | 2026-04-15 | 2026-05-12 | Approved | 100% |  |  | 6262-UPS-001 | Check the Tag Number in Name | 4HCH018007 | ABB CH | For Approval
6105A | E516B | 6292 | E | CAL | 0004 | 0 | 6105AE516B-6292-ECAL-0004 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | UPS Battery Sizing - 6292-UPS-001 | Calculation | 11/33kV Solar PV Substation 1 and Control Room 1 - UPS Battery Sizing - 6292-UPS-001 - Calculation | 06.03.2026 | Alvaro Martin | 2026-04-15 | 2026-05-12 | Approved | 100% |  |  | 6292-UPS-001 |  | 4HCH018009 | ABB CH | For Approval
6105A | E516B | 6286 | E | CAL | 0011 | 0 | 6105AE516B-6286-ECAL-0011 |  | Mining Open Pit | UPS Battery Sizing - 6286-UPS-004 | Calculation | Mining Open Pit - UPS Battery Sizing - 6286-UPS-004 - Calculation | 06.03.2026 | Alvaro Martin | 2026-04-15 | 2026-05-12 | Approved | 100% |  |  | 6286-UPS-004 | 11kv Open Pit | 4HCH018010 | ABB CH | For Approval
6105A | E516B | 6286 | E | CAL | 0009 | 0 | 6105AE516B-6286-ECAL-0009 |  | Mining Open Pit | UPS Battery Sizing - 6286-UPS-002 | Calculation | Mining Open Pit - UPS Battery Sizing - 6286-UPS-002 - Calculation | 06.03.2026 | Alvaro Martin | 2026-04-15 | 2026-05-12 | Approved | 100% |  |  | 6286-UPS-002 |  | 4HCH018011 | ABB CH | For Approval
6105A | E516B | 6292 | E | TRP | 0005 | A | 6105AE516B-6292-ETRP-0005 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS - 6292-SB-001 | Test Report | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS - 6292-SB-001 - Test Report | 09.10.2026 | Milan Djurdjevic |  |  |  | 0% |  |  | 6292-SB-001 |  | 4HCH018017 | ABB CZ | For Information
6105A | E516B | 6292 | E | GAD | 0003 | B | 6105AE516B-6292-EGAD-0003 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS - 6292-SB-001 | General Arrangement | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS - 6292-SB-001 - General Arrangement | 30.01.2026 | Milan Djurdjevic | 2026-05-22 |  | Reviewed | 33% |  |  | 6292-SB-001 |  | 4HCH018018 | ABB CZ | For Approval
6105A | E516B | 6292 | E | DIA | 0007 | B | 6105AE516B-6292-EDIA-0007 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS Single Line - 6292-SB-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS Single Line - 6292-SB-001 - Diagram | 30.01.2026 | Milan Djurdjevic | 2026-06-04 |  | Reviewed | 33% |  |  | 6292-SB-001 |  | 4HCH018019 | ABB CZ | For Approval
6105A | E516B | 6292 | E | DIA | 0008 | A | 6105AE516B-6292-EDIA-0008 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS Typical Wiring Incomer Bus A & Bus C - 6292-SB-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS Typical Wiring Incomer Bus A & Bus C - 6292-SB-001 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-05-18 |  | Reviewed | 33% |  |  | 6292-SB-001 |  | 4HCH018020 | ABB CZ | For Approval
6105A | E516B | 6292 | E | DIA | 0009 | A | 6105AE516B-6292-EDIA-0009 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS Typical Wiring Metering Bus A & Bus B - 6292-SB-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS Typical Wiring Metering Bus A & Bus B - 6292-SB-001 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-05-18 |  | Approved | 100% |  |  | 6292-SB-001 |  | 4HCH018021 | ABB CZ | For Approval
6105A | E516B | 6292 | E | DIA | 0010 | A | 6105AE516B-6292-EDIA-0010 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS Typical Wiring Outgoing Feeder H01 - 6292-SB-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS Typical Wiring Outgoing Feeder H01 - 6292-SB-001 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-05-18 |  | Reviewed | 33% |  |  | 6292-SB-001 |  | 4HCH018022 | ABB CZ | For Approval
6105A | E516B | 6292 | E | DIA | 0011 | A | 6105AE516B-6292-EDIA-0011 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS Typical Wiring Bus Coupler Bus B & Bus C - 6292-SB-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS Typical Wiring Bus Coupler Bus B & Bus C - 6292-SB-001 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-05-18 |  | Reviewed | 33% |  |  | 6292-SB-001 |  | 4HCH018023 | ABB CZ | For Approval
6105A | E516B | 6292 | E | DIA | 0012 | A | 6105AE516B-6292-EDIA-0012 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS Typical Wiring Bus Coupler Bus A & Bus B - 6292-SB-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS Typical Wiring Bus Coupler Bus A & Bus B - 6292-SB-001 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-05-18 |  | Reviewed | 33% |  |  | 6292-SB-001 |  | 4HCH018024 | ABB CZ | For Approval
6105A | E516B | 6292 | E | DIA | 0013 | A | 6105AE516B-6292-EDIA-0013 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS Typical Wiring Feeder Aux. TR - 6292-SB-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS Typical Wiring Feeder Aux. TR - 6292-SB-001 - Diagram | 24.03.2026 | Milan Djurdjevic | 2026-05-18 |  | Approved | 100% |  |  | 6292-SB-001 |  | 4HCH018025 | ABB CZ | For Approval
6105A | E516B | 6260 | E | TRP | 0001 | A | 6105AE516B-6260-ETRP-0001 |  | Emergency Power Generation | Kiosk Sub - 6260-KI-002 | Test Report | Emergency Power Generation - Kiosk Sub - 6260-KI-002 - Test Report | 15.01.2027 | Alvaro Martin |  |  |  | 0% |  |  | 6260-KI-002, 6260-TXP-002, 6260-Kiosk Sub-002 |  | 4HCH018026 | ABB EG | For Information
6105A | E516B | 6260 | E | GAD | 0001 | B | 6105AE516B-6260-EGAD-0001 |  | Emergency Power Generation | Kiosk Sub Outline Drawing - 6260-KI-002 | General Arrangement | Emergency Power Generation - Kiosk Sub Outline Drawing - 6260-KI-002 - General Arrangement | 27.03.2026 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6260-KI-002, 6260-TXP-002, 6260-Kiosk Sub-002 |  | 4HCH018027 | ABB EG | For Approval
6105A | E516B | 6260 | E | DIA | 0001 | A | 6105AE516B-6260-EDIA-0001 |  | Emergency Power Generation | Kiosk Sub Wiring s - 6260-KI-002 | Diagram | Emergency Power Generation - Kiosk Sub Wiring s - 6260-KI-002 - Diagram | 24.04.2026 | Alvaro Martin | 2026-04-14 |  | Reviewed | 33% |  |  | 6260-KI-002, 6260-TXP-002, 6260-Kiosk Sub-002 |  | 4HCH018028 | ABB EG | For Approval
6105A | E516B | 6260 | E | TRP | 0002 | A | 6105AE516B-6260-ETRP-0002 |  | Emergency Power Generation | Kiosk Sub - 6260-KI-003 | Test Report | Emergency Power Generation - Kiosk Sub - 6260-KI-003 - Test Report | 15.01.2027 | Alvaro Martin |  |  |  | 0% |  |  | 6260-KI-003, 6260-TXP-003, 6260-Kiosk Sub-003 |  | 4HCH018029 | ABB EG | For Information
6105A | E516B | 6260 | E | GAD | 0002 | B | 6105AE516B-6260-EGAD-0002 |  | Emergency Power Generation | Kiosk Sub Outline Drawing - 6260-KI-003 | General Arrangement | Emergency Power Generation - Kiosk Sub Outline Drawing - 6260-KI-003 - General Arrangement | 27.03.2026 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6260-KI-003, 6260-TXP-003, 6260-Kiosk Sub-003 |  | 4HCH018030 | ABB EG | For Approval
6105A | E516B | 6260 | E | DIA | 0002 | A | 6105AE516B-6260-EDIA-0002 |  | Emergency Power Generation | Kiosk Sub Wiring s - 6260-KI-003 | Diagram | Emergency Power Generation - Kiosk Sub Wiring s - 6260-KI-003 - Diagram | 24.04.2026 | Alvaro Martin | 2026-04-14 |  | Reviewed | 33% |  |  | 6260-KI-003, 6260-TXP-003, 6260-Kiosk Sub-003 |  | 4HCH018031 | ABB EG | For Approval
6105A | E516B | 6200 | E | TRP | 0006 | A | 6105AE516B-6200-ETRP-0006 |  | On-Site Power Supply and Transmission | Kiosk Sub - 6200-KI-056 | Test Report | On-Site Power Supply and Transmission - Kiosk Sub - 6200-KI-056 - Test Report | 15.01.2027 | Alvaro Martin |  |  |  | 0% |  |  | 6200-KI-056, 6200-TXD-056, 6200-Kiosk Sub-056 |  | 4HCH018032 | ABB EG | For Information
6105A | E516B | 6200 | E | GAD | 0006 | B | 6105AE516B-6200-EGAD-0006 |  | On-Site Power Supply and Transmission | Kiosk Sub Outline Drawing - 6200-KI-056 | General Arrangement | On-Site Power Supply and Transmission - Kiosk Sub Outline Drawing - 6200-KI-056 - General Arrangement | 27.03.2026 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6200-KI-056, 6200-TXD-056, 6200-Kiosk Sub-056 |  | 4HCH018033 | ABB EG | For Approval
6105A | E516B | 6200 | E | DIA | 0005 | A | 6105AE516B-6200-EDIA-0005 |  | On-Site Power Supply and Transmission | Kiosk Sub Wiring s - 6200-KI-056 | Diagram | On-Site Power Supply and Transmission - Kiosk Sub Wiring s - 6200-KI-056 - Diagram | 24.04.2026 | Alvaro Martin | 2026-04-14 |  | Reviewed | 33% |  |  | 6200-KI-056, 6200-TXD-056, 6200-Kiosk Sub-056 |  | 4HCH018034 | ABB EG | For Approval
6105A | E516B | 6290 | E | TRP | 0001 | A | 6105AE516B-6290-ETRP-0001 |  | Renewable Energy | Kiosk Sub - 6290-KI-001 | Test Report | Renewable Energy - Kiosk Sub - 6290-KI-001 - Test Report | 15.01.2027 | Alvaro Martin |  |  |  | 0% |  |  | 6290-KI-001, 6290-TXD-001, 6290-Kiosk Sub-001 |  | 4HCH018035 | ABB EG | For Information
6105A | E516B | 6290 | E | GAD | 0001 | B | 6105AE516B-6290-EGAD-0001 |  | Renewable Energy | Kiosk Sub Outline Drawing - 6290-KI-001 | General Arrangement | Renewable Energy - Kiosk Sub Outline Drawing - 6290-KI-001 - General Arrangement | 27.03.2026 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6290-KI-001, 6290-TXD-001, 6290-Kiosk Sub-001 |  | 4HCH018036 | ABB EG | For Approval
6105A | E516B | 6290 | E | DIA | 0001 | A | 6105AE516B-6290-EDIA-0001 |  | Renewable Energy | Kiosk Sub Wiring s - 6290-KI-001 | Diagram | Renewable Energy - Kiosk Sub Wiring s - 6290-KI-001 - Diagram | 24.04.2026 | Alvaro Martin | 2026-04-14 |  | Reviewed | 33% |  |  | 6290-KI-001, 6290-TXD-001, 6290-Kiosk Sub-001 |  | 4HCH018037 | ABB EG | For Approval
6105A | E516B | 6253 | E | TRP | 0001 | A | 6105AE516B-6253-ETRP-0001 |  | Synchronous Condenser 1 | Kiosk Sub - 6253-KI-001 | Test Report | Synchronous Condenser 1 - Kiosk Sub - 6253-KI-001 - Test Report | 15.01.2027 | Alvaro Martin |  |  |  | 0% |  |  | 6253-KI-001, 6253-TXP-001, 6253-Kiosk Sub-001 |  | 4HCH018038 | ABB EG | For Information
6105A | E516B | 6253 | E | GAD | 0001 | B | 6105AE516B-6253-EGAD-0001 |  | Synchronous Condenser 1 | Kiosk Sub Outline Drawing - 6253-KI-001 | General Arrangement | Synchronous Condenser 1 - Kiosk Sub Outline Drawing - 6253-KI-001 - General Arrangement | 27.03.2026 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6253-KI-001, 6253-TXP-001, 6253-Kiosk Sub-001 |  | 4HCH018039 | ABB EG | For Approval
6105A | E516B | 6253 | E | DIA | 0001 | A | 6105AE516B-6253-EDIA-0001 |  | Synchronous Condenser 1 | Kiosk Sub Wiring s - 6253-KI-001 | Diagram | Synchronous Condenser 1 - Kiosk Sub Wiring s - 6253-KI-001 - Diagram | 24.04.2026 | Alvaro Martin | 2026-04-14 |  | Reviewed | 33% |  |  | 6253-KI-001, 6253-TXP-001, 6253-Kiosk Sub-001 |  | 4HCH018040 | ABB EG | For Approval
6105A | E516B | 6253 | E | TRP | 0002 | A | 6105AE516B-6253-ETRP-0002 |  | Synchronous Condenser 1 | Kiosk Sub - 6253-KI-002 | Test Report | Synchronous Condenser 1 - Kiosk Sub - 6253-KI-002 - Test Report | 15.01.2027 | Alvaro Martin |  |  |  | 0% |  |  | 6253-KI-002, 6253-TXP-002, 6253-Kiosk Sub-002 |  | 4HCH018041 | ABB EG | For Information
6105A | E516B | 6253 | E | GAD | 0002 | B | 6105AE516B-6253-EGAD-0002 |  | Synchronous Condenser 1 | Kiosk Sub Outline Drawing - 6253-KI-002 | General Arrangement | Synchronous Condenser 1 - Kiosk Sub Outline Drawing - 6253-KI-002 - General Arrangement | 27.03.2026 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6253-KI-002, 6253-TXP-002, 6253-Kiosk Sub-002 |  | 4HCH018042 | ABB EG | For Approval
6105A | E516B | 6253 | E | DIA | 0002 | A | 6105AE516B-6253-EDIA-0002 |  | Synchronous Condenser 1 | Kiosk Sub Wiring s - 6253-KI-002 | Diagram | Synchronous Condenser 1 - Kiosk Sub Wiring s - 6253-KI-002 - Diagram | 24.04.2026 | Alvaro Martin | 2026-04-14 |  | Reviewed | 33% |  |  | 6253-KI-002, 6253-TXP-002, 6253-Kiosk Sub-002 |  | 4HCH018043 | ABB EG | For Approval
6105A | E516B | 6260 | E | TRP | 0003 | A | 6105AE516B-6260-ETRP-0003 |  | Emergency Power Generation | Kiosk Sub - 6260-KI-001 | Test Report | Emergency Power Generation - Kiosk Sub - 6260-KI-001 - Test Report | 15.01.2027 | Alvaro Martin |  |  |  | 0% |  |  | 6260-KI-001, 6260-TXP-001, 6260-Kiosk Sub-001 |  | 4HCH018044 | ABB EG | For Information
6105A | E516B | 6260 | E | GAD | 0003 | B | 6105AE516B-6260-EGAD-0003 |  | Emergency Power Generation | Kiosk Sub Outline Drawing - 6260-KI-001 | General Arrangement | Emergency Power Generation - Kiosk Sub Outline Drawing - 6260-KI-001 - General Arrangement | 27.03.2026 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6260-KI-001, 6260-TXP-001, 6260-Kiosk Sub-001 |  | 4HCH018045 | ABB EG | For Approval
6105A | E516B | 6260 | E | DIA | 0003 | A | 6105AE516B-6260-EDIA-0003 |  | Emergency Power Generation | Kiosk Sub Wiring s - 6260-KI-001 | Diagram | Emergency Power Generation - Kiosk Sub Wiring s - 6260-KI-001 - Diagram | 24.04.2026 | Alvaro Martin | 2026-04-14 |  | Reviewed | 33% |  |  | 6260-KI-001, 6260-TXP-001, 6260-Kiosk Sub-001 |  | 4HCH018046 | ABB EG | For Approval
6105A | E516B | 6286 | E | TRP | 0011 | A | 6105AE516B-6286-ETRP-0011 |  | Mining Open Pit | Kiosk Sub - 6286-KI-001 | Test Report | Mining Open Pit - Kiosk Sub - 6286-KI-001 - Test Report | 15.01.2027 | Alvaro Martin |  |  |  | 0% |  |  | 6286-KI-001, 6286-TXP-001, 6286-Kiosk Sub-001 |  | 4HCH018047 | ABB EG | For Information
6105A | E516B | 6286 | E | GAD | 0011 | B | 6105AE516B-6286-EGAD-0011 |  | Mining Open Pit | Kiosk Sub Outline Drawing - 6286-KI-001 | General Arrangement | Mining Open Pit - Kiosk Sub Outline Drawing - 6286-KI-001 - General Arrangement | 27.03.2026 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6286-KI-001, 6286-TXP-001, 6286-Kiosk Sub-001 |  | 4HCH018048 | ABB EG | For Approval
6105A | E516B | 6286 | E | DIA | 0002 | A | 6105AE516B-6286-EDIA-0002 |  | Mining Open Pit | Kiosk Sub Wiring s - 6286-KI-001 | Diagram | Mining Open Pit - Kiosk Sub Wiring s - 6286-KI-001 - Diagram | 20.03.2026 | Alvaro Martin | 2026-04-14 |  | Reviewed | 33% |  |  | 6286-KI-001, 6286-TXP-001, 6286-Kiosk Sub-001 |  | 4HCH018049 | ABB EG | For Approval
6105A | E516B | 0000 | E | PRC | 0006 | A | 6105AE516B-0000-EPRC-0006 |  | General | DC Power Supply System Factory Acceptance Test | Procedure | General - DC Power Supply System Factory Acceptance Test - Procedure | 24.04.2026 | Maurizio Brescia | 2026-05-21 |  |  | 33% |  |  | General |  | 4HCH018050 | ABB CH | For Information
6105A | E516B | 0000 | E | PRC | 0007 | A | 6105AE516B-0000-EPRC-0007 |  | General | UPS Factory Acceptance Test | Procedure | General - UPS Factory Acceptance Test - Procedure | 03.04.2026 | Alvaro Martin |  |  |  | 0% |  |  | General |  | 4HCH018051 | ABB CH | For Information
6105A | E516B | 0000 | E | PRC | 0009 | A | 6105AE516B-0000-EPRC-0009 |  | General | Kiosk Sub Factory Acceptance Test | Procedure | General - Kiosk Sub Factory Acceptance Test - Procedure |  | Alvaro Martin | 2026-04-08 |  | Approved | 100% |  |  | General |  | 4HCH018053 | ABB EG | For Information
6105A | E516B | 0000 | E | IOM | 0005 | A | 6105AE516B-0000-EIOM-0005 |  | General | Kiosk Sub (IOM) | Installation Operation and Maintenance Manual | General - Kiosk Sub (IOM) - Installation Operation and Maintenance Manual | 15.01.2027 | Alvaro Martin | 2026-04-08 |  | Approved | 100% |  |  | General |  | 4HCH018054 | ABB EG | For Information
6105A | E516B | 0000 | E | PRC | 0008 | B | 6105AE516B-0000-EPRC-0008 |  | General | Kiosk Sub Manufacturers Standard Painting | Procedure | General - Kiosk Sub Manufacturers Standard Painting - Procedure | 15.01.2027 | Alvaro Martin | 2026-05-17 |  |  | 33% |  |  | General |  | 4HCH018055 | ABB EG | For Information
6105A | E516B | 6286 | E | CAL | 0010 | A | 6105AE516B-6286-ECAL-0010 |  | Mining Open Pit | E-House Design Lighting - 6286-SR-001 | Calculation | Mining Open Pit - E-House Design Lighting - 6286-SR-001 - Calculation | 15.05.2026 | Lazar Kobiljski | 2026-06-04 |  |  | 33% |  |  | 6286-SR-001 |  | 4HCH018486 | Alex Sistemi | For Information
6105A | E516B | 0000 | G | BOS | 0001 | A | 6105AE516B-0000-GBOS-0001 |  | General | Basis of | Schedule | General - Basis of - Schedule | 27.03.2026 | Milan Vucelic |  |  |  | 0% |  |  | General |  | 4HCH018710 | ABB | For Approval
6105A | E516B | 0000 | G | RPT | 0001 | A | 6105AE516B-0000-GRPT-0001 |  | General | Monthly Progress | Report | General - Monthly Progress - Report | 26.02.2026 | Thomas Krueger |  |  |  | 0% |  |  | General |  | 4HCH018711 | ABB | For Information
6105A | E516B | 6286 | E | CAL | 0012 | B | 6105AE516B-6286-ECAL-0012 |  | Mining Open Pit | MV AIS CT - 6286-SB-002 | Calculation | Mining Open Pit - MV AIS CT - 6286-SB-002 - Calculation | 20.02.2026 | Sanja Todoran | 2026-04-23 |  | Approved | 100% |  |  | 6286-SB-002 |  | 4HCH018732 | ABB CZ | For Approval
6105A | E516B | 6292 | E | CAL | 0007 | A | 6105AE516B-6292-ECAL-0007 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS CT - 6292-SB-001 | Calculation | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS CT - 6292-SB-001 - Calculation | 20.02.2026 | Milan Djurdjevic |  |  |  | 0% |  |  | 6292-SB-001 |  | 4HCH018733 | ABB CZ | For Approval
6105A | E516B | 6286 | E | CAL | 0013 | B | 6105AE516B-6286-ECAL-0013 |  | Mining Open Pit | 33kV MV GIS CT - 6286-SB-001 | Calculation | Mining Open Pit - 33kV MV GIS CT - 6286-SB-001 - Calculation | 20.02.2026 | Milan Djurdjevic | 2026-04-08 |  | Approved | 100% |  |  | 6286-SB-001 |  | 4HCH018734 | ABB CZ | For Approval
6105A | E516B | 0000 | E | ITP | 0007 | A | 6105AE516B-0000-EITP-0007 |  | General | Kiosk (ITP) | Inspection Test Plan | General - Kiosk (ITP) - Inspection Test Plan | 01.05.2026 | Alvaro Martin |  |  |  | 0% |  |  | General |  | 4HCH018735 | ABB EG | For Approval
6105A | E516B | 6262 | E | GAD | 0006 | 0 | 6105AE516B-6262-EGAD-0006 |  | Emergency Power Substation 1 and Control Room 1 | UPS 6262-UPS-001 | General Arrangement | Emergency Power Substation 1 and Control Room 1 - UPS 6262-UPS-001 - General Arrangement | 06.02.2026 | Alvaro Martin | 2026-05-07 | 2026-05-13 | Approved | 100% |  |  | 6262-UPS-001 |  | 4HCH018746 | ABB CH | For Approval
6105A | E516B | 6262 | E | DIA | 0017 | 1 | 6105AE516B-6262-EDIA-0017 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS Typical Wiring Aux supply - 6262-SB-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - MV AIS Typical Wiring Aux supply - 6262-SB-001 - Diagram | 24/03/2026 | Sanja Todoran | 2026-04-17 | 2026-05-26 | Approved | 100% |  |  |  |  | 4HCH019006 | ABB CZ | For Review
6105A | E516B | 6262 | E | DIA | 0018 | 1 | 6105AE516B-6262-EDIA-0018 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS Typical Wiring Common - 6262-SB-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - MV AIS Typical Wiring Common - 6262-SB-001 - Diagram | 24/03/2026 | Sanja Todoran | 2026-04-15 | 2026-05-26 | Approved | 100% |  |  |  |  | 4HCH019007 | ABB CZ | For Review
6105A | E516B | 6262 | E | DIA | 0019 | D | 6105AE516B-6262-EDIA-0019 |  | Emergency Power Substation 1 and Control Room 1 | MV AIS Typical Wiring Communication - 6262-SB-001 | Diagram | Emergency Power Substation 1 and Control Room 1 - MV AIS Typical Wiring Communication - 6262-SB-001 - Diagram | 24/03/2026 | Sanja Todoran | 2026-05-26 |  | Reviewed | 33% |  |  |  |  | 4HCH019008 | ABB CZ | For Review
6105A | E516B | 6286 | E | DIA | 0033 | C | 6105AE516B-6286-EDIA-0033 |  | Mining Open Pit | MV AIS Typical Wiring Communication - 6286-SB-002 | Diagram | Mining Open Pit - MV AIS Typical Wiring Communication - 6286-SB-002 - Diagram | 24/03/2026 | Sanja Todoran | 2026-05-26 |  | Approved | 100% |  |  |  |  | 4HCH019009 | ABB CZ | For Review
6105A | E516B | 6260 | E | DIA | 0004 | A | 6105AE516B-6260-EDIA-0004 |  | Emergency Power Generation | Kiosk Sub Single Line - 6260-KI-002 | Diagram | Emergency Power Generation - Kiosk Sub Single Line - 6260-KI-002 - Diagram | 2026-03-27 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6260-KI-002, 6260-TXP-002, 6260-Kiosk Sub-002 |  | 4HCH019097 | ABB EG | For Review
6105A | E516B | 6260 | E | DIA | 0005 | A | 6105AE516B-6260-EDIA-0005 |  | Emergency Power Generation | Kiosk Sub Single Line - 6260-KI-003 | Diagram | Emergency Power Generation - Kiosk Sub Single Line - 6260-KI-003 - Diagram | 2026-03-27 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6260-KI-003, 6260-TXP-003, 6260-Kiosk Sub-003 |  | 4HCH019098 | ABB EG | For Review
6105A | E516B | 6200 | E | DIA | 0021 | A | 6105AE516B-6200-EDIA-0021 |  | On-Site Power Supply and Transmission | Kiosk Sub Single Line - 6200-KI-056 | Diagram | On-Site Power Supply and Transmission - Kiosk Sub Single Line - 6200-KI-056 - Diagram | 2026-03-27 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6200-KI-056, 6200-TXD-056, 6200-Kiosk Sub-056 |  | 4HCH019099 | ABB EG | For Review
6105A | E516B | 6290 | E | DIA | 0002 | A | 6105AE516B-6290-EDIA-0002 |  | Renewable Energy | Kiosk Sub Single Line - 6290-KI-001 | Diagram | Renewable Energy - Kiosk Sub Single Line - 6290-KI-001 - Diagram | 2026-03-27 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6290-KI-001, 6290-TXD-001, 6290-Kiosk Sub-001 |  | 4HCH019100 | ABB EG | For Review
6105A | E516B | 6253 | E | DIA | 0003 | A | 6105AE516B-6253-EDIA-0003 |  | Synchronous Condenser 1 | Kiosk Sub Single Line - 6253-KI-001 | Diagram | Synchronous Condenser 1 - Kiosk Sub Single Line - 6253-KI-001 - Diagram | 2026-03-27 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6253-KI-001, 6253-TXP-001, 6253-Kiosk Sub-001 |  | 4HCH019101 | ABB EG | For Review
6105A | E516B | 6253 | E | DIA | 0004 | A | 6105AE516B-6253-EDIA-0004 |  | Synchronous Condenser 1 | Kiosk Sub Single Line - 6253-KI-002 | Diagram | Synchronous Condenser 1 - Kiosk Sub Single Line - 6253-KI-002 - Diagram | 2026-03-27 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6253-KI-002, 6253-TXP-002, 6253-Kiosk Sub-002 |  | 4HCH019102 | ABB EG | For Review
6105A | E516B | 6260 | E | DIA | 0006 | A | 6105AE516B-6260-EDIA-0006 |  | Emergency Power Generation | Kiosk Sub Single Line - 6260-KI-001 | Diagram | Emergency Power Generation - Kiosk Sub Single Line - 6260-KI-001 - Diagram | 2026-03-27 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6260-KI-001, 6260-TXP-001, 6260-Kiosk Sub-001 |  | 4HCH019103 | ABB EG | For Review
6105A | E516B | 6286 | E | DIA | 0034 | A | 6105AE516B-6286-EDIA-0034 |  | Mining Open Pit | Kiosk Sub Single Line - 6286-KI-001 | Diagram | Mining Open Pit - Kiosk Sub Single Line - 6286-KI-001 - Diagram | 2026-03-27 | Alvaro Martin | 2026-05-17 |  | Reviewed | 33% |  |  | 6286-KI-001, 6286-TXP-001, 6286-Kiosk Sub-001 |  | 4HCH019104 | ABB EG | For Review
6105A | E516B | 0000 | E | ITP | 0008 | A | 6105AE516B-0000-EITP-0008 |  | General | Kiosk Sub (ITP) | Inspection Test Plan | General - Kiosk Sub (ITP) - Inspection Test Plan | 2027-01-15 | Alvaro Martin |  |  |  | 0% |  |  |  |  | 4HCH019105 | ABB EG | For Review
6105A | E516B | 0000 | A | DST | 0001 | B | 6105AE516B-0000-ADST-0001 |  | General | Pre-fabricated E-House | Datasheet | General - Pre-fabricated E-House - Datasheet | 2026-06-06 | Lazar Kobiljski | 2026-05-12 |  | Approved | 100% |  |  |  |  | 4HCH019280 | Alex Sistemi | For Review
6105A | E516B | 6286 | E | DIA | 0035 | 0 | 6105AE516B-6286-EDIA-0035 |  | Mining Open Pit | 33kV MV GIS Typical Wiring Spare Feeder H08 - 6286-SB-001 | Diagram | Mining Open Pit - 33kV MV GIS Typical Wiring Spare Feeder H08 - 6286-SB-001 - Diagram | 24/03/2030 | Milan Djurdjevic | 2026-05-18 | 2026-06-04 | Approved | 100% |  |  | 6286-SB-001 |  | 4HCH019316 | ABB CZ | For Review
6105A | E516B | 6286 | E | DIA | 0036 | C | 6105AE516B-6286-EDIA-0036 |  | Mining Open Pit | 33kV MV GIS Typical Wiring Common drawings - 6286-SB-001 | Diagram | Mining Open Pit - 33kV MV GIS Typical Wiring Common drawings - 6286-SB-001 - Diagram | 24/03/2031 | Milan Djurdjevic | 2026-06-04 |  | Reviewed | 33% |  |  | 6286-SB-001 |  | 4HCH019317 | ABB CZ | For Review
6105A | E516B | 6200 | E | DIA | 0022 | B | 6105AE516B-6200-EDIA-0022 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Incomer Bus B - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Incomer Bus B - 6200-SB-051 - Diagram | 2026-03-24 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH019347 | ABB CZ | For Review
6105A | E516B | 6200 | E | DIA | 0023 | B | 6105AE516B-6200-EDIA-0023 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Metering Bus C - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Metering Bus C - 6200-SB-051 - Diagram | 2026-03-24 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH019348 | ABB CZ | For Review
6105A | E516B | 6200 | E | DIA | 0024 | B | 6105AE516B-6200-EDIA-0024 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Spare Feeder H14 - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Spare Feeder H14 - 6200-SB-051 - Diagram | 2026-03-24 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH019349 | ABB CZ | For Review
6105A | E516B | 6200 | E | DIA | 0025 | B | 6105AE516B-6200-EDIA-0025 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Spare Feeder H30 - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Spare Feeder H30 - 6200-SB-051 - Diagram | 2026-03-24 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH019350 | ABB CZ | For Review
6105A | E516B | 6200 | E | DIA | 0026 | B | 6105AE516B-6200-EDIA-0026 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Feeder BESS - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Feeder BESS - 6200-SB-051 - Diagram | 2026-03-24 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH019351 | ABB CZ | For Review
6105A | E516B | 6200 | E | DIA | 0027 | B | 6105AE516B-6200-EDIA-0027 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Syncon TX Bus B Feeder - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Syncon TX Bus B Feeder - 6200-SB-051 - Diagram | 2026-03-24 | Milan Djurdjevic | 2026-06-05 |  | Approved | 100% |  |  | 6200-SB-051 |  | 4HCH019352 | ABB CZ | For Review
6105A | E516B | 6200 | E | DIA | 0028 | B | 6105AE516B-6200-EDIA-0028 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Emergency DG Feeder - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Emergency DG Feeder - 6200-SB-051 - Diagram | 2026-03-24 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH019353 | ABB CZ | For Review
6105A | E516B | 6200 | E | DIA | 0029 | B | 6105AE516B-6200-EDIA-0029 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring OHL Feeder Bus B - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring OHL Feeder Bus B - 6200-SB-051 - Diagram | 2026-03-24 | Milan Djurdjevic | 2026-06-05 |  | Reviewed | 33% |  |  | 6200-SB-051 |  | 4HCH019354 | ABB CZ | For Review
6105A | E516B | 6200 | E | DIA | 0030 | B | 6105AE516B-6200-EDIA-0030 |  | On-Site Power Supply and Transmission | 33kV MV GIS Typical Wiring Common Drawings - 6200-SB-051 | Diagram | On-Site Power Supply and Transmission - 33kV MV GIS Typical Wiring Common Drawings - 6200-SB-051 - Diagram | 2026-03-24 | Milan Djurdjevic | 2026-06-05 |  | Approved | 100% |  |  | 6200-SB-051 |  | 4HCH019355 | ABB CZ | For Review
6105A | E516B | 6292 | E | DIA | 0016 | A | 6105AE516B-6292-EDIA-0016 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS Typical Wiring Incomer Bus B- 6292-SB-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS Typical Wiring Incomer Bus B- 6292-SB-001 - Diagram | 24.03.2027 | Milan Djurdjevic | 2026-05-18 |  | Reviewed | 33% |  |  | 6292-SB-001 |  | 4HCH019382 | ABB CZ | For Approval
6105A | E516B | 6292 | E | DIA | 0017 | A | 6105AE516B-6292-EDIA-0017 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS Typical Wiring Metering Bus C - 6292-SB-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS Typical Wiring Metering Bus C - 6292-SB-001 - Diagram | 24.03.2029 | Milan Djurdjevic | 2026-05-18 |  | Approved | 100% |  |  | 6292-SB-001 |  | 4HCH019383 | ABB CZ | For Approval
6105A | E516B | 6292 | E | DIA | 0018 | A | 6105AE516B-6292-EDIA-0018 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS Typical Wiring Outgoing Feeder Bus A & Bus C - 6292-SB-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS Typical Wiring Outgoing Feeder Bus A & Bus C - 6292-SB-001 - Diagram | 24.03.2031 | Milan Djurdjevic | 2026-05-18 |  | Reviewed | 33% |  |  | 6292-SB-001 |  | 4HCH019384 | ABB CZ | For Approval
6105A | E516B | 6292 | E | DIA | 0019 | A | 6105AE516B-6292-EDIA-0019 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS Typical Wiring Outgoing Feeder Bus B - 6292-SB-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS Typical Wiring Outgoing Feeder Bus B - 6292-SB-001 - Diagram | 24.03.2032 | Milan Djurdjevic | 2026-05-18 |  | Reviewed | 33% |  |  | 6292-SB-001 |  | 4HCH019385 | ABB CZ | For Approval
6105A | E516B | 6292 | E | DIA | 0020 | A | 6105AE516B-6292-EDIA-0020 |  | 11/33kV Solar PV Substation 1 and Control Room 1 | 33kV MV GIS Typical Wiring Common Drawings - 6292-SB-001 | Diagram | 11/33kV Solar PV Substation 1 and Control Room 1 - 33kV MV GIS Typical Wiring Common Drawings - 6292-SB-001 - Diagram | 24.03.2036 | Milan Djurdjevic | 2026-05-18 |  | Reviewed | 33% |  |  | 6292-SB-001 |  | 4HCH019386 | ABB CZ | For Approval
6105A | E516B | 6286 | E | DIA | 0037 | A | 6105AE516B-6286-EDIA-0037 |  | Mining Open Pit | MV AIS Typical Wiring 400V aux supply - 6286-SB-002 | Diagram | Mining Open Pit - MV AIS Typical Wiring 400V aux supply - 6286-SB-002 - Diagram | 24.03.2036 | Sanja Todoran | 2026-05-26 |  | Approved | 100% |  |  | 6286-SB-002 |  | 4HCH019896 | ABB CZ | For Approval
6105A | E516B | 0000 | E | MAN | 0001 | A | 6105AE516B-0000-EMAN-0001 |  | General | MV GIS ZX0.2 (IOM) | Installation Operation and Maintenance Manual | General - MV GIS ZX0.2 (IOM) - Installation Operation and Maintenance Manual | 24.03.2036 | Milan Djurdjevic | 2026-05-19 |  | Approved | 100% |  |  |  |  | 4HCH019897 | ABB CZ | For Approval

## Progress Tracker (hidden)
Total Del. | 249
| Monthly Incremental |  |  | Cumulative to Date
Progress Category | Plan | Forecast | Actual | Plan | NA | Actual
Engineering | 262 | NA | 189 |  |  | 72.14%
Total Del. | 249
2026-02-26
| Monthly Incremental | [5 empty] | Cumulative to Date |  |  |  | ABB - 23.2.26
Progress Category | Plan | Forecast | Actual | % Planned | % Forecast | % Actual | % Plan | % Forecast | % Actual | % Delta | % Plan | % Forecast | % Actual
Engineering | 77 | 77 | 0 | 30.92% | 30.92% | 0% | 30.92% | 30.92% | 0% | -30.92% | 32.69% | 15.2% | 15.2%
2026-03-26
| Monthly Incremental | [5 empty] | Cumulative to Date |  |  |  | ABB - 23.3.26
Progress Category | Plan | Forecast | Actual | % Planned | % Forecast | % Actual | % Plan | % Forecast | % Actual | % Delta | % Plan | % Forecast | % Actual
Engineering | 41 | 118 | 40 | 16.47% | 47.39% | 33.9% | 47.39% | 30.92% | 16.06% | -31.33% | 53.05% | 0% | 0%
2026-04-26
| Monthly Incremental | [5 empty] | Cumulative to Date |  |  |  | ABB - 27.4.26
Progress Category | Plan | Forecast | Actual | % Planned | % Forecast | % Actual | % Plan | % Forecast | % Actual | % Delta | % Plan | % Forecast | % Actual
Engineering | 19 | 97 | 60 | 7.631% | 38.96% | 61.86% | 55.02% | 55.02% | 40.16% | -14.86% | 72.3% | 0% | 0%
2026-05-26
| Monthly Incremental | [5 empty] | Cumulative to Date |  |  |  | ABB - 25.5.26
Progress Category | Plan | Forecast | Actual | % Planned | % Forecast | % Actual | % Plan | % Forecast | % Actual | % Delta | % Plan | % Forecast | % Actual
Engineering | 20 | 57 | 0 | 8.032% | 22.89% | 0% | 63.05% | 63.05% | 40.16% | -22.89% | 83.25% | 0% | 0%
2026-06-26
| Monthly Incremental | [5 empty] | Cumulative to Date |  |  |  | ABB - 22.6.26
Progress Category | Plan | Forecast | Actual | % Planned | % Forecast | % Actual | % Plan | % Forecast | % Actual | % Delta | % Plan | % Forecast | % Actual
Engineering | 0 | 57 | 0 | 0% | 22.89% | 0% | 32.13% | 63.05% | 40.16% | 8.032% | 87.18% | 0% | 0%
2026-07-26
| Monthly Incremental | [5 empty] | Cumulative to Date |  |  |  | ABB - 27.7.26
Progress Category | Plan | Forecast | Actual | % Planned | % Forecast | % Actual | % Plan | % Forecast | % Actual | % Delta | % Plan | % Forecast | % Actual
Engineering | 16 | 0 | 0 | 6.426% | 0% | #DIV/0! | 69.48% | 40.16% | 40.16% | -29.32% | 92.88% | 0% | 0%
2026-08-26
| Monthly Incremental | [5 empty] | Cumulative to Date |  |  |  | ABB - 24.8.26
Progress Category | Plan | Forecast | Actual | % Planned | % Forecast | % Actual | % Plan | % Forecast | % Actual | % Delta | % Plan | % Forecast | % Actual
Engineering | 19 | 0 | 0 | 7.631% | 0% | #DIV/0! | 77.11% | 40.16% | 40.16% | -36.95% | 92.93% | 0% | 0%
2027-02-27
| Monthly Incremental | [5 empty] | Cumulative to Date |  |  |  | ABB - 22.2.27
Progress Category | Plan | Forecast | Actual | % Planned | % Forecast | % Actual | % Plan | % Forecast | % Actual | % Delta | % Plan | % Forecast | % Actual
Engineering | 10 | 0 | 0 | 4.016% | 0% | #DIV/0! | 81.12% | 40.16% | 40.16% | -40.96% | 96.06% | 0% | 0%
2027-08-27
| Monthly Incremental | [5 empty] | Cumulative to Date |  |  |  | ABB - 23.8.27
Progress Category | Plan | Forecast | Actual | % Planned | % Forecast | % Actual | % Plan | % Forecast | % Actual | % Delta | % Plan | % Forecast | % Actual
Engineering | 2 | 0 | 0 | 0.8032% | 0% | #DIV/0! | 81.93% | 40.16% | 40.16% | -41.77% | 99.19% | 0% | 0%

## E516B WBS Codes
L1 | L2 | L3 | L4 | Code | Reko Diq Copper - Gold Project Facility Name
0 | 0 | 0 | 0 | 0000 | General | 0000 - General
0 | 1 | 0 | 0 | 0100 | Project Site Wide | 0100 - Project Site Wide
6 | 2 | 0 | 0 | 6200 | On-Site Power Supply and Transmission | 6200 - On-Site Power Supply and Transmission
6 | 2 | 5 | 3 | 6253 | Synchronous Condenser 1 | 6253 - Synchronous Condenser 1
6 | 2 | 6 | 0 | 6260 | Emergency Power Generation | 6260 - Emergency Power Generation
6 | 2 | 6 | 1 | 6261 | Administration and General Buildings | 6261 - Administration and General Buildings
6 | 2 | 6 | 2 | 6262 | Emergency Power Substation 1 and Control Room 1 | 6262 - Emergency Power Substation 1 and Control Room 1
6 | 2 | 6 | 3 | 6263 | 36 MVA Power Station 1 | 6263 - 36 MVA Power Station 1
6 | 2 | 6 | 4 | 6264 | Bulk Diesel Storage 1 | 6264 - Bulk Diesel Storage 1
6 | 2 | 6 | 5 | 6265 | Truck Diesel Unloading and Power Station 1 | 6265 - Truck Diesel Unloading and Power Station 1
6 | 2 | 6 | 6 | 6266 | Emergency Power Substation 2 and Control Room 2 | 6266 - Emergency Power Substation 2 and Control Room 2
6 | 2 | 6 | 7 | 6267 | 36 MVA Power Station 2 | 6267 - 36 MVA Power Station 2
6 | 2 | 6 | 8 | 6268 | Bulk Diesel Storage 2 | 6268 - Bulk Diesel Storage 2
6 | 2 | 6 | 9 | 6269 | Truck Diesel Unloading and Power Station 2 | 6269 - Truck Diesel Unloading and Power Station 2
6 | 2 | 8 | 6 | 6286 | Mining Open Pit | 6286 - Mining Open Pit
6 | 2 | 9 | 0 | 6290 | Renewable Energy | 6290 - Renewable Energy
6 | 2 | 9 | 2 | 6292 | 11/33kV Solar PV Substation 1 and Control Room 1 | 6292 - 11/33kV Solar PV Substation 1 and Control Room 1

## Rev10 RDMC WBS Areas
| Facility Level ID |  |  | Facility Code | Reko Diq Project Facility Name | Engineering | Procurement | Contracts | Construction Management
L1 | L2 | L3 | L4
0 | 0 | 0 | 0 | 0 | General | - | - | - | -
0 | 1 | 0 | 0 | 100 | Project Site Wide | - | - | - | -
1 | 0 | 0 | 0 | 1000 | Mining - OP | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
1 | 1 | 0 | 0 | 1100 | Open Pit Mine | RDMC/Fluo r | RDMC/Fluo r | RDMC/Fluo r | RDMC/Fluo r
1 | 1 | 1 | 0 | 1110 | Open Pit Mine Development | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 1 | 1111 | Pre-Stripping | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 2 | 1112 | Stockpiling | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 3 | 1113 | Waste Dumps | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 4 | 1114 | Run-of-Mine Pad | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 5 | 1115 | Clearing, Grubbing and Topsoil Stockpiling | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 9 | 1119 | Common Facilities and Services | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 0 | 1120 | Open Pit Mining Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 1 | 1121 | Drilling Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 2 | 1122 | Loading Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 3 | 1123 | Hauling Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 4 | 1124 | Support Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 5 | 1125 | Maintenance Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 3 | 0 | 1130 | Infrastructure | RDMC/Fluor/PPE | RDMC/Fluor/PPE | RDMC/Fluor/PPE | RDMC/Fluor/PPE
1 | 1 | 3 | 1 | 1131 | Haul Roads | RDMC | RDMC | RDMC | RDMC
1 | 1 | 3 | 2 | 1132 | Pioneering | RDMC | RDMC | RDMC | RDMC
1 | 1 | 3 | 3 | 1133 | Dewatering | Fluor | Fluor | Fluor | Fluor
1 | 1 | 3 | 4 | 1134 | Trailing Cables and Shovel Reticulation | PPE | PPE | PPE | PPE
1 | 1 | 3 | 7 | 1137 | Planning and Exploration | RDMC | RDMC | RDMC | RDMC
1 | 1 | 3 | 9 | 1139 | Common Facilities and Services | Fluor/PPE | Fluor/PPE | Fluor/PPE | Fluor/PPE
1 | 1 | 8 | 0 | 1180 | Explosives Plant, Magazine and Storage | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 1 | 1181 | Explosives and Detonator Magazines | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 2 | 1182 | Manufacturing Plant | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 3 | 1183 | Raw Materials Warehouse | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 4 | 1184 | Ammonium Nitrate Warehouse | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 5 | 1185 | Office and Dry Mess | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 6 | 1186 | Change Room and Ablutions | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 7 | 1187 | Workshop | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 8 | 1188 | Washdown Facility | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 9 | 1189 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 0 | 0 | 1200 | Mine Infrastructure Area and Services | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
1 | 2 | 1 | 0 | 1210 | Site Preparation | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
1 | 2 | 1 | 1 | 1211 | Bulk Earthworks | Fluor | Fluor | Fluor | Fluor
1 | 2 | 1 | 2 | 1212 | Drainage and Culverts | Fluor | Fluor | Fluor | Fluor
1 | 2 | 1 | 3 | 1213 | Improvements | Fluor | Fluor | Fluor | Fluor
1 | 2 | 1 | 4 | 1214 | Security Fencing | RDMC | RDMC | RDMC | RDMC
1 | 2 | 2 | 0 | 1220 | Roads and Paving | Fluor | Fluor | Fluor | Fluor
1 | 2 | 2 | 1 | 1221 | In-Plant Roads | Fluor | Fluor | Fluor | Fluor
1 | 2 | 2 | 2 | 1222 | Carparks and Hardstand Areas | Fluor | Fluor | Fluor | Fluor
1 | 2 | 3 | 0 | 1230 | Central Facilities | Fluor | Fluor | Fluor | Fluor
1 | 2 | 3 | 1 | 1231 | Administration Buildings | Fluor | Fluor | Fluor | Fluor
1 | 2 | 3 | 2 | 1232 | Change Rooms and Ablution Blocks | Fluor | Fluor | Fluor | Fluor
1 | 2 | 3 | 9 | 1239 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 0 | 1240 | Heavy Equipment Maintenance Facilities | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 1 | 1241 | Preventive Maintenance Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 2 | 1242 | Utilities Area | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 3 | 1243 | Repair Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 4 | 1244 | Tyre Storage and Change | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 5 | 1245 | Washdown Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 6 | 1246 | Warehouse | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 7 | 1247 | Fabrication Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 8 | 1248 | Assembly Area | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 9 | 1249 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 0 | 1250 | Light Vehicle Equipment Maintenance Facilities | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 1 | 1251 | Preventive Maintenance Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 2 | 1252 | Hydraulics and Electrical Repair Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 3 | 1253 | Repair/Rebuild Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 4 | 1254 | Tyre Storage and Change | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 5 | 1255 | Washdown Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 6 | 1256 | Warehouse | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 8 | 1258 | Laydown Area | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 9 | 1259 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 0 | 1260 | Water and Waste Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 1 | 1261 | Raw Water Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 2 | 1262 | Fire Water Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 3 | 1263 | Potable Water Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 4 | 1264 | Waste Water Disposal | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 5 | 1265 | Sewage Effluent Disposal | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 6 | 1266 | Raw Water Distribution | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 7 | 1267 | Firewater Distribution | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 8 | 1268 | Potable Water Distribution | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 9 | 1269 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 7 | 0 | 1270 | Power, Communications and Security Systems | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
1 | 2 | 7 | 1 | 1271 | Light Vehicle Power Supply and Distribution | Fluor | Fluor | Fluor | Fluor
1 | 2 | 7 | 2 | 1272 | Communication | Fluor | Fluor | Fluor | Fluor
1 | 2 | 7 | 3 | 1273 | Mine Dispatch | RDMC | RDMC | RDMC | RDMC
1 | 2 | 7 | 4 | 1274 | Security | RDMC | RDMC | RDMC | RDMC
1 | 2 | 7 | 9 | 1279 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 0 | 1280 | Compressed Air Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 1 | 1281 | Compression | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 2 | 1282 | Wet Receiving | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 3 | 1283 | Drying | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 4 | 1284 | Dry Receiving | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 5 | 1285 | Distribution | - | - | - | -
1 | 2 | 8 | 9 | 1289 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 0 | 1290 | Fuel and Lubrication Storage and Reticulation | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 1 | 1291 | Diesel Bulk Storage Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 2 | 1292 | Central Refuelling Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 3 | 1293 | Remote Refuelling Bay 1 | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 4 | 1294 | Remote Refuelling Bay 2 | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 5 | 1295 | Remote Refuelling Bay 3 | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 6 | 1296 | Heavy Vehicle Lube Unloading and Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 7 | 1297 | Light Vehicle Refuelling Area | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 8 | 1298 | Light Vehicle Lube Unloading and Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 9 | 1299 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
2 | 0 | 0 | 0 | 2000 | Mining - Underground | - | - | - | -
2 | 1 | 0 | 0 | 2100 | Underground Mine | - | - | - | -
2 | 1 | 1 | 0 | 2110 | Mine Development | - | - | - | -
2 | 1 | 1 | 1 | 2111 | Access Development | - | - | - | -
2 | 1 | 1 | 2 | 2112 | Mine Stockpiling | - | - | - | -
2 | 1 | 1 | 3 | 2113 | Waste Dumps | - | - | - | -
2 | 1 | 1 | 4 | 2114 | Level Access Development | - | - | - | -
2 | 1 | 1 | 5 | 2115 | Haulage Development | - | - | - | -
2 | 1 | 1 | 6 | 2116 | Reef Development | - | - | - | -
2 | 1 | 1 | 7 | 2117 | Raw | - | - | - | -
2 | 1 | 2 | 0 | 2120 | Underground Mining Equipment | - | - | - | -
2 | 1 | 2 | 1 | 2121 | Drilling Equipment | - | - | - | -
2 | 1 | 2 | 2 | 2122 | Loading Equipment | - | - | - | -
2 | 1 | 2 | 3 | 2123 | Hauling Equipment | - | - | - | -
2 | 1 | 2 | 4 | 2124 | Support Equipment | - | - | - | -
2 | 1 | 2 | 5 | 2125 | Mine Maintenance Equipment | - | - | - | -
2 | 1 | 2 | 6 | 2126 | Underground Communication | - | - | - | -
2 | 1 | 2 | 7 | 2127 | Reinforcements | - | - | - | -
2 | 1 | 2 | 8 | 2128 | Control and Instrumentation | - | - | - | -
2 | 1 | 3 | 0 | 2130 | Underground Mine Infrastructure | - | - | - | -
2 | 1 | 3 | 1 | 2131 | Mine Roads | - | - | - | -
2 | 1 | 3 | 2 | 2132 | Development | - | - | - | -
2 | 1 | 3 | 3 | 2133 | Dewatering | - | - | - | -
2 | 1 | 3 | 4 | 2134 | Truck Shop | - | - | - | -
2 | 1 | 3 | 5 | 2135 | Explosive Magazine | - | - | - | -
2 | 1 | 3 | 6 | 2136 | Mine Stockpiling Platforms | - | - | - | -
2 | 1 | 3 | 7 | 2137 | Timber Preparation Facilities | - | - | - | -
2 | 1 | 3 | 8 | 2138 | Mine Facilities and Services | - | - | - | -
2 | 1 | 3 | 9 | 2139 | Planning and Exploration | - | - | - | -
2 | 1 | 4 | 0 | 2140 | Underground Mine Shaft | - | - | - | -
2 | 1 | 4 | 1 | 2141 | Shaft Development | - | - | - | -
2 | 1 | 4 | 2 | 2142 | Head Frame | - | - | - | -
2 | 1 | 4 | 3 | 2143 | Hoisting | - | - | - | -
2 | 1 | 5 | 0 | 2150 | Ventilation and Services | - | - | - | -
2 | 1 | 5 | 1 | 2151 | Ventilation Shafts | - | - | - | -
2 | 1 | 5 | 2 | 2152 | Ventilation Fans and Equipment | - | - | - | -
2 | 1 | 5 | 3 | 2153 | Refrigeration | - | - | - | -
2 | 1 | 5 | 4 | 2154 | Compressed Air Plant | - | - | - | -
2 | 1 | 6 | 0 | 2160 | Underground Material Handling | - | - | - | -
2 | 1 | 6 | 1 | 2161 | Ore and Waste Passes | - | - | - | -
2 | 1 | 6 | 2 | 2162 | Underground Crushing | - | - | - | -
2 | 1 | 6 | 3 | 2163 | Underground Conveying | - | - | - | -
3 | 0 | 0 | 0 | 3000 | Dry Plant | Fluor | Fluor | Fluor | Fluor
3 | 1 | 0 | 0 | 3100 | Primary Crushing | Fluor | Fluor | Fluor | Fluor
3 | 1 | 1 | 0 | 3110 | Crushers | Fluor | Fluor | Fluor | Fluor
3 | 1 | 1 | 1 | 3111 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 1 | 2 | 3112 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 2 | 0 | 3120 | Truck Dump Pad | Fluor | Fluor | Fluor | Fluor
3 | 1 | 2 | 1 | 3121 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 2 | 2 | 3122 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 3 | 0 | 3130 | Chamber | Fluor | Fluor | Fluor | Fluor
3 | 1 | 3 | 1 | 3131 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 3 | 2 | 3132 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 4 | 0 | 3140 | Tunnel | Fluor | Fluor | Fluor | Fluor
3 | 1 | 4 | 1 | 3141 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 4 | 2 | 3142 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 5 | 0 | 3150 | Crusher Discharge Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 1 | 5 | 1 | 3151 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 5 | 2 | 3152 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 6 | 0 | 3160 | Transfer Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 1 | 6 | 2 | 3162 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 9 | 0 | 3190 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 1 | 9 | 7 | 3197 | Dust Control | Fluor | Fluor | Fluor | Fluor
3 | 1 | 9 | 8 | 3198 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 1 | 9 | 9 | 3199 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 2 | 0 | 0 | 3200 | Coarse Ore Transport | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 0 | 3210 | Stockpile Feed | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 1 | 3211 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 2 | 3212 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 3 | 3213 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 4 | 3214 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 5 | 3215 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 2 | 9 | 0 | 3290 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 2 | 9 | 7 | 3297 | Dust Control | Fluor | Fluor | Fluor | Fluor
3 | 2 | 9 | 8 | 3298 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 2 | 9 | 9 | 3299 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 3 | 0 | 0 | 3300 | Coarse Ore Storage & Reclaim | Fluor | Fluor | Fluor | Fluor
3 | 3 | 1 | 0 | 3310 | Base Pad | Fluor | Fluor | Fluor | Fluor
3 | 3 | 2 | 0 | 3320 | Chamber | Fluor | Fluor | Fluor | Fluor
3 | 3 | 3 | 0 | 3330 | Tunnel | Fluor | Fluor | Fluor | Fluor
3 | 3 | 3 | 1 | 3331 | Reclaim | Fluor | Fluor | Fluor | Fluor
3 | 3 | 3 | 2 | 3332 | Escape | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 0 | 3340 | Coarse Ore Reclaim | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 1 | 3341 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 2 | 3342 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 3 | 3343 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 4 | 3344 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 5 | 3345 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 3 | 9 | 0 | 3390 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 3 | 9 | 7 | 3397 | Dust Control | Fluor | Fluor | Fluor | Fluor
3 | 3 | 9 | 8 | 3398 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 3 | 9 | 9 | 3399 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 4 | 0 | 0 | 3400 | Coarse Ore Screening and Transport | Fluor | Fluor | Fluor | Fluor
3 | 4 | 1 | 0 | 3410 | Screening | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 0 | 3420 | Coarse Ore Screen Oversize | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 1 | 3421 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 2 | 3422 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 3 | 3423 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 4 | 3424 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 5 | 3425 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 0 | 3430 | Coarse Ore Screen Undersize | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 1 | 3431 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 2 | 3432 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 3 | 3433 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 4 | 3434 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 5 | 3435 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 0 | 3440 | HPGR Feed | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 1 | 3441 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 2 | 3442 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 3 | 3443 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 4 | 3444 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 5 | 3445 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 9 | 0 | 3490 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 4 | 9 | 7 | 3497 | Dust Control | Fluor | Fluor | Fluor | Fluor
3 | 4 | 9 | 8 | 3498 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 4 | 9 | 9 | 3499 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 5 | 0 | 0 | 3500 | Secondary Crushing | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 0 | 3520 | Secondary Crushing | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 1 | 3521 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 2 | 3522 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 3 | 3523 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 4 | 3524 | Train 4 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 5 | 3525 | Train 5 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 9 | 0 | 3590 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 5 | 9 | 7 | 3597 | Dust collection | Fluor | Fluor | Fluor | Fluor
3 | 5 | 9 | 8 | 3598 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 5 | 9 | 9 | 3599 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 6 | 0 | 0 | 3600 | Tertiary Crushing | Fluor | Fluor | Fluor | Fluor
3 | 6 | 1 | 0 | 3610 | High Pressure Grinding | Fluor | Fluor | Fluor | Fluor
3 | 6 | 1 | 1 | 3611 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 6 | 1 | 2 | 3612 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 6 | 1 | 3 | 3613 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 0 | 3620 | Fine Ore Storage Feed | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 1 | 3621 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 2 | 3622 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 3 | 3623 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 4 | 3624 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 5 | 3625 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 6 | 9 | 0 | 3690 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 6 | 9 | 7 | 3697 | Dust Collection | Fluor | Fluor | Fluor | Fluor
3 | 6 | 9 | 8 | 3698 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 6 | 9 | 9 | 3699 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 7 | 0 | 0 | 3700 | Fine Ore | Fluor | Fluor | Fluor | Fluor
3 | 7 | 1 | 0 | 3710 | Storage Bins | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 0 | 3720 | Reclaim Feeders | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 1 | 3721 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 2 | 3722 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 3 | 3723 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 4 | 3724 | Train 4 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 5 | 3725 | Train 5 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 6 | 3726 | Train 6 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 0 | 3730 | Screen Conveyors | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 1 | 3731 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 2 | 3732 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 3 | 3733 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 4 | 3734 | Train 4 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 5 | 3735 | Train 5 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 6 | 3736 | Train 6 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 0 | 3740 | Screens | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 1 | 3741 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 2 | 3742 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 3 | 3743 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 4 | 3744 | Train 4 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 5 | 3745 | Train 5 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 6 | 3746 | Train 6 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 0 | 3750 | Screen Oversize | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 1 | 3751 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 2 | 3752 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 3 | 3753 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 4 | 3754 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 5 | 3755 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 7 | 9 | 0 | 3790 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 7 | 9 | 7 | 3797 | Dust Collection | Fluor | Fluor | Fluor | Fluor
3 | 7 | 9 | 8 | 3798 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 7 | 9 | 9 | 3799 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 8 | 0 | 0 | 3800 | HPGR Oversize | Fluor | Fluor | Fluor | Fluor
3 | 8 | 1 | 0 | 3810 | Surge Bin | Fluor | Fluor | Fluor | Fluor
3 | 8 | 2 | 0 | 3820 | Reclaim Feeder | Fluor | Fluor | Fluor | Fluor
3 | 8 | 3 | 0 | 3830 | Reclaim Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 0 | 3840 | Surge Bin Overflow | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 1 | 3841 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 2 | 3842 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 3 | 3843 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 4 | 3844 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 5 | 3845 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 8 | 5 | 0 | 3850 | Dead Stockpile | Fluor | Fluor | Fluor | Fluor
3 | 8 | 9 | 0 | 3890 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 8 | 9 | 8 | 3898 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 8 | 9 | 9 | 3899 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 0 | 0 | 0 | 4000 | Wet Plant | Fluor | Fluor | Fluor | Fluor
4 | 1 | 0 | 0 | 4100 | Grinding and Classification | Fluor | Fluor | Fluor | Fluor
4 | 1 | 1 | 0 | 4110 | Grinding | Fluor | Fluor | Fluor | Fluor
4 | 1 | 1 | 1 | 4111 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 1 | 2 | 4112 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 1 | 3 | 4113 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 3 | 0 | 4130 | Classification | Fluor | Fluor | Fluor | Fluor
4 | 1 | 3 | 1 | 4131 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 3 | 2 | 4132 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 3 | 3 | 4133 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 4 | 0 | 4140 | Flash Flotation (future) | Future | Future | Future | Future
4 | 1 | 5 | 0 | 4150 | Gravity Gold Recovery (future) | Future | Future | Future | Future
4 | 1 | 6 | 0 | 4160 | Gold Room (future) | Future | Future | Future | Future
4 | 1 | 7 | 0 | 4170 | Reagent Distribution | Fluor | Fluor | Fluor | Fluor
4 | 1 | 8 | 0 | 4180 | Media Handling | Fluor | Fluor | Fluor | Fluor
4 | 1 | 8 | 1 | 4181 | Ball Unloading | Fluor | Fluor | Fluor | Fluor
4 | 1 | 8 | 2 | 4182 | Ball Storage | Fluor | Fluor | Fluor | Fluor
4 | 1 | 8 | 3 | 4183 | Ball Conveying | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 0 | 4190 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 1 | 4191 | Grinding Train 1 Cooling Water | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 2 | 4192 | Grinding Train 2 Cooling Water | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 3 | 4193 | Grinding Train 3 Cooling Water | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 8 | 4198 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 9 | 4199 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 2 | 0 | 0 | 4200 | Copper Rougher Processing | Fluor | Fluor | Fluor | Fluor
4 | 2 | 1 | 0 | 4210 | Surge and Conditioning | Fluor | Fluor | Fluor | Fluor
4 | 2 | 1 | 1 | 4211 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 1 | 2 | 4212 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 1 | 3 | 4213 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 3 | 0 | 4230 | Flotation | Fluor | Fluor | Fluor | Fluor
4 | 2 | 3 | 1 | 4231 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 3 | 2 | 4232 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 3 | 3 | 4233 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 0 | 4240 | Concentrate Regrinding | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 1 | 4241 | Stage 1 Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 2 | 4242 | Stage 1 Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 3 | 4243 | Stage 1 Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 4 | 4244 | Stage 1 Train 4 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 5 | 4245 | Stage 2 Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 6 | 4246 | Stage 2 Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 7 | 4247 | Stage 2 Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 8 | 4248 | Stage 2 Train 4 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 5 | 0 | 4250 | Concentrate Regrind Media Handling | Fluor | Fluor | Fluor | Fluor
4 | 2 | 5 | 5 | 4255 | Stage 2 Header | Fluor | Fluor | Fluor | Fluor
4 | 2 | 5 | 6 | 4256 | Stage 2 Dewatering | Fluor | Fluor | Fluor | Fluor
4 | 2 | 5 | 7 | 4257 | Stage 2 Recirculation | Fluor | Fluor | Fluor | Fluor
4 | 2 | 6 | 0 | 4260 | Tailings Collection | Fluor | Fluor | Fluor | Fluor
4 | 2 | 6 | 1 | 4261 | Tank | Fluor | Fluor | Fluor | Fluor
4 | 2 | 6 | 2 | 4262 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 2 | 7 | 0 | 4270 | Reagent Distribution (not used) | Fluor | Fluor | Fluor | Fluor
4 | 2 | 8 | 0 | 4280 | Sampling and Analysis | Fluor | Fluor | Fluor | Fluor
4 | 2 | 8 | 1 | 4281 | On-Stream Analyser 1 | - | - | - | -
4 | 2 | 8 | 2 | 4282 | On-Stream Analyser 2 | - | - | - | -
4 | 2 | 8 | 3 | 4283 | Stage 1 Train 1/2 Mill Product | - | - | - | -
4 | 2 | 8 | 4 | 4284 | Stage 1 Train 3/4 Mill Product | - | - | - | -
4 | 2 | 8 | 5 | 4285 | Stage 2 Train 1/2 Cyclone Overflow | - | - | - | -
4 | 2 | 8 | 6 | 4286 | Stage 2 train 1/2 Cyclone Overflow | - | - | - | -
4 | 2 | 8 | 7 | 4287 | Stage 2 Train 1/2 Mill Product | - | - | - | -
4 | 2 | 8 | 8 | 4288 | Stage 2 Train 3/4 Mill Product | - | - | - | -
4 | 2 | 9 | 0 | 4290 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 2 | 9 | 8 | 4298 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 2 | 9 | 9 | 4299 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 3 | 0 | 0 | 4300 | Copper Cleaner Processing | Fluor | Fluor | Fluor | Fluor
4 | 3 | 2 | 0 | 4320 | Aeration | Fluor | Fluor | Fluor | Fluor
4 | 3 | 2 | 1 | 4321 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 2 | 2 | 4322 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 2 | 3 | 4323 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 3 | 0 | 4330 | Conditioning | Fluor | Fluor | Fluor | Fluor
4 | 3 | 3 | 1 | 4331 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 3 | 2 | 4332 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 3 | 3 | 4333 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 4 | 0 | 4340 | First Cleaner Flotation - Scalper Flotation | Fluor | Fluor | Fluor | Fluor
4 | 3 | 4 | 1 | 4341 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 4 | 2 | 4342 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 4 | 3 | 4343 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 5 | 0 | 4350 | Second Cleaner Flotation - Scavenger Conditioning and Flotation | Fluor | Fluor | Fluor | Fluor
4 | 3 | 5 | 1 | 4351 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 5 | 2 | 4352 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 5 | 3 | 4353 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 6 | 0 | 4360 | Third Cleaner Flotation - Recleaner Conditioning and Flotation | Fluor | Fluor | Fluor | Fluor
4 | 3 | 6 | 1 | 4361 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 6 | 2 | 4362 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 6 | 3 | 4363 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 8 | 0 | 4380 | Sampling and Analysis | Fluor | Fluor | Fluor | Fluor
4 | 3 | 8 | 1 | 4381 | On-Stream Analyser 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 8 | 2 | 4382 | On-Stream Analyser 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 8 | 3 | 4383 | On-Stream Analyser 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 9 | 0 | 4390 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 3 | 9 | 8 | 4398 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 3 | 9 | 9 | 4399 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 4 | 0 | 0 | 4400 | Coarse Particle Processing (future) | Future | Future | Future | Future
4 | 4 | 1 | 0 | 4410 | Feed Classification (future) | Future | Future | Future | Future
4 | 4 | 1 | 1 | 4411 | Train 1 (future) | Future | Future | Future | Future
4 | 4 | 1 | 2 | 4412 | Train 2 (future) | Future | Future | Future | Future
4 | 4 | 1 | 3 | 4413 | Train 3 (future) | Future | Future | Future | Future
4 | 4 | 2 | 0 | 4420 | Conditioning (future) | Future | Future | Future | Future
4 | 4 | 2 | 1 | 4421 | Train 1 (future) | Future | Future | Future | Future
4 | 4 | 2 | 2 | 4422 | Train 2 (future) | Future | Future | Future | Future
4 | 4 | 2 | 3 | 4423 | Train 3 (future) | Future | Future | Future | Future
4 | 4 | 3 | 0 | 4430 | Flotation (future) | Future | Future | Future | Future
4 | 4 | 3 | 1 | 4431 | Train 1 (future) | Future | Future | Future | Future
4 | 4 | 3 | 2 | 4432 | Train 2 (future) | Future | Future | Future | Future
4 | 4 | 3 | 3 | 4433 | Train 3 (future) | Future | Future | Future | Future
4 | 4 | 4 | 0 | 4440 | Concentrate Regrind (future) | Future | Future | Future | Future
4 | 4 | 4 | 1 | 4441 | Train 1 (future) | Future | Future | Future | Future
4 | 4 | 4 | 2 | 4442 | Train 2 (future) | Future | Future | Future | Future
4 | 4 | 4 | 3 | 4443 | Train 3 (future) | Future | Future | Future | Future
4 | 4 | 5 | 0 | 4450 | Regrind Media Handling (future) | Future | Future | Future | Future
4 | 4 | 8 | 0 | 4480 | Sampling and Analysis (future) | Future | Future | Future | Future
4 | 4 | 9 | 0 | 4490 | Facilities and Services (future) | Future | Future | Future | Future
4 | 4 | 9 | 8 | 4498 | Building or Structure (future) | Future | Future | Future | Future
4 | 4 | 9 | 9 | 4499 | Electrical (future) | Future | Future | Future | Future
4 | 5 | 0 | 0 | 4500 | Molybdenum Processing (future) | Future | Future | Future | Future
4 | 5 | 1 | 0 | 4510 | Bulk Concentrate Thickening (future) | Future | Future | Future | Future
4 | 5 | 2 | 0 | 4520 | Rougher Conditioning (future) | Future | Future | Future | Future
4 | 5 | 3 | 0 | 4530 | Rougher Flotation (future) | Future | Future | Future | Future
4 | 5 | 4 | 0 | 4540 | Cleaner Flotation (future) | Future | Future | Future | Future
4 | 5 | 8 | 0 | 4580 | Sampling and Analysis (future) | Future | Future | Future | Future
4 | 5 | 9 | 0 | 4590 | Common Facilities and Services (future) | Future | Future | Future | Future
4 | 6 | 0 | 0 | 4600 | Concentrate Handling | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 0 | 4610 | Copper Concentrate Thickening | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 1 | 4611 | Feed | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 2 | 4612 | Thickener | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 3 | 4613 | Overflow | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 4 | 4614 | Underflow | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 0 | 4620 | Copper Concentrate Filtration and Storage | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 1 | 4621 | Train 1 (filter 1) | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 2 | 4622 | Train 2 (filter 2) | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 3 | 4623 | Train 3 (filter 3) | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 4 | 4624 | Train 4 (filter 4) | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 5 | 4625 | Filtrate Transfer Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 6 | 4626 | Storage Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 7 | 4627 | Sampler Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 0 | 4630 | Copper Concentrate Reclaim and Loadout | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 1 | 4631 | Reclaim | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 2 | 4632 | Loadout Storage Reclaim Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 4 | 4634 | Product Sampler Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 6 | 4636 | Loadout Conveyor | - | - | - | -
4 | 6 | 5 | 0 | 4650 | Molybdenum Concentrate Thickening (future) | Future | Future | Future | Future
4 | 6 | 6 | 0 | 4660 | Molybdenum Concentrate Filtration and Storage (future) | Future | Future | Future | Future
4 | 6 | 7 | 0 | 4670 | Molybdenum Concentrate Bagging (future) | Future | Future | Future | Future
4 | 6 | 9 | 0 | 4690 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 6 | 9 | 7 | 4697 | Truck Wash | Fluor | Fluor | Fluor | Fluor
4 | 6 | 9 | 8 | 4698 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 6 | 9 | 9 | 4699 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 7 | 0 | 0 | 4700 | Tailings Handling | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 0 | 4710 | Rougher Thickening | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 1 | 4711 | Feed Distribution | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 2 | 4712 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 3 | 4713 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 4 | 4714 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 5 | 4715 | Overflow | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 6 | 4716 | Underflow | Fluor | Fluor | Fluor | Fluor
4 | 7 | 2 | 0 | 4720 | Rougher Disposal Pumping | Fluor | Fluor | Fluor | Fluor
4 | 7 | 2 | 1 | 4721 | Line 1 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 2 | 2 | 4722 | Line 2 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 2 | 3 | 4723 | Line 3 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 3 | 0 | 4730 | Filtration (future) | Future | Future | Future | Future
4 | 7 | 4 | 0 | 4740 | CPF Sands De-Watering (future) | Future | Future | Future | Future
4 | 7 | 4 | 1 | 4741 | Train 1 (future) | Future | Future | Future | Future
4 | 7 | 4 | 2 | 4742 | Train 2 (future) | Future | Future | Future | Future
4 | 7 | 4 | 3 | 4743 | Train 3 (future) | Future | Future | Future | Future
4 | 7 | 5 | 0 | 4750 | Cleaner Thickening | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 1 | 4751 | Feed Distribution | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 2 | 4752 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 6 | 4756 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 4 | 4754 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 5 | 4755 | Overflow | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 6 | 4756 | Underflow | Fluor | Fluor | Fluor | Fluor
4 | 7 | 6 | 0 | 4760 | Cleaner Disposal Pumping | Fluor | Fluor | Fluor | Fluor
4 | 7 | 6 | 1 | 4761 | Line 1 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 6 | 2 | 4762 | Line 2 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 7 | 0 | 4770 | Tailings Overland Conveying (future) | Future | Future | Future | Future
4 | 7 | 9 | 0 | 4790 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 7 | 9 | 8 | 4798 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 7 | 9 | 9 | 4799 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 8 | 0 | 0 | 4800 | Reagents | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 0 | 4810 | General | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 1 | 4811 | Exterior Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 2 | 4812 | Interior Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 3 | 4813 | Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 4 | 4814 | Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 5 | 4815 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 2 | 0 | 4820 | Collector | Fluor | Fluor | Fluor | Fluor
4 | 8 | 2 | 1 | 4821 | Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 2 | 2 | 4822 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 0 | 4830 | Promoter | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 1 | 4831 | Promoter 1 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 2 | 4832 | Promoter 1 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 3 | 4833 | Promoter 2 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 4 | 4834 | Promoter 2 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 5 | 4835 | Promoter 3 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 6 | 4836 | Promoter 3 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 0 | 4840 | Frother | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 1 | 4841 | Frother 1 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 2 | 4842 | Frother 1 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 3 | 4843 | Frother 2 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 4 | 4844 | Frother 2 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 0 | 4850 | SMBS | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 1 | 4851 | SMBS 1 Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 2 | 4852 | SMBS 1 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 3 | 4853 | SMBS 1 Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 4 | 4854 | SMBS 1 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 5 | 4855 | SMBS 2 Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 6 | 4856 | SMBS 2 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 7 | 4857 | SMBS 2 Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 8 | 4858 | SMBS 2 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 0 | 4860 | Flocculant | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 1 | 4861 | Flocculant 1 Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 2 | 4862 | Flocculant 1 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 3 | 4863 | Flocculant 1 Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 4 | 4864 | Flocculant 1 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 5 | 4865 | Flocculant 2 Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 6 | 4866 | Flocculant 2 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 7 | 4867 | Flocculant 2 Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 8 | 4868 | Flocculant 2 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 7 | 0 | 4870 | Spare Reagent Systems | Fluor | Fluor | Fluor | Fluor
4 | 8 | 7 | 1 | 4871 | Spare Reagent 1 | Fluor | Fluor | Fluor | Fluor
4 | 8 | 7 | 2 | 4872 | Spare Reagent 2 | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 0 | 4880 | Dosing | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 1 | 4881 | General | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 2 | 4882 | Collector | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 3 | 4883 | Promoter | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 4 | 4884 | Frother | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 5 | 4885 | SMBS | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 6 | 4886 | Flocculant | Fluor | Fluor | Fluor | Fluor
4 | 8 | 9 | 0 | 4890 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 8 | 9 | 8 | 4898 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 8 | 9 | 9 | 4899 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 9 | 0 | 0 | 4900 | Plant Services | Fluor | Fluor | Fluor | Fluor
4 | 9 | 1 | 0 | 4910 | Raw Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 1 | 1 | 4911 | Storage | Fluor | Fluor | Fluor | Fluor
4 | 9 | 1 | 2 | 4912 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 1 | 3 | 4913 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 2 | 0 | 4920 | Process Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 2 | 2 | 4922 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 2 | 3 | 4923 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 3 | 0 | 4930 | Gland Seal Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 3 | 1 | 4931 | Storage | Fluor | Fluor | Fluor | Fluor
4 | 9 | 3 | 2 | 4932 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 3 | 3 | 4933 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 4 | 0 | 4940 | Cooling Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 4 | 1 | 4941 | Storage | Fluor | Fluor | Fluor | Fluor
4 | 9 | 4 | 2 | 4942 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 4 | 3 | 4943 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 0 | 4950 | Treated Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 1 | 4951 | Plant | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 2 | 4952 | Storage | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 3 | 4953 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 4 | 4954 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 0 | 4960 | Plant Air | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 1 | 4961 | Processing Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 2 | 4962 | CPF Hydrofloat Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 3 | 4963 | CPF Tailings Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 4 | 4964 | Concentrate Filtration Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 5 | 4965 | Concentrate Drying Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 0 | 4970 | Instrument Air | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 1 | 4971 | Processing Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 2 | 4972 | CPF Hydrofloat Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 3 | 4973 | CPF Tailings Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 4 | 4974 | Concentrate Filtration Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 5 | 4975 | Concentrate Drying Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 0 | 4980 | Flotation Blower Air | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 1 | 4981 | Rougher Flotation | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 2 | 4982 | Cleaner Aeration Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 3 | 4983 | Cleaner Flotation | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 4 | 4984 | Cleaner Scavenger Flotation | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 5 | 4985 | SMBS Neutralisation | Fluor | Fluor | Fluor | Fluor
4 | 9 | 9 | 0 | 4990 | Nitrogen (future) | Future | Future | Future | Future
5 | 0 | 0 | 0 | 5000 | Tailings and Water Management | Fluor/KP | IPMT | IPMT/Fluor | IPMT/Fluor/RDMC
5 | 1 | 0 | 0 | 5100 | Tailings Management | KP/Fluor | IPMT | IPMT/Fluor | IMPT/Fluor
5 | 1 | 1 | 0 | 5110 | Rougher Dams | KP | IPMT | IPMT | RDMC/IPMT
5 | 1 | 1 | 1 | 5111 | Compartment 1 | KP | IPMT | IPMT | RDMC
5 | 1 | 1 | 2 | 5112 | Compartment 2 | KP | IPMT | IPMT | IPMT
5 | 1 | 1 | 3 | 5113 | Compartment 3 | KP | IPMT | IPMT | IPMT
5 | 1 | 1 | 5 | 5115 | Monitoring Wells | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 0 | 5120 | Cleaner Dams | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 1 | 5121 | Compartment 1 | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 2 | 5122 | Compartment 2 | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 3 | 5123 | Compartment 3 | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 5 | 5125 | Monitoring Wells | KP | IPMT | IPMT | IPMT
5 | 1 | 3 | 0 | 5130 | Seepage System and Return | Fluor | Fluor | Fluor | Fluor
5 | 1 | 3 | 1 | 5131 | Rougher Collection | Fluor | Fluor | Fluor | Fluor
5 | 1 | 3 | 2 | 5132 | Rougher Return | Fluor | Fluor | Fluor | Fluor
5 | 1 | 3 | 5 | 5135 | Cleaner Collection | Fluor | Fluor | Fluor | Fluor
5 | 1 | 3 | 6 | 5136 | Cleaner Return | Fluor | Fluor | Fluor | Fluor
5 | 1 | 4 | 0 | 5140 | Sand Deposition (future) | Future | Future | Future | Future
5 | 1 | 5 | 0 | 5150 | Transport and Deposition | Fluor/KP | Fluor/IPMT | Fluor/IPMT | Fluor/IPMT
5 | 1 | 5 | 1 | 5151 | Rougher Pipeline 1 | Fluor | Fluor | Fluor | Fluor
5 | 1 | 5 | 2 | 5152 | Rougher Pipeline 2 | Fluor | Fluor | Fluor | Fluor
5 | 1 | 5 | 3 | 5153 | Rougher Pipeline 3 | Fluor | Fluor | Fluor | Fluor
5 | 1 | 5 | 4 | 5154 | Rougher Deposition | KP | IMPT | IMPT | IPMT
5 | 1 | 5 | 5 | 5155 | Cleaner Transport | Fluor | Fluor | Fluor | Fluor
5 | 1 | 5 | 6 | 5156 | Cleaner Deposition | KP | IMPT | IMPT | IPMT
5 | 1 | 9 | 0 | 5190 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
5 | 1 | 9 | 8 | 5198 | Building or Structure | Fluor | Fluor | Fluor | Fluor
5 | 1 | 9 | 9 | 5199 | Electrical | Fluor | Fluor | Fluor | Fluor
5 | 2 | 0 | 0 | 5200 | Reclaim Water | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 0 | 5210 | Rougher TSF | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 1 | 5211 | Pontoons | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 2 | 5212 | Return Pumping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 3 | 5213 | Return Piping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 4 | 5214 | Transfer Pumping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 5 | 5215 | Transfer Piping | - | - | - | -
5 | 2 | 2 | 0 | 5220 | Cleaner TSF | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 1 | 5211 | Pontoons | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 2 | 5212 | Return Pumping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 3 | 5213 | Return Piping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 4 | 5214 | Transfer Pumping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 5 | 5215 | Transfer Piping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 9 | 0 | 5290 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
5 | 2 | 9 | 8 | 5298 | Building or Structure | Fluor | Fluor | Fluor | Fluor
5 | 2 | 9 | 9 | 5299 | Electrical | Fluor | Fluor | Fluor | Fluor
5 | 3 | 0 | 0 | 5300 | Water Management | Fluor/KP | Fluor/IPMT/RDMC | Fluor/IPMT/RDMC | Fluor/IPMT/RDMC
5 | 3 | 1 | 0 | 5310 | Surface Water Diversion | Fluor/KP | Fluor/IPMT | RDMC/Fluor/IPMT | RDMC/Fluor/IPMT
5 | 3 | 1 | 1 | 5311 | Mining | KP | IPMT | RDMC | RDMC
5 | 3 | 1 | 2 | 5312 | Dry Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 1 | 3 | 5313 | Wet Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 1 | 4 | 5314 | TSF | KP | IPMT | IPMT | IPMT
5 | 3 | 1 | 5 | 5315 | Infrastructure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 2 | 0 | 5320 | Surface Water Collection and Storage | Fluor/KP | Fluor/IPMT | Fluor/IMPT/ RDMC | Fluor/IPMT/RDMC
5 | 3 | 2 | 1 | 5321 | Mining | KP | IPMT | RDMC | RDMC
5 | 3 | 2 | 2 | 5322 | Dry Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 2 | 3 | 5323 | Wet Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 2 | 4 | 5324 | TSF | KP | IPMT | IPMT | IPMT
5 | 3 | 2 | 5 | 5325 | Infrastructure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 3 | 0 | 5330 | Surface Water Pumping and Distribution | Fluor | Fluor | Fluor | Fluor
5 | 3 | 3 | 1 | 5331 | Mining | KP | IPMT | RDMC | RDMC
5 | 3 | 3 | 2 | 5332 | Dry Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 3 | 3 | 5333 | Wet Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 3 | 4 | 5334 | TSF | KP | IPMT | IPMT | IPMT
5 | 3 | 3 | 5 | 5335 | Infrastructure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 4 | 0 | 5340 | Surface Water Sediment and Erosion Control | Fluor | Fluor | Fluor | Fluor
5 | 3 | 4 | 1 | 5341 | Mining | KP | IPMT | RDMC | RDMC
5 | 3 | 4 | 2 | 5342 | Dry Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 4 | 3 | 5343 | Wet Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 4 | 4 | 5344 | TSF | KP | IPMT | IPMT | IPMT
5 | 3 | 4 | 5 | 5345 | Infrastructure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 5 | 0 | 5350 | Process Water Dams | KP | IPMT | IPMT | IPMT
5 | 3 | 6 | 0 | 5360 | Raw Water Dams | KP | IPMT | IPMT | IPMT
5 | 3 | 7 | 0 | 5370 | Turkey Nests | RDMC | RDMC | RDMC | RDMC
5 | 3 | 8 | 0 | 5380 | Rejects Pond | KP | IPMT | IPMT | IPMT
5 | 3 | 8 | 1 | 5381 | Earthworks | KP | IPMT | IPMT | IPMT
5 | 3 | 8 | 2 | 5382 | Transfer Pumping | KP | IPMT | IPMT | IPMT
5 | 3 | 8 | 3 | 5383 | Transfer Piping | KP | IPMT | IPMT | IPMT
5 | 3 | 8 | 4 | 5384 | Sprayfield | KP | IPMT | IPMT | IPMT
5 | 3 | 9 | 0 | 5390 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
5 | 3 | 9 | 8 | 5398 | Building or Structure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 9 | 9 | 5399 | Electrical | Fluor | Fluor | Fluor | Fluor
5 | 4 | 0 | 0 | 5400 | Acid Rock Drainage Treatment | - | - | - | -
5 | 4 | 1 | 0 | 5410 | Dams | - | - | - | -
5 | 4 | 2 | 0 | 5420 | Pumps and Pipelines | - | - | - | -
5 | 4 | 3 | 0 | 5430 | Seepage Control | - | - | - | -
5 | 4 | 9 | 0 | 5490 | Common Facilities and Services | - | - | - | -
5 | 5 | 0 | 0 | 5500 | Effluent Treatment | Fluor | Fluor | Fluor | Fluor
5 | 5 | 1 | 0 | 5510 | Industrial | - | - | - | -
5 | 5 | 2 | 0 | 5520 | Plant Sewage | Fluor | Fluor | Fluor | Fluor
5 | 5 | 2 | 1 | 5521 | Collection | Fluor | Fluor | Fluor | Fluor
5 | 5 | 2 | 2 | 5522 | Pumping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 2 | 3 | 5523 | Piping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 0 | 5530 | Village Sewage | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 1 | 5531 | Collection | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 2 | 5532 | Pumping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 3 | 5533 | Plant 1 | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 4 | 5534 | Plant 2 | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 5 | 5535 | Treated Effluent Storage | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 6 | 5536 | Treated Effluent Pumping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 7 | 5537 | Treated Effluent Piping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 4 | 0 | 5540 | Agricultural | - | - | - | -
5 | 5 | 9 | 0 | 5590 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
5 | 5 | 9 | 8 | 5598 | Building or Structure | Fluor | Fluor | Fluor | Fluor
5 | 5 | 9 | 9 | 5599 | Electrical | Fluor | Fluor | Fluor | Fluor
5 | 6 | 0 | 0 | 5600 | Water Services | Fluor | Fluor | Fluor | Fluor
5 | 6 | 1 | 0 | 5610 | Firewater Storage | Fluor | Fluor | Fluor | Fluor
5 | 6 | 2 | 0 | 5620 | Firewater Pumping and Distribution | Fluor | Fluor | Fluor | Fluor
5 | 6 | 3 | 0 | 5630 | Potable Water Treatment | Fluor | Fluor | Fluor | Fluor
5 | 6 | 3 | 2 | 5632 | Plant 1 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 3 | 3 | 5633 | Plant 2 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 0 | 5640 | Potable Water Storage | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 1 | 5641 | Common | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 2 | 5642 | System 1 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 3 | 5643 | System 2 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 4 | 5644 | Plant | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 0 | 5650 | Potable Water Pumping and Distribution | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 1 | 5651 | Common | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 2 | 5652 | System 1 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 3 | 5653 | System 2 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 4 | 5654 | Plant | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 5 | 5655 | Safety Shower | Fluor | Fluor | Fluor | Fluor
6 | 0 | 0 | 0 | 6000 | Internal Infrastructure | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 0 | 0 | 6100 | On-Site Infrastructure | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 1 | 0 | 6110 | Site Preparation, Earthworks and Fencing | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 1 | 3 | 6113 | Site Security Fencing | RDMC | RDMC | RDMC | RDMC
6 | 1 | 1 | 4 | 6114 | Bulk Earthworks | Fluor | Fluor | Fluor | Fluor
6 | 1 | 1 | 5 | 6115 | Detailed Earthworks | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 0 | 6120 | Roads and Platforms | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 2 | 1 | 6121 | Processing Plant Roads | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 2 | 6122 | Crushing Plant Roads | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 3 | 6123 | Exploration Roads | RDMC | RDMC | RDMC | RDMC
6 | 1 | 2 | 4 | 6124 | Parking Areas and Hardstand Areas | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 5 | 6125 | Exploration Platforms | RDMC | RDMC | RDMC | RDMC
6 | 1 | 2 | 6 | 6126 | On-Site Helipad and Airstrip | RDMC | RDMC | RDMC | RDMC
6 | 1 | 2 | 8 | 6128 | Permanent Village Road | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 9 | 6129 | Mine Site Access Road | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 0 | 6130 | Non-Process Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 1 | 6131 | Fire, Ambulance, and Emergency Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 2 | 6132 | Security and Medical Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 3 | 6133 | Main Administration Building | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 4 | 6134 | Laboratories | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 5 | 6135 | Plant Warehouse and Maintenance Shop | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 6 | 6136 | Change House and Dry Building | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 7 | 6137 | Training Building and Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 8 | 6138 | Stores and Warehouse | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 9 | 6139 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 4 | 0 | 6140 | Mobile Equipment | RDMC | RDMC | RDMC | RDMC
6 | 1 | 4 | 1 | 6141 | Maintenance | RDMC | RDMC | RDMC | RDMC
6 | 1 | 4 | 2 | 6142 | General and Administration | RDMC | RDMC | RDMC | RDMC
6 | 1 | 5 | 0 | 6150 | Bulk Storage (NB Storage of Utilities) | Fluor/PPE | Fluor/PPE | Fluor/PPE | Fluor/PPE
6 | 1 | 5 | 5 | 6155 | Diesel | Fluor | Fluor | Fluor | Fluor
6 | 1 | 5 | 7 | 6157 | Reagents Receival and Storage | Fluor | Fluor | Fluor | Fluor
6 | 1 | 5 | 8 | 6158 | Container Receival and Storage | Fluor | Fluor | Fluor | Fluor
6 | 1 | 5 | 9 | 6159 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 6 | 0 | 6160 | Services and Utilities (NB Distribution of Utilities) | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 6 | 5 | 6165 | Environmental Monitoring | RDMC | RDMC | RDMC | RDMC
6 | 1 | 6 | 6 | 6166 | Compressed Air | Fluor | Fluor | Fluor | Fluor
6 | 1 | 6 | 8 | 6168 | Diesel Fuel Distribution and Refuelling | Fluor | Fluor | Fluor | Fluor
6 | 1 | 6 | 9 | 6169 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 7 | 0 | 6170 | Communications | Fluor | Fluor | Fluor | Fluor
6 | 1 | 7 | 1 | 6171 | Distributed Control System | Fluor | Fluor | Fluor | Fluor
6 | 1 | 7 | 2 | 6172 | Communications and Networks | Fluor | Fluor | Fluor | Fluor
6 | 1 | 7 | 9 | 6179 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 0 | 6180 | Village | Fluor/PPE | Fluor/PPE | Fluor/PPE | Fluor/PPE
6 | 1 | 8 | 1 | 6181 | Accommodation | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 2 | 6182 | Mess Hall and Food Storage | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 3 | 6183 | Leisure Amenities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 4 | 6184 | Laundry Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 5 | 6185 | Potable Water | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 6 | 6186 | Firewater | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 7 | 6187 | Support Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 8 | 6188 | Underground Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 9 | 6189 | Common Facilities and Services | Fluor/PPE | Fluor/PPE | Fluor/PPE | Fluor/PPE
6 | 1 | 9 | 0 | 6190 | Rail | Vec | Vec | Vec | Vec
6 | 2 | 0 | 0 | 6200 | On-Site Power Supply and Transmission | PPE/WAR | PPE/WAR | PPE/WAR | PPE/WAR
6 | 2 | 1 | 0 | 6210 | Power Stations | WAR | WAR | WAR | WAR
6 | 2 | 1 | 1 | 6211 | Administration and General Buildings | WAR | WAR | WAR | WAR
6 | 2 | 1 | 2 | 6212 | Power Station 1 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 3 | 6213 | HFO Storage Power Station 1 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 4 | 6214 | Truck Unloading and Pumping Power Station 1 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 5 | 6215 | Power Station 2 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 6 | 6216 | HFO Storage Power Station 2 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 7 | 6217 | Truck Unloading and Pumping Power Station 2 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 8 | 6218 | Rail Unloading | WAR | WAR | WAR | WAR
6 | 2 | 1 | 9 | 6219 | Common Facilities and Services | WAR | WAR | WAR | WAR
6 | 2 | 3 | 0 | 6230 | High Voltage (220 kV) Transmission Lines | PPE | PPE | PPE | PPE
6 | 2 | 3 | 1 | 6231 | Solar PV Substation to Power Station Substation | PPE | PPE | PPE | PPE
6 | 2 | 3 | 2 | 6232 | Power Station Substation to Plant Main Substation | PPE | PPE | PPE | PPE
6 | 2 | 3 | 3 | 6233 | NDTC (Pakistan Grid Operator) Power Supply (future) | PPE | PPE | PPE | PPE
6 | 2 | 4 | 0 | 6240 | High Voltage Substations | PPE | PPE | PPE | PPE
6 | 2 | 4 | 1 | 6241 | 33/220 kV Solar PV Substation | PPE | PPE | PPE | PPE
6 | 2 | 4 | 2 | 6242 | 33/220 kV Power Station Substation | PPE | PPE | PPE | PPE
6 | 2 | 4 | 3 | 6243 | 220/33 kV Plant Main Substation | PPE | PPE | PPE | PPE
6 | 2 | 5 | 0 | 6250 | Power Conditioning Equipment | PPE | PPE | PPE | PPE
6 | 2 | 5 | 1 | 6251 | Load Bank | PPE | PPE | PPE | PPE
6 | 2 | 5 | 2 | 6252 | Harmonic Filters 1 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 3 | 6253 | Synchronous Condenser 1 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 4 | 6254 | Battery Energy Storage System 1 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 5 | 6255 | Harmonic Filters 2 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 6 | 6256 | Synchronous Condenser 2 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 7 | 6257 | Battery Energy Storage System 2 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 0 | 6260 | Emergency Power Generation | PPE | PPE | PPE | PPE
6 | 2 | 6 | 1 | 6261 | Administration and General Buildings | PPE | PPE | PPE | PPE
6 | 2 | 6 | 2 | 6262 | Emergency Power Substation 1 and Control Room 1 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 3 | 6263 | 36 MVA Power Station 1 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 4 | 6264 | Bulk Diesel Storage 1 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 5 | 6265 | Truck Diesel Unloading and Power Station 1 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 6 | 6266 | Emergency Power Substation 2 and Control Room 2 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 7 | 6267 | 36 MVA Power Station 2 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 8 | 6268 | Bulk Diesel Storage 2 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 9 | 6269 | Truck Diesel Unloading and Power Station 2 | PPE | PPE | PPE | PPE
6 | 2 | 8 | 0 | 6280 | Medium Voltage (33 kV) Overhead Powerlines | PPE | PPE | PPE | PPE
6 | 2 | 8 | 1 | 6281 | Booster Pump Station | PPE | PPE | PPE | PPE
6 | 2 | 8 | 2 | 6282 | Borefields | PPE | PPE | PPE | PPE
6 | 2 | 8 | 3 | 6283 | Potable Water Treatment Plant | PPE | PPE | PPE | PPE
6 | 2 | 8 | 4 | 6284 | Sewage Treatment Plant | PPE | PPE | PPE | PPE
6 | 2 | 8 | 5 | 6285 | Village | PPE | PPE | PPE | PPE
6 | 2 | 8 | 6 | 6286 | Mining Open Pit | PPE | PPE | PPE | PPE
6 | 2 | 8 | 7 | 6287 | Primary Crushing | PPE | PPE | PPE | PPE
6 | 2 | 8 | 8 | 6288 | Tailings Storage Facility | PPE | PPE | PPE | PPE
6 | 2 | 8 | 9 | 6289 | Rail Offloading Facility | PPE | PPE | PPE | PPE
6 | 2 | 9 | 0 | 6290 | Renewable Energy | PPE | PPE | PPE | PPE
6 | 2 | 9 | 1 | 6291 | Administration and General Buildings | PPE | PPE | PPE | PPE
6 | 2 | 9 | 2 | 6292 | 11/33 kV Solar PV Substation 1 and Control Room 1 | PPE | PPE | PPE | PPE
6 | 2 | 9 | 3 | 6293 | Power Station 1 Photovoltaic Array, Inverters, and Transformers | PPE | PPE | PPE | PPE
6 | 2 | 9 | 4 | 6294 | 11/33 kV Solar PV Substation 2 and Control Room 2 (future) | Future | Future | Future | Future
6 | 2 | 9 | 5 | 6295 | Power Station 2 Photovoltaic Array, Inverters, and Transformers (future) | Future | Future | Future | Future
6 | 3 | 0 | 0 | 6300 | On-Site Rail | - | - | - | -
6 | 3 | 1 | 0 | 6310 | Site Preparation | - | - | - | -
6 | 3 | 1 | 1 | 6311 | Embankment & Cuttings | - | - | - | -
6 | 3 | 1 | 2 | 6312 | Drainage & Culverts | - | - | - | -
6 | 3 | 1 | 3 | 6313 | Site Security Fencing | - | - | - | -
6 | 3 | 1 | 4 | 6314 | Bulk Site Earthworks | - | - | - | -
6 | 3 | 1 | 5 | 6315 | Detailed Site Earthworks | - | - | - | -
6 | 3 | 1 | 6 | 6316 | Roads | - | - | - | -
6 | 3 | 1 | 7 | 6317 | Signaling | - | - | - | -
6 | 3 | 2 | 0 | 6320 | Site Utilities and Services | - | - | - | -
6 | 3 | 2 | 2 | 6322 | Fire Water Storage | - | - | - | -
6 | 3 | 2 | 3 | 6323 | Fire Water Pump House & Reticulation | - | - | - | -
6 | 3 | 2 | 4 | 6324 | Fuel Storage | - | - | - | -
6 | 3 | 2 | 5 | 6325 | Potable Water System | - | - | - | -
6 | 3 | 2 | 6 | 6326 | Sewage Collection & Distribution | - | - | - | -
6 | 3 | 2 | 7 | 6327 | Waste Sorting Facility | - | - | - | -
6 | 3 | 4 | 0 | 6340 | Rail Facilities | - | - | - | -
6 | 3 | 4 | 1 | 6341 | Incoming Train Covered Inspection Shed | - | - | - | -
6 | 3 | 4 | 2 | 6342 | Operation Staff Building | - | - | - | -
6 | 3 | 4 | 3 | 6343 | CuCon Filling Point | - | - | - | -
6 | 3 | 4 | 4 | 6344 | In-Motion Weighing Bridge + Office | - | - | - | -
6 | 3 | 4 | 5 | 6345 | Washing Station | - | - | - | -
6 | 3 | 4 | 6 | 6346 | Wagons and Locomotives Running Shed and Refueling Station | - | - | - | -
6 | 3 | 4 | 7 | 6347 | Rotainers and Containers Handling and Repairing Platform | - | - | - | -
6 | 3 | 6 | 0 | 6360 | Comms, IT and Controls | - | - | - | -
6 | 3 | 6 | 1 | 6361 | Telecommunications | - | - | - | -
6 | 3 | 6 | 2 | 6362 | CCTV System | - | - | - | -
6 | 3 | 6 | 3 | 6363 | IT and Systems | - | - | - | -
6 | 3 | 6 | 4 | 6364 | Control System | - | - | - | -
6 | 3 | 9 | 0 | 6390 | Rail Electrical | - | - | - | -
6 | 3 | 9 | 1 | 6391 | Sub-Station | - | - | - | -
6 | 3 | 9 | 2 | 6392 | Site Wide Area Lighting | - | - | - | -
7 | 0 | 0 | 0 | 7000 | External Infrastructure | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW
7 | 1 | 0 | 0 | 7100 | Off-Site Infrastructure | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW
7 | 1 | 1 | 0 | 7110 | Off-Site Roads / Water Diversions | Fluor | Fluor | Fluor | Fluor
7 | 1 | 1 | 1 | 7111 | Site Access Road (45km) | Fluor | Fluor | Fluor | Fluor
7 | 1 | 2 | 0 | 7120 | Off-Site Facilities | RDMC/Fluor/Vec | RDMC/Fluor/Vec | RDMC/Fluor/Vec | RDMC/Fluor/Vec
7 | 1 | 2 | 1 | 7121 | Off-Site Permanent Buildings (Not Accomodation) | - | - | - | -
7 | 1 | 2 | 2 | 7122 | Off-Site Railways | - | - | - | -
7 | 1 | 2 | 3 | 7123 | Off-Site Accommodation | RDMC | RDMC | RDMC | RDMC
7 | 1 | 2 | 4 | 7124 | Off-Site Solid Waste Storage | Fluor | Fluor | Fluor | Fluor
7 | 1 | 2 | 5 | 7125 | Off-Site Hazardous Waste Storage | Fluor | Fluor | Fluor | Fluor
7 | 1 | 2 | 6 | 7126 | Site Bulk Road & Bulk Rail Loading | Vec | Vec | Vec | Vec
7 | 1 | 2 | 7 | 7127 | Port Qasim Bulk Road & Bulk Rail Unloading | - | - | - | -
7 | 1 | 3 | 0 | 7130 | Off-Site Mobile Maintenance Equipment | RDMC | RDMC | RDMC | RDMC
7 | 1 | 4 | 0 | 7140 | Off-Site Utilities Pipelines & Bulk Storage (exclude water) | Vecturis/PRDW | Vecturis/PRDW | Vecturis/PRDW | Vecturis/PRDW
7 | 1 | 4 | 2 | 7142 | Off-Site Fuel Pipeline | - | - | - | -
7 | 1 | 4 | 3 | 7143 | Off-Site Concentrate Pipeline | Future | Future | Future | Future
7 | 1 | 4 | 5 | 7145 | Off-Site Fuel Bulk Storage | Vecturis/PR DW | Vecturis/PR DW | Vecturis/PR DW | Vecturis/PR DW
7 | 1 | 4 | 6 | 7146 | Off-Site Concentrate Bulk Storage | PRDW | PRDW | PRDW | PRDW
7 | 1 | 4 | 7 | 7147 | Off-Site Effluent Utilities | Vecturis/PR DW | Vecturis/PR DW | Vecturis/PR DW | Vecturis/PR DW
7 | 1 | 4 | 9 | 7149 | Natural Gas Pipeline & Associated Equipment (K&T) | - | - | - | -
7 | 1 | 6 | 0 | 7160 | Off-Site Airport Facilities | - | - | - | -
7 | 1 | 6 | 1 | 7161 | Airport Runways | - | - | - | -
7 | 1 | 6 | 2 | 7162 | Airport Taxiways | - | - | - | -
7 | 1 | 6 | 3 | 7163 | Airport Aprons | - | - | - | -
7 | 1 | 6 | 4 | 7164 | Airport Passenger Terminal Buildings | - | - | - | -
7 | 1 | 6 | 5 | 7165 | Airport Freight Handling Facilities | - | - | - | -
7 | 1 | 6 | 9 | 7169 | Airport Facilities & Services | - | - | - | -
7 | 1 | 7 | 0 | 7170 | Off-Site Water Pipelines & Bulk Storage | Fluor | Fluor | Fluor | Fluor
7 | 1 | 7 | 1 | 7171 | Off-Site Desalinated Water Pipeline | Future | Future | Future | Future
7 | 1 | 7 | 4 | 7174 | Off-Site Water Bulk Storage
7 | 1 | 7 | 5 | 7175 | Off-Site Hamun-i-Mashkel (HIM) Bore Field | Future | Future | Future | Future
7 | 1 | 7 | 6 | 7176 | Off-Site Borehole Fieldwater Pipeline - Hamun-i-Mashkel (HIM) | Future | Future | Future | Future
7 | 1 | 7 | 7 | 7177 | Off-Site Fan Sediments Bore Field | Fluor | Fluor | Fluor | Fluor
7 | 1 | 7 | 8 | 7178 | Off-Site Borehole Fieldwater Pipeline - Fan Sediments Main Line | Fluor | Fluor | Fluor | Fluor
7 | 1 | 7 | 9 | 7179 | Off-Site Borehole Fieldwater Pipeline - Fan Sediments Construction Line | RDMC | RDMC | Fluor | Fluor
7 | 1 | 8 | 0 | 7180 | Off-Site Services/Utilities | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 1 | 7181 | Off-Site Fresh Water Distribution | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 2 | 7182 | Off-Site Potable Water Distribution | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 3 | 7183 | Off-Site Acid Rock Drainage (ARD) Water Distribution
7 | 1 | 8 | 4 | 7184 | Off-Site Fire Water Distribution | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 5 | 7185 | Off-Site Environmental Monitoring | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 6 | 7186 | Off-Site Communications | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 7 | 7187 | Off-Site Effluent Utilities | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 8 | 7188 | Off-Site Other Utilities (Compressed Air & Propane, etc.) | RDMC | RDMC | RDMC | RDMC
7 | 1 | 9 | 0 | 7190 | Off-Site Power Supply & Transmission
7 | 1 | 9 | 1 | 7191 | Switchyard
7 | 1 | 9 | 2 | 7192 | Off-Site Transmission
7 | 1 | 9 | 3 | 7193 | Main Substation
7 | 1 | 9 | 4 | 7194 | Power Generation
7 | 1 | 9 | 9 | 7199 | Off-Site Power Facilities & Services
7 | 2 | 0 | 0 | 7200 | Off-Site Port (Qasim & Gwadar) - (Not in Scope) | - | - | - | -
7 | 2 | 1 | 0 | 7210 | Port Concentrate Handling | - | - | - | -
7 | 2 | 1 | 1 | 7211 | Port Copper Concentrate Thickening | - | - | - | -
7 | 2 | 1 | 2 | 7212 | Port Concentrate Filtration | - | - | - | -
7 | 2 | 1 | 3 | 7213 | Port Concentrate Conveyor & Handling | - | - | - | -
7 | 2 | 1 | 4 | 7214 | Port Concentrate Stacking Conveyor | - | - | - | -
7 | 2 | 1 | 5 | 7215 | Port Concentrate Storage | - | - | - | -
7 | 2 | 1 | 6 | 7216 | Port Concentrate Emergencg Dump Pond | - | - | - | -
7 | 2 | 1 | 7 | 7217 | Process Water Treatment | - | - | - | -
7 | 2 | 1 | 8 | 7218 | Sampling Plant | - | - | - | -
7 | 2 | 1 | 9 | 7219 | Utilities & Services | - | - | - | -
7 | 2 | 2 | 0 | 7220 | Port Site Utilities & Services | - | - | - | -
7 | 2 | 2 | 1 | 7221 | Reagents Handling Facility | - | - | - | -
7 | 2 | 2 | 2 | 7222 | Utilities Services For Port Conveying Onshore | - | - | - | -
7 | 2 | 2 | 3 | 7223 | Fuel offloading & Refuelling | - | - | - | -
7 | 2 | 2 | 4 | 7224 | Fuel Storage & Dispensing | - | - | - | -
7 | 2 | 2 | 5 | 7225 | Fuel Pipeline | - | - | - | -
7 | 2 | 2 | 6 | 7226 | Potable Water System | - | - | - | -
7 | 2 | 2 | 7 | 7227 | Sewage Collection & Treatment | - | - | - | -
7 | 2 | 2 | 8 | 7228 | Waste Sorting Facility | - | - | - | -
7 | 2 | 2 | 9 | 7229 | Fresh & Fire Water System | - | - | - | -
7 | 2 | 3 | 0 | 7230 | Port Facilities | - | - | - | -
7 | 2 | 3 | 1 | 7231 | Port Gwadar Gatehouse | - | - | - | -
7 | 2 | 3 | 2 | 7232 | Port Gwadar Maintenance Shop | - | - | - | -
7 | 2 | 3 | 3 | 7233 | Port Gwadar Security Building | - | - | - | -
7 | 2 | 3 | 4 | 7234 | Port Gwadar Electrical Switchrooms | - | - | - | -
7 | 2 | 3 | 5 | 7235 | Guardhouse & Security Gate | - | - | - | -
7 | 2 | 3 | 6 | 7236 | Mobile Equipment | - | - | - | -
7 | 2 | 3 | 9 | 7239 | Utilities & Services | - | - | - | -
7 | 2 | 4 | 0 | 7240 | Port Earthworks & Drainage | - | - | - | -
7 | 2 | 4 | 1 | 7241 | Bulk Site Earthworks | - | - | - | -
7 | 2 | 4 | 2 | 7242 | Detailed Site Earthworks | - | - | - | -
7 | 2 | 4 | 3 | 7243 | Site Drainage & Culverts | - | - | - | -
7 | 2 | 4 | 4 | 7244 | In-Plant Roads | - | - | - | -
7 | 2 | 4 | 5 | 7245 | Carparks & Hardstand Areas | - | - | - | -
7 | 2 | 4 | 6 | 7246 | Site Improvements | - | - | - | -
7 | 2 | 4 | 7 | 7247 | Site Security Fencing | - | - | - | -
7 | 2 | 4 | 8 | 7248 | Underground Services | - | - | - | -
7 | 2 | 4 | 9 | 7249 | Utilities & Services | - | - | - | -
7 | 2 | 5 | 0 | 7250 | Concentrate Port offshore | - | - | - | -
7 | 2 | 5 | 1 | 7251 | Navigation & Dredging | - | - | - | -
7 | 2 | 5 | 2 | 7252 | Berth Structure | - | - | - | -
7 | 2 | 5 | 3 | 7253 | Shiploading | - | - | - | -
7 | 2 | 5 | 4 | 7254 | Marine Services | - | - | - | -
7 | 2 | 5 | 5 | 7255 | Coastal Structures | - | - | - | -
7 | 2 | 5 | 6 | 7256 | Navigation Aids | - | - | - | -
7 | 2 | 5 | 7 | 7257 | Mooring Systems | - | - | - | -
7 | 2 | 5 | 9 | 7259 | Utilities & Services | - | - | - | -
7 | 2 | 6 | 0 | 7260 | LNG Import Terminal | - | - | - | -
7 | 2 | 6 | 1 | 7261 | Navigation & Dredging | - | - | - | -
7 | 2 | 6 | 2 | 7262 | Berth Structure | - | - | - | -
7 | 2 | 6 | 3 | 7263 | Unloading System | - | - | - | -
7 | 2 | 6 | 4 | 7264 | Marine Services | - | - | - | -
7 | 2 | 6 | 5 | 7265 | Coastal Structures | - | - | - | -
7 | 2 | 6 | 6 | 7266 | Navigation Aids | - | - | - | -
7 | 2 | 6 | 7 | 7267 | Mooring Systems | - | - | - | -
7 | 2 | 6 | 9 | 7269 | Utilities & Services | - | - | - | -
7 | 2 | 8 | 0 | 7280 | SWRO Plant | - | - | - | -
7 | 2 | 8 | 1 | 7281 | Intake System | - | - | - | -
7 | 2 | 8 | 2 | 7282 | Ro Plant | - | - | - | -
7 | 2 | 8 | 3 | 7283 | Brine Discharge System | - | - | - | -
7 | 2 | 8 | 4 | 7284 | Coastal Structures | - | - | - | -
7 | 2 | 8 | 5 | 7285 | Bulk Earthworks | - | - | - | -
7 | 2 | 8 | 6 | 7286 | Roads & Paving | - | - | - | -
7 | 2 | 8 | 9 | 7289 | Utilities & Services | - | - | - | -
7 | 3 | 0 | 0 | 7300 | Off-Site Port Qasim - PIBT | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 0 | 7310 | Port Earthworks & Drainage | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 1 | 7311 | Bulk Site Earthworks | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 3 | 7313 | Site Drainage & Culverts | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 4 | 7314 | In-Plant Roads | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 5 | 7315 | Carparks & Hardstand Areas | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 6 | 7316 | Site and Soil Improvements | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 7 | 7317 | Site Security Fencing | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 8 | 7318 | Underground Services | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 0 | 7320 | Port Site Utilities & Services | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 1 | 7321 | Stormwater Piping | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 2 | 7322 | Fire Water Storage | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 3 | 7323 | Fire Water Pump House & Reticulation | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 4 | 7324 | Fuel Storage & Dispensing | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 6 | 7326 | Potable Water System | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 7 | 7327 | Sewage Collection & Treatment | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 8 | 7328 | Waste Sorting Facility | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 9 | 7329 | Services Building | - | - | - | -
7 | 3 | 3 | 0 | 7330 | Port Facilities | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 1 | 7331 | Port Qasim PIBT Gatehouse | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 2 | 7332 | Port Qasim PIBT Workshop & Engineering Offices | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 3 | 7333 | Port Qasim PIBT Security Building | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 4 | 7334 | Port Qasim PIBT Weighbridge | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 5 | 7335 | Port Qasim PIBT Security & Weighbridge Office | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 6 | 7336 | Port Qasim PIBT Administration Building | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 7 | 7337 | Port Qasim PIBT Control Room | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 8 | 7338 | Port Qasim PIBT Sampling & Laboratory | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 9 | 7339 | Port Qasim PIBT Washdown Facility | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 0 | 7340 | Port Concentrate Handling | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 1 | 7341 | Truck Discharge Station | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 2 | 7342 | Port Concentrate Conveyor CV-101 & TR-101 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 3 | 7343 | Port Concentrate Conveyor CV-102 & TR-102 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 4 | 7344 | Port Concentrate Port Storage Shed | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 5 | 7345 | Port Concentrate Conveyor CV-103 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 6 | 7346 | Port Concentrate Conveyor CV-104 & TR-103 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 7 | 7347 | Port Concentrate Conveyor CV-105 & TR-104 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 8 | 7348 | PIBT Port Handling Upgrade | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 9 | 7349 | Conveyor Galleries & Structures | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 0 | 7350 | Port Concentrate Offshore | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 1 | 7351 | Navigation & Dredging | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 2 | 7352 | Berth Structure | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 3 | 7353 | Shiploading | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 4 | 7354 | Marine Services | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 5 | 7355 | Coastal Structures | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 6 | 7356 | Navigation Aids | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 7 | 7357 | Mooring Systems | PRDW | PRDW | PRDW | PRDW
7 | 3 | 6 | 0 | 7360 | Port Comms, IT and Controls | PRDW | PRDW | PRDW | PRDW
7 | 3 | 6 | 1 | 7361 | CCTV and Security System | PRDW | PRDW | PRDW | PRDW
7 | 3 | 6 | 2 | 7362 | Port Handling Control System | PRDW | PRDW | PRDW | PRDW
7 | 3 | 6 | 3 | 7363 | IT | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 0 | 7390 | Port Electrical | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 1 | 7391 | Sub Station 1 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 2 | 7392 | Sub Station 2 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 3 | 7393 | Sub Station 3 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 4 | 7394 | PIBT Karachi Electric Substation | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 5 | 7395 | Site Wide Area Lighting | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 6 | 7396 | HV Reticulation | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 7 | 7397 | PIBT Port Generator | - | - | - | -
7 | 4 | 0 | 0 | 7400 | Off-Site Rail Facilities
7 | 4 | 1 | 0 | 7410 | Earthworks & Drainage
7 | 4 | 1 | 1 | 7411 | Bulk Site Earthworks
7 | 4 | 1 | 3 | 7413 | Site Drainage & Culverts
7 | 4 | 1 | 4 | 7414 | In-Plant Roads
7 | 4 | 1 | 5 | 7415 | Carparks & Hardstand Areas
7 | 4 | 1 | 6 | 7416 | Site and Soil Improvements
7 | 4 | 1 | 7 | 7417 | Site Security Fencing
7 | 4 | 1 | 8 | 7418 | Underground Services
7 | 4 | 2 | 0 | 7420 | Site Utilities and Services
7 | 4 | 2 | 1 | 7421 | Stormwater Piping
7 | 4 | 2 | 2 | 7422 | Fire Water Storage
7 | 4 | 2 | 3 | 7423 | Fire Water Pump House & Reticulation
7 | 4 | 2 | 4 | 7424 | Fuel Storage & Dispensing
7 | 4 | 2 | 5 | 7425 | Potable Water System
7 | 4 | 2 | 6 | 7426 | Sewage Collection & Treatment
7 | 4 | 2 | 7 | 7427 | Waste Sorting Facility
7 | 4 | 2 | 8 | 7428 | Telecommunications
7 | 4 | 2 | 9 | 7429 | Signaling
7 | 4 | 3 | 0 | 7430 | Infrastructure and Systems
7 | 4 | 3 | 1 | 7431 | Maintenance Yard Sidings
7 | 4 | 3 | 2 | 7432 | Operation Sidings
7 | 4 | 3 | 3 | 7433 | Telecommunications
7 | 4 | 3 | 4 | 7434 | CCTV System
7 | 4 | 3 | 5 | 7435 | IT and Systems
7 | 4 | 3 | 6 | 7436 | Control System
7 | 4 | 3 | 7 | 7437 | ML-3 Upgrade Works
7 | 4 | 3 | 8 | 7438 | Rolling Stock Maintenance Facility
7 | 4 | 3 | 9 | 7439 | Rolling Stock Refueling Station
7 | 4 | 4 | 0 | 7440 | Operational Facilities Port
7 | 4 | 4 | 1 | 7441 | Incoming Train Covered Inspection Shed
7 | 4 | 4 | 2 | 7442 | Operation Staff Building
7 | 4 | 4 | 3 | 7443 | In-Motion Weighing Bridge + Weight Bridge Office
7 | 4 | 4 | 4 | 7444 | Reagents FIBC Management Platform
7 | 4 | 4 | 5 | 7445 | Rotainers Management Platform
7 | 4 | 4 | 6 | 7446 | Tank Containers, Containers and IBC Management Platform
7 | 4 | 4 | 7 | 7447 | Canteen, Drivers’ Dorm and Training Rooms Building
7 | 4 | 4 | 8 | 7448 | CuCon Security + Weight Bridge Office
7 | 4 | 4 | 9 | 7449 | Truck Access Gate + Truck Weight Bridge
7 | 4 | 5 | 0 | 7450 | Maintenance Facilities Port
7 | 4 | 5 | 1 | 7451 | Shunting Locomotives Parking Garage
7 | 4 | 5 | 2 | 7452 | Locomotives & Wagons Wash Station
7 | 4 | 5 | 3 | 7453 | Wagons And Locomotives Paint Booth
7 | 4 | 5 | 4 | 7454 | Underfloor Wheel Lathe
7 | 4 | 5 | 5 | 7455 | Fuel Storage
7 | 4 | 5 | 6 | 7456 | Pre-inpection and Refuelling shed
7 | 4 | 5 | 7 | 7457 | Major Assemblies and Spare Parts Store
7 | 4 | 5 | 8 | 7458 | Main Maintenance Workshop
7 | 4 | 6 | 0 | 7460 | Spur Line & Main line
7 | 4 | 6 | 1 | 7461 | Permanent Way
7 | 4 | 6 | 2 | 7462 | Koh-i-Dalil Station
7 | 4 | 6 | 3 | 7463 | Reko Diq Terminal Station
7 | 4 | 6 | 4 | 7464 | Engineering Structures
7 | 4 | 6 | 5 | 7465 | Level Crossings
7 | 4 | 6 | 6 | 7466 | Electrical and Power
7 | 4 | 6 | 7 | 7467 | Signaling
7 | 4 | 6 | 8 | 7468 | Telecommunications
7 | 4 | 7 | 0 | 7470 | Temporary Loading Facility
7 | 4 | 7 | 1 | 7471 | Incoming Train Covered Inspection Shed
7 | 4 | 7 | 2 | 7472 | Operation Staff Building
7 | 4 | 7 | 3 | 7473 | In-motion Weighing Bridge + Office
7 | 4 | 7 | 4 | 7474 | Washing Station
7 | 4 | 7 | 5 | 7475 | Wagons and Locomotives Running Shed + Refueling Station
7 | 4 | 7 | 6 | 7476 | Rotainers and Containers Handling and Repairing Platform
7 | 4 | 7 | 7 | 7477 | Fencing and Gates
7 | 4 | 7 | 8 | 7478 | CCTV System
7 | 4 | 7 | 9 | 7479 | Power Supply and Distribution
7 | 4 | 8 | 0 | 7480 | Rolling Stock
7 | 4 | 8 | 1 | 7481 | Main Line ocomotives
7 | 4 | 8 | 2 | 7482 | Shunting Locomotives
7 | 4 | 8 | 3 | 7483 | Wagons
7 | 4 | 8 | 4 | 7484 | Rotainers
7 | 4 | 8 | 5 | 7485 | Tanktainers
7 | 4 | 8 | 6 | 7486 | Shipping Containers
7 | 4 | 8 | 7 | 7487 | Mobile Equipment
7 | 4 | 9 | 0 | 7490 | Electrical Port
7 | 4 | 9 | 1 | 7491 | Sub-station
7 | 4 | 9 | 2 | 7492 | Site Wide Area Lighting
8 | 0 | 0 | 0 | 8000 | Indirect Costs (Owner)
8 | 1 | 0 | 0 | 8100 | Owner's Costs (Common Construction Facilities and Services)
8 | 1 | 0 | 0 | 8100 | Project Costs
8 | 1 | 1 | 1 | 8111 | Project Management | - | - | - | -
8 | 1 | 1 | 2 | 8112 | Project Controls
8 | 1 | 1 | 3 | 8113 | Engineering and Procurement
8 | 1 | 1 | 4 | 8114 | Construction Management
8 | 1 | 1 | 5 | 8115 | Legal and Permitting
8 | 1 | 1 | 6 | 8116 | Public Relations
8 | 1 | 1 | 8 | 8118 | Community Engagement
8 | 1 | 1 | 9 | 8119 | General and Administration
8 | 1 | 2 | 0 | 8120 | Spares and Inventory | RDMC | RDMC | RDMC | RDMC
8 | 1 | 2 | 1 | 8121 | Spares
8 | 1 | 2 | 2 | 8122 | First Fills
8 | 1 | 3 | 0 | 8130 | Pre-Production Operations
8 | 1 | 3 | 1 | 8131 | Recruitment and Training of Operation and Maintenance Staff
8 | 1 | 3 | 2 | 8132 | Mobile Fleet Supporting Operations
8 | 1 | 3 | 3 | 8133 | Wet Commissioning
8 | 1 | 3 | 4 | 8134 | Post-Commissioning Modifications
8 | 1 | 3 | 5 | 8135 | Ramp-Up
8 | 1 | 3 | 6 | 8136 | Working Capital
8 | 1 | 4 | 0 | 8140 | Studies
8 | 1 | 5 | 0 | 8150 | Closure and Rehabilitation
8 | 1 | 6 | 0 | 8160 | Health Security and Safety
8 | 1 | 6 | 1 | 8161 | Clinic
8 | 1 | 6 | 2 | 8162 | Emergency Response
8 | 1 | 6 | 3 | 8163 | Security
8 | 1 | 6 | 4 | 8164 | Safety
8 | 1 | 7 | 0 | 8170 | Operational Readiness | - | - | - | -
8 | 1 | 8 | 0 | 8180 | Owner’s Management
8 | 1 | 8 | 1 | 8181 | Team
8 | 1 | 8 | 2 | 8182 | Nonmanual Labour Expenses
8 | 1 | 8 | 3 | 8183 | Home Office Expenses
8 | 1 | 8 | 4 | 8184 | Project Office Expenses
8 | 1 | 8 | 5 | 8185 | Site Office Expenses
8 | 8 | 1 | 0 | 8810 | Allowance (Early Works)
8 | 9 | 0 | 0 | 8900 | Contingency and Reserve
8 | 9 | 1 | 0 | 8910 | Cost Contingency
8 | 9 | 2 | 0 | 8920 | Schedule Contingency
8 | 9 | 3 | 0 | 8930 | Owner Cost Reserve
9 | 0 | 0 | 0 | 9000 | Indirect Costs (Other Parties)
9 | 1 | 0 | 0 | 9100 | Indirect Costs (Implementation Contractors, EPCM)
9 | 1 | 1 | 0 | 9110 | EPCM Cost | - | - | - | -
9 | 1 | 1 | 1 | 9111 | EP Cost | - | - | - | -
9 | 1 | 1 | 2 | 9112 | CM Cost | - | - | - | -
9 | 1 | 1 | 6 | 9116 | Vendor Field Representatives | - | - | - | -
9 | 1 | 1 | 9 | 9119 | Miscellaneous Engineering, Construction Management Services Costs | - | - | - | -
9 | 1 | 2 | 0 | 9120 | Temporary Facilities
9 | 1 | 2 | 1 | 9121 | Offices and Support Buildings
9 | 1 | 2 | 2 | 9122 | Warehouse and Yards
9 | 1 | 2 | 3 | 9123 | Shelters
9 | 1 | 2 | 4 | 9124 | Power Generation
9 | 1 | 2 | 5 | 9125 | Aggregate and Concrete
9 | 1 | 2 | 6 | 9126 | Water System
9 | 1 | 2 | 7 | 9127 | Fuel Stations
9 | 1 | 3 | 0 | 9130 | Temporary Services
9 | 1 | 3 | 1 | 9131 | Power
9 | 1 | 3 | 2 | 9132 | Maintenance and Cleanup
9 | 1 | 3 | 3 | 9133 | Personnel Transportation
9 | 1 | 3 | 4 | 9134 | Survey, Inspection, and Quality Control
9 | 1 | 3 | 5 | 9135 | Medical and Security
9 | 1 | 3 | 6 | 9136 | Heating
9 | 1 | 3 | 7 | 9137 | Fuel Supply
9 | 1 | 3 | 8 | 9138 | Water, Sewage, and Waste Disposal
9 | 1 | 3 | 9 | 9139 | Other Functions
9 | 1 | 4 | 0 | 9140 | Construction Equipment
9 | 1 | 4 | 1 | 9141 | Cranes
9 | 1 | 4 | 2 | 9142 | Vehicles
9 | 1 | 4 | 3 | 9143 | Mobile Equipment
9 | 1 | 4 | 4 | 9144 | Specialty Equipment
9 | 1 | 5 | 0 | 9150 | Environmental, Safety, and Health
9 | 1 | 5 | 1 | 9151 | Environmental
9 | 1 | 5 | 2 | 9152 | Safety
9 | 1 | 5 | 3 | 9153 | Health
9 | 1 | 6 | 0 | 9160 | Temporary Camp and Catering
9 | 1 | 6 | 1 | 9161 | Facilities
9 | 1 | 6 | 2 | 9162 | Catering
9 | 1 | 7 | 0 | 9170 | Freight / Traffic Warehouse Services and Logistics
9 | 1 | 7 | 1 | 9171 | Offshore Inland Freight
9 | 1 | 7 | 2 | 9172 | Marine Transportation
9 | 1 | 7 | 3 | 9173 | Onshore Inland Freight
9 | 1 | 7 | 4 | 9174 | Air Freight
9 | 1 | 7 | 5 | 9175 | Brokerage and Agent Fees
9 | 1 | 7 | 6 | 9176 | Import Duties
9 | 1 | 7 | 7 | 9177 | Warehousing Service
9 | 1 | 8 | 0 | 9180 | Commissioning
9 | 1 | 8 | 1 | 9181 | Owners Team
9 | 1 | 8 | 2 | 9182 | EPCM
9 | 1 | 8 | 3 | 9183 | Contractor Support

## Document and Drawing Type
Document and Drawing Types
Code | Document Type identifier | Description
GENERAL
AUT | Authority | - Permitting - Authority Implementation Plan - Authority Approval Packages - Regulatory Compliance - Environmental Permitting Compliance Requirements | AUT
BLT | Battery Limit | - Battery Limit Table | BLT
BOE | Basis of Estimate |  | BOE
BOS | Basis of Schedule |  | BOS
BOM | Bill of Material |  | BOM
CAL | Calculation |  | CAL
CHR | Chart | Organization Chart, Department Chart | CHR
CON | Contract | Any contract documentation | CON
DBD | Design Basis and Criteria | Design Criteria of the Project | DBD
DBK | Project Data Book | - Manufacturer Data Records | DBK
DDR | Document and Data Register | Master Data and Document Register for Supplier, Sub-Contractors | DDR
DEM | Demolition | Demolition Documents | DEM
DST | Datasheet |  | DST
DTA | Data (Digital Record) | Any data e.g. Survey Data | DTA
EQL | Equipment List | Specific list for equipments | EQL
EST | Estimates |  | EST
EXE | Execution | Can be used for Supplier Data - if not specify on the list | EXE
FRM | Forms |  | FRM
GDL | Guideline | - Guideline - Protocols | GDL
HAC | Hazard Classification | HAZOP, Hazard Analysis, Hazard identification | HAC
HMB | Heat Material Balance |  | HMB
IDX | Index | Technical and Non-technical | IDX
INS | Instructions | e.g. operation instructions, installation instructions | INS
IOM | Installation Operation and Maintenance Manual |  | IOM
ITP | Inspection Test Plan |  | ITP
IWP | Installation Work Package |  | IWP
LST | List/Matrix | Technical List: Valve List, Motor List, Instrument List, Spare Part List Non-Technical List: Distribution Matrix, Communication Matrix | LST
LTR | Letter |  | LTR
MAN | Manual |  | MAN
MDL | Models | - 3Models | MDL
MDR | Master Document Register | Document Register for Engineering - Documentation System Description - Document Filing Index - Transmittal Log - Gate Review Completed | MDR
MEM | Memorandum |  | MEM
MOM | Minutes of Meeting |  | MOM
MTO | Material Take Off |  | MTO
NAR | Narrative | - Process Control Narrative - Safeguarding Narrative | NAR
NCR | Non-Conformance Report |  | NCR
PCN | Project Change Notice |  | PCN
PDR | Procedure Deviation Request |  | PDR
PHL | Philosophy |  | PHL
DOCUMENTS |  |  | PLN
PLN | Plan | Used for non-technical plan i.e. Engineering Plan, Risk Plan, HSE Plan, Contract & Procurement Plan, HR plan, Project Execution Plan, Study Plan. etc. | PLC
PLC | Policy |  | PRC
PRC | Procedure | Document represents the procedure as prescribed by the various departments. The practices generally relate to the way in which work is to be done within or for the department and also the approved way in which the Company deals with Contractors, and other organizations | PRO
PRO | Procurement | Any procurement documentation | QAD
QAD | Quality Assurance Documents | Any quality assurance documents. Except Quality Management Plan can use PLN | QRA
QRA | Quantitive Risk Assessment | Structured approach to measuring and analyzing risk using numerical data | REQ
REQ | Request | - Travel request - Any requests | RFA
RFA | Recommendation for Award |  | RFI
RFI | Request for Information |  | RPT
RPT | Report | Technical Report: Geotechnical Investigation Report, , etc. Non-technical Report: Safety Monthly report | SCH
SCH | Schedule |  | SMP
SMP | Sample | - Interior Design and Furniture Sample - Finish Boards | SOP
SOP | Standard Operating Procedure |  | SOW
SOW | Scope of Work | Document outlines the extent of work to be performed by others. The SOW may include functional specifications when a functional specification is not written which typically occurs when the contents of a functional specification is minimal (2 pages). | SPC
SPC | Specification | Document represents the design and performance requirements for materials, parts, plant and equipment | SPL
SPL | Piping Specialty Item List |  | STD
STD | Standards | For any standards, codes, and regulation documents, are generally controlled | STR
STR | Strategy |  | SUM
SUM | Summary |  | TDM
TDM | Technical Decision Memorandum |  | TDN
TDN | Trends | Project Controls Trends | TMP
TMP | Templates |  | TOR
TOR | Terms of Reference |  | TRP
TRP | Test Report | - Concrete test report - Any test report - Soil test report - Non-Destruction Examination Test Report - Any Test Report | TVR
TVR | Turnover Dossier |  | VIS
VIS | Visualisation | - Drone Video | WLD
WLD | Welding | Any welding documents | BLT
DRAWINGS |  |  | CAE
PCK | Drawing Pack | - Pack consisting out of Cover Page, Index, GA, SCH and Parts List. | PCK
BLT | Battery Limit | - Battery Limit Drawings | CRV
CAE | Cause and Effect Drawing | - Cause and Effect Drawing, etc. | DEM
CRV | Curves |  | DIA
DEM | Demolition | Demolition Drawings | DID
DIA | Diagram | - Traffic Diagram - Schematic Diagram - Block Diagram | DTL
DID | Ducting and Instrument Diagram | HVAC Utility Piping Ducting and Instrumentation Diagram | EHT
DTL | Details | Any drawings details | ELE
EHT | Electrical Heat Tracing Isometric |  | FND
ELE | Elevation | Any drawings elevation | GAD
FND | Foundation Drawings | Any foundation drawings | ITD
GAD | General Arrangement | Any general arrangements drawings | ISO
ITD | Instrumentation Drawing |  | LAY
ISO | Isometrics | Drawing provides a three-dimensional layout of the equipment and piping. | MSD
LAY | Layout | Any drawings layout | PFD
MSD | Material Selection Diagram |  | PID
PFD | Process Flow Diagram |  | PLN
PID | Piping and Instrumentation Diagram |  | PPL
PLN | Plan | Any drawings plan | PSP
PPL | Plot Plan | Site Plot Plan | SEC
PSP | Piping Support | Drawing piping support. | SHP
SEC | Section | Any drawings section | SKT
SHP | Shop Drawings | Supplier Shop Drawings - Fabrication Drawings - Fabrication Steel Drawings - Erection Drawings - Plate Schedule - Spool Drawings - etc. | SLD
SKT | Sketch | Any drawings sketch | SSD
SLD | Single Line Diagram | Drawing provides a representation of an electrical system. | STD
SSD | Structural Steel Drawings | Engineering (Design) | TIE
STD | Standard Drawings | Drawing shows the materials, set out standard construction details and provide general design data.
TIE | Tie-In

## Discipline Codes
DISCIPLINE CODES |  | REVIEW OUTCOMES
Code | Discipline/Function Identifier | Codes
• Reviewed
A | Architectural | • A1 – Data Complete, No Comments, Do Not Resubmit
B | Project Controls | • B1 – Data Complete, With Comments, Proceed – Resubmit
C | Civil/Concrete | • B2 – Data Incomplete – Proceed – Resubmit
D | Supply Chain | • C1 – Data Incomplete – Hold Work – Resubmit
E | Electrical | • D1 – For Information Only – Do Not Resubmit
F | Process | • V1 – Cancelled
G | General | • S1 – Superseded
H | Health & Safety / Security | • Q1 – Quality Below Standard – Revise and Resubmit
I | Instrumentation
J | Environmental / Social Impact
L | Human Resources
M | Mechanical
N | Mining
P | Piping
Q | Quality & Control / HAZOP / HAZID / Risk
S | Structural
T | Geotechnical
U | Pipeline
W | Earthworks / Drainage / Fencing / Roads / Water