## Tracker (hidden)
Area/ WBS No. | Discipline | RDMC Document Number | Sum of % Complete
6200 | B | 6105AK124-6200-BBOS-0001 | 33.33%
| B Total |  | 33.33%
| E | 6105AK124-6200-EBOM-0001 | 0%
|  | 6105AK124-6200-EBOM-0002 | 0%
|  | 6105AK124-6200-EBOM-0003 | 0%
|  | 6105AK124-6200-EDST-0001 | 0%
|  | 6105AK124-6200-EDST-0016 | 0%
|  | 6105AK124-6200-ESOW-0001 | 0%
| E Total |  | 0%
6200 Total |  |  | 33.33%
6240 | E | 6105AK124-6240-EGAD-0001 | 0%
|  | 6105AK124-6240-EGAD-0002 | 0%
| E Total |  | 0%
6240 Total |  |  | 0%
6243 | E | 6105AK124-6243-EDST-0002 | 33.33%
|  | 6105AK124-6243-EDST-0003 | 33.33%
|  | 6105AK124-6243-EDST-0004 | 33.33%
|  | 6105AK124-6243-EDST-0005 | 33.33%
|  | 6105AK124-6243-ESLD-0001 | 33.33%
|  | 6105AK124-6243-ESOW-0001 | 33.33%
| E Total |  | 200%
| M | 6105AK124-6243-MGAD-0001 | 33.33%
|  | 6105AK124-6243-MGAD-0002 | 33.33%
|  | 6105AK124-6243-MGAD-0003 | 33.33%
|  | 6105AK124-6243-MGAD-0004 | 33.33%
|  | 6105AK124-6243-MGAD-0005 | 33.33%
|  | 6105AK124-6243-MGAD-0006 | 33.33%
|  | 6105AK124-6243-MGAD-0007 | 33.33%
|  | 6105AK124-6243-MGAD-0008 | 33.33%
|  | 6105AK124-6243-MGAD-0009 | 33.33%
|  | 6105AK124-6243-MGAD-0010 | 33.33%
|  | 6105AK124-6243-MGAD-0011 | 33.33%
|  | 6105AK124-6243-MGAD-0012 | 33.33%
|  | 6105AK124-6243-MGAD-0013 | 0%
|  | 6105AK124-6243-MGAD-0014 | 0%
|  | 6105AK124-6243-MGAD-0015 | 0%
| M Total |  | 400%
6243 Total |  |  | 599.9%
6250 | E | 6105AK124-6250-EDST-0001 | 33.33%
|  | 6105AK124-6250-EREQ-0001 | 33.33%
|  | 6105AK124-6250-ESLD-0001 | 33.33%
|  | 6105AK124-6250-ESOW-0001 | 33.33%
| E Total |  | 133.3%
6250 Total |  |  | 133.3%
6260 | E | 6105AK124-6260-EDST-0005 | 33.33%
|  | 6105AK124-6260-EDST-0008 | 0%
|  | 6105AK124-6260-EDST-0016 | 0%
|  | 6105AK124-6260-EDST-0017 | 0%
|  | 6105AK124-6260-EDTL-0001 | 33.33%
|  | 6105AK124-6260-EGAD-0002 | 33.33%
|  | 6105AK124-6260-EGAD-0005 | 0%
|  | 6105AK124-6260-EGAD-0006 | 0%
|  | 6105AK124-6260-EGAD-0007 | 0%
|  | 6105AK124-6260-EGAD-0008 | 0%
|  | 6105AK124-6260-EGAD-0009 | 0%
|  | 6105AK124-6260-EGAD-0010 | 0%
|  | 6105AK124-6260-EGAD-0011 | 0%
|  | 6105AK124-6260-EGAD-0012 | 0%
|  | 6105AK124-6260-EGAD-0013 | 0%
|  | 6105AK124-6260-EGAD-0014 | 0%
|  | 6105AK124-6260-ELAY-0001 | 0%
|  | 6105AK124-6260-ESEC-0001 | 33.33%
|  | 6105AK124-6260-ESLD-0001 | 33.33%
|  | 6105AK124-6260-ESLD-0002 | 0%
|  | 6105AK124-6260-ESLD-0003 | 0%
|  | 6105AK124-6260-ESLD-0004 | 0%
|  | 6105AK124-6260-ESOW-0003 | 0%
| E Total |  | 166.6%
| M | 6105AK124-6260-MGAD-0002 | 0%
|  | 6105AK124-6260-MGAD-0003 | 0%
|  | 6105AK124-6260-MGAD-0004 | 0%
|  | 6105AK124-6260-MGAD-0005 | 0%
|  | 6105AK124-6260-MGAD-0006 | 0%
|  | 6105AK124-6260-MGAD-0007 | 0%
|  | 6105AK124-6260-MGAD-0008 | 0%
|  | 6105AK124-6260-MGAD-0009 | 0%
| M Total |  | 0%
6260 Total |  |  | 166.6%
6262 | E | 6105AK124-6262-EDST-0001 | 0%
|  | 6105AK124-6262-EDST-0002 | 0%
|  | 6105AK124-6262-EDST-0003 | 0%
|  | 6105AK124-6262-EDST-0004 | 0%
|  | 6105AK124-6262-ESOW-0001 | 0%
| E Total |  | 0%
| M | 6105AK124-6262-MGAD-0001 | 0%
|  | 6105AK124-6262-MGAD-0002 | 0%
|  | 6105AK124-6262-MGAD-0003 | 0%
|  | 6105AK124-6262-MGAD-0004 | 0%
|  | 6105AK124-6262-MGAD-0005 | 0%
|  | 6105AK124-6262-MGAD-0006 | 0%
|  | 6105AK124-6262-MGAD-0007 | 0%
|  | 6105AK124-6262-MGAD-0008 | 0%
|  | 6105AK124-6262-MGAD-0009 | 0%
|  | 6105AK124-6262-MGAD-0010 | 0%
| M Total |  | 0%
6262 Total |  |  | 0%
6263 | E | 6105AK124-6263-EBOM-0001 | 0%
|  | 6105AK124-6263-EDST-0002 | 0%
|  | 6105AK124-6263-EDST-0003 | 0%
|  | 6105AK124-6263-EDST-0004 | 0%
|  | 6105AK124-6263-EDST-0005 | 0%
|  | 6105AK124-6263-ESOW-0001 | 0%
|  | 6105AK124-6263-ESOW-0002 | 0%
| E Total |  | 0%
6263 Total |  |  | 0%
6264 | E | 6105AK124-6264-EDST-0001 | 0%
|  | 6105AK124-6264-ESOW-0001 | 0%
| E Total |  | 0%
6264 Total |  |  | 0%
6280 | E | 6105AK124-6280-ESLD-0001 | 0%
| E Total |  | 0%
6280 Total |  |  | 0%
6286 | E | 6105AK124-6286-EDST-0001 | 0%
|  | 6105AK124-6286-EDST-0002 | 0%
|  | 6105AK124-6286-EDST-0003 | 0%
|  | 6105AK124-6286-EDST-0004 | 0%
|  | 6105AK124-6286-EDST-0005 | 0%
|  | 6105AK124-6286-EDTL-0001 | 0%
|  | 6105AK124-6286-EDTL-0002 | 0%
|  | 6105AK124-6286-EGAD-0001 | 0%
|  | 6105AK124-6286-ELAY-0001 | 0%
|  | 6105AK124-6286-ESLD-0001 | 0%
| E Total |  | 0%
| M | 6105AK124-6286-MGAD-0001 | 0%
|  | 6105AK124-6286-MGAD-0002 | 0%
|  | 6105AK124-6286-MGAD-0003 | 0%
|  | 6105AK124-6286-MGAD-0004 | 0%
|  | 6105AK124-6286-MGAD-0005 | 0%
|  | 6105AK124-6286-MGAD-0006 | 0%
|  | 6105AK124-6286-MGAD-0007 | 0%
|  | 6105AK124-6286-MGAD-0008 | 0%
|  | 6105AK124-6286-MGAD-0009 | 0%
|  | 6105AK124-6286-MGAD-0010 | 0%
|  | 6105AK124-6286-MGAD-0011 | 0%
|  | 6105AK124-6286-MGAD-0012 | 0%
|  | 6105AK124-6286-MGAD-0013 | 0%
|  | 6105AK124-6286-MGAD-0014 | 0%
|  | 6105AK124-6286-MGAD-0015 | 0%
| M Total |  | 0%
6286 Total |  |  | 0%
6292 | E | 6105AK124-6292-EDST-0001 | 0%
|  | 6105AK124-6292-EDST-0002 | 0%
|  | 6105AK124-6292-EDST-0003 | 0%
|  | 6105AK124-6292-EDST-0004 | 0%
|  | 6105AK124-6292-ESOW-0001 | 0%
| E Total |  | 0%
6292 Total |  |  | 0%
0000 | B | 6105AK124-0000-BPLN-0001 | 0%
| B Total |  | 0%
| G | 6105AK124-0000-GDDR-0001 | 0%
| G Total |  | 0%
0000 Total |  |  | 0%
0100 | E | 6105AK124-0100-EDST-0002 | 0%
|  | 6105AK124-0100-EDST-0003 | 0%
| E Total |  | 0%
| H | 6105AK124-0100-HDST-0001 | 0%
|  | 6105AK124-0100-HDST-0002 | 0%
|  | 6105AK124-0100-HFRM-0001 | 0%
|  | 6105AK124-0100-HFRM-0002 | 0%
|  | 6105AK124-0100-HFRM-0003 | 0%
|  | 6105AK124-0100-HFRM-0004 | 0%
|  | 6105AK124-0100-HFRM-0005 | 0%
|  | 6105AK124-0100-HFRM-0006 | 0%
|  | 6105AK124-0100-HFRM-0007 | 0%
|  | 6105AK124-0100-HFRM-0008 | 0%
|  | 6105AK124-0100-HFRM-0009 | 0%
|  | 6105AK124-0100-HFRM-0010 | 0%
|  | 6105AK124-0100-HFRM-0011 | 0%
|  | 6105AK124-0100-HFRM-0012 | 0%
|  | 6105AK124-0100-HFRM-0013 | 0%
|  | 6105AK124-0100-HFRM-0014 | 0%
|  | 6105AK124-0100-HFRM-0015 | 0%
|  | 6105AK124-0100-HFRM-0016 | 0%
|  | 6105AK124-0100-HFRM-0017 | 0%
|  | 6105AK124-0100-HFRM-0018 | 0%
|  | 6105AK124-0100-HFRM-0019 | 0%
|  | 6105AK124-0100-HFRM-0020 | 0%
|  | 6105AK124-0100-HFRM-0021 | 0%
|  | 6105AK124-0100-HFRM-0022 | 0%
|  | 6105AK124-0100-HFRM-0023 | 0%
|  | 6105AK124-0100-HFRM-0024 | 0%
|  | 6105AK124-0100-HFRM-0025 | 0%
|  | 6105AK124-0100-HFRM-0026 | 0%
|  | 6105AK124-0100-HFRM-0027 | 0%
|  | 6105AK124-0100-HFRM-0028 | 0%
|  | 6105AK124-0100-HFRM-0029 | 0%
|  | 6105AK124-0100-HFRM-0030 | 0%
|  | 6105AK124-0100-HGDL-0001 | 0%
|  | 6105AK124-0100-HGDL-0002 | 0%
|  | 6105AK124-0100-HGDL-0003 | 0%
|  | 6105AK124-0100-HGDL-0004 | 0%
|  | 6105AK124-0100-HGDL-0005 | 0%
|  | 6105AK124-0100-HLST-0001 | 0%
|  | 6105AK124-0100-HLST-0002 | 0%
|  | 6105AK124-0100-HLST-0003 | 0%
|  | 6105AK124-0100-HLST-0004 | 0%
|  | 6105AK124-0100-HLST-0005 | 0%
|  | 6105AK124-0100-HLST-0006 | 0%
|  | 6105AK124-0100-HLST-0007 | 0%
|  | 6105AK124-0100-HLST-0008 | 0%
|  | 6105AK124-0100-HLST-0009 | 0%
|  | 6105AK124-0100-HLST-0010 | 0%
|  | 6105AK124-0100-HLST-0011 | 0%
|  | 6105AK124-0100-HLST-0012 | 0%
|  | 6105AK124-0100-HLST-0013 | 0%
|  | 6105AK124-0100-HLST-0014 | 0%
|  | 6105AK124-0100-HLST-0015 | 0%
|  | 6105AK124-0100-HLST-0016 | 0%
|  | 6105AK124-0100-HLST-0017 | 0%
|  | 6105AK124-0100-HLST-0018 | 0%
|  | 6105AK124-0100-HLST-0019 | 0%
|  | 6105AK124-0100-HLST-0020 | 0%
|  | 6105AK124-0100-HLST-0021 | 0%
|  | 6105AK124-0100-HLST-0022 | 0%
|  | 6105AK124-0100-HLST-0023 | 0%
|  | 6105AK124-0100-HLST-0024 | 0%
|  | 6105AK124-0100-HLST-0025 | 0%
|  | 6105AK124-0100-HLST-0026 | 0%
|  | 6105AK124-0100-HLST-0027 | 0%
|  | 6105AK124-0100-HMAN-0001 | 0%
|  | 6105AK124-0100-HPLN-0001 | 0%
|  | 6105AK124-0100-HPLN-0002 | 0%
|  | 6105AK124-0100-HPLN-0003 | 0%
|  | 6105AK124-0100-HPLN-0004 | 0%
|  | 6105AK124-0100-HPLN-0005 | 0%
|  | 6105AK124-0100-HPLN-0006 | 0%
|  | 6105AK124-0100-HPLN-0007 | 0%
|  | 6105AK124-0100-HPLN-0008 | 0%
|  | 6105AK124-0100-HPLN-0009 | 0%
|  | 6105AK124-0100-HPLN-0010 | 0%
|  | 6105AK124-0100-HPLN-0011 | 0%
|  | 6105AK124-0100-HPLN-0012 | 0%
|  | 6105AK124-0100-HPRC-0001 | 0%
|  | 6105AK124-0100-HPRC-0002 | 0%
|  | 6105AK124-0100-HPRC-0003 | 0%
|  | 6105AK124-0100-HPRC-0004 | 0%
|  | 6105AK124-0100-HPRC-0005 | 0%
|  | 6105AK124-0100-HPRC-0006 | 0%
|  | 6105AK124-0100-HPRC-0007 | 0%
|  | 6105AK124-0100-HPRC-0008 | 0%
|  | 6105AK124-0100-HPRC-0009 | 0%
|  | 6105AK124-0100-HPRC-0010 | 0%
|  | 6105AK124-0100-HPRC-0011 | 0%
|  | 6105AK124-0100-HPRC-0012 | 0%
|  | 6105AK124-0100-HPRC-0013 | 0%
|  | 6105AK124-0100-HPRC-0014 | 0%
|  | 6105AK124-0100-HPRC-0015 | 0%
|  | 6105AK124-0100-HPRC-0016 | 0%
|  | 6105AK124-0100-HPRC-0017 | 0%
|  | 6105AK124-0100-HPRC-0018 | 0%
|  | 6105AK124-0100-HPRC-0019 | 0%
|  | 6105AK124-0100-HPRC-0020 | 0%
|  | 6105AK124-0100-HPRC-0021 | 0%
|  | 6105AK124-0100-HPRC-0022 | 0%
|  | 6105AK124-0100-HPRC-0023 | 0%
|  | 6105AK124-0100-HPRC-0024 | 0%
|  | 6105AK124-0100-HPRC-0025 | 0%
|  | 6105AK124-0100-HPRC-0026 | 0%
|  | 6105AK124-0100-HPRC-0027 | 0%
|  | 6105AK124-0100-HPRC-0028 | 0%
|  | 6105AK124-0100-HPRC-0029 | 0%
|  | 6105AK124-0100-HPRC-0030 | 0%
|  | 6105AK124-0100-HPRC-0031 | 0%
|  | 6105AK124-0100-HPRC-0032 | 0%
|  | 6105AK124-0100-HPRC-0033 | 0%
|  | 6105AK124-0100-HPRC-0034 | 0%
|  | 6105AK124-0100-HPRC-0035 | 0%
|  | 6105AK124-0100-HPRC-0036 | 0%
|  | 6105AK124-0100-HPRC-0037 | 0%
|  | 6105AK124-0100-HPRC-0038 | 0%
|  | 6105AK124-0100-HPRC-0039 | 0%
|  | 6105AK124-0100-HPRC-0040 | 0%
|  | 6105AK124-0100-HPRC-0041 | 0%
|  | 6105AK124-0100-HPRC-0042 | 0%
|  | 6105AK124-0100-HPRC-0043 | 0%
|  | 6105AK124-0100-HPRC-0044 | 0%
|  | 6105AK124-0100-HPRC-0045 | 0%
|  | 6105AK124-0100-HPRC-0046 | 0%
|  | 6105AK124-0100-HPRC-0047 | 0%
|  | 6105AK124-0100-HPRC-0048 | 0%
|  | 6105AK124-0100-HPRC-0049 | 0%
|  | 6105AK124-0100-HPRC-0050 | 0%
|  | 6105AK124-0100-HPRC-0051 | 0%
|  | 6105AK124-0100-HPRC-0052 | 0%
|  | 6105AK124-0100-HPRC-0053 | 0%
|  | 6105AK124-0100-HPRC-0054 | 0%
|  | 6105AK124-0100-HPRC-0055 | 0%
|  | 6105AK124-0100-HPRC-0056 | 0%
|  | 6105AK124-0100-HPRC-0057 | 0%
|  | 6105AK124-0100-HPRC-0058 | 0%
|  | 6105AK124-0100-HPRC-0059 | 0%
|  | 6105AK124-0100-HPRC-0060 | 0%
|  | 6105AK124-0100-HPRC-0061 | 0%
|  | 6105AK124-0100-HPRC-0062 | 0%
|  | 6105AK124-0100-HPRC-0063 | 0%
|  | 6105AK124-0100-HPRC-0064 | 0%
|  | 6105AK124-0100-HPRC-0065 | 0%
|  | 6105AK124-0100-HPRC-0066 | 0%
|  | 6105AK124-0100-HPRC-0067 | 0%
|  | 6105AK124-0100-HPRC-0068 | 0%
|  | 6105AK124-0100-HPRC-0069 | 0%
|  | 6105AK124-0100-HPRC-0070 | 0%
|  | 6105AK124-0100-HPRC-0071 | 0%
|  | 6105AK124-0100-HPRC-0072 | 0%
|  | 6105AK124-0100-HPRC-0073 | 0%
|  | 6105AK124-0100-HPRC-0074 | 0%
|  | 6105AK124-0100-HPRC-0075 | 0%
|  | 6105AK124-0100-HPRC-0076 | 0%
|  | 6105AK124-0100-HPRC-0077 | 0%
|  | 6105AK124-0100-HPRC-0078 | 0%
|  | 6105AK124-0100-HPRC-0079 | 0%
|  | 6105AK124-0100-HPRC-0080 | 0%
|  | 6105AK124-0100-HPRC-0081 | 0%
|  | 6105AK124-0100-HPRC-0082 | 0%
|  | 6105AK124-0100-HRPT-0001 | 0%
|  | 6105AK124-0100-HSCH-0001 | 0%
|  | 6105AK124-0100-HSTD-0001 | 0%
|  | 6105AK124-0100-HSUM-0001 | 0%
| H Total |  | 0%
0100 Total |  |  | 0%
Grand Total |  |  | 933.2%

## Register
REKO DIQ MINING PROJECT - K125 - Supplier Document & Drawing Register (SDDR)
Project Number | Package Number | Area/ WBS No. | Discipline | Document Type | Sequential Number | Revision | Document Number | Sht. # of # | Area / Facility | Major Description | Broad Type | Full Title | Due Date | IFR Transmittal Date | IFC/IFU Transmittal Date | PPE Doc Status | % Complete | As Built Required (Y/N) | Certified Final Required (Y/N) | Tag Number (if any) | Comments
6105A | K125 | 0000 | G | PLN | 0001 | A | 6105AK125-0000-GPLN-0001 |  | General | Project Management / Execution | Plan | General - Project Management / Execution - Plan | - | 2026-03-31 |  |  | 33%
6105A | K125 | 0000 | G | PLN | 0002 | A | 6105AK125-0000-GPLN-0002 |  | General | Project Procurement Management | Plan | General - Project Procurement Management - Plan | - | 2026-03-31 |  |  | 33%
6105A | K125 | 0000 | G | PLN | 0003 | A | 6105AK125-0000-GPLN-0003 |  | General | Project Quality Management | Plan | General - Project Quality Management - Plan | - | 2026-03-31 |  |  | 33%
6105A | K125 | 0000 | G | PLN | 0004 | A | 6105AK125-0000-GPLN-0004 |  | General | Project Risk Management | Plan | General - Project Risk Management - Plan | - | 2026-03-31 |  |  | 33%
6105A | K125 | 0000 | H | PLN | 0001 | A | 6105AK125-0000-HPLN-0001 |  | General | EHS | Plan | General - EHS - Plan | 2026-04-15 | 2026-04-17 |  |  | 33%
6105A | K125 | 0000 | G | PLN | 0005 | A | 6105AK125-0000-GPLN-0005 |  | General | Project Logistics Management | Plan | General - Project Logistics Management - Plan | - | 2026-05-15 |  |  | 33%
6105A | K125 | 0000 | G | PLN | 0006 | A | 6105AK125-0000-GPLN-0006 |  | General | Site Facilities | Plan | General - Site Facilities - Plan |  | 2026-04-29 |  |  | 33%
6105A | K125 | 0000 | G | RPT | 0001 | A | 6105AK125-0000-GRPT-0001 |  | General | Monthly Progress | Report | General - Monthly Progress - Report |  | 2026-04-28 |  |  | 33%
6105A | K125 | 0000 | G | DDR | 0002 | A | 6105AK125-0000-GDDR-0002 |  | General | Document Control | Document and Data Register | General - Document Control - Document and Data Register |  |  |  |  | 0%
6105A | K125 | 0000 | C | MAN | 0001 | A | 6105AK125-0000-CMAN-0001 |  | General | Civil Contractor | Mannual | General - Civil Contractor - Mannual |  |  |  |  | 0%
6105A | K125 | 0000 | E | MAN | 0001 | A | 6105AK125-0000-EMAN-0001 |  | General | ETC Contractor | Mannual | General - ETC Contractor - Mannual |  |  |  |  | 0%
6105A | K125 | 6242 | G | LAY | 0001 | 0 | 6105AK125-6242-GLAY-0001 | Sht. 1 of 1 | 33/220 kV Power Station Substation | Site Office Arrangement | Layout | 33/220 kV Power Station Substation - Site Office Arrangement - Layout | - | 2026-04-03 | 2026-05-19 | Approved | 100%
6105A | K125 | 6242 | E | SLD | 0001 | A | 6105AK125-6242-ESLD-0001 | Sht. 1 of 1 | 33/220 kV Power Station Substation | Overall | Single Line Diagram | 33/220 kV Power Station Substation - Overall - Single Line Diagram | 2026-02-04 | 2026-02-10 |  | Approved | 100% | 2026-06-08
6105A | K125 | 6242 | E | LAY | 0001 | A | 6105AK125-6242-ELAY-0001 |  | 33/220 kV Power Station Substation | Equipment | Layout | 33/220 kV Power Station Substation - Equipment - Layout | 2026-04-30 | 2026-02-13 |  | Reviewed | 33%
6105A | K125 | 6242 | E | LAY | 0002 | A | 6105AK125-6242-ELAY-0002 |  | 33/220 kV Power Station Substation | E-House | Layout | 33/220 kV Power Station Substation - E-House - Layout | 2026-06-11 |  |  |  | 0%
6105A | K125 | 6242 | E | LAY | 0003 | A | 6105AK125-6242-ELAY-0003 |  | 33/220 kV Power Station Substation | Foundation and Trench | Layout | 33/220 kV Power Station Substation - Foundation and Trench - Layout | 2026-06-17 |  |  |  | 0%
6105A | K125 | 6242 | E | LAY | 0004 | A | 6105AK125-6242-ELAY-0004 |  | 33/220 kV Power Station Substation | Cable Tray | Layout | 33/220 kV Power Station Substation - Cable Tray - Layout | 2026-07-29 |  |  |  | 0%
6105A | K125 | 6242 | E | LAY | 0005 | A | 6105AK125-6242-ELAY-0005 |  | 33/220 kV Power Station Substation | Buried Earthing | Layout | 33/220 kV Power Station Substation - Buried Earthing - Layout | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6242 | E | LAY | 0006 | A | 6105AK125-6242-ELAY-0006 |  | 33/220 kV Power Station Substation | Indoor Earthing | Layout | 33/220 kV Power Station Substation - Indoor Earthing - Layout | 2026-09-10 |  |  |  | 0%
6105A | K125 | 6242 | E | LAY | 0007 | A | 6105AK125-6242-ELAY-0007 |  | 33/220 kV Power Station Substation | Lightning Protection | Layout | 33/220 kV Power Station Substation - Lightning Protection - Layout | 2026-09-17 |  |  |  | 0%
6105A | K125 | 6242 | E | CAL | 0001 | A | 6105AK125-6242-ECAL-0001 |  | 33/220 kV Power Station Substation | Earthing Design | Calculation | 33/220 kV Power Station Substation - Earthing Design - Calculation | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6242 | E | CAL | 0002 | A | 6105AK125-6242-ECAL-0002 |  | 33/220 kV Power Station Substation | Lightning Protection | Calculation | 33/220 kV Power Station Substation - Lightning Protection - Calculation | 2026-09-17 |  |  |  | 0%
6105A | K125 | 6242 | E | CAL | 0003 | A | 6105AK125-6242-ECAL-0003 |  | 33/220 kV Power Station Substation | LVAC Cable Sizing | Calculation | 33/220 kV Power Station Substation - LVAC Cable Sizing - Calculation | 2026-07-13 |  |  |  | 0%
6105A | K125 | 6242 | E | CAL | 0004 | A | 6105AK125-6242-ECAL-0004 |  | 33/220 kV Power Station Substation | LVDC Cable Sizing | Calculation | 33/220 kV Power Station Substation - LVDC Cable Sizing - Calculation | 2026-07-13 |  |  |  | 0%
6105A | K125 | 6242 | E | CAL | 0005 | B | 6105AK125-6242-ECAL-0005 |  | 33/220 kV Power Station Substation | MV Cable Sizing | Calculation | 33/220 kV Power Station Substation - MV Cable Sizing - Calculation | 2026-06-12 | 2026-05-25 |  | Approved | 100%
6105A | K125 | 6242 | E | SLD | 0002 | A | 6105AK125-6242-ESLD-0002 |  | 33/220 kV Power Station Substation | 220kV Protection Concept | Single Line Diagram | 33/220 kV Power Station Substation - 220kV Protection Concept - Single Line Diagram | 2026-04-07 | 2026-02-16 |  | Reviewed | 33%
6105A | K125 | 6242 | E | LST | 0001 | B | 6105AK125-6242-ELST-0001 |  | 33/220 kV Power Station Substation | 220kV Relay | List | 33/220 kV Power Station Substation - 220kV Relay - List | 2026-02-19 | 2026-06-02 |  | Approved | 100%
6105A | K125 | 6242 | E | CAL | 0006 | B | 6105AK125-6242-ECAL-0006 |  | 33/220 kV Power Station Substation | 220kV CT Sizing | Calculation | 33/220 kV Power Station Substation - 220kV CT Sizing - Calculation | 2026-04-21 | 2026-05-25 |  | Approved | 100%
6105A | K125 | 6242 | E | DIA | 0001 | B | 6105AK125-6242-EDIA-0001 |  | 33/220 kV Power Station Substation | 220kV Protection Trip Logic | Diagram | 33/220 kV Power Station Substation - 220kV Protection Trip Logic - Diagram | 2026-04-07 | 2026-04-17 |  | Approved | 100%
6105A | K125 | 6242 | E | DIA | 0002 | B | 6105AK125-6242-EDIA-0002 |  | 33/220 kV Power Station Substation | 220kV Interlocking Logic | Diagram | 33/220 kV Power Station Substation - 220kV Interlocking Logic - Diagram | 2026-06-12 | 2026-04-17 |  | Approved | 100%
6105A | K125 | 6242 | E | SLD | 0003 | A | 6105AK125-6242-ESLD-0003 |  | 33/220 kV Power Station Substation | LVAC System | Single Line Diagram | 33/220 kV Power Station Substation - LVAC System - Single Line Diagram | 2026-06-12 |  |  |  | 0%
6105A | K125 | 6242 | E | LST | 0002 | C | 6105AK125-6242-ELST-0002 |  | 33/220 kV Power Station Substation | 220kV Signal | List | 33/220 kV Power Station Substation - 220kV Signal - List | 2026-04-09 | 2026-06-04 |  | Approved | 100%
6105A | K125 | 6242 | E | SLD | 0004 | A | 6105AK125-6242-ESLD-0004 |  | 33/220 kV Power Station Substation | 110V DC System | Single Line Diagram | 33/220 kV Power Station Substation - 110V DC System - Single Line Diagram | 2026-06-12 |  |  |  | 0%
6105A | K125 | 6242 | E | CAL | 0007 | A | 6105AK125-6242-ECAL-0007 |  | 33/220 kV Power Station Substation | Battery Bank & Charger Sizing | Calculation | 33/220 kV Power Station Substation - Battery Bank & Charger Sizing - Calculation | 2026-06-12 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0003 | A | 6105AK125-6242-EDIA-0003 |  | 33/220 kV Power Station Substation | 220kV Transformer Control & Protection Panels | Diagram | 33/220 kV Power Station Substation - 220kV Transformer Control & Protection Panels - Diagram | 2026-06-05 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0004 | A | 6105AK125-6242-EDIA-0004 |  | 33/220 kV Power Station Substation | 220kV Line Control & Protection Panels | Diagram | 33/220 kV Power Station Substation - 220kV Line Control & Protection Panels - Diagram | 2026-07-07 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0005 | A | 6105AK125-6242-EDIA-0005 |  | 33/220 kV Power Station Substation | 220kV BusCoupler Control & Protection Panels | Diagram | 33/220 kV Power Station Substation - 220kV BusCoupler Control & Protection Panels - Diagram | 2026-08-04 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0006 | A | 6105AK125-6242-EDIA-0006 |  | 33/220 kV Power Station Substation | 220kV Trip Circuit Supervision Panels | Diagram | 33/220 kV Power Station Substation - 220kV Trip Circuit Supervision Panels - Diagram | 2026-05-19 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0007 | A | 6105AK125-6242-EDIA-0007 |  | 33/220 kV Power Station Substation | 220kV Busbar Protection Panels | Diagram | 33/220 kV Power Station Substation - 220kV Busbar Protection Panels - Diagram | 2026-08-19 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0008 | A | 6105AK125-6242-EDIA-0008 |  | 33/220 kV Power Station Substation | 220kV Common Control Panel | Diagram | 33/220 kV Power Station Substation - 220kV Common Control Panel - Diagram | 2026-05-19 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0009 | A | 6105AK125-6242-EDIA-0009 |  | 33/220 kV Power Station Substation | Energy Metering Panels | Diagram | 33/220 kV Power Station Substation - Energy Metering Panels - Diagram | 2026-08-19 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0010 | A | 6105AK125-6242-EDIA-0010 |  | 33/220 kV Power Station Substation | 220kV Transformer LCC Panels | Diagram | 33/220 kV Power Station Substation - 220kV Transformer LCC Panels - Diagram | 2026-06-05 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0011 | A | 6105AK125-6242-EDIA-0011 |  | 33/220 kV Power Station Substation | 220kV Line LCC Panels | Diagram | 33/220 kV Power Station Substation - 220kV Line LCC Panels - Diagram | 2026-07-07 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0012 | A | 6105AK125-6242-EDIA-0012 |  | 33/220 kV Power Station Substation | 220kV BusCoupler LCCPanels | Diagram | 33/220 kV Power Station Substation - 220kV BusCoupler LCCPanels - Diagram | 2026-08-04 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0013 | A | 6105AK125-6242-EDIA-0013 |  | 33/220 kV Power Station Substation | Network Switch Panel | Diagram | 33/220 kV Power Station Substation - Network Switch Panel - Diagram | 2026-09-03 |  |  |  | 0%
6105A | K125 | 6242 | E | CAL | 0008 | A | 6105AK125-6242-ECAL-0008 |  | 33/220 kV Power Station Substation | 220kV CT VT MK | Calculation | 33/220 kV Power Station Substation - 220kV CT VT MK - Calculation | 2026-10-01 |  |  |  | 0%
6105A | K125 | 6242 | E | CAL | 0009 | A | 6105AK125-6242-ECAL-0009 |  | 33/220 kV Power Station Substation | 220kV Relay Settings | Calculation | 33/220 kV Power Station Substation - 220kV Relay Settings - Calculation |  |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0001 | 0 | 6105AK125-6242-EDST-0001 |  | 33/220 kV Power Station Substation | Power Transformer Technical | Data Sheet | 33/220 kV Power Station Substation - Power Transformer Technical - Data Sheet | 2026-02-10 | 2026-03-05 | 2026-04-23 | Reviewed | 66%
6105A | K125 | 6242 | E | LAY | 0008 | 0 | 6105AK125-6242-ELAY-0008 |  | 33/220 kV Power Station Substation | Power Transformer Dimensional | Layout | 33/220 kV Power Station Substation - Power Transformer Dimensional - Layout | 2026-03-31 | 2026-04-30 | 2026-05-05 | Approved | 100%
6105A | K125 | 6242 | E | ITP | 0001 | A | 6105AK125-6242-EITP-0001 |  | 33/220 kV Power Station Substation | Power Transformer Inspection and Test | Plan | 33/220 kV Power Station Substation - Power Transformer Inspection and Test - Plan | 2026-11-01 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0001 | A | 6105AK125-6242-ERPT-0001 |  | 33/220 kV Power Station Substation | Power Transformer (Lot - 1) Factory Acceptance Test | Report | 33/220 kV Power Station Substation - Power Transformer (Lot - 1) Factory Acceptance Test - Report | 2027-01-06 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0002 | A | 6105AK125-6242-ERPT-0002 |  | 33/220 kV Power Station Substation | Power Transformer (Lot - 2) Factory Acceptance Test | Report | 33/220 kV Power Station Substation - Power Transformer (Lot - 2) Factory Acceptance Test - Report | 2027-03-08 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0003 | A | 6105AK125-6242-ERPT-0003 |  | 33/220 kV Power Station Substation | Power Transformer (Lot - 3) Factory Acceptance Test | Report | 33/220 kV Power Station Substation - Power Transformer (Lot - 3) Factory Acceptance Test - Report | 2027-03-08 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0014 | 0 | 6105AK125-6242-EDIA-0014 |  | 33/220 kV Power Station Substation | Power Transformer Motor Drive Unit Circuit | Diagram | 33/220 kV Power Station Substation - Power Transformer Motor Drive Unit Circuit - Diagram | 2026-05-01 | 2026-05-20 | 2026-05-21 | Approved | 100%
6105A | K125 | 6242 | E | DIA | 0030 | 0 | 6105AK125-6242-EDIA-0030 |  | 33/220 kV Power Station Substation | Power Transformer Local Control Cubicle Schematic | Diagram | 33/220 kV Power Station Substation - Power Transformer Local Control Cubicle Schematic - Diagram | - | 2026-05-20 | 2026-06-02 | Approved
6105A | K125 | 6242 | E | DIA | 0015 | A | 6105AK125-6242-EDIA-0015 |  | 33/220 kV Power Station Substation | Power Transformer AVR/RTCC Schematics | Diagram | 33/220 kV Power Station Substation - Power Transformer AVR/RTCC Schematics - Diagram | 2026-05-01 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0002 | A | 6105AK125-6242-EDST-0002 |  | 33/220 kV Power Station Substation | Earthing Tranformer Technical | Data Sheet | 33/220 kV Power Station Substation - Earthing Tranformer Technical - Data Sheet | 2026-05-27 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0016 | A | 6105AK125-6242-EDIA-0016 |  | 33/220 kV Power Station Substation | Earthing Transformer Dimensional | Diagram | 33/220 kV Power Station Substation - Earthing Transformer Dimensional - Diagram | 2026-05-27 |  |  |  | 0%
6105A | K125 | 6242 | E | ITP | 0002 | A | 6105AK125-6242-EITP-0002 |  | 33/220 kV Power Station Substation | Earthing Transformer Inspection and Test | Plan | 33/220 kV Power Station Substation - Earthing Transformer Inspection and Test - Plan | 2026-11-01 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0004 | A | 6105AK125-6242-ERPT-0004 |  | 33/220 kV Power Station Substation | Earthing Transformer Routine Test | Report | 33/220 kV Power Station Substation - Earthing Transformer Routine Test - Report | 2027-01-31 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0003 | A | 6105AK125-6242-EDST-0003 |  | 33/220 kV Power Station Substation | NGR Technical | Data Sheet | 33/220 kV Power Station Substation - NGR Technical - Data Sheet | 2026-05-27 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0017 | A | 6105AK125-6242-EDIA-0017 |  | 33/220 kV Power Station Substation | NGR Dimensional | Diagram | 33/220 kV Power Station Substation - NGR Dimensional - Diagram | 2026-05-27 |  |  |  | 0%
6105A | K125 | 6242 | E | ITP | 0003 | A | 6105AK125-6242-EITP-0003 |  | 33/220 kV Power Station Substation | NGR Inspection and Test | Plan | 33/220 kV Power Station Substation - NGR Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0005 | A | 6105AK125-6242-ERPT-0005 |  | 33/220 kV Power Station Substation | NGR Routine Test | Report | 33/220 kV Power Station Substation - NGR Routine Test - Report | 2026-11-20 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0004 | 0 | 6105AK125-6242-EDST-0004 |  | 33/220 kV Power Station Substation | 220kV Surge Arrester Technical | Data Sheet | 33/220 kV Power Station Substation - 220kV Surge Arrester Technical - Data Sheet | 2026-04-22 | 2026-05-05 | 2026-05-08 | Approved | 100%
6105A | K125 | 6242 | E | DIA | 0018 | 0 | 6105AK125-6242-EDIA-0018 |  | 33/220 kV Power Station Substation | 220kV Surge Arrester Dimensional | Diagram | 33/220 kV Power Station Substation - 220kV Surge Arrester Dimensional - Diagram | 2026-04-22 | 2026-05-05 | 2026-05-07 | Approved | 100%
6105A | K125 | 6242 | E | ITP | 0004 | A | 6105AK125-6242-EITP-0004 |  | 33/220 kV Power Station Substation | 220kV Surge Arrester Inspection and Test | Plan | 33/220 kV Power Station Substation - 220kV Surge Arrester Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0006 | A | 6105AK125-6242-ERPT-0006 |  | 33/220 kV Power Station Substation | 220kV Surge Arrester FAT | Report | 33/220 kV Power Station Substation - 220kV Surge Arrester FAT - Report | 2026-11-12 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0005 | 0 | 6105AK125-6242-EDST-0005 |  | 33/220 kV Power Station Substation | 220kV Circuit Breaker Technical | Data Sheet | 33/220 kV Power Station Substation - 220kV Circuit Breaker Technical - Data Sheet | 2026-03-30 | 2026-03-24 | 2026-04-30 | Approved | 100%
6105A | K125 | 6242 | E | DIA | 0019 | 0 | 6105AK125-6242-EDIA-0019 |  | 33/220 kV Power Station Substation | 220kV Circuit Breaker Schematic | Diagram | 33/220 kV Power Station Substation - 220kV Circuit Breaker Schematic - Diagram | 2026-03-30 | 2026-03-31 | 2026-04-30 | Approved | 100%
6105A | K125 | 6242 | E | ITP | 0005 | A | 6105AK125-6242-EITP-0005 |  | 33/220 kV Power Station Substation | 220kV Circuit Breaker Inspection and Test | Plan | 33/220 kV Power Station Substation - 220kV Circuit Breaker Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0007 | A | 6105AK125-6242-ERPT-0007 |  | 33/220 kV Power Station Substation | 220kV Circuit Breaker FAT | Report | 33/220 kV Power Station Substation - 220kV Circuit Breaker FAT - Report | 2026-11-15 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0006 | 0 | 6105AK125-6242-EDST-0006 |  | 33/220 kV Power Station Substation | Isolator / Disconnector Technical | Data Sheet | 33/220 kV Power Station Substation - Isolator / Disconnector Technical - Data Sheet | 2026-03-30 | 2026-03-24 | 2026-04-23 | Approved | 100%
6105A | K125 | 6242 | E | DIA | 0020 | 0 | 6105AK125-6242-EDIA-0020 |  | 33/220 kV Power Station Substation | 220kV Isolator / Disconnector Schematic (Drive Disconnector) | Diagram | 33/220 kV Power Station Substation - 220kV Isolator / Disconnector Schematic (Drive Disconnector) - Diagram | 2026-03-30 | 2026-03-31 | 2026-04-23 | Approved | 100%
6105A | K125 | 6242 | E | DIA | 0021 | 0 | 6105AK125-6242-EDIA-0021 |  | 33/220 kV Power Station Substation | 220kV Isolator / Disconnector Schematic (Drive Earthing Switch) | Diagram | 33/220 kV Power Station Substation - 220kV Isolator / Disconnector Schematic (Drive Earthing Switch) - Diagram | 2026-03-30 | 2026-03-31 | 2026-04-23 | Approved | 100%
6105A | K125 | 6242 | E | ITP | 0006 | A | 6105AK125-6242-EITP-0006 |  | 33/220 kV Power Station Substation | Isolator / Disconnector Inspection and Test | Plan | 33/220 kV Power Station Substation - Isolator / Disconnector Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0008 | A | 6105AK125-6242-ERPT-0008 |  | 33/220 kV Power Station Substation | Isolator / Disconnector FAT | Report | 33/220 kV Power Station Substation - Isolator / Disconnector FAT - Report | 2026-11-15 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0022 | 0 | 6105AK125-6242-EDIA-0022 |  | 33/220 kV Power Station Substation | 220kV Circuit Breaker Outline | Diagram | 33/220 kV Power Station Substation - 220kV Circuit Breaker Outline - Diagram | - | 2026-04-02 | 2026-05-04 | Reviewed | 66%
6105A | K125 | 6242 | E | DST | 0007 | 0 | 6105AK125-6242-EDST-0007 |  | 33/220 kV Power Station Substation | Instrument Transformer (CT) Technical | Data Sheet | 33/220 kV Power Station Substation - Instrument Transformer (CT) Technical - Data Sheet | 2026-03-25 | 2026-05-21 | 2026-06-01 | Approved | 100%
6105A | K125 | 6242 | E | DIA | 0023 | 0 | 6105AK125-6242-EDIA-0023 |  | 33/220 kV Power Station Substation | 220kV Isolator / Disconnector Outline | Diagram | 33/220 kV Power Station Substation - 220kV Isolator / Disconnector Outline - Diagram | - | 2026-04-07 | 2026-04-23 | Approved | 100%
6105A | K125 | 6242 | E | LAY | 0009 | 0 | 6105AK125-6242-ELAY-0009 |  | 33/220 kV Power Station Substation | Instrument Transformer (CT) Dimentional | Layout | 33/220 kV Power Station Substation - Instrument Transformer (CT) Dimentional - Layout | 2026-03-25 | 2026-06-05 | 2026-06-08 | Approved | 100%
6105A | K125 | 6242 | E | RPT | 0009 | A | 6105AK125-6242-ERPT-0009 |  | 33/220 kV Power Station Substation | Instrument Transformer (CT) FAT | Report | 33/220 kV Power Station Substation - Instrument Transformer (CT) FAT - Report | 2026-11-15 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0008 | 0 | 6105AK125-6242-EDST-0008 |  | 33/220 kV Power Station Substation | Instrument Transformer (VT) Technical | Data Sheet | 33/220 kV Power Station Substation - Instrument Transformer (VT) Technical - Data Sheet | 2026-03-25 | 2026-05-08 | 2026-05-13 | Approved | 100%
6105A | K125 | 6242 | E | LAY | 0010 | 0 | 6105AK125-6242-ELAY-0010 |  | 33/220 kV Power Station Substation | Instrument Transformer (VT) Dimentional | Layout | 33/220 kV Power Station Substation - Instrument Transformer (VT) Dimentional - Layout | 2026-03-25 | 2026-06-05 | 2026-06-08 | Approved | 100%
6105A | K125 | 6242 | E | RPT | 0010 | A | 6105AK125-6242-ERPT-0010 |  | 33/220 kV Power Station Substation | Instrument Transformer (VT) FAT | Report | 33/220 kV Power Station Substation - Instrument Transformer (VT) FAT - Report | 2026-11-15 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0009 | A | 6105AK125-6242-EDST-0009 |  | 33/220 kV Power Station Substation | AC Panel Technical | Data Sheet | 33/220 kV Power Station Substation - AC Panel Technical - Data Sheet | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0024 | A | 6105AK125-6242-EDIA-0024 |  | 33/220 kV Power Station Substation | AC Panel Schematics | Diagram | 33/220 kV Power Station Substation - AC Panel Schematics - Diagram | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0011 | A | 6105AK125-6242-ERPT-0011 |  | 33/220 kV Power Station Substation | AC Panel FAT | Report | 33/220 kV Power Station Substation - AC Panel FAT - Report | 2026-11-30 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0010 | A | 6105AK125-6242-EDST-0010 |  | 33/220 kV Power Station Substation | DC Panel Technical | Data Sheet | 33/220 kV Power Station Substation - DC Panel Technical - Data Sheet | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0025 | A | 6105AK125-6242-EDIA-0025 |  | 33/220 kV Power Station Substation | DC Panel Schematics | Diagram | 33/220 kV Power Station Substation - DC Panel Schematics - Diagram | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0012 | A | 6105AK125-6242-ERPT-0012 |  | 33/220 kV Power Station Substation | DC Panel FAT | Report | 33/220 kV Power Station Substation - DC Panel FAT - Report | 2026-11-30 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0011 | A | 6105AK125-6242-EDST-0011 |  | 33/220 kV Power Station Substation | Battery Bank Technical | Data Sheet | 33/220 kV Power Station Substation - Battery Bank Technical - Data Sheet | 2026-04-20 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0026 | A | 6105AK125-6242-EDIA-0026 |  | 33/220 kV Power Station Substation | Battery Bank (Connection/Fuse Box) | Diagram | 33/220 kV Power Station Substation - Battery Bank (Connection/Fuse Box) - Diagram | 2026-04-20 |  |  |  | 0%
6105A | K125 | 6242 | E | SPC | 0001 | A | 6105AK125-6242-ESPC-0001 |  | 33/220 kV Power Station Substation | Battery Bank Details / Rack Design | Specification | 33/220 kV Power Station Substation - Battery Bank Details / Rack Design - Specification | 2026-04-20 |  |  |  | 0%
6105A | K125 | 6242 | E | ITP | 0007 | A | 6105AK125-6242-EITP-0007 |  | 33/220 kV Power Station Substation | Battery Bank Inspection and Test | Plan | 33/220 kV Power Station Substation - Battery Bank Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0013 | A | 6105AK125-6242-ERPT-0013 |  | 33/220 kV Power Station Substation | Battery Bank FAT | Report | 33/220 kV Power Station Substation - Battery Bank FAT - Report | 2026-11-05 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0012 | A | 6105AK125-6242-EDST-0012 |  | 33/220 kV Power Station Substation | Battery Charger Technical | Data Sheet | 33/220 kV Power Station Substation - Battery Charger Technical - Data Sheet | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0027 | A | 6105AK125-6242-EDIA-0027 |  | 33/220 kV Power Station Substation | Battery Charger Schematic | Diagram | 33/220 kV Power Station Substation - Battery Charger Schematic - Diagram | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6242 | E | ITP | 0008 | A | 6105AK125-6242-EITP-0008 |  | 33/220 kV Power Station Substation | Battery Charger Inspection and Test | Plan | 33/220 kV Power Station Substation - Battery Charger Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0014 | A | 6105AK125-6242-ERPT-0014 |  | 33/220 kV Power Station Substation | Battery Charger FAT | Report | 33/220 kV Power Station Substation - Battery Charger FAT - Report | 2026-11-16 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0013 | A | 6105AK125-6242-EDST-0013 |  | 33/220 kV Power Station Substation | Inverter Technical | Data Sheet | 33/220 kV Power Station Substation - Inverter Technical - Data Sheet | 2026-04-20 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0014 | A | 6105AK125-6242-EDST-0014 |  | 33/220 kV Power Station Substation | Post Insulator Technical | Data Sheet | 33/220 kV Power Station Substation - Post Insulator Technical - Data Sheet | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6242 | E | LAY | 0011 | A | 6105AK125-6242-ELAY-0011 |  | 33/220 kV Power Station Substation | Post Insulator Outline & Dimentional | Layout | 33/220 kV Power Station Substation - Post Insulator Outline & Dimentional - Layout | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0015 | A | 6105AK125-6242-ERPT-0015 |  | 33/220 kV Power Station Substation | Post Insulator FAT | Report | 33/220 kV Power Station Substation - Post Insulator FAT - Report | 2027-01-15 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0015 | A | 6105AK125-6242-EDST-0015 |  | 33/220 kV Power Station Substation | Disc Insulator Technical | Data Sheet | 33/220 kV Power Station Substation - Disc Insulator Technical - Data Sheet | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6242 | E | LAY | 0012 | A | 6105AK125-6242-ELAY-0012 |  | 33/220 kV Power Station Substation | Disc Insulator Outline & Dimentional | Layout | 33/220 kV Power Station Substation - Disc Insulator Outline & Dimentional - Layout | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6242 | E | RPT | 0016 | A | 6105AK125-6242-ERPT-0016 |  | 33/220 kV Power Station Substation | Disc Insulator FAT | Report | 33/220 kV Power Station Substation - Disc Insulator FAT - Report | 2027-01-15 |  |  |  | 0%
6105A | K125 | 6242 | E | SSD | 0001 | A | 6105AK125-6242-ESSD-0001 |  | 33/220 kV Power Station Substation | Steel Structure | Drawing | 33/220 kV Power Station Substation - Steel Structure - Drawing | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6242 | E | SPC | 0002 | A | 6105AK125-6242-ESPC-0002 |  | 33/220 kV Power Station Substation | Termination Kit Outdoor Termination & Joints | Specification | 33/220 kV Power Station Substation - Termination Kit Outdoor Termination & Joints - Specification | 2026-10-21 |  |  |  | 0%
6105A | K125 | 6242 | E | DST | 0016 | A | 6105AK125-6242-EDST-0016 |  | 33/220 kV Power Station Substation | Cables & Conductors Technical | Data Sheet | 33/220 kV Power Station Substation - Cables & Conductors Technical - Data Sheet | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6242 | E | SPC | 0003 | A | 6105AK125-6242-ESPC-0003 |  | 33/220 kV Power Station Substation | Grounding Technical Documentation | Specification | 33/220 kV Power Station Substation - Grounding Technical Documentation - Specification | 2026-09-24 |  |  |  | 0%
6105A | K125 | 6242 | E | SPC | 0004 | A | 6105AK125-6242-ESPC-0004 |  | 33/220 kV Power Station Substation | Hardware & Connector Technical Documentation | Specification | 33/220 kV Power Station Substation - Hardware & Connector Technical Documentation - Specification | 2026-07-24 |  |  |  | 0%
6105A | K125 | 6242 | E | DIA | 0029 | 0 | 6105AK125-6242-EDIA-0029 |  | 33/220 kV Power Station Substation | Surge Monitor for 220kV Surge Arrester | Diagram | 33/220 kV Power Station Substation - Surge Monitor for 220kV Surge Arrester - Diagram | - | 2026-05-12 | 2026-05-15 | Approved | 100%
6105A | K125 | 6242 | C | DBD | 0001 | 0 | 6105AK125-6242-CDBD-0001 |  | 33/220 kV Power Station Substation | Civil | Design Basis and Criteria | 33/220 kV Power Station Substation - Civil - Design Basis and Criteria | 2026-04-15 | 2026-04-24 | 2026-05-08 | Approved | 100%
6105A | K125 | 6242 | C | FND | 0001 | A | 6105AK125-6242-CFND-0001 |  | 33/220 kV Power Station Substation | Power Transformer Foundation | Plan | 33/220 kV Power Station Substation - Power Transformer Foundation - Plan | 2026-07-01 | 2026-06-05 |  | Reviewed | 33%
6105A | K125 | 6242 | C | DTL | 0001 | B | 6105AK125-6242-CDTL-0001 |  | 33/220 kV Power Station Substation | Power Transformer Concrete Outline Plan and | Details | 33/220 kV Power Station Substation - Power Transformer Concrete Outline Plan and - Details | 2026-07-01 | 2026-06-05 |  | Reviewed | 33%
6105A | K125 | 6242 | C | DTL | 0002 | B | 6105AK125-6242-CDTL-0002 |  | 33/220 kV Power Station Substation | Power Transformer Reinforcement Plan and | Details | 33/220 kV Power Station Substation - Power Transformer Reinforcement Plan and - Details | 2026-07-01 | 2026-06-05 |  | Reviewed | 33%
6105A | K125 | 6242 | C | DTL | 0003 | B | 6105AK125-6242-CDTL-0003 |  | 33/220 kV Power Station Substation | Power Transformer Gravel & Grating | Details | 33/220 kV Power Station Substation - Power Transformer Gravel & Grating - Details | 2026-07-01 | 2026-06-05 |  | Reviewed | 33%
6105A | K125 | 6242 | C | RPT | 0001 | A | 6105AK125-6242-CRPT-0001 |  | 33/220 kV Power Station Substation | Power Transformer Design | Report | 33/220 kV Power Station Substation - Power Transformer Design - Report | 2026-07-01 | 2026-06-05 |  |  | 33%
6105A | K125 | 6242 | C | PLN | 0001 | A | 6105AK125-6242-CPLN-0001 |  | 33/220 kV Power Station Substation | Fire Wall Foundation | Plan | 33/220 kV Power Station Substation - Fire Wall Foundation - Plan | 2026-07-01 | 2026-06-02 |  | Approved | 100%
6105A | K125 | 6242 | C | DTL | 0004 | B | 6105AK125-6242-CDTL-0004 |  | 33/220 kV Power Station Substation | Fire Wall Concrete Outline Plan and | Details | 33/220 kV Power Station Substation - Fire Wall Concrete Outline Plan and - Details | 2026-07-01 | 2026-06-05 |  | Reviewed | 33%
6105A | K125 | 6242 | C | DTL | 0005 | B | 6105AK125-6242-CDTL-0005 |  | 33/220 kV Power Station Substation | Fire Wall Reinforcement Plan and | Details | 33/220 kV Power Station Substation - Fire Wall Reinforcement Plan and - Details | 2026-07-01 | 2026-06-05 |  | Reviewed | 33%
6105A | K125 | 6242 | C | RPT | 0002 | A | 6105AK125-6242-CRPT-0002 |  | 33/220 kV Power Station Substation | Fire Wall Design | Report | 33/220 kV Power Station Substation - Fire Wall Design - Report | 2026-07-01 | 2026-06-05 |  |  | 33%
6105A | K125 | 6242 | C | PLN | 0002 | A | 6105AK125-6242-CPLN-0002 |  | 33/220 kV Power Station Substation | 220 kV Ganrty Foundation Layout | Plan | 33/220 kV Power Station Substation - 220 kV Ganrty Foundation Layout - Plan | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0006 | A | 6105AK125-6242-CDTL-0006 |  | 33/220 kV Power Station Substation | 220 kV Ganrty Foundation Concrete Outline Plan and | Details | 33/220 kV Power Station Substation - 220 kV Ganrty Foundation Concrete Outline Plan and - Details | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0007 | A | 6105AK125-6242-CDTL-0007 |  | 33/220 kV Power Station Substation | 220 kV Ganrty Foundation Reinforcement Plan and | Details | 33/220 kV Power Station Substation - 220 kV Ganrty Foundation Reinforcement Plan and - Details | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6242 | C | RPT | 0003 | A | 6105AK125-6242-CRPT-0003 |  | 33/220 kV Power Station Substation | 220 kV Ganrty Foundation Design | Report | 33/220 kV Power Station Substation - 220 kV Ganrty Foundation Design - Report | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6242 | C | PLN | 0003 | A | 6105AK125-6242-CPLN-0003 |  | 33/220 kV Power Station Substation | DG Set Foundation | Plan | 33/220 kV Power Station Substation - DG Set Foundation - Plan | 2026-07-13 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0008 | A | 6105AK125-6242-CDTL-0008 |  | 33/220 kV Power Station Substation | DG Set Foundation Concrete Outline Plan and | Details | 33/220 kV Power Station Substation - DG Set Foundation Concrete Outline Plan and - Details | 2026-07-13 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0009 | A | 6105AK125-6242-CDTL-0009 |  | 33/220 kV Power Station Substation | DG Set Foundation Reinforcement Plan and | Details | 33/220 kV Power Station Substation - DG Set Foundation Reinforcement Plan and - Details | 2026-07-13 |  |  |  | 0%
6105A | K125 | 6242 | C | RPT | 0004 | A | 6105AK125-6242-CRPT-0004 |  | 33/220 kV Power Station Substation | DG Set Foundation Design | Report | 33/220 kV Power Station Substation - DG Set Foundation Design - Report | 2026-07-13 |  |  |  | 0%
6105A | K125 | 6242 | C | PLN | 0004 | A | 6105AK125-6242-CPLN-0004 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Foundation Layout | Plan | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Foundation Layout - Plan | 2026-07-08 |  |  |  | 0%
6105A | K125 | 6242 | C | FND | 0002 | A | 6105AK125-6242-CFND-0002 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details Surge Arrester | Foundation | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details Surge Arrester - Foundation | 2026-08-10 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0010 | A | 6105AK125-6242-CDTL-0010 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Surge Arrester Foundation Reinforcement Plan and | Details | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Surge Arrester Foundation Reinforcement Plan and - Details | 2026-08-10 |  |  |  | 0%
6105A | K125 | 6242 | C | RPT | 0005 | A | 6105AK125-6242-CRPT-0005 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Surge Arrester Foundation Design | Report | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Surge Arrester Foundation Design - Report | 2026-08-10 |  |  |  | 0%
6105A | K125 | 6242 | C | FND | 0003 | A | 6105AK125-6242-CFND-0003 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details DS+ES | Foundation | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details DS+ES - Foundation | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0011 | A | 6105AK125-6242-CDTL-0011 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment DS+ES Foundation Reinforcement Plan and | Details | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment DS+ES Foundation Reinforcement Plan and - Details | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6242 | C | RPT | 0006 | A | 6105AK125-6242-CRPT-0006 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment DS+ES Foundation Design | Report | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment DS+ES Foundation Design - Report | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6242 | C | FND | 0004 | A | 6105AK125-6242-CFND-0004 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details Current Transformer | Foundation | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details Current Transformer - Foundation | 2026-08-01 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0012 | A | 6105AK125-6242-CDTL-0012 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Current Transformer Foundation Reinforcement Plan and | Details | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Current Transformer Foundation Reinforcement Plan and - Details | 2026-08-01 |  |  |  | 0%
6105A | K125 | 6242 | C | RPT | 0007 | A | 6105AK125-6242-CRPT-0007 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Current Transformer Foundation Design | Report | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Current Transformer Foundation Design - Report | 2026-08-01 |  |  |  | 0%
6105A | K125 | 6242 | C | FND | 0005 | 0 | 6105AK125-6242-CFND-0005 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details Circuit Breaker | Foundation | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details Circuit Breaker - Foundation | 2026-07-25 | 2026-05-18 | 2026-06-02 | Approved | 100%
6105A | K125 | 6242 | C | DTL | 0013 | 0 | 6105AK125-6242-CDTL-0013 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Circuit Breaker Foundation Reinforcement Plan and | Details | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Circuit Breaker Foundation Reinforcement Plan and - Details | 2026-07-25 | 2026-05-18 | 2026-06-02 | Approved | 100%
6105A | K125 | 6242 | C | RPT | 0008 | 0 | 6105AK125-6242-CRPT-0008 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Circuit Breaker Foundation Design | Report | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Circuit Breaker Foundation Design - Report | 2026-07-25 | 2026-05-18 | 2026-06-02 | Approved | 100%
6105A | K125 | 6242 | C | FND | 0006 | A | 6105AK125-6242-CFND-0006 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details Voltage Transformer | Foundation | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details Voltage Transformer - Foundation | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0014 | A | 6105AK125-6242-CDTL-0014 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Voltage Transformer Foundation Reinforcement Plan and | Details | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Voltage Transformer Foundation Reinforcement Plan and - Details | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6242 | C | RPT | 0009 | A | 6105AK125-6242-CRPT-0009 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Voltage Transformer Foundation Design | Report | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Voltage Transformer Foundation Design - Report | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6242 | C | FND | 0007 | A | 6105AK125-6242-CFND-0007 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Concrete Outline Plan & Details Post Insulator | Foundation | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Concrete Outline Plan & Details Post Insulator - Foundation | 2026-07-10 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0015 | A | 6105AK125-6242-CDTL-0015 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Post Insulator Foundation Reinforcement Plan and | Details | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Post Insulator Foundation Reinforcement Plan and - Details | 2026-07-10 |  |  |  | 0%
6105A | K125 | 6242 | C | RPT | 0010 | A | 6105AK125-6242-CRPT-0010 |  | 33/220 kV Power Station Substation | 220 kV Switchyard Equipment Post Insulator Foundation Design | Report | 33/220 kV Power Station Substation - 220 kV Switchyard Equipment Post Insulator Foundation Design - Report | 2026-07-10 |  |  |  | 0%
6105A | K125 | 6242 | C | PLN | 0005 | A | 6105AK125-6242-CPLN-0005 |  | 33/220 kV Power Station Substation | Switchyard Trenches Layout | Plan | 33/220 kV Power Station Substation - Switchyard Trenches Layout - Plan | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6242 | C | SEC | 0001 | A | 6105AK125-6242-CSEC-0001 |  | 33/220 kV Power Station Substation | Switchyard Trenches Concrete Outline Section and Trench Covers | Section | 33/220 kV Power Station Substation - Switchyard Trenches Concrete Outline Section and Trench Covers - Section | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6242 | C | SEC | 0002 | A | 6105AK125-6242-CSEC-0002 |  | 33/220 kV Power Station Substation | Switchyard Trenches Reinforcement Section and Trench Covers | Section | 33/220 kV Power Station Substation - Switchyard Trenches Reinforcement Section and Trench Covers - Section | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6242 | C | SEC | 0003 | A | 6105AK125-6242-CSEC-0003 |  | 33/220 kV Power Station Substation | Switchyard Trenches Draw Pit Concrete Outline | Section | 33/220 kV Power Station Substation - Switchyard Trenches Draw Pit Concrete Outline - Section | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0016 | A | 6105AK125-6242-CDTL-0016 |  | 33/220 kV Power Station Substation | Switchyard Trenches Draw Pit Reinforcement Plan and | Details | 33/220 kV Power Station Substation - Switchyard Trenches Draw Pit Reinforcement Plan and - Details | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6242 | C | RPT | 0011 | A | 6105AK125-6242-CRPT-0011 |  | 33/220 kV Power Station Substation | Switchyard Trenches Design | Report | 33/220 kV Power Station Substation - Switchyard Trenches Design - Report | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0017 | A | 6105AK125-6242-CDTL-0017 |  | 33/220 kV Power Station Substation | Switchyard Trenches Duct bank | Details | 33/220 kV Power Station Substation - Switchyard Trenches Duct bank - Details | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6242 | W | PLN | 0001 | A | 6105AK125-6242-WPLN-0001 |  | 33/220 kV Power Station Substation | Road Layout | Plan | 33/220 kV Power Station Substation - Road Layout - Plan | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6242 | W | SEC | 0001 | A | 6105AK125-6242-WSEC-0001 |  | 33/220 kV Power Station Substation | Road Concrete Outline | Section | 33/220 kV Power Station Substation - Road Concrete Outline - Section | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6242 | W | SEC | 0002 | A | 6105AK125-6242-WSEC-0002 |  | 33/220 kV Power Station Substation | Road Reinforcement | Section | 33/220 kV Power Station Substation - Road Reinforcement - Section | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6242 | W | PLN | 0002 | A | 6105AK125-6242-WPLN-0002 |  | 33/220 kV Power Station Substation | Surface Drainage Layout | Plan | 33/220 kV Power Station Substation - Surface Drainage Layout - Plan | 2026-09-02 |  |  |  | 0%
6105A | K125 | 6242 | W | DTL | 0001 | A | 6105AK125-6242-WDTL-0001 |  | 33/220 kV Power Station Substation | Surface Drainage Main Hole | Details | 33/220 kV Power Station Substation - Surface Drainage Main Hole - Details | 2026-09-02 |  |  |  | 0%
6105A | K125 | 6242 | W | DTL | 0002 | A | 6105AK125-6242-WDTL-0002 |  | 33/220 kV Power Station Substation | Surface Drainage Pipe Laying | Details | 33/220 kV Power Station Substation - Surface Drainage Pipe Laying - Details | 2026-09-02 |  |  |  | 0%
6105A | K125 | 6242 | W | RPT | 0001 | A | 6105AK125-6242-WRPT-0001 |  | 33/220 kV Power Station Substation | Surface Drainage Design | Report | 33/220 kV Power Station Substation - Surface Drainage Design - Report | 2026-09-02 |  |  |  | 0%
6105A | K125 | 6242 | W | PLN | 0003 | A | 6105AK125-6242-WPLN-0003 |  | 33/220 kV Power Station Substation | Fence Wall Layout | Plan | 33/220 kV Power Station Substation - Fence Wall Layout - Plan | 2026-09-23 |  |  |  | 0%
6105A | K125 | 6242 | W | DTL | 0003 | A | 6105AK125-6242-WDTL-0003 |  | 33/220 kV Power Station Substation | Fence Wall Foundation Plan and | Details | 33/220 kV Power Station Substation - Fence Wall Foundation Plan and - Details | 2026-09-23 |  |  |  | 0%
6105A | K125 | 6242 | W | DTL | 0004 | A | 6105AK125-6242-WDTL-0004 |  | 33/220 kV Power Station Substation | Fence Wall Fence Section Plan and | Details | 33/220 kV Power Station Substation - Fence Wall Fence Section Plan and - Details | 2026-09-23 |  |  |  | 0%
6105A | K125 | 6242 | W | SEC | 0003 | A | 6105AK125-6242-WSEC-0003 |  | 33/220 kV Power Station Substation | Fence Wall Gate Plan and | Section | 33/220 kV Power Station Substation - Fence Wall Gate Plan and - Section | 2026-09-23 |  |  |  | 0%
6105A | K125 | 6242 | C | PLN | 0006 | A | 6105AK125-6242-CPLN-0006 |  | 33/220 kV Power Station Substation | E-House Foundation Concrete Outline | Plan | 33/220 kV Power Station Substation - E-House Foundation Concrete Outline - Plan | 2026-07-24 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0018 | A | 6105AK125-6242-CDTL-0018 |  | 33/220 kV Power Station Substation | E-House Foundation Reinforcement Plan and | Details | 33/220 kV Power Station Substation - E-House Foundation Reinforcement Plan and - Details | 2026-07-24 |  |  |  | 0%
6105A | K125 | 6242 | C | RPT | 0012 | A | 6105AK125-6242-CRPT-0012 |  | 33/220 kV Power Station Substation | E-House Foundation Design | Report | 33/220 kV Power Station Substation - E-House Foundation Design - Report | 2026-07-24 |  |  |  | 0%
6105A | K125 | 6242 | C | PLN | 0007 | A | 6105AK125-6242-CPLN-0007 |  | 33/220 kV Power Station Substation | Aux-Trafo Foundation Concrete Outline | Plan | 33/220 kV Power Station Substation - Aux-Trafo Foundation Concrete Outline - Plan | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0019 | A | 6105AK125-6242-CDTL-0019 |  | 33/220 kV Power Station Substation | Aux-Trafo Foundation Reinforcement Plan and | Details | 33/220 kV Power Station Substation - Aux-Trafo Foundation Reinforcement Plan and - Details | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6242 | C | RPT | 0013 | A | 6105AK125-6242-CRPT-0013 |  | 33/220 kV Power Station Substation | Aux-Trafo Foundation Design | Report | 33/220 kV Power Station Substation - Aux-Trafo Foundation Design - Report | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6242 | C | PLN | 0008 | A | 6105AK125-6242-CPLN-0008 |  | 33/220 kV Power Station Substation | NGR & ET Foundation Concrete Outline | Plan | 33/220 kV Power Station Substation - NGR & ET Foundation Concrete Outline - Plan | 2026-06-19 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0020 | A | 6105AK125-6242-CDTL-0020 |  | 33/220 kV Power Station Substation | NGR & ET Foundation Reinforcement Plan and | Details | 33/220 kV Power Station Substation - NGR & ET Foundation Reinforcement Plan and - Details | 2026-06-19 |  |  |  | 0%
6105A | K125 | 6242 | C | RPT | 0014 | A | 6105AK125-6242-CRPT-0014 |  | 33/220 kV Power Station Substation | NGR & ET Foundation Design | Report | 33/220 kV Power Station Substation - NGR & ET Foundation Design - Report | 2026-06-19 |  |  |  | 0%
6105A | K125 | 6242 | C | PLN | 0009 | A | 6105AK125-6242-CPLN-0009 |  | 33/220 kV Power Station Substation | Transformer - Way Concrete Outline | Plan | 33/220 kV Power Station Substation - Transformer - Way Concrete Outline - Plan | 2026-07-22 |  |  |  | 0%
6105A | K125 | 6242 | C | PLN | 0010 | A | 6105AK125-6242-CPLN-0010 |  | 33/220 kV Power Station Substation | Light Pole Foundation Layout | Plan | 33/220 kV Power Station Substation - Light Pole Foundation Layout - Plan | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0021 | A | 6105AK125-6242-CDTL-0021 |  | 33/220 kV Power Station Substation | Light Pole Foundation Concrete Outline & Reinforcement | Details | 33/220 kV Power Station Substation - Light Pole Foundation Concrete Outline & Reinforcement - Details | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6242 | C | RPT | 0015 | A | 6105AK125-6242-CRPT-0015 |  | 33/220 kV Power Station Substation | Light Pole Foundation Design | RPT | 33/220 kV Power Station Substation - Light Pole Foundation Design - RPT | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6242 | W | PLN | 0004 | A | 6105AK125-6242-WPLN-0004 |  | 33/220 kV Power Station Substation | Gravel Layout | Plan | 33/220 kV Power Station Substation - Gravel Layout - Plan | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6242 | C | PLN | 0011 | 0 | 6105AK125-6242-CPLN-0011 |  | 33/220 kV Power Station Substation | Site Grading | Plan | 33/220 kV Power Station Substation - Site Grading - Plan | - | 2026-05-04 | 2026-05-06 | Approved | 100%
6105A | K125 | 6242 | C | LST | 0001 | A | 6105AK125-6242-CLST-0001 |  | 33/220 kV Power Station Substation | Drawings, Legends, Notes | List | 33/220 kV Power Station Substation - Drawings, Legends, Notes - List | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6242 | C | DIA | 0001 | A | 6105AK125-6242-CDIA-0001 |  | 33/220 kV Power Station Substation | Distribution Board | Single Line Diagram | 33/220 kV Power Station Substation - Distribution Board - Single Line Diagram | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6242 | C | LAY | 0001 | A | 6105AK125-6242-CLAY-0001 |  | 33/220 kV Power Station Substation | Outdoor Switchyard Lighting and Small Power Layout | Layout | 33/220 kV Power Station Substation - Outdoor Switchyard Lighting and Small Power Layout - Layout | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6242 | C | LAY | 0002 | A | 6105AK125-6242-CLAY-0002 |  | 33/220 kV Power Station Substation | Outdoor switchyard Lighting and Small Power Cable Route | Layout | 33/220 kV Power Station Substation - Outdoor switchyard Lighting and Small Power Cable Route - Layout | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6242 | C | DTL | 0022 | A | 6105AK125-6242-CDTL-0022 |  | 33/220 kV Power Station Substation | Installation Detail for Outdoor Lighting and Small Power | Details | 33/220 kV Power Station Substation - Installation Detail for Outdoor Lighting and Small Power - Details | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6242 | C | CAL | 0001 | A | 6105AK125-6242-CCAL-0001 |  | 33/220 kV Power Station Substation | Outdoor Lighting Lux | Calculation | 33/220 kV Power Station Substation - Outdoor Lighting Lux - Calculation | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6242 | C | SHP | 0001 | A | 6105AK125-6242-CSHP-0001 |  | 33/220 kV Power Station Substation | Shop / Manufacturing Drawings of Distribution Boards | Shop Drawing | 33/220 kV Power Station Substation - Shop / Manufacturing Drawings of Distribution Boards - Shop Drawing | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6243 | G | LAY | 0001 | 0 | 6105AK125-6243-GLAY-0001 | Sht. 1 of 1 | 220/33 kV Plant Main Substation | Site Office Arrangement | Layout | 220/33 kV Plant Main Substation - Site Office Arrangement - Layout | - | 2026-04-03 | 2026-05-19 | Approved | 100%
6105A | K125 | 6243 | E | SLD | 0001 | A | 6105AK125-6243-ESLD-0001 | Sht. 1 of 1 | 220/33 kV Plant Main Substation | Overall | Single Line Diagram | 220/33 kV Plant Main Substation - Overall - Single Line Diagram | 2026-02-04 | 2026-02-10 |  | Approved | 100% | 2026-06-08
6105A | K125 | 6243 | E | LAY | 0001 | A | 6105AK125-6243-ELAY-0001 |  | 220/33 kV Plant Main Substation | Equipment | Layout | 220/33 kV Plant Main Substation - Equipment - Layout | 2026-04-30 | 2026-02-13 |  | Reviewed | 33%
6105A | K125 | 6243 | E | LAY | 0002 | A | 6105AK125-6243-ELAY-0002 |  | 220/33 kV Plant Main Substation | E-House | Layout | 220/33 kV Plant Main Substation - E-House - Layout | 2026-06-11 |  |  |  | 0%
6105A | K125 | 6243 | E | LAY | 0003 | A | 6105AK125-6243-ELAY-0003 |  | 220/33 kV Plant Main Substation | Foundation and Trench | Layout | 220/33 kV Plant Main Substation - Foundation and Trench - Layout | 2026-06-17 |  |  |  | 0%
6105A | K125 | 6243 | E | LAY | 0004 | A | 6105AK125-6243-ELAY-0004 |  | 220/33 kV Plant Main Substation | Cable Tray | Layout | 220/33 kV Plant Main Substation - Cable Tray - Layout | 2026-07-29 |  |  |  | 0%
6105A | K125 | 6243 | E | LAY | 0005 | A | 6105AK125-6243-ELAY-0005 |  | 220/33 kV Plant Main Substation | Buried Earthing | Layout | 220/33 kV Plant Main Substation - Buried Earthing - Layout | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6243 | E | LAY | 0006 | A | 6105AK125-6243-ELAY-0006 |  | 220/33 kV Plant Main Substation | Indoor Earthing | Layout | 220/33 kV Plant Main Substation - Indoor Earthing - Layout | 2026-09-10 |  |  |  | 0%
6105A | K125 | 6243 | E | LAY | 0007 | A | 6105AK125-6243-ELAY-0007 |  | 220/33 kV Plant Main Substation | Lightning Protection | Layout | 220/33 kV Plant Main Substation - Lightning Protection - Layout | 2026-09-17 |  |  |  | 0%
6105A | K125 | 6243 | E | CAL | 0001 | A | 6105AK125-6243-ECAL-0001 |  | 220/33 kV Plant Main Substation | Earthing Design | Calculation | 220/33 kV Plant Main Substation - Earthing Design - Calculation | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6243 | E | CAL | 0002 | A | 6105AK125-6243-ECAL-0002 |  | 220/33 kV Plant Main Substation | Lightning Protection | Calculation | 220/33 kV Plant Main Substation - Lightning Protection - Calculation | 2026-09-17 |  |  |  | 0%
6105A | K125 | 6243 | E | CAL | 0003 | A | 6105AK125-6243-ECAL-0003 |  | 220/33 kV Plant Main Substation | LVAC Cable Sizing | Calculation | 220/33 kV Plant Main Substation - LVAC Cable Sizing - Calculation | 2026-07-13 |  |  |  | 0%
6105A | K125 | 6243 | E | CAL | 0004 | A | 6105AK125-6243-ECAL-0004 |  | 220/33 kV Plant Main Substation | LVDC Cable Sizing | Calculation | 220/33 kV Plant Main Substation - LVDC Cable Sizing - Calculation | 2026-07-13 |  |  |  | 0%
6105A | K125 | 6243 | E | CAL | 0005 | B | 6105AK125-6243-ECAL-0005 |  | 220/33 kV Plant Main Substation | MV Cable Sizing | Calculation | 220/33 kV Plant Main Substation - MV Cable Sizing - Calculation | 2026-06-12 | 2026-05-25 |  | Approved | 100%
6105A | K125 | 6243 | E | SLD | 0002 | B | 6105AK125-6243-ESLD-0002 |  | 220/33 kV Plant Main Substation | 220kV Protection Concept | Single Line Diagram | 220/33 kV Plant Main Substation - 220kV Protection Concept - Single Line Diagram | 2026-04-07 | 2026-04-20 |  | Approved | 100%
6105A | K125 | 6243 | E | LST | 0001 | A | 6105AK125-6243-ELST-0001 |  | 220/33 kV Plant Main Substation | 220kV Relay | List | 220/33 kV Plant Main Substation - 220kV Relay - List | 2026-02-19 | 2026-03-17 |  | Reviewed | 33%
6105A | K125 | 6243 | E | CAL | 0006 | A | 6105AK125-6243-ECAL-0006 |  | 220/33 kV Plant Main Substation | 220kV CT/VT Dimensioning | Calculation | 220/33 kV Plant Main Substation - 220kV CT/VT Dimensioning - Calculation | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0001 | B | 6105AK125-6243-EDIA-0001 |  | 220/33 kV Plant Main Substation | 220kV Protection Trip Logic | Diagram | 220/33 kV Plant Main Substation - 220kV Protection Trip Logic - Diagram | 2026-03-05 | 2026-04-20 |  | Approved | 100%
6105A | K125 | 6243 | E | DIA | 0002 | B | 6105AK125-6243-EDIA-0002 |  | 220/33 kV Plant Main Substation | 220kV Interlocking Logic | Diagram | 220/33 kV Plant Main Substation - 220kV Interlocking Logic - Diagram | 2026-06-12 | 2026-04-20 |  | Approved | 100%
6105A | K125 | 6243 | E | SLD | 0003 | A | 6105AK125-6243-ESLD-0003 |  | 220/33 kV Plant Main Substation | LVAC System | Single Line Diagram | 220/33 kV Plant Main Substation - LVAC System - Single Line Diagram | 2026-06-12 |  |  |  | 0%
6105A | K125 | 6243 | E | LST | 0002 | A | 6105AK125-6243-ELST-0002 |  | 220/33 kV Plant Main Substation | 220kV Signal | List | 220/33 kV Plant Main Substation - 220kV Signal - List | 2026-04-09 | 2026-03-17 |  | Reviewed | 33%
6105A | K125 | 6243 | E | SLD | 0004 | A | 6105AK125-6243-ESLD-0004 |  | 220/33 kV Plant Main Substation | 110V DC System | Single Line Diagram | 220/33 kV Plant Main Substation - 110V DC System - Single Line Diagram | 2026-06-12 |  |  |  | 0%
6105A | K125 | 6243 | E | CAL | 0007 | A | 6105AK125-6243-ECAL-0007 |  | 220/33 kV Plant Main Substation | Battery Bank & Charger Sizing | Calculation | 220/33 kV Plant Main Substation - Battery Bank & Charger Sizing - Calculation | 2026-06-12 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0003 | A | 6105AK125-6243-EDIA-0003 |  | 220/33 kV Plant Main Substation | 220kV Transformer Control & Protection Panels | Diagram | 220/33 kV Plant Main Substation - 220kV Transformer Control & Protection Panels - Diagram | 2026-06-05 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0004 | A | 6105AK125-6243-EDIA-0004 |  | 220/33 kV Plant Main Substation | 220kV Line Control & Protection Panels | Diagram | 220/33 kV Plant Main Substation - 220kV Line Control & Protection Panels - Diagram | 2026-07-07 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0005 | A | 6105AK125-6243-EDIA-0005 |  | 220/33 kV Plant Main Substation | 220kV Trip Circuit Supervision Panels | Diagram | 220/33 kV Plant Main Substation - 220kV Trip Circuit Supervision Panels - Diagram | 2026-05-19 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0006 | A | 6105AK125-6243-EDIA-0006 |  | 220/33 kV Plant Main Substation | 220kV Busbar Protection Panels | Diagram | 220/33 kV Plant Main Substation - 220kV Busbar Protection Panels - Diagram | 2026-08-19 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0007 | A | 6105AK125-6243-EDIA-0007 |  | 220/33 kV Plant Main Substation | 220kV Common Control Panel | Diagram | 220/33 kV Plant Main Substation - 220kV Common Control Panel - Diagram | 2026-05-19 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0008 | A | 6105AK125-6243-EDIA-0008 |  | 220/33 kV Plant Main Substation | Energy Metering Panels | Diagram | 220/33 kV Plant Main Substation - Energy Metering Panels - Diagram | 2026-08-19 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0009 | A | 6105AK125-6243-EDIA-0009 |  | 220/33 kV Plant Main Substation | 220kV Transformer LCC Panels | Diagram | 220/33 kV Plant Main Substation - 220kV Transformer LCC Panels - Diagram | 2026-06-05 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0010 | A | 6105AK125-6243-EDIA-0010 |  | 220/33 kV Plant Main Substation | 220kV Line LCC Panels | Diagram | 220/33 kV Plant Main Substation - 220kV Line LCC Panels - Diagram | 2026-07-07 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0011 | A | 6105AK125-6243-EDIA-0011 |  | 220/33 kV Plant Main Substation | Network Switch Panel | Diagram | 220/33 kV Plant Main Substation - Network Switch Panel - Diagram | 2026-09-03 |  |  |  | 0%
6105A | K125 | 6243 | E | CAL | 0008 | A | 6105AK125-6243-ECAL-0008 |  | 220/33 kV Plant Main Substation | 220kV CT VT MK | Calculation | 220/33 kV Plant Main Substation - 220kV CT VT MK - Calculation | 2026-10-01 |  |  |  | 0%
6105A | K125 | 6243 | E | CAL | 0009 | A | 6105AK125-6243-ECAL-0009 |  | 220/33 kV Plant Main Substation | 220kV Relay Settings | Calculation | 220/33 kV Plant Main Substation - 220kV Relay Settings - Calculation |  |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0001 | 0 | 6105AK125-6243-EDST-0001 |  | 220/33 kV Plant Main Substation | Power Transformer Technical | Data Sheet | 220/33 kV Plant Main Substation - Power Transformer Technical - Data Sheet | 2026-02-10 | 2026-03-05 | 2026-04-23 | Reviewed | 66%
6105A | K125 | 6243 | E | LAY | 0008 | 0 | 6105AK125-6243-ELAY-0008 |  | 220/33 kV Plant Main Substation | Power Transformer Dimensional | Layout | 220/33 kV Plant Main Substation - Power Transformer Dimensional - Layout | 2026-03-31 | 2026-04-30 | 2026-05-05 | Approved | 100%
6105A | K125 | 6243 | E | ITP | 0001 | A | 6105AK125-6243-EITP-0001 |  | 220/33 kV Plant Main Substation | Power Transformer Inspection and Test | Plan | 220/33 kV Plant Main Substation - Power Transformer Inspection and Test - Plan | 2026-11-01 |  |  |  | 0%
6105A | K125 | 6243 | E | RPT | 0001 | A | 6105AK125-6243-ERPT-0001 |  | 220/33 kV Plant Main Substation | Power Transformer (Lot - 1) Factory Acceptance Test | Report | 220/33 kV Plant Main Substation - Power Transformer (Lot - 1) Factory Acceptance Test - Report | 2027-01-06 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0012 | 0 | 6105AK125-6243-EDIA-0012 |  | 220/33 kV Plant Main Substation | Power Transformer Motor Drive Unit Circuit | Diagram | 220/33 kV Plant Main Substation - Power Transformer Motor Drive Unit Circuit - Diagram | 2026-05-01 | 2026-05-20 | 2026-05-21 | Approved | 100%
6105A | K125 | 6243 | E | DIA | 0028 | 0 | 6105AK125-6243-EDIA-0028 |  | 220/33 kV Plant Main Substation | Power Transformer Local Control Cubicle Schematic | Diagram | 220/33 kV Plant Main Substation - Power Transformer Local Control Cubicle Schematic - Diagram | - | 2026-05-20 | 2026-06-02 | Approved
6105A | K125 | 6243 | E | DIA | 0013 | A | 6105AK125-6243-EDIA-0013 |  | 220/33 kV Plant Main Substation | Power Transformer AVR/RTCC Schematics | Diagram | 220/33 kV Plant Main Substation - Power Transformer AVR/RTCC Schematics - Diagram | 2026-05-01 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0002 | A | 6105AK125-6243-EDST-0002 |  | 220/33 kV Plant Main Substation | Earthing Tranformer Technical | Data Sheet | 220/33 kV Plant Main Substation - Earthing Tranformer Technical - Data Sheet | 2026-05-27 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0014 | A | 6105AK125-6243-EDIA-0014 |  | 220/33 kV Plant Main Substation | Earthing Transformer Dimensional | Diagram | 220/33 kV Plant Main Substation - Earthing Transformer Dimensional - Diagram | 2026-05-27 |  |  |  | 0%
6105A | K125 | 6243 | E | ITP | 0002 | A | 6105AK125-6243-EITP-0002 |  | 220/33 kV Plant Main Substation | Earthing Transformer Inspection and Test | Plan | 220/33 kV Plant Main Substation - Earthing Transformer Inspection and Test - Plan | 2026-11-01 |  |  |  | 0%
6105A | K125 | 6243 | E | RPT | 0002 | A | 6105AK125-6243-ERPT-0002 |  | 220/33 kV Plant Main Substation | Earthing Transformer Routine Test | Report | 220/33 kV Plant Main Substation - Earthing Transformer Routine Test - Report | 2027-01-31 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0003 | A | 6105AK125-6243-EDST-0003 |  | 220/33 kV Plant Main Substation | NGR Technical | Data Sheet | 220/33 kV Plant Main Substation - NGR Technical - Data Sheet | 2026-05-27 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0015 | A | 6105AK125-6243-EDIA-0015 |  | 220/33 kV Plant Main Substation | NGR Dimensional | Diagram | 220/33 kV Plant Main Substation - NGR Dimensional - Diagram | 2026-05-27 |  |  |  | 0%
6105A | K125 | 6243 | E | ITP | 0003 | A | 6105AK125-6243-EITP-0003 |  | 220/33 kV Plant Main Substation | NGR Inspection and Test | Plan | 220/33 kV Plant Main Substation - NGR Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6243 | E | RPT | 0003 | A | 6105AK125-6243-ERPT-0003 |  | 220/33 kV Plant Main Substation | NGR Routine Test | Report | 220/33 kV Plant Main Substation - NGR Routine Test - Report | 2026-11-20 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0004 | 0 | 6105AK125-6243-EDST-0004 |  | 220/33 kV Plant Main Substation | 220kV Surge Arrester Technical | Data Sheet | 220/33 kV Plant Main Substation - 220kV Surge Arrester Technical - Data Sheet | 2026-04-22 | 2026-04-22 | 2026-05-08 | Approved | 100%
6105A | K125 | 6243 | E | DIA | 0016 | 0 | 6105AK125-6243-EDIA-0016 |  | 220/33 kV Plant Main Substation | 220kV Surge Arrester Dimensional | Diagram | 220/33 kV Plant Main Substation - 220kV Surge Arrester Dimensional - Diagram | 2026-04-22 | 2026-05-05 | 2026-05-07 | Approved | 100%
6105A | K125 | 6243 | E | ITP | 0004 | A | 6105AK125-6243-EITP-0004 |  | 220/33 kV Plant Main Substation | 220kV Surge Arrester Inspection and Test | Plan | 220/33 kV Plant Main Substation - 220kV Surge Arrester Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6243 | E | RPT | 0004 | A | 6105AK125-6243-ERPT-0004 |  | 220/33 kV Plant Main Substation | 220kV Surge Arrester FAT | Report | 220/33 kV Plant Main Substation - 220kV Surge Arrester FAT - Report | 2026-11-12 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0005 | 0 | 6105AK125-6243-EDST-0005 |  | 220/33 kV Plant Main Substation | 220kV Circuit Breaker Technical | Data Sheet | 220/33 kV Plant Main Substation - 220kV Circuit Breaker Technical - Data Sheet | 2026-03-30 | 2026-03-24 | 2026-04-30 | Approved | 100%
6105A | K125 | 6243 | E | DIA | 0017 | 0 | 6105AK125-6243-EDIA-0017 |  | 220/33 kV Plant Main Substation | 220kV Circuit Breaker Schematic | Diagram | 220/33 kV Plant Main Substation - 220kV Circuit Breaker Schematic - Diagram | 2026-03-30 | 2026-03-31 | 2026-04-30 | Approved | 100%
6105A | K125 | 6243 | E | ITP | 0005 | A | 6105AK125-6243-EITP-0005 |  | 220/33 kV Plant Main Substation | 220kV Circuit Breaker Inspection and Test | Plan | 220/33 kV Plant Main Substation - 220kV Circuit Breaker Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6243 | E | RPT | 0005 | A | 6105AK125-6243-ERPT-0005 |  | 220/33 kV Plant Main Substation | 220kV Circuit Breaker FAT | Report | 220/33 kV Plant Main Substation - 220kV Circuit Breaker FAT - Report | 2026-11-15 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0006 | 0 | 6105AK125-6243-EDST-0006 |  | 220/33 kV Plant Main Substation | Isolator / Disconnector Technical | Data Sheet | 220/33 kV Plant Main Substation - Isolator / Disconnector Technical - Data Sheet | 2026-03-30 | 2026-03-24 | 2026-04-23 | Approved | 100%
6105A | K125 | 6243 | E | DIA | 0018 | 0 | 6105AK125-6243-EDIA-0018 |  | 220/33 kV Plant Main Substation | 220kV Isolator / Disconnector Schematic (Drive Disconnector) | Diagram | 220/33 kV Plant Main Substation - 220kV Isolator / Disconnector Schematic (Drive Disconnector) - Diagram | 2026-03-30 | 2026-03-31 | 2026-04-23 | Approved | 100%
6105A | K125 | 6243 | E | DIA | 0019 | 0 | 6105AK125-6243-EDIA-0019 |  | 220/33 kV Plant Main Substation | 220kV Isolator / Disconnector Schematic (Drive Earthing Switch) | Diagram | 220/33 kV Plant Main Substation - 220kV Isolator / Disconnector Schematic (Drive Earthing Switch) - Diagram | 2026-03-30 | 2026-03-31 | 2026-04-23 | Approved | 100%
6105A | K125 | 6243 | E | ITP | 0006 | A | 6105AK125-6243-EITP-0006 |  | 220/33 kV Plant Main Substation | Isolator / Disconnector Inspection and Test | Plan | 220/33 kV Plant Main Substation - Isolator / Disconnector Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6243 | E | RPT | 0006 | A | 6105AK125-6243-ERPT-0006 |  | 220/33 kV Plant Main Substation | Isolator / Disconnector FAT | Report | 220/33 kV Plant Main Substation - Isolator / Disconnector FAT - Report | 2026-11-15 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0020 | 0 | 6105AK125-6243-EDIA-0020 |  | 220/33 kV Plant Main Substation | 220kV Circuit Breaker Outline | Diagram | 220/33 kV Plant Main Substation - 220kV Circuit Breaker Outline - Diagram | - | 2026-04-02 | 2026-05-04 | Reviewed | 66%
6105A | K125 | 6243 | E | DIA | 0021 | 0 | 6105AK125-6243-EDIA-0021 |  | 220/33 kV Plant Main Substation | 220kV Isolator / Disconnector Outline | Diagram | 220/33 kV Plant Main Substation - 220kV Isolator / Disconnector Outline - Diagram | - | 2026-04-07 | 2026-04-23 | Approved | 100%
6105A | K125 | 6243 | E | DST | 0007 | 0 | 6105AK125-6243-EDST-0007 |  | 220/33 kV Plant Main Substation | Instrument Transformer (CT) Technical | Data Sheet | 220/33 kV Plant Main Substation - Instrument Transformer (CT) Technical - Data Sheet | 2026-03-25 | 2026-05-21 | 2026-06-01 | Approved | 100%
6105A | K125 | 6243 | E | LAY | 0009 | 0 | 6105AK125-6243-ELAY-0009 |  | 220/33 kV Plant Main Substation | Instrument Transformer (CT) Dimentional | Layout | 220/33 kV Plant Main Substation - Instrument Transformer (CT) Dimentional - Layout | 2026-03-25 | 2026-06-05 | 2026-06-08 | Approved | 100%
6105A | K125 | 6243 | E | RPT | 0007 | A | 6105AK125-6243-ERPT-0007 |  | 220/33 kV Plant Main Substation | Instrument Transformer (CT) FAT | Report | 220/33 kV Plant Main Substation - Instrument Transformer (CT) FAT - Report | 2026-11-15 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0008 | 0 | 6105AK125-6243-EDST-0008 |  | 220/33 kV Plant Main Substation | Instrument Transformer (VT) Technical | Data Sheet | 220/33 kV Plant Main Substation - Instrument Transformer (VT) Technical - Data Sheet | 2026-03-25 | 2026-05-08 | 2026-05-13 | Approved | 100%
6105A | K125 | 6243 | E | LAY | 0010 | 0 | 6105AK125-6243-ELAY-0010 |  | 220/33 kV Plant Main Substation | Instrument Transformer (VT) Dimentional | Layout | 220/33 kV Plant Main Substation - Instrument Transformer (VT) Dimentional - Layout | 2026-03-25 | 2026-06-05 | 2026-06-08 | Approved | 100%
6105A | K125 | 6243 | E | RPT | 0008 | A | 6105AK125-6243-ERPT-0008 |  | 220/33 kV Plant Main Substation | Instrument Transformer (VT) FAT | Report | 220/33 kV Plant Main Substation - Instrument Transformer (VT) FAT - Report | 2026-11-15 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0009 | A | 6105AK125-6243-EDST-0009 |  | 220/33 kV Plant Main Substation | AC Panel Technical | Data Sheet | 220/33 kV Plant Main Substation - AC Panel Technical - Data Sheet | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0022 | A | 6105AK125-6243-EDIA-0022 |  | 220/33 kV Plant Main Substation | AC Panel Schematics | Diagram | 220/33 kV Plant Main Substation - AC Panel Schematics - Diagram | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6243 | E | RPT | 0009 | A | 6105AK125-6243-ERPT-0009 |  | 220/33 kV Plant Main Substation | AC Panel FAT | Report | 220/33 kV Plant Main Substation - AC Panel FAT - Report | 2026-11-30 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0010 | A | 6105AK125-6243-EDST-0010 |  | 220/33 kV Plant Main Substation | DC Panel Technical | Data Sheet | 220/33 kV Plant Main Substation - DC Panel Technical - Data Sheet | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0023 | A | 6105AK125-6243-EDIA-0023 |  | 220/33 kV Plant Main Substation | DC Panel Schematics | Diagram | 220/33 kV Plant Main Substation - DC Panel Schematics - Diagram | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6243 | E | RPT | 0010 | A | 6105AK125-6243-ERPT-0010 |  | 220/33 kV Plant Main Substation | DC Panel FAT | Report | 220/33 kV Plant Main Substation - DC Panel FAT - Report | 2026-11-30 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0011 | A | 6105AK125-6243-EDST-0011 |  | 220/33 kV Plant Main Substation | Battery Bank Technical | Data Sheet | 220/33 kV Plant Main Substation - Battery Bank Technical - Data Sheet | 2026-04-20 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0024 | A | 6105AK125-6243-EDIA-0024 |  | 220/33 kV Plant Main Substation | Battery Bank (Connection/Fuse Box) | Diagram | 220/33 kV Plant Main Substation - Battery Bank (Connection/Fuse Box) - Diagram | 2026-04-20 |  |  |  | 0%
6105A | K125 | 6243 | E | SPC | 0001 | A | 6105AK125-6243-ESPC-0001 |  | 220/33 kV Plant Main Substation | Battery Bank Details / Rack Design | Specification | 220/33 kV Plant Main Substation - Battery Bank Details / Rack Design - Specification | 2026-04-20 |  |  |  | 0%
6105A | K125 | 6243 | E | ITP | 0007 | A | 6105AK125-6243-EITP-0007 |  | 220/33 kV Plant Main Substation | Battery Bank Inspection and Test | Plan | 220/33 kV Plant Main Substation - Battery Bank Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6243 | E | RPT | 0011 | A | 6105AK125-6243-ERPT-0011 |  | 220/33 kV Plant Main Substation | Battery Bank FAT | Report | 220/33 kV Plant Main Substation - Battery Bank FAT - Report | 2026-11-05 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0012 | A | 6105AK125-6243-EDST-0012 |  | 220/33 kV Plant Main Substation | Battery Charger Technical | Data Sheet | 220/33 kV Plant Main Substation - Battery Charger Technical - Data Sheet | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0025 | A | 6105AK125-6243-EDIA-0025 |  | 220/33 kV Plant Main Substation | Battery Charger Schematic | Diagram | 220/33 kV Plant Main Substation - Battery Charger Schematic - Diagram | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6243 | E | ITP | 0008 | A | 6105AK125-6243-EITP-0008 |  | 220/33 kV Plant Main Substation | Battery Charger Inspection and Test | Plan | 220/33 kV Plant Main Substation - Battery Charger Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6243 | E | RPT | 0012 | A | 6105AK125-6243-ERPT-0012 |  | 220/33 kV Plant Main Substation | Battery Charger FAT | Report | 220/33 kV Plant Main Substation - Battery Charger FAT - Report | 2026-11-16 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0013 | A | 6105AK125-6243-EDST-0013 |  | 220/33 kV Plant Main Substation | Inverter Technical | Data Sheet | 220/33 kV Plant Main Substation - Inverter Technical - Data Sheet | 2026-04-20 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0014 | A | 6105AK125-6243-EDST-0014 |  | 220/33 kV Plant Main Substation | Post Insulator Technical | Data Sheet | 220/33 kV Plant Main Substation - Post Insulator Technical - Data Sheet | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6243 | E | LAY | 0011 | A | 6105AK125-6243-ELAY-0011 |  | 220/33 kV Plant Main Substation | Post Insulator Outline & Dimentional | Layout | 220/33 kV Plant Main Substation - Post Insulator Outline & Dimentional - Layout | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6243 | E | RPT | 0013 | A | 6105AK125-6243-ERPT-0013 |  | 220/33 kV Plant Main Substation | Post Insulator FAT | Report | 220/33 kV Plant Main Substation - Post Insulator FAT - Report | 2027-01-15 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0015 | A | 6105AK125-6243-EDST-0015 |  | 220/33 kV Plant Main Substation | Disc Insulator Technical | Data Sheet | 220/33 kV Plant Main Substation - Disc Insulator Technical - Data Sheet | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6243 | E | LAY | 0012 | A | 6105AK125-6243-ELAY-0012 |  | 220/33 kV Plant Main Substation | Disc Insulator Outline & Dimentional | Layout | 220/33 kV Plant Main Substation - Disc Insulator Outline & Dimentional - Layout | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6243 | E | RPT | 0014 | A | 6105AK125-6243-ERPT-0014 |  | 220/33 kV Plant Main Substation | Disc Insulator FAT | Report | 220/33 kV Plant Main Substation - Disc Insulator FAT - Report | 2027-01-15 |  |  |  | 0%
6105A | K125 | 6243 | E | SSD | 0001 | A | 6105AK125-6243-ESSD-0001 |  | 220/33 kV Plant Main Substation | Steel Structure | Drawing | 220/33 kV Plant Main Substation - Steel Structure - Drawing | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6243 | E | SPC | 0002 | A | 6105AK125-6243-ESPC-0002 |  | 220/33 kV Plant Main Substation | Termination Kit Outdoor Termination & Joints | Specification | 220/33 kV Plant Main Substation - Termination Kit Outdoor Termination & Joints - Specification | 2026-10-21 |  |  |  | 0%
6105A | K125 | 6243 | E | DST | 0016 | A | 6105AK125-6243-EDST-0016 |  | 220/33 kV Plant Main Substation | Cables & Conductors Technical | Data Sheet | 220/33 kV Plant Main Substation - Cables & Conductors Technical - Data Sheet | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6243 | E | SPC | 0003 | A | 6105AK125-6243-ESPC-0003 |  | 220/33 kV Plant Main Substation | Grounding Technical Documentation | Specification | 220/33 kV Plant Main Substation - Grounding Technical Documentation - Specification | 2026-09-24 |  |  |  | 0%
6105A | K125 | 6243 | E | SPC | 0004 | A | 6105AK125-6243-ESPC-0004 |  | 220/33 kV Plant Main Substation | Hardware & Connector Technical Documentation | Specification | 220/33 kV Plant Main Substation - Hardware & Connector Technical Documentation - Specification | 2026-07-24 |  |  |  | 0%
6105A | K125 | 6243 | E | DIA | 0027 | 0 | 6105AK125-6243-EDIA-0027 |  | 220/33 kV Plant Main Substation | Surge Monitor for 220kV Surge Arrester | Diagram | 220/33 kV Plant Main Substation - Surge Monitor for 220kV Surge Arrester - Diagram | - | 2026-05-12 | 2026-05-15 | Approved | 100%
6105A | K125 | 6243 | C | DBD | 0001 | 0 | 6105AK125-6243-CDBD-0001 |  | 220/33 kV Plant Main Substation | Civil | Design Basis and Criteria | 220/33 kV Plant Main Substation - Civil - Design Basis and Criteria | 2026-04-15 | 2026-04-24 | 2026-05-08 | Approved | 100%
6105A | K125 | 6243 | C | FND | 0001 | A | 6105AK125-6243-CFND-0001 |  | 220/33 kV Plant Main Substation | Power Transformer Foundation | Plan | 220/33 kV Plant Main Substation - Power Transformer Foundation - Plan | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0001 | A | 6105AK125-6243-CDTL-0001 |  | 220/33 kV Plant Main Substation | Power Transformer Concrete Outline Plan and | Details | 220/33 kV Plant Main Substation - Power Transformer Concrete Outline Plan and - Details | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0002 | A | 6105AK125-6243-CDTL-0002 |  | 220/33 kV Plant Main Substation | Power Transformer Reinforcement Plan and | Details | 220/33 kV Plant Main Substation - Power Transformer Reinforcement Plan and - Details | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0003 | A | 6105AK125-6243-CDTL-0003 |  | 220/33 kV Plant Main Substation | Power Transformer Gravel & Grating | Details | 220/33 kV Plant Main Substation - Power Transformer Gravel & Grating - Details | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6243 | C | RPT | 0001 | A | 6105AK125-6243-CRPT-0001 |  | 220/33 kV Plant Main Substation | Power Transformer Design | Report | 220/33 kV Plant Main Substation - Power Transformer Design - Report | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6243 | C | PLN | 0001 | A | 6105AK125-6243-CPLN-0001 |  | 220/33 kV Plant Main Substation | Fire Wall Foundation | Plan | 220/33 kV Plant Main Substation - Fire Wall Foundation - Plan | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0004 | A | 6105AK125-6243-CDTL-0004 |  | 220/33 kV Plant Main Substation | Fire Wall Concrete Outline Plan and | Details | 220/33 kV Plant Main Substation - Fire Wall Concrete Outline Plan and - Details | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0005 | A | 6105AK125-6243-CDTL-0005 |  | 220/33 kV Plant Main Substation | Fire Wall Reinforcement Plan and | Details | 220/33 kV Plant Main Substation - Fire Wall Reinforcement Plan and - Details | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6243 | C | RPT | 0002 | A | 6105AK125-6243-CRPT-0002 |  | 220/33 kV Plant Main Substation | Fire Wall Design | Report | 220/33 kV Plant Main Substation - Fire Wall Design - Report | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6243 | C | PLN | 0002 | A | 6105AK125-6243-CPLN-0002 |  | 220/33 kV Plant Main Substation | 220 kV Ganrty Foundation Layout | Plan | 220/33 kV Plant Main Substation - 220 kV Ganrty Foundation Layout - Plan | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0006 | A | 6105AK125-6243-CDTL-0006 |  | 220/33 kV Plant Main Substation | 220 kV Ganrty Foundation Concrete Outline Plan and | Details | 220/33 kV Plant Main Substation - 220 kV Ganrty Foundation Concrete Outline Plan and - Details | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0007 | A | 6105AK125-6243-CDTL-0007 |  | 220/33 kV Plant Main Substation | 220 kV Ganrty Foundation Reinforcement Plan and | Details | 220/33 kV Plant Main Substation - 220 kV Ganrty Foundation Reinforcement Plan and - Details | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6243 | C | RPT | 0003 | A | 6105AK125-6243-CRPT-0003 |  | 220/33 kV Plant Main Substation | 220 kV Ganrty Foundation Design | Report | 220/33 kV Plant Main Substation - 220 kV Ganrty Foundation Design - Report | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6243 | C | PLN | 0003 | A | 6105AK125-6243-CPLN-0003 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Foundation Layout | Plan | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Foundation Layout - Plan | 2026-07-08 |  |  |  | 0%
6105A | K125 | 6243 | C | FND | 0002 | A | 6105AK125-6243-CFND-0002 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details Surge Arrester | Foundation | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details Surge Arrester - Foundation | 2026-08-10 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0008 | A | 6105AK125-6243-CDTL-0008 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Surge Arrester Foundation Reinforcement Plan and | Details | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Surge Arrester Foundation Reinforcement Plan and - Details | 2026-08-10 |  |  |  | 0%
6105A | K125 | 6243 | C | RPT | 0004 | A | 6105AK125-6243-CRPT-0004 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Surge Arrester Foundation Design | Report | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Surge Arrester Foundation Design - Report | 2026-08-10 |  |  |  | 0%
6105A | K125 | 6243 | C | FND | 0003 | A | 6105AK125-6243-CFND-0003 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details DS+ES | Foundation | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details DS+ES - Foundation | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0009 | A | 6105AK125-6243-CDTL-0009 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment DS+ES Foundation Reinforcement Plan and | Details | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment DS+ES Foundation Reinforcement Plan and - Details | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6243 | C | RPT | 0005 | A | 6105AK125-6243-CRPT-0005 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment DS+ES Foundation Design | Report | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment DS+ES Foundation Design - Report | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6243 | C | FND | 0004 | A | 6105AK125-6243-CFND-0004 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details Current Transformer | Foundation | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details Current Transformer - Foundation | 2026-08-01 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0010 | A | 6105AK125-6243-CDTL-0010 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Current Transformer Foundation Reinforcement Plan and | Details | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Current Transformer Foundation Reinforcement Plan and - Details | 2026-08-01 |  |  |  | 0%
6105A | K125 | 6243 | C | RPT | 0006 | A | 6105AK125-6243-CRPT-0006 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Current Transformer Foundation Design | Report | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Current Transformer Foundation Design - Report | 2026-08-01 |  |  |  | 0%
6105A | K125 | 6243 | C | FND | 0005 | A | 6105AK125-6243-CFND-0005 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details Circuit Breaker | Foundation | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details Circuit Breaker - Foundation | 2026-07-25 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0011 | A | 6105AK125-6243-CDTL-0011 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Circuit Breaker Foundation Reinforcement Plan and | Details | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Circuit Breaker Foundation Reinforcement Plan and - Details | 2026-07-25 |  |  |  | 0%
6105A | K125 | 6243 | C | RPT | 0007 | A | 6105AK125-6243-CRPT-0007 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Circuit Breaker Foundation Design | Report | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Circuit Breaker Foundation Design - Report | 2026-07-25 |  |  |  | 0%
6105A | K125 | 6243 | C | FND | 0006 | A | 6105AK125-6243-CFND-0006 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details Voltage Transformer | Foundation | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details Voltage Transformer - Foundation | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0012 | A | 6105AK125-6243-CDTL-0012 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Voltage Transformer Foundation Reinforcement Plan and | Details | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Voltage Transformer Foundation Reinforcement Plan and - Details | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6243 | C | RPT | 0008 | A | 6105AK125-6243-CRPT-0008 |  | 220/33 kV Plant Main Substation | 220 kV Switchyard Equipment Voltage Transformer Foundation Design | Report | 220/33 kV Plant Main Substation - 220 kV Switchyard Equipment Voltage Transformer Foundation Design - Report | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6243 | C | PLN | 0004 | A | 6105AK125-6243-CPLN-0004 |  | 220/33 kV Plant Main Substation | Switchyard Trenches Layout | Plan | 220/33 kV Plant Main Substation - Switchyard Trenches Layout - Plan | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6243 | C | SEC | 0001 | A | 6105AK125-6243-CSEC-0001 |  | 220/33 kV Plant Main Substation | Switchyard Trenches Concrete Outline Section and Trench Covers | Section | 220/33 kV Plant Main Substation - Switchyard Trenches Concrete Outline Section and Trench Covers - Section | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6243 | C | SEC | 0002 | A | 6105AK125-6243-CSEC-0002 |  | 220/33 kV Plant Main Substation | Switchyard Trenches Reinforcement Section and Trench Covers | Section | 220/33 kV Plant Main Substation - Switchyard Trenches Reinforcement Section and Trench Covers - Section | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6243 | C | SEC | 0003 | A | 6105AK125-6243-CSEC-0003 |  | 220/33 kV Plant Main Substation | Switchyard Trenches Draw Pit Concrete Outline | Section | 220/33 kV Plant Main Substation - Switchyard Trenches Draw Pit Concrete Outline - Section | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0013 | A | 6105AK125-6243-CDTL-0013 |  | 220/33 kV Plant Main Substation | Switchyard Trenches Draw Pit Reinforcement Plan and | Details | 220/33 kV Plant Main Substation - Switchyard Trenches Draw Pit Reinforcement Plan and - Details | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6243 | C | RPT | 0009 | A | 6105AK125-6243-CRPT-0009 |  | 220/33 kV Plant Main Substation | Switchyard Trenches Design | Report | 220/33 kV Plant Main Substation - Switchyard Trenches Design - Report | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0014 | A | 6105AK125-6243-CDTL-0014 |  | 220/33 kV Plant Main Substation | Switchyard Trenches Duct bank | Details | 220/33 kV Plant Main Substation - Switchyard Trenches Duct bank - Details | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6243 | W | PLN | 0001 | A | 6105AK125-6243-WPLN-0001 |  | 220/33 kV Plant Main Substation | Road Layout | Plan | 220/33 kV Plant Main Substation - Road Layout - Plan | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6243 | W | SEC | 0001 | A | 6105AK125-6243-WSEC-0001 |  | 220/33 kV Plant Main Substation | Road Concrete Outline | Section | 220/33 kV Plant Main Substation - Road Concrete Outline - Section | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6243 | W | SEC | 0002 | A | 6105AK125-6243-WSEC-0002 |  | 220/33 kV Plant Main Substation | Road Reinforcement | Section | 220/33 kV Plant Main Substation - Road Reinforcement - Section | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6243 | W | PLN | 0002 | A | 6105AK125-6243-WPLN-0002 |  | 220/33 kV Plant Main Substation | Surface Drainage Layout | Plan | 220/33 kV Plant Main Substation - Surface Drainage Layout - Plan | 2026-09-02 |  |  |  | 0%
6105A | K125 | 6243 | W | DTL | 0001 | A | 6105AK125-6243-WDTL-0001 |  | 220/33 kV Plant Main Substation | Surface Drainage Main Hole | Details | 220/33 kV Plant Main Substation - Surface Drainage Main Hole - Details | 2026-09-02 |  |  |  | 0%
6105A | K125 | 6243 | W | DTL | 0002 | A | 6105AK125-6243-WDTL-0002 |  | 220/33 kV Plant Main Substation | Surface Drainage Pipe Laying | Details | 220/33 kV Plant Main Substation - Surface Drainage Pipe Laying - Details | 2026-09-02 |  |  |  | 0%
6105A | K125 | 6243 | W | RPT | 0001 | A | 6105AK125-6243-WRPT-0001 |  | 220/33 kV Plant Main Substation | Surface Drainage Design | Report | 220/33 kV Plant Main Substation - Surface Drainage Design - Report | 2026-09-02 |  |  |  | 0%
6105A | K125 | 6243 | W | PLN | 0003 | A | 6105AK125-6243-WPLN-0003 |  | 220/33 kV Plant Main Substation | Fence Wall Layout | Plan | 220/33 kV Plant Main Substation - Fence Wall Layout - Plan | 2026-09-23 |  |  |  | 0%
6105A | K125 | 6243 | W | DTL | 0003 | A | 6105AK125-6243-WDTL-0003 |  | 220/33 kV Plant Main Substation | Fence Wall Foundation Plan and | Details | 220/33 kV Plant Main Substation - Fence Wall Foundation Plan and - Details | 2026-09-23 |  |  |  | 0%
6105A | K125 | 6243 | W | DTL | 0004 | A | 6105AK125-6243-WDTL-0004 |  | 220/33 kV Plant Main Substation | Fence Wall Fence Section Plan and | Details | 220/33 kV Plant Main Substation - Fence Wall Fence Section Plan and - Details | 2026-09-23 |  |  |  | 0%
6105A | K125 | 6243 | W | SEC | 0003 | A | 6105AK125-6243-WSEC-0003 |  | 220/33 kV Plant Main Substation | Fence Wall Gate Plan and | Section | 220/33 kV Plant Main Substation - Fence Wall Gate Plan and - Section | 2026-09-23 |  |  |  | 0%
6105A | K125 | 6243 | C | PLN | 0005 | A | 6105AK125-6243-CPLN-0005 |  | 220/33 kV Plant Main Substation | E-House Foundation Concrete Outline | Plan | 220/33 kV Plant Main Substation - E-House Foundation Concrete Outline - Plan | 2026-07-24 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0015 | A | 6105AK125-6243-CDTL-0015 |  | 220/33 kV Plant Main Substation | E-House Foundation Reinforcement Plan and | Details | 220/33 kV Plant Main Substation - E-House Foundation Reinforcement Plan and - Details | 2026-07-24 |  |  |  | 0%
6105A | K125 | 6243 | C | RPT | 0010 | A | 6105AK125-6243-CRPT-0010 |  | 220/33 kV Plant Main Substation | E-House Foundation Design | Report | 220/33 kV Plant Main Substation - E-House Foundation Design - Report | 2026-07-24 |  |  |  | 0%
6105A | K125 | 6243 | C | PLN | 0006 | A | 6105AK125-6243-CPLN-0006 |  | 220/33 kV Plant Main Substation | NGR & ET Foundation Concrete Outline | Plan | 220/33 kV Plant Main Substation - NGR & ET Foundation Concrete Outline - Plan | 2026-06-19 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0016 | A | 6105AK125-6243-CDTL-0016 |  | 220/33 kV Plant Main Substation | NGR & ET Foundation Reinforcement Plan and | Details | 220/33 kV Plant Main Substation - NGR & ET Foundation Reinforcement Plan and - Details | 2026-06-19 |  |  |  | 0%
6105A | K125 | 6243 | C | RPT | 0011 | A | 6105AK125-6243-CRPT-0011 |  | 220/33 kV Plant Main Substation | NGR & ET Foundation Design | Report | 220/33 kV Plant Main Substation - NGR & ET Foundation Design - Report | 2026-06-19 |  |  |  | 0%
6105A | K125 | 6243 | C | PLN | 0007 | A | 6105AK125-6243-CPLN-0007 |  | 220/33 kV Plant Main Substation | Transformer - Way Concrete Outline | Plan | 220/33 kV Plant Main Substation - Transformer - Way Concrete Outline - Plan | 2026-07-22 |  |  |  | 0%
6105A | K125 | 6243 | C | PLN | 0008 | A | 6105AK125-6243-CPLN-0008 |  | 220/33 kV Plant Main Substation | Light Pole Foundation Layout | Plan | 220/33 kV Plant Main Substation - Light Pole Foundation Layout - Plan | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0017 | A | 6105AK125-6243-CDTL-0017 |  | 220/33 kV Plant Main Substation | Light Pole Foundation Concrete Outline & Reinforcement | Details | 220/33 kV Plant Main Substation - Light Pole Foundation Concrete Outline & Reinforcement - Details | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6243 | C | RPT | 0012 | A | 6105AK125-6243-CRPT-0012 |  | 220/33 kV Plant Main Substation | Light Pole Foundation Design | RPT | 220/33 kV Plant Main Substation - Light Pole Foundation Design - RPT | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6243 | W | PLN | 0004 | A | 6105AK125-6243-WPLN-0004 |  | 220/33 kV Plant Main Substation | Gravel Layout | Plan | 220/33 kV Plant Main Substation - Gravel Layout - Plan | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6243 | C | PLN | 0009 | B | 6105AK125-6243-CPLN-0009 |  | 220/33 kV Plant Main Substation | Site Grading | Plan | 220/33 kV Plant Main Substation - Site Grading - Plan | - | 2026-04-14 |  | Reviewed | 33%
6105A | K125 | 6243 | C | LST | 0001 | A | 6105AK125-6243-CLST-0001 |  | 220/33 kV Plant Main Substation | Drawings, Legends, Notes | List | 220/33 kV Plant Main Substation - Drawings, Legends, Notes - List | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6243 | C | DIA | 0001 | A | 6105AK125-6243-CDIA-0001 |  | 220/33 kV Plant Main Substation | Distribution Board | Single Line Diagram | 220/33 kV Plant Main Substation - Distribution Board - Single Line Diagram | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6243 | C | LAY | 0001 | A | 6105AK125-6243-CLAY-0001 |  | 220/33 kV Plant Main Substation | Outdoor Switchyard Lighting and Small Power Layout | Layout | 220/33 kV Plant Main Substation - Outdoor Switchyard Lighting and Small Power Layout - Layout | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6243 | C | LAY | 0002 | A | 6105AK125-6243-CLAY-0002 |  | 220/33 kV Plant Main Substation | Outdoor switchyard Lighting and Small Power Cable Route | Layout | 220/33 kV Plant Main Substation - Outdoor switchyard Lighting and Small Power Cable Route - Layout | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6243 | C | DTL | 0018 | A | 6105AK125-6243-CDTL-0018 |  | 220/33 kV Plant Main Substation | Installation Detail for Outdoor Lighting and Small Power | Details | 220/33 kV Plant Main Substation - Installation Detail for Outdoor Lighting and Small Power - Details | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6243 | C | CAL | 0001 | A | 6105AK125-6243-CCAL-0001 |  | 220/33 kV Plant Main Substation | Outdoor Lighting Lux | Calculation | 220/33 kV Plant Main Substation - Outdoor Lighting Lux - Calculation | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6243 | C | SHP | 0001 | A | 6105AK125-6243-CSHP-0001 |  | 220/33 kV Plant Main Substation | Shop / Manufacturing Drawings of Distribution Boards | Shop Drawing | 220/33 kV Plant Main Substation - Shop / Manufacturing Drawings of Distribution Boards - Shop Drawing | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6241 | G | LAY | 0001 | 0 | 6105AK125-6241-GLAY-0001 | Sht. 1 of 1 | 33/220 kV Solar PV Substation | Site Office Arrangement | Layout | 33/220 kV Solar PV Substation - Site Office Arrangement - Layout | - | 2026-04-03 | 2026-05-19 | Approved | 100%
6105A | K125 | 6241 | E | SLD | 0001 | A | 6105AK125-6241-ESLD-0001 | Sht. 1 of 1 | 33/220 kV Solar PV Substation | Overall | Single Line Diagram | 33/220 kV Solar PV Substation - Overall - Single Line Diagram | 2026-02-04 | 2026-02-10 |  | Approved | 100% | 2026-06-08
6105A | K125 | 6241 | E | LAY | 0001 | A | 6105AK125-6241-ELAY-0001 |  | 33/220 kV Solar PV Substation | Equipment | Layout | 33/220 kV Solar PV Substation - Equipment - Layout | 2026-04-30 | 2026-02-13 |  | Reviewed | 33%
6105A | K125 | 6241 | E | LAY | 0002 | A | 6105AK125-6241-ELAY-0002 |  | 33/220 kV Solar PV Substation | E-House | Layout | 33/220 kV Solar PV Substation - E-House - Layout | 2026-06-11 |  |  |  | 0%
6105A | K125 | 6241 | E | LAY | 0003 | A | 6105AK125-6241-ELAY-0003 |  | 33/220 kV Solar PV Substation | Foundation and Trench | Layout | 33/220 kV Solar PV Substation - Foundation and Trench - Layout | 2026-06-17 |  |  |  | 0%
6105A | K125 | 6241 | E | LAY | 0004 | A | 6105AK125-6241-ELAY-0004 |  | 33/220 kV Solar PV Substation | Cable Tray | Layout | 33/220 kV Solar PV Substation - Cable Tray - Layout | 2026-07-29 |  |  |  | 0%
6105A | K125 | 6241 | E | LAY | 0005 | A | 6105AK125-6241-ELAY-0005 |  | 33/220 kV Solar PV Substation | Buried Earthing | Layout | 33/220 kV Solar PV Substation - Buried Earthing - Layout | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6241 | E | LAY | 0006 | A | 6105AK125-6241-ELAY-0006 |  | 33/220 kV Solar PV Substation | Indoor Earthing | Layout | 33/220 kV Solar PV Substation - Indoor Earthing - Layout | 2026-09-10 |  |  |  | 0%
6105A | K125 | 6241 | E | LAY | 0007 | A | 6105AK125-6241-ELAY-0007 |  | 33/220 kV Solar PV Substation | Lightning Protection | Layout | 33/220 kV Solar PV Substation - Lightning Protection - Layout | 2026-09-17 |  |  |  | 0%
6105A | K125 | 6241 | E | CAL | 0001 | A | 6105AK125-6241-ECAL-0001 |  | 33/220 kV Solar PV Substation | Earthing Design | Calculation | 33/220 kV Solar PV Substation - Earthing Design - Calculation | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6241 | E | CAL | 0002 | A | 6105AK125-6241-ECAL-0002 |  | 33/220 kV Solar PV Substation | Lightning Protection | Calculation | 33/220 kV Solar PV Substation - Lightning Protection - Calculation | 2026-09-17 |  |  |  | 0%
6105A | K125 | 6241 | E | CAL | 0003 | A | 6105AK125-6241-ECAL-0003 |  | 33/220 kV Solar PV Substation | LVAC Cable Sizing | Calculation | 33/220 kV Solar PV Substation - LVAC Cable Sizing - Calculation | 2026-07-13 |  |  |  | 0%
6105A | K125 | 6241 | E | CAL | 0004 | A | 6105AK125-6241-ECAL-0004 |  | 33/220 kV Solar PV Substation | LVDC Cable Sizing | Calculation | 33/220 kV Solar PV Substation - LVDC Cable Sizing - Calculation | 2026-07-13 |  |  |  | 0%
6105A | K125 | 6241 | E | CAL | 0005 | B | 6105AK125-6241-ECAL-0005 |  | 33/220 kV Solar PV Substation | MV Cable Sizing | Calculation | 33/220 kV Solar PV Substation - MV Cable Sizing - Calculation | 2026-06-12 | 2026-05-25 |  | Approved | 100%
6105A | K125 | 6241 | E | SLD | 0002 | A | 6105AK125-6241-ESLD-0002 |  | 33/220 kV Solar PV Substation | 220kV Protection Concept | Single Line Diagram | 33/220 kV Solar PV Substation - 220kV Protection Concept - Single Line Diagram | 2026-04-07 | 2026-03-17 |  | Reviewed | 33%
6105A | K125 | 6241 | E | LST | 0001 | A | 6105AK125-6241-ELST-0001 |  | 33/220 kV Solar PV Substation | 220kV Relay | List | 33/220 kV Solar PV Substation - 220kV Relay - List | 2026-02-19 | 2026-03-17 |  | Reviewed | 33%
6105A | K125 | 6241 | E | CAL | 0006 | A | 6105AK125-6241-ECAL-0006 |  | 33/220 kV Solar PV Substation | 220kV CT/VT Dimensioning | Calculation | 33/220 kV Solar PV Substation - 220kV CT/VT Dimensioning - Calculation | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0001 | B | 6105AK125-6241-EDIA-0001 |  | 33/220 kV Solar PV Substation | 220kV Protection Trip Logic | Diagram | 33/220 kV Solar PV Substation - 220kV Protection Trip Logic - Diagram | 2026-03-05 | 2026-04-17 |  | Approved | 100%
6105A | K125 | 6241 | E | DIA | 0002 | D | 6105AK125-6241-EDIA-0002 |  | 33/220 kV Solar PV Substation | 220kV Interlocking Logic | Diagram | 33/220 kV Solar PV Substation - 220kV Interlocking Logic - Diagram | 2026-06-12 | 2026-06-05 |  | Approved | 100%
6105A | K125 | 6241 | E | SLD | 0003 | A | 6105AK125-6241-ESLD-0003 |  | 33/220 kV Solar PV Substation | LVAC System | Single Line Diagram | 33/220 kV Solar PV Substation - LVAC System - Single Line Diagram | 2026-06-12 |  |  |  | 0%
6105A | K125 | 6241 | E | LST | 0002 | B | 6105AK125-6241-ELST-0002 |  | 33/220 kV Solar PV Substation | 220kV Signal | List | 33/220 kV Solar PV Substation - 220kV Signal - List | 2026-04-09 | 2026-04-17 |  | Approved | 100%
6105A | K125 | 6241 | E | SLD | 0004 | A | 6105AK125-6241-ESLD-0004 |  | 33/220 kV Solar PV Substation | 110V DC System | Single Line Diagram | 33/220 kV Solar PV Substation - 110V DC System - Single Line Diagram | 2026-06-12 |  |  |  | 0%
6105A | K125 | 6241 | E | CAL | 0007 | A | 6105AK125-6241-ECAL-0007 |  | 33/220 kV Solar PV Substation | Battery Bank & Charger Sizing | Calculation | 33/220 kV Solar PV Substation - Battery Bank & Charger Sizing - Calculation | 2026-06-12 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0003 | A | 6105AK125-6241-EDIA-0003 |  | 33/220 kV Solar PV Substation | 220kV Transformer Control & Protection Panels | Diagram | 33/220 kV Solar PV Substation - 220kV Transformer Control & Protection Panels - Diagram | 2026-06-05 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0004 | A | 6105AK125-6241-EDIA-0004 |  | 33/220 kV Solar PV Substation | 220kV Line Control & Protection Panels | Diagram | 33/220 kV Solar PV Substation - 220kV Line Control & Protection Panels - Diagram | 2026-07-07 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0005 | A | 6105AK125-6241-EDIA-0005 |  | 33/220 kV Solar PV Substation | 220kV Trip Circuit Supervision Panels | Diagram | 33/220 kV Solar PV Substation - 220kV Trip Circuit Supervision Panels - Diagram | 2026-05-19 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0006 | A | 6105AK125-6241-EDIA-0006 |  | 33/220 kV Solar PV Substation | 220kV Busbar Protection Panels | Diagram | 33/220 kV Solar PV Substation - 220kV Busbar Protection Panels - Diagram | 2026-08-19 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0007 | A | 6105AK125-6241-EDIA-0007 |  | 33/220 kV Solar PV Substation | 220kV Common Control Panel | Diagram | 33/220 kV Solar PV Substation - 220kV Common Control Panel - Diagram | 2026-05-19 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0008 | A | 6105AK125-6241-EDIA-0008 |  | 33/220 kV Solar PV Substation | Energy Metering Panels | Diagram | 33/220 kV Solar PV Substation - Energy Metering Panels - Diagram | 2026-08-19 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0009 | A | 6105AK125-6241-EDIA-0009 |  | 33/220 kV Solar PV Substation | 220kV Transformer LCC Panels | Diagram | 33/220 kV Solar PV Substation - 220kV Transformer LCC Panels - Diagram | 2026-06-05 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0010 | A | 6105AK125-6241-EDIA-0010 |  | 33/220 kV Solar PV Substation | 220kV Line LCC Panels | Diagram | 33/220 kV Solar PV Substation - 220kV Line LCC Panels - Diagram | 2026-07-07 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0011 | A | 6105AK125-6241-EDIA-0011 |  | 33/220 kV Solar PV Substation | Network Switch Panel | Diagram | 33/220 kV Solar PV Substation - Network Switch Panel - Diagram | 2026-09-03 |  |  |  | 0%
6105A | K125 | 6241 | E | CAL | 0008 | A | 6105AK125-6241-ECAL-0008 |  | 33/220 kV Solar PV Substation | 220kV CT VT MK | Calculation | 33/220 kV Solar PV Substation - 220kV CT VT MK - Calculation | 2026-10-01 |  |  |  | 0%
6105A | K125 | 6241 | E | CAL | 0009 | A | 6105AK125-6241-ECAL-0009 |  | 33/220 kV Solar PV Substation | 220kV Relay Settings | Calculation | 33/220 kV Solar PV Substation - 220kV Relay Settings - Calculation |  |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0001 | 0 | 6105AK125-6241-EDST-0001 |  | 33/220 kV Solar PV Substation | Power Transformer Technical | Data Sheet | 33/220 kV Solar PV Substation - Power Transformer Technical - Data Sheet | 2026-02-10 | 2026-03-05 | 2026-04-23 | Reviewed | 66%
6105A | K125 | 6241 | E | LAY | 0008 | 0 | 6105AK125-6241-ELAY-0008 |  | 33/220 kV Solar PV Substation | Power Transformer Dimensional | Layout | 33/220 kV Solar PV Substation - Power Transformer Dimensional - Layout | 2026-03-31 | 2026-04-30 | 2026-05-05 | Approved | 100%
6105A | K125 | 6241 | E | ITP | 0001 | A | 6105AK125-6241-EITP-0001 |  | 33/220 kV Solar PV Substation | Power Transformer Inspection and Test | Plan | 33/220 kV Solar PV Substation - Power Transformer Inspection and Test - Plan | 2026-11-01 |  |  |  | 0%
6105A | K125 | 6241 | E | RPT | 0001 | A | 6105AK125-6241-ERPT-0001 |  | 33/220 kV Solar PV Substation | Power Transformer (Lot - 1) Factory Acceptance Test | Report | 33/220 kV Solar PV Substation - Power Transformer (Lot - 1) Factory Acceptance Test - Report | 2027-01-06 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0012 | 0 | 6105AK125-6241-EDIA-0012 |  | 33/220 kV Solar PV Substation | Power Transformer Motor Drive Unit Circuit | Diagram | 33/220 kV Solar PV Substation - Power Transformer Motor Drive Unit Circuit - Diagram | 2026-05-01 | 2026-05-20 | 2026-05-21 | Approved | 100%
6105A | K125 | 6241 | E | DIA | 0028 | 0 | 6105AK125-6241-EDIA-0028 |  | 33/220 kV Solar PV Substation | Power Transformer Local Control Cubicle Schematic | Diagram | 33/220 kV Solar PV Substation - Power Transformer Local Control Cubicle Schematic - Diagram | - | 2026-05-20 | 2026-06-02 | Approved
6105A | K125 | 6241 | E | DIA | 0013 | A | 6105AK125-6241-EDIA-0013 |  | 33/220 kV Solar PV Substation | Power Transformer AVR/RTCC Schematics | Diagram | 33/220 kV Solar PV Substation - Power Transformer AVR/RTCC Schematics - Diagram | 2026-05-01 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0002 | A | 6105AK125-6241-EDST-0002 |  | 33/220 kV Solar PV Substation | Earthing Tranformer Technical | Data Sheet | 33/220 kV Solar PV Substation - Earthing Tranformer Technical - Data Sheet | 2026-05-27 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0014 | A | 6105AK125-6241-EDIA-0014 |  | 33/220 kV Solar PV Substation | Earthing Transformer Dimensional | Diagram | 33/220 kV Solar PV Substation - Earthing Transformer Dimensional - Diagram | 2026-05-27 |  |  |  | 0%
6105A | K125 | 6241 | E | ITP | 0002 | A | 6105AK125-6241-EITP-0002 |  | 33/220 kV Solar PV Substation | Earthing Transformer Inspection and Test | Plan | 33/220 kV Solar PV Substation - Earthing Transformer Inspection and Test - Plan | 2026-11-01 |  |  |  | 0%
6105A | K125 | 6241 | E | RPT | 0002 | A | 6105AK125-6241-ERPT-0002 |  | 33/220 kV Solar PV Substation | Earthing Transformer Routine Test | Report | 33/220 kV Solar PV Substation - Earthing Transformer Routine Test - Report | 2027-01-31 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0003 | A | 6105AK125-6241-EDST-0003 |  | 33/220 kV Solar PV Substation | NGR Technical | Data Sheet | 33/220 kV Solar PV Substation - NGR Technical - Data Sheet | 2026-05-27 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0015 | A | 6105AK125-6241-EDIA-0015 |  | 33/220 kV Solar PV Substation | NGR Dimensional | Diagram | 33/220 kV Solar PV Substation - NGR Dimensional - Diagram | 2026-05-27 |  |  |  | 0%
6105A | K125 | 6241 | E | ITP | 0003 | A | 6105AK125-6241-EITP-0003 |  | 33/220 kV Solar PV Substation | NGR Inspection and Test | Plan | 33/220 kV Solar PV Substation - NGR Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6241 | E | RPT | 0003 | A | 6105AK125-6241-ERPT-0003 |  | 33/220 kV Solar PV Substation | NGR Routine Test | Report | 33/220 kV Solar PV Substation - NGR Routine Test - Report | 2026-11-20 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0004 | 0 | 6105AK125-6241-EDST-0004 |  | 33/220 kV Solar PV Substation | 220kV Surge Arrester Technical | Data Sheet | 33/220 kV Solar PV Substation - 220kV Surge Arrester Technical - Data Sheet | 2026-04-22 | 2026-04-22 | 2026-05-08 | Approved | 100%
6105A | K125 | 6241 | E | DIA | 0016 | 0 | 6105AK125-6241-EDIA-0016 |  | 33/220 kV Solar PV Substation | 220kV Surge Arrester Dimensional | Diagram | 33/220 kV Solar PV Substation - 220kV Surge Arrester Dimensional - Diagram | 2026-04-22 | 2026-05-05 | 2026-05-07 | Approved | 100%
6105A | K125 | 6241 | E | ITP | 0004 | A | 6105AK125-6241-EITP-0004 |  | 33/220 kV Solar PV Substation | 220kV Surge Arrester Inspection and Test | Plan | 33/220 kV Solar PV Substation - 220kV Surge Arrester Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6241 | E | RPT | 0004 | A | 6105AK125-6241-ERPT-0004 |  | 33/220 kV Solar PV Substation | 220kV Surge Arrester FAT | Report | 33/220 kV Solar PV Substation - 220kV Surge Arrester FAT - Report | 2026-11-12 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0005 | 0 | 6105AK125-6241-EDST-0005 |  | 33/220 kV Solar PV Substation | 220kV Circuit Breaker Technical | Data Sheet | 33/220 kV Solar PV Substation - 220kV Circuit Breaker Technical - Data Sheet | 2026-03-30 | 2026-03-24 | 2026-04-30 | Approved | 100%
6105A | K125 | 6241 | E | DIA | 0017 | 0 | 6105AK125-6241-EDIA-0017 |  | 33/220 kV Solar PV Substation | 220kV Circuit Breaker Schematic | Diagram | 33/220 kV Solar PV Substation - 220kV Circuit Breaker Schematic - Diagram | 2026-03-30 | 2026-03-31 | 2026-04-30 | Approved | 100%
6105A | K125 | 6241 | E | ITP | 0005 | A | 6105AK125-6241-EITP-0005 |  | 33/220 kV Solar PV Substation | 220kV Circuit Breaker Inspection and Test | Plan | 33/220 kV Solar PV Substation - 220kV Circuit Breaker Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6241 | E | RPT | 0005 | A | 6105AK125-6241-ERPT-0005 |  | 33/220 kV Solar PV Substation | 220kV Circuit Breaker FAT | Report | 33/220 kV Solar PV Substation - 220kV Circuit Breaker FAT - Report | 2026-11-15 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0006 | 0 | 6105AK125-6241-EDST-0006 |  | 33/220 kV Solar PV Substation | Isolator / Disconnector Technical | Data Sheet | 33/220 kV Solar PV Substation - Isolator / Disconnector Technical - Data Sheet | 2026-03-30 | 2026-03-24 | 2026-04-23 | Approved | 100%
6105A | K125 | 6241 | E | DIA | 0018 | 0 | 6105AK125-6241-EDIA-0018 |  | 33/220 kV Solar PV Substation | 220kV Isolator / Disconnector Schematic (Drive Disconnector) | Diagram | 33/220 kV Solar PV Substation - 220kV Isolator / Disconnector Schematic (Drive Disconnector) - Diagram | 2026-03-30 | 2026-03-31 | 2026-04-23 | Approved | 100%
6105A | K125 | 6241 | E | DIA | 0019 | 0 | 6105AK125-6241-EDIA-0019 |  | 33/220 kV Solar PV Substation | 220kV Isolator / Disconnector Schematic (Drive Earthing Switch) | Diagram | 33/220 kV Solar PV Substation - 220kV Isolator / Disconnector Schematic (Drive Earthing Switch) - Diagram | 2026-03-30 | 2026-03-31 | 2026-04-23 | Approved | 100%
6105A | K125 | 6241 | E | ITP | 0006 | A | 6105AK125-6241-EITP-0006 |  | 33/220 kV Solar PV Substation | Isolator / Disconnector Inspection and Test | Plan | 33/220 kV Solar PV Substation - Isolator / Disconnector Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6241 | E | RPT | 0006 | A | 6105AK125-6241-ERPT-0006 |  | 33/220 kV Solar PV Substation | Isolator / Disconnector FAT | Report | 33/220 kV Solar PV Substation - Isolator / Disconnector FAT - Report | 2026-11-15 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0020 | 0 | 6105AK125-6241-EDIA-0020 |  | 33/220 kV Solar PV Substation | 220kV Circuit Breaker Outline | Diagram | 33/220 kV Solar PV Substation - 220kV Circuit Breaker Outline - Diagram | - | 2026-04-02 | 2026-05-04 | Reviewed | 66%
6105A | K125 | 6241 | E | DIA | 0021 | 0 | 6105AK125-6241-EDIA-0021 |  | 33/220 kV Solar PV Substation | 220kV Isolator / Disconnector Outline | Diagram | 33/220 kV Solar PV Substation - 220kV Isolator / Disconnector Outline - Diagram | - | 2026-04-07 | 2026-04-23 | Reviewed | 66%
6105A | K125 | 6241 | E | DST | 0007 | 0 | 6105AK125-6241-EDST-0007 |  | 33/220 kV Solar PV Substation | Instrument Transformer (CT) Technical | Data Sheet | 33/220 kV Solar PV Substation - Instrument Transformer (CT) Technical - Data Sheet | 2026-03-25 | 2026-05-21 | 2026-06-01 | Approved | 100%
6105A | K125 | 6241 | E | LAY | 0009 | 0 | 6105AK125-6241-ELAY-0009 |  | 33/220 kV Solar PV Substation | Instrument Transformer (CT) Dimentional | Layout | 33/220 kV Solar PV Substation - Instrument Transformer (CT) Dimentional - Layout | 2026-03-25 | 2026-06-05 | 2026-06-08 | Approved | 100%
6105A | K125 | 6241 | E | RPT | 0007 | A | 6105AK125-6241-ERPT-0007 |  | 33/220 kV Solar PV Substation | Instrument Transformer (CT) FAT | Report | 33/220 kV Solar PV Substation - Instrument Transformer (CT) FAT - Report | 2026-11-15 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0008 | 0 | 6105AK125-6241-EDST-0008 |  | 33/220 kV Solar PV Substation | Instrument Transformer (VT) Technical | Data Sheet | 33/220 kV Solar PV Substation - Instrument Transformer (VT) Technical - Data Sheet | 2026-03-25 | 2026-05-08 | 2026-05-13 | Approved | 100%
6105A | K125 | 6241 | E | LAY | 0010 | 0 | 6105AK125-6241-ELAY-0010 |  | 33/220 kV Solar PV Substation | Instrument Transformer (VT) Dimentional | Layout | 33/220 kV Solar PV Substation - Instrument Transformer (VT) Dimentional - Layout | 2026-03-25 | 2026-06-05 | 2026-06-08 | Approved | 100%
6105A | K125 | 6241 | E | RPT | 0008 | A | 6105AK125-6241-ERPT-0008 |  | 33/220 kV Solar PV Substation | Instrument Transformer (VT) FAT | Report | 33/220 kV Solar PV Substation - Instrument Transformer (VT) FAT - Report | 2026-11-15 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0009 | A | 6105AK125-6241-EDST-0009 |  | 33/220 kV Solar PV Substation | AC Panel Technical | Data Sheet | 33/220 kV Solar PV Substation - AC Panel Technical - Data Sheet | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0022 | A | 6105AK125-6241-EDIA-0022 |  | 33/220 kV Solar PV Substation | AC Panel Schematics | Diagram | 33/220 kV Solar PV Substation - AC Panel Schematics - Diagram | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6241 | E | RPT | 0009 | A | 6105AK125-6241-ERPT-0009 |  | 33/220 kV Solar PV Substation | AC Panel FAT | Report | 33/220 kV Solar PV Substation - AC Panel FAT - Report | 2026-11-30 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0010 | A | 6105AK125-6241-EDST-0010 |  | 33/220 kV Solar PV Substation | DC Panel Technical | Data Sheet | 33/220 kV Solar PV Substation - DC Panel Technical - Data Sheet | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0023 | A | 6105AK125-6241-EDIA-0023 |  | 33/220 kV Solar PV Substation | DC Panel Schematics | Diagram | 33/220 kV Solar PV Substation - DC Panel Schematics - Diagram | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6241 | E | RPT | 0010 | A | 6105AK125-6241-ERPT-0010 |  | 33/220 kV Solar PV Substation | DC Panel FAT | Report | 33/220 kV Solar PV Substation - DC Panel FAT - Report | 2026-11-30 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0011 | A | 6105AK125-6241-EDST-0011 |  | 33/220 kV Solar PV Substation | Battery Bank Technical | Data Sheet | 33/220 kV Solar PV Substation - Battery Bank Technical - Data Sheet | 2026-04-20 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0024 | A | 6105AK125-6241-EDIA-0024 |  | 33/220 kV Solar PV Substation | Battery Bank (Connection/Fuse Box) | Diagram | 33/220 kV Solar PV Substation - Battery Bank (Connection/Fuse Box) - Diagram | 2026-04-20 |  |  |  | 0%
6105A | K125 | 6241 | E | SPC | 0001 | A | 6105AK125-6241-ESPC-0001 |  | 33/220 kV Solar PV Substation | Battery Bank Details / Rack Design | Specification | 33/220 kV Solar PV Substation - Battery Bank Details / Rack Design - Specification | 2026-04-20 |  |  |  | 0%
6105A | K125 | 6241 | E | ITP | 0007 | A | 6105AK125-6241-EITP-0007 |  | 33/220 kV Solar PV Substation | Battery Bank Inspection and Test | Plan | 33/220 kV Solar PV Substation - Battery Bank Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6241 | E | RPT | 0011 | A | 6105AK125-6241-ERPT-0011 |  | 33/220 kV Solar PV Substation | Battery Bank FAT | Report | 33/220 kV Solar PV Substation - Battery Bank FAT - Report | 2026-11-05 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0012 | A | 6105AK125-6241-EDST-0012 |  | 33/220 kV Solar PV Substation | Battery Charger Technical | Data Sheet | 33/220 kV Solar PV Substation - Battery Charger Technical - Data Sheet | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0025 | A | 6105AK125-6241-EDIA-0025 |  | 33/220 kV Solar PV Substation | Battery Charger Schematic | Diagram | 33/220 kV Solar PV Substation - Battery Charger Schematic - Diagram | 2026-05-05 |  |  |  | 0%
6105A | K125 | 6241 | E | ITP | 0008 | A | 6105AK125-6241-EITP-0008 |  | 33/220 kV Solar PV Substation | Battery Charger Inspection and Test | Plan | 33/220 kV Solar PV Substation - Battery Charger Inspection and Test - Plan | 2026-09-01 |  |  |  | 0%
6105A | K125 | 6241 | E | RPT | 0012 | A | 6105AK125-6241-ERPT-0012 |  | 33/220 kV Solar PV Substation | Battery Charger FAT | Report | 33/220 kV Solar PV Substation - Battery Charger FAT - Report | 2026-11-16 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0013 | A | 6105AK125-6241-EDST-0013 |  | 33/220 kV Solar PV Substation | Inverter Technical | Data Sheet | 33/220 kV Solar PV Substation - Inverter Technical - Data Sheet | 2026-04-20 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0014 | A | 6105AK125-6241-EDST-0014 |  | 33/220 kV Solar PV Substation | Post Insulator Technical | Data Sheet | 33/220 kV Solar PV Substation - Post Insulator Technical - Data Sheet | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6241 | E | LAY | 0011 | A | 6105AK125-6241-ELAY-0011 |  | 33/220 kV Solar PV Substation | Post Insulator Outline & Dimentional | Layout | 33/220 kV Solar PV Substation - Post Insulator Outline & Dimentional - Layout | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6241 | E | RPT | 0013 | A | 6105AK125-6241-ERPT-0013 |  | 33/220 kV Solar PV Substation | Post Insulator FAT | Report | 33/220 kV Solar PV Substation - Post Insulator FAT - Report | 2027-01-15 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0015 | A | 6105AK125-6241-EDST-0015 |  | 33/220 kV Solar PV Substation | Disc Insulator Technical | Data Sheet | 33/220 kV Solar PV Substation - Disc Insulator Technical - Data Sheet | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6241 | E | LAY | 0012 | A | 6105AK125-6241-ELAY-0012 |  | 33/220 kV Solar PV Substation | Disc Insulator Outline & Dimentional | Layout | 33/220 kV Solar PV Substation - Disc Insulator Outline & Dimentional - Layout | 2026-04-21 |  |  |  | 0%
6105A | K125 | 6241 | E | RPT | 0014 | A | 6105AK125-6241-ERPT-0014 |  | 33/220 kV Solar PV Substation | Disc Insulator FAT | Report | 33/220 kV Solar PV Substation - Disc Insulator FAT - Report | 2027-01-15 |  |  |  | 0%
6105A | K125 | 6241 | E | SSD | 0001 | A | 6105AK125-6241-ESSD-0001 |  | 33/220 kV Solar PV Substation | Steel Structure | Drawing | 33/220 kV Solar PV Substation - Steel Structure - Drawing | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6241 | E | SPC | 0002 | A | 6105AK125-6241-ESPC-0002 |  | 33/220 kV Solar PV Substation | Termination Kit Outdoor Termination & Joints | Specification | 33/220 kV Solar PV Substation - Termination Kit Outdoor Termination & Joints - Specification | 2026-10-21 |  |  |  | 0%
6105A | K125 | 6241 | E | DST | 0016 | A | 6105AK125-6241-EDST-0016 |  | 33/220 kV Solar PV Substation | Cables & Conductors Technical | Data Sheet | 33/220 kV Solar PV Substation - Cables & Conductors Technical - Data Sheet | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6241 | E | SPC | 0003 | A | 6105AK125-6241-ESPC-0003 |  | 33/220 kV Solar PV Substation | Grounding Technical Documentation | Specification | 33/220 kV Solar PV Substation - Grounding Technical Documentation - Specification | 2026-09-24 |  |  |  | 0%
6105A | K125 | 6241 | E | SPC | 0004 | A | 6105AK125-6241-ESPC-0004 |  | 33/220 kV Solar PV Substation | Hardware & Connector Technical Documentation | Specification | 33/220 kV Solar PV Substation - Hardware & Connector Technical Documentation - Specification | 2026-07-24 |  |  |  | 0%
6105A | K125 | 6241 | E | DIA | 0027 | 0 | 6105AK125-6241-EDIA-0027 |  | 33/220 kV Solar PV Substation | Surge Monitor for 220kV Surge Arrester | Diagram | 33/220 kV Solar PV Substation - Surge Monitor for 220kV Surge Arrester - Diagram | - | 2026-05-12 | 2026-05-15 | Approved | 100%
6105A | K125 | 6241 | C | DBD | 0001 | 0 | 6105AK125-6241-CDBD-0001 |  | 33/220 kV Solar PV Substation | Civil | Design Basis and Criteria | 33/220 kV Solar PV Substation - Civil - Design Basis and Criteria | 2026-04-15 | 2026-04-24 | 2026-05-08 | Approved | 100%
6105A | K125 | 6241 | C | FND | 0001 | A | 6105AK125-6241-CFND-0001 |  | 33/220 kV Solar PV Substation | Power Transformer Foundation | Plan | 33/220 kV Solar PV Substation - Power Transformer Foundation - Plan | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0001 | A | 6105AK125-6241-CDTL-0001 |  | 33/220 kV Solar PV Substation | Power Transformer Concrete Outline Plan and | Details | 33/220 kV Solar PV Substation - Power Transformer Concrete Outline Plan and - Details | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0002 | A | 6105AK125-6241-CDTL-0002 |  | 33/220 kV Solar PV Substation | Power Transformer Reinforcement Plan and | Details | 33/220 kV Solar PV Substation - Power Transformer Reinforcement Plan and - Details | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0003 | A | 6105AK125-6241-CDTL-0003 |  | 33/220 kV Solar PV Substation | Power Transformer Gravel & Grating | Details | 33/220 kV Solar PV Substation - Power Transformer Gravel & Grating - Details | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0001 | A | 6105AK125-6241-CRPT-0001 |  | 33/220 kV Solar PV Substation | Power Transformer Design | Report | 33/220 kV Solar PV Substation - Power Transformer Design - Report | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6241 | C | PLN | 0001 | A | 6105AK125-6241-CPLN-0001 |  | 33/220 kV Solar PV Substation | Fire Wall Foundation | Plan | 33/220 kV Solar PV Substation - Fire Wall Foundation - Plan | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0004 | A | 6105AK125-6241-CDTL-0004 |  | 33/220 kV Solar PV Substation | Fire Wall Concrete Outline Plan and | Details | 33/220 kV Solar PV Substation - Fire Wall Concrete Outline Plan and - Details | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0005 | A | 6105AK125-6241-CDTL-0005 |  | 33/220 kV Solar PV Substation | Fire Wall Reinforcement Plan and | Details | 33/220 kV Solar PV Substation - Fire Wall Reinforcement Plan and - Details | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0002 | A | 6105AK125-6241-CRPT-0002 |  | 33/220 kV Solar PV Substation | Fire Wall Design | Report | 33/220 kV Solar PV Substation - Fire Wall Design - Report | 2026-07-01 |  |  |  | 0%
6105A | K125 | 6241 | C | PLN | 0002 | A | 6105AK125-6241-CPLN-0002 |  | 33/220 kV Solar PV Substation | 220 kV Ganrty Foundation Layout | Plan | 33/220 kV Solar PV Substation - 220 kV Ganrty Foundation Layout - Plan | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0006 | A | 6105AK125-6241-CDTL-0006 |  | 33/220 kV Solar PV Substation | 220 kV Ganrty Foundation Concrete Outline Plan and | Details | 33/220 kV Solar PV Substation - 220 kV Ganrty Foundation Concrete Outline Plan and - Details | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0007 | A | 6105AK125-6241-CDTL-0007 |  | 33/220 kV Solar PV Substation | 220 kV Ganrty Foundation Reinforcement Plan and | Details | 33/220 kV Solar PV Substation - 220 kV Ganrty Foundation Reinforcement Plan and - Details | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0003 | A | 6105AK125-6241-CRPT-0003 |  | 33/220 kV Solar PV Substation | 220 kV Ganrty Foundation Design | Report | 33/220 kV Solar PV Substation - 220 kV Ganrty Foundation Design - Report | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6241 | C | PLN | 0003 | A | 6105AK125-6241-CPLN-0003 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Foundation Layout | Plan | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Foundation Layout - Plan | 2026-07-08 |  |  |  | 0%
6105A | K125 | 6241 | C | FND | 0002 | A | 6105AK125-6241-CFND-0002 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details Surge Arrester | Foundation | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details Surge Arrester - Foundation | 2026-08-10 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0008 | A | 6105AK125-6241-CDTL-0008 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Surge Arrester Foundation Reinforcement Plan and | Details | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Surge Arrester Foundation Reinforcement Plan and - Details | 2026-08-10 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0004 | A | 6105AK125-6241-CRPT-0004 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Surge Arrester Foundation Design | Report | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Surge Arrester Foundation Design - Report | 2026-08-10 |  |  |  | 0%
6105A | K125 | 6241 | C | FND | 0003 | A | 6105AK125-6241-CFND-0003 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details DS+ES | Foundation | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details DS+ES - Foundation | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0009 | A | 6105AK125-6241-CDTL-0009 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment DS+ES Foundation Reinforcement Plan and | Details | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment DS+ES Foundation Reinforcement Plan and - Details | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0005 | A | 6105AK125-6241-CRPT-0005 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment DS+ES Foundation Design | Report | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment DS+ES Foundation Design - Report | 2026-08-05 |  |  |  | 0%
6105A | K125 | 6241 | C | FND | 0004 | A | 6105AK125-6241-CFND-0004 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details Current Transformer | Foundation | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details Current Transformer - Foundation | 2026-08-01 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0010 | A | 6105AK125-6241-CDTL-0010 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Current Transformer Foundation Reinforcement Plan and | Details | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Current Transformer Foundation Reinforcement Plan and - Details | 2026-08-01 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0006 | A | 6105AK125-6241-CRPT-0006 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Current Transformer Foundation Design | Report | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Current Transformer Foundation Design - Report | 2026-08-01 |  |  |  | 0%
6105A | K125 | 6241 | C | FND | 0005 | A | 6105AK125-6241-CFND-0005 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details Circuit Breaker | Foundation | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details Circuit Breaker - Foundation | 2026-07-25 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0011 | A | 6105AK125-6241-CDTL-0011 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Circuit Breaker Foundation Reinforcement Plan and | Details | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Circuit Breaker Foundation Reinforcement Plan and - Details | 2026-07-25 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0007 | A | 6105AK125-6241-CRPT-0007 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Circuit Breaker Foundation Design | Report | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Circuit Breaker Foundation Design - Report | 2026-07-25 |  |  |  | 0%
6105A | K125 | 6241 | C | FND | 0006 | A | 6105AK125-6241-CFND-0006 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Concrete Outline Plan and Details Voltage Transformer | Foundation | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Concrete Outline Plan and Details Voltage Transformer - Foundation | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0012 | A | 6105AK125-6241-CDTL-0012 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Voltage Transformer Foundation Reinforcement Plan and | Details | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Voltage Transformer Foundation Reinforcement Plan and - Details | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0008 | A | 6105AK125-6241-CRPT-0008 |  | 33/220 kV Solar PV Substation | 220 kV Switchyard Equipment Voltage Transformer Foundation Design | Report | 33/220 kV Solar PV Substation - 220 kV Switchyard Equipment Voltage Transformer Foundation Design - Report | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6241 | C | PLN | 0004 | A | 6105AK125-6241-CPLN-0004 |  | 33/220 kV Solar PV Substation | Switchyard Trenches Layout | Plan | 33/220 kV Solar PV Substation - Switchyard Trenches Layout - Plan | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6241 | C | SEC | 0001 | A | 6105AK125-6241-CSEC-0001 |  | 33/220 kV Solar PV Substation | Switchyard Trenches Concrete Outline Section and Trench Covers | Section | 33/220 kV Solar PV Substation - Switchyard Trenches Concrete Outline Section and Trench Covers - Section | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6241 | C | SEC | 0002 | A | 6105AK125-6241-CSEC-0002 |  | 33/220 kV Solar PV Substation | Switchyard Trenches Reinforcement Section and Trench Covers | Section | 33/220 kV Solar PV Substation - Switchyard Trenches Reinforcement Section and Trench Covers - Section | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6241 | C | SEC | 0003 | A | 6105AK125-6241-CSEC-0003 |  | 33/220 kV Solar PV Substation | Switchyard Trenches Draw Pit Concrete Outline | Section | 33/220 kV Solar PV Substation - Switchyard Trenches Draw Pit Concrete Outline - Section | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0013 | A | 6105AK125-6241-CDTL-0013 |  | 33/220 kV Solar PV Substation | Switchyard Trenches Draw Pit Reinforcement Plan and | Details | 33/220 kV Solar PV Substation - Switchyard Trenches Draw Pit Reinforcement Plan and - Details | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0009 | A | 6105AK125-6241-CRPT-0009 |  | 33/220 kV Solar PV Substation | Switchyard Trenches Design | Report | 33/220 kV Solar PV Substation - Switchyard Trenches Design - Report | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0014 | A | 6105AK125-6241-CDTL-0014 |  | 33/220 kV Solar PV Substation | Switchyard Trenches Duct bank | Details | 33/220 kV Solar PV Substation - Switchyard Trenches Duct bank - Details | 2026-08-03 |  |  |  | 0%
6105A | K125 | 6241 | W | PLN | 0001 | A | 6105AK125-6241-WPLN-0001 |  | 33/220 kV Solar PV Substation | Road Layout | Plan | 33/220 kV Solar PV Substation - Road Layout - Plan | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6241 | W | SEC | 0001 | A | 6105AK125-6241-WSEC-0001 |  | 33/220 kV Solar PV Substation | Road Concrete Outline | Section | 33/220 kV Solar PV Substation - Road Concrete Outline - Section | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6241 | W | SEC | 0002 | A | 6105AK125-6241-WSEC-0002 |  | 33/220 kV Solar PV Substation | Road Reinforcement | Section | 33/220 kV Solar PV Substation - Road Reinforcement - Section | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6241 | W | PLN | 0002 | A | 6105AK125-6241-WPLN-0002 |  | 33/220 kV Solar PV Substation | Surface Drainage Layout | Plan | 33/220 kV Solar PV Substation - Surface Drainage Layout - Plan | 2026-09-02 |  |  |  | 0%
6105A | K125 | 6241 | W | DTL | 0001 | A | 6105AK125-6241-WDTL-0001 |  | 33/220 kV Solar PV Substation | Surface Drainage Main Hole | Details | 33/220 kV Solar PV Substation - Surface Drainage Main Hole - Details | 2026-09-02 |  |  |  | 0%
6105A | K125 | 6241 | W | DTL | 0002 | A | 6105AK125-6241-WDTL-0002 |  | 33/220 kV Solar PV Substation | Surface Drainage Pipe Laying | Details | 33/220 kV Solar PV Substation - Surface Drainage Pipe Laying - Details | 2026-09-02 |  |  |  | 0%
6105A | K125 | 6241 | W | RPT | 0001 | A | 6105AK125-6241-WRPT-0001 |  | 33/220 kV Solar PV Substation | Surface Drainage Design | Report | 33/220 kV Solar PV Substation - Surface Drainage Design - Report | 2026-09-02 |  |  |  | 0%
6105A | K125 | 6241 | W | PLN | 0003 | A | 6105AK125-6241-WPLN-0003 |  | 33/220 kV Solar PV Substation | Fence Wall Layout | Plan | 33/220 kV Solar PV Substation - Fence Wall Layout - Plan | 2026-09-23 |  |  |  | 0%
6105A | K125 | 6241 | W | DTL | 0003 | A | 6105AK125-6241-WDTL-0003 |  | 33/220 kV Solar PV Substation | Fence Wall Foundation Plan and | Details | 33/220 kV Solar PV Substation - Fence Wall Foundation Plan and - Details | 2026-09-23 |  |  |  | 0%
6105A | K125 | 6241 | W | DTL | 0004 | A | 6105AK125-6241-WDTL-0004 |  | 33/220 kV Solar PV Substation | Fence Wall Fence Section Plan and | Details | 33/220 kV Solar PV Substation - Fence Wall Fence Section Plan and - Details | 2026-09-23 |  |  |  | 0%
6105A | K125 | 6241 | W | SEC | 0003 | A | 6105AK125-6241-WSEC-0003 |  | 33/220 kV Solar PV Substation | Fence Wall Gate Plan and | Section | 33/220 kV Solar PV Substation - Fence Wall Gate Plan and - Section | 2026-09-23 |  |  |  | 0%
6105A | K125 | 6241 | C | PLN | 0005 | A | 6105AK125-6241-CPLN-0005 |  | 33/220 kV Solar PV Substation | E-House Foundation Concrete Outline | Plan | 33/220 kV Solar PV Substation - E-House Foundation Concrete Outline - Plan | 2026-07-24 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0015 | A | 6105AK125-6241-CDTL-0015 |  | 33/220 kV Solar PV Substation | E-House Foundation Reinforcement Plan and | Details | 33/220 kV Solar PV Substation - E-House Foundation Reinforcement Plan and - Details | 2026-07-24 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0010 | A | 6105AK125-6241-CRPT-0010 |  | 33/220 kV Solar PV Substation | E-House Foundation Design | Report | 33/220 kV Solar PV Substation - E-House Foundation Design - Report | 2026-07-24 |  |  |  | 0%
6105A | K125 | 6241 | C | PLN | 0006 | A | 6105AK125-6241-CPLN-0006 |  | 33/220 kV Solar PV Substation | Aux-Trafo Foundation Concrete Outline | Plan | 33/220 kV Solar PV Substation - Aux-Trafo Foundation Concrete Outline - Plan | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0016 | A | 6105AK125-6241-CDTL-0016 |  | 33/220 kV Solar PV Substation | Aux-Trafo Foundation Reinforcement Plan and | Details | 33/220 kV Solar PV Substation - Aux-Trafo Foundation Reinforcement Plan and - Details | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0011 | A | 6105AK125-6241-CRPT-0011 |  | 33/220 kV Solar PV Substation | Aux-Trafo Foundation Design | Report | 33/220 kV Solar PV Substation - Aux-Trafo Foundation Design - Report | 2026-07-20 |  |  |  | 0%
6105A | K125 | 6241 | C | PLN | 0007 | A | 6105AK125-6241-CPLN-0007 |  | 33/220 kV Solar PV Substation | NGR & ET Foundation Concrete Outline | Plan | 33/220 kV Solar PV Substation - NGR & ET Foundation Concrete Outline - Plan | 2026-06-19 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0017 | A | 6105AK125-6241-CDTL-0017 |  | 33/220 kV Solar PV Substation | NGR & ET Foundation Reinforcement Plan and | Details | 33/220 kV Solar PV Substation - NGR & ET Foundation Reinforcement Plan and - Details | 2026-06-19 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0012 | A | 6105AK125-6241-CRPT-0012 |  | 33/220 kV Solar PV Substation | NGR & ET Foundation Design | Report | 33/220 kV Solar PV Substation - NGR & ET Foundation Design - Report | 2026-06-19 |  |  |  | 0%
6105A | K125 | 6241 | C | PLN | 0008 | A | 6105AK125-6241-CPLN-0008 |  | 33/220 kV Solar PV Substation | Transformer - Way Concrete Outline | Plan | 33/220 kV Solar PV Substation - Transformer - Way Concrete Outline - Plan | 2026-07-22 |  |  |  | 0%
6105A | K125 | 6241 | C | PLN | 0009 | A | 6105AK125-6241-CPLN-0009 |  | 33/220 kV Solar PV Substation | Light Pole Foundation Layout | Plan | 33/220 kV Solar PV Substation - Light Pole Foundation Layout - Plan | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0018 | A | 6105AK125-6241-CDTL-0018 |  | 33/220 kV Solar PV Substation | Light Pole Foundation Concrete Outline & Reinforcement | Details | 33/220 kV Solar PV Substation - Light Pole Foundation Concrete Outline & Reinforcement - Details | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6241 | C | RPT | 0013 | A | 6105AK125-6241-CRPT-0013 |  | 33/220 kV Solar PV Substation | Light Pole Foundation Design | RPT | 33/220 kV Solar PV Substation - Light Pole Foundation Design - RPT | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6241 | W | PLN | 0004 | A | 6105AK125-6241-WPLN-0004 |  | 33/220 kV Solar PV Substation | Gravel Layout | Plan | 33/220 kV Solar PV Substation - Gravel Layout - Plan | 2026-10-14 |  |  |  | 0%
6105A | K125 | 6241 | C | PLN | 0010 | A | 6105AK125-6241-CPLN-0010 |  | 33/220 kV Solar PV Substation | Site Grading | Plan | 33/220 kV Solar PV Substation - Site Grading - Plan | - | 2026-05-07 |  | Reviewed
6105A | K125 | 6241 | C | LST | 0001 | A | 6105AK125-6241-CLST-0001 |  | 33/220 kV Solar PV Substation | Drawings, Legends, Notes | List | 33/220 kV Solar PV Substation - Drawings, Legends, Notes - List | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6241 | C | DIA | 0001 | A | 6105AK125-6241-CDIA-0001 |  | 33/220 kV Solar PV Substation | Distribution Board | Single Line Diagram | 33/220 kV Solar PV Substation - Distribution Board - Single Line Diagram | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6241 | C | LAY | 0001 | A | 6105AK125-6241-CLAY-0001 |  | 33/220 kV Solar PV Substation | Outdoor Switchyard Lighting and Small Power Layout | Layout | 33/220 kV Solar PV Substation - Outdoor Switchyard Lighting and Small Power Layout - Layout | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6241 | C | LAY | 0002 | A | 6105AK125-6241-CLAY-0002 |  | 33/220 kV Solar PV Substation | Outdoor switchyard Lighting and Small Power Cable Route | Layout | 33/220 kV Solar PV Substation - Outdoor switchyard Lighting and Small Power Cable Route - Layout | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6241 | C | DTL | 0019 | A | 6105AK125-6241-CDTL-0019 |  | 33/220 kV Solar PV Substation | Installation Detail for Outdoor Lighting and Small Power | Details | 33/220 kV Solar PV Substation - Installation Detail for Outdoor Lighting and Small Power - Details | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6241 | C | CAL | 0001 | A | 6105AK125-6241-CCAL-0001 |  | 33/220 kV Solar PV Substation | Outdoor Lighting Lux | Calculation | 33/220 kV Solar PV Substation - Outdoor Lighting Lux - Calculation | 2026-09-09 |  |  |  | 0%
6105A | K125 | 6241 | C | SHP | 0001 | A | 6105AK125-6241-CSHP-0001 |  | 33/220 kV Solar PV Substation | Shop / Manufacturing Drawings of Distribution Boards | Shop Drawing | 33/220 kV Solar PV Substation - Shop / Manufacturing Drawings of Distribution Boards - Shop Drawing | 2026-09-09 |  |  |  | 0%
6105A | K125 | 0000 | G | LTR | 0001 | A | 6105AK125-0000-GLTR-0001 |  | General | Submission of Insurance Cover Notes | Letter | General - Submission of Insurance Cover Notes - Letter | - | 2026-01-28 |  |  | 33%
6105A | K125 | 6240 | E | SLD | 0001 | A | 6105AK125-6240-ESLD-0001 | Sht. 1 of 1 | High Voltage Substations | Overall | Single Line Diagram | High Voltage Substations - Overall - Single Line Diagram | - | 2026-02-10 |  | Approved | 100% | 2026-06-08
6105A | K125 | 0000 | G | LTR | 0002 | A | 6105AK125-0000-GLTR-0002 |  | General | Local Content Plan | Letter | General - Local Content Plan - Letter | - | 2026-03-13 |  | Approved | 100%
6105A | K125 | 0000 | E | TRP | 0001 | A | 6105AK125-0000-ETRP-0001 |  | General | Disconnector | Test Report | General - Disconnector - Test Report | - | 2026-03-17 |  | Approved | 100%
6105A | K125 | 0000 | E | TRP | 0002 | A | 6105AK125-0000-ETRP-0002 |  | General | Circuit Breaker | Test Report | General - Circuit Breaker - Test Report | - | 2026-03-17 |  |  | 33%
6105A | K125 | 0000 | E | TRP | 0003 | A | 6105AK125-0000-ETRP-0003 |  | General | Current Transformer | Test Report | General - Current Transformer - Test Report | - | 2026-04-06 |  | Approved | 100%
6105A | K125 | 0000 | E | TRP | 0004 | A | 6105AK125-0000-ETRP-0004 |  | General | Capacitive Voltage Transformer | Test Report | General - Capacitive Voltage Transformer - Test Report | - | 2026-04-06 |  | Approved | 100%
6105A | K125 | 6241 | E | RPT | 0015 | 0 | 6105AK125-6241-ERPT-0015 |  | 33/220 kV Solar PV Substation | Power Transformer Short Circuit Verification & Transient Voltage Transfer Characteristics Calculation | Report | 33/220 kV Solar PV Substation - Power Transformer Short Circuit Verification & Transient Voltage Transfer Characteristics Calculation - Report | - | 2026-05-15 | 2026-06-04 | Approved | 100%
6105A | K125 | 6242 | E | RPT | 0017 | 0 | 6105AK125-6242-ERPT-0017 |  | 33/220 kV Power Station Substation | Power Transformer Short Circuit Verification & Transient Voltage Transfer Characteristics Calculation | Report | 33/220 kV Power Station Substation - Power Transformer Short Circuit Verification & Transient Voltage Transfer Characteristics Calculation - Report | - | 2026-05-15 | 2026-06-04 | Approved | 100%
6105A | K125 | 6243 | E | RPT | 0015 | 0 | 6105AK125-6243-ERPT-0015 |  | 220/33 kV Plant Main Substation | Power Transformer Short Circuit Verification & Transient Voltage Transfer Characteristics Calculation | Report | 220/33 kV Plant Main Substation - Power Transformer Short Circuit Verification & Transient Voltage Transfer Characteristics Calculation - Report | - | 2026-05-12 | 2026-06-04 | Approved | 100%
6105A | K125 | 6241 | E | DIA | 0026 | B | 6105AK125-6241-EDIA-0026 |  | 33/220 kV Solar PV Substation | Power Transformer (Bushing & Surge Arrestor) | Diagram | 33/220 kV Solar PV Substation - Power Transformer (Bushing & Surge Arrestor) - Diagram | - | 2026-06-02 | 2026-06-04 | Approved | 100%
6105A | K125 | 6242 | E | DIA | 0028 | A | 6105AK125-6242-EDIA-0028 |  | 33/220 kV Power Station Substation | Power Transformer (Bushing & Surge Arrestor) | Diagram | 33/220 kV Power Station Substation - Power Transformer (Bushing & Surge Arrestor) - Diagram | - | 2026-06-02 | 2026-06-04 | Approved | 100%
6105A | K125 | 6243 | E | DIA | 0026 | B | 6105AK125-6243-EDIA-0026 |  | 220/33 kV Plant Main Substation | Power Transformer (Bushing & Surge Arrestor) | Diagram | 220/33 kV Plant Main Substation - Power Transformer (Bushing & Surge Arrestor) - Diagram | - | 2026-06-02 | 2026-06-04 | Approved | 100%
6105A | K125 | 0000 | C | DBD | 0001 | D | 6105AK125-0000-CDBD-0001 |  | General | Steel Structure | Design Basis and Criteria | General - Steel Structure - Design Basis and Criteria | - | 2026-05-25 |  | Reviewed | 33% | 2026-06-08
6105A | K125 | 0000 | E | TRP | 0005 | A | 6105AK125-0000-ETRP-0005 |  | General | Surge Arrester | Test Report | General - Surge Arrester - Test Report | - | 2026-04-22 |  | Approved | 100%
6105A | K125 | 0000 | E | PLN | 0001 | A | 6105AK125-0000-EPLN-0001 |  | General | Steel Structure Febrication Inspection & Test | Plan | General - Steel Structure Febrication Inspection & Test - Plan | - | 2026-04-29 |  | Reviewed | 33%
6105A | K125 | 0000 | E | PLN | 0002 | A | 6105AK125-0000-EPLN-0002 |  | General | Steel Structure Corrosion Inspection & Test | Plan | General - Steel Structure Corrosion Inspection & Test - Plan | - | 2026-04-29 |  | Reviewed | 33%
6105A | K125 | 0000 | E | PRC | 0001 | A | 6105AK125-0000-EPRC-0001 |  | General | Steel Structure Galvanizing | Procedure | General - Steel Structure Galvanizing - Procedure |  | 2026-04-29 |  | Reviewed | 33%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
1.994%

## K125 WBS Codes
L1 | L2 | L3 | L4 | Code | Reko Diq Copper - Gold Project Facility Name
0 | 0 | 0 | 0 | 0000 | General | 0000 - General
0 | 1 | 0 | 0 | 0100 | Project Site Wide | 0100 - Project Site Wide
6 | 2 | 4 | 0 | 6240 | High Voltage Substations | 6240 - High Voltage Substations
6 | 2 | 4 | 1 | 6241 | 33/220 kV Solar PV Substation | 6241 - 33/220 kV Solar PV Substation
6 | 2 | 4 | 2 | 6242 | 33/220 kV Power Station Substation | 6242 - 33/220 kV Power Station Substation
6 | 2 | 4 | 3 | 6243 | 220/33 kV Plant Main Substation | 6243 - 220/33 kV Plant Main Substation

## Rev10 RDMC WBS Areas
| Facility Level ID |  |  | Facility Code | Reko Diq Project Facility Name | Engineering | Procurement | Contracts | Construction Management
L1 | L2 | L3 | L4
0 | 0 | 0 | 0 | 0 | General | - | - | - | -
0 | 1 | 0 | 0 | 100 | Project Site Wide | - | - | - | -
1 | 0 | 0 | 0 | 1000 | Mining - OP | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
1 | 1 | 0 | 0 | 1100 | Open Pit Mine | RDMC/Fluo r | RDMC/Fluo r | RDMC/Fluo r | RDMC/Fluo r
1 | 1 | 1 | 0 | 1110 | Open Pit Mine Development | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 1 | 1111 | Pre-Stripping | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 2 | 1112 | Stockpiling | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 3 | 1113 | Waste Dumps | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 4 | 1114 | Run-of-Mine Pad | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 5 | 1115 | Clearing, Grubbing and Topsoil Stockpiling | RDMC | RDMC | RDMC | RDMC
1 | 1 | 1 | 9 | 1119 | Common Facilities and Services | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 0 | 1120 | Open Pit Mining Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 1 | 1121 | Drilling Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 2 | 1122 | Loading Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 3 | 1123 | Hauling Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 4 | 1124 | Support Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 2 | 5 | 1125 | Maintenance Equipment | RDMC | RDMC | RDMC | RDMC
1 | 1 | 3 | 0 | 1130 | Infrastructure | RDMC/Fluor/PPE | RDMC/Fluor/PPE | RDMC/Fluor/PPE | RDMC/Fluor/PPE
1 | 1 | 3 | 1 | 1131 | Haul Roads | RDMC | RDMC | RDMC | RDMC
1 | 1 | 3 | 2 | 1132 | Pioneering | RDMC | RDMC | RDMC | RDMC
1 | 1 | 3 | 3 | 1133 | Dewatering | Fluor | Fluor | Fluor | Fluor
1 | 1 | 3 | 4 | 1134 | Trailing Cables and Shovel Reticulation | PPE | PPE | PPE | PPE
1 | 1 | 3 | 7 | 1137 | Planning and Exploration | RDMC | RDMC | RDMC | RDMC
1 | 1 | 3 | 9 | 1139 | Common Facilities and Services | Fluor/PPE | Fluor/PPE | Fluor/PPE | Fluor/PPE
1 | 1 | 8 | 0 | 1180 | Explosives Plant, Magazine and Storage | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 1 | 1181 | Explosives and Detonator Magazines | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 2 | 1182 | Manufacturing Plant | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 3 | 1183 | Raw Materials Warehouse | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 4 | 1184 | Ammonium Nitrate Warehouse | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 5 | 1185 | Office and Dry Mess | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 6 | 1186 | Change Room and Ablutions | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 7 | 1187 | Workshop | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 8 | 1188 | Washdown Facility | Fluor | Fluor | Fluor | Fluor
1 | 1 | 8 | 9 | 1189 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 0 | 0 | 1200 | Mine Infrastructure Area and Services | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
1 | 2 | 1 | 0 | 1210 | Site Preparation | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
1 | 2 | 1 | 1 | 1211 | Bulk Earthworks | Fluor | Fluor | Fluor | Fluor
1 | 2 | 1 | 2 | 1212 | Drainage and Culverts | Fluor | Fluor | Fluor | Fluor
1 | 2 | 1 | 3 | 1213 | Improvements | Fluor | Fluor | Fluor | Fluor
1 | 2 | 1 | 4 | 1214 | Security Fencing | RDMC | RDMC | RDMC | RDMC
1 | 2 | 2 | 0 | 1220 | Roads and Paving | Fluor | Fluor | Fluor | Fluor
1 | 2 | 2 | 1 | 1221 | In-Plant Roads | Fluor | Fluor | Fluor | Fluor
1 | 2 | 2 | 2 | 1222 | Carparks and Hardstand Areas | Fluor | Fluor | Fluor | Fluor
1 | 2 | 3 | 0 | 1230 | Central Facilities | Fluor | Fluor | Fluor | Fluor
1 | 2 | 3 | 1 | 1231 | Administration Buildings | Fluor | Fluor | Fluor | Fluor
1 | 2 | 3 | 2 | 1232 | Change Rooms and Ablution Blocks | Fluor | Fluor | Fluor | Fluor
1 | 2 | 3 | 9 | 1239 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 0 | 1240 | Heavy Equipment Maintenance Facilities | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 1 | 1241 | Preventive Maintenance Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 2 | 1242 | Utilities Area | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 3 | 1243 | Repair Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 4 | 1244 | Tyre Storage and Change | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 5 | 1245 | Washdown Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 6 | 1246 | Warehouse | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 7 | 1247 | Fabrication Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 8 | 1248 | Assembly Area | Fluor | Fluor | Fluor | Fluor
1 | 2 | 4 | 9 | 1249 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 0 | 1250 | Light Vehicle Equipment Maintenance Facilities | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 1 | 1251 | Preventive Maintenance Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 2 | 1252 | Hydraulics and Electrical Repair Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 3 | 1253 | Repair/Rebuild Workshop | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 4 | 1254 | Tyre Storage and Change | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 5 | 1255 | Washdown Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 6 | 1256 | Warehouse | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 8 | 1258 | Laydown Area | Fluor | Fluor | Fluor | Fluor
1 | 2 | 5 | 9 | 1259 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 0 | 1260 | Water and Waste Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 1 | 1261 | Raw Water Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 2 | 1262 | Fire Water Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 3 | 1263 | Potable Water Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 4 | 1264 | Waste Water Disposal | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 5 | 1265 | Sewage Effluent Disposal | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 6 | 1266 | Raw Water Distribution | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 7 | 1267 | Firewater Distribution | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 8 | 1268 | Potable Water Distribution | Fluor | Fluor | Fluor | Fluor
1 | 2 | 6 | 9 | 1269 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 7 | 0 | 1270 | Power, Communications and Security Systems | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
1 | 2 | 7 | 1 | 1271 | Light Vehicle Power Supply and Distribution | Fluor | Fluor | Fluor | Fluor
1 | 2 | 7 | 2 | 1272 | Communication | Fluor | Fluor | Fluor | Fluor
1 | 2 | 7 | 3 | 1273 | Mine Dispatch | RDMC | RDMC | RDMC | RDMC
1 | 2 | 7 | 4 | 1274 | Security | RDMC | RDMC | RDMC | RDMC
1 | 2 | 7 | 9 | 1279 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 0 | 1280 | Compressed Air Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 1 | 1281 | Compression | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 2 | 1282 | Wet Receiving | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 3 | 1283 | Drying | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 4 | 1284 | Dry Receiving | Fluor | Fluor | Fluor | Fluor
1 | 2 | 8 | 5 | 1285 | Distribution | - | - | - | -
1 | 2 | 8 | 9 | 1289 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 0 | 1290 | Fuel and Lubrication Storage and Reticulation | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 1 | 1291 | Diesel Bulk Storage Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 2 | 1292 | Central Refuelling Facility | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 3 | 1293 | Remote Refuelling Bay 1 | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 4 | 1294 | Remote Refuelling Bay 2 | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 5 | 1295 | Remote Refuelling Bay 3 | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 6 | 1296 | Heavy Vehicle Lube Unloading and Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 7 | 1297 | Light Vehicle Refuelling Area | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 8 | 1298 | Light Vehicle Lube Unloading and Storage | Fluor | Fluor | Fluor | Fluor
1 | 2 | 9 | 9 | 1299 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
2 | 0 | 0 | 0 | 2000 | Mining - Underground | - | - | - | -
2 | 1 | 0 | 0 | 2100 | Underground Mine | - | - | - | -
2 | 1 | 1 | 0 | 2110 | Mine Development | - | - | - | -
2 | 1 | 1 | 1 | 2111 | Access Development | - | - | - | -
2 | 1 | 1 | 2 | 2112 | Mine Stockpiling | - | - | - | -
2 | 1 | 1 | 3 | 2113 | Waste Dumps | - | - | - | -
2 | 1 | 1 | 4 | 2114 | Level Access Development | - | - | - | -
2 | 1 | 1 | 5 | 2115 | Haulage Development | - | - | - | -
2 | 1 | 1 | 6 | 2116 | Reef Development | - | - | - | -
2 | 1 | 1 | 7 | 2117 | Raw | - | - | - | -
2 | 1 | 2 | 0 | 2120 | Underground Mining Equipment | - | - | - | -
2 | 1 | 2 | 1 | 2121 | Drilling Equipment | - | - | - | -
2 | 1 | 2 | 2 | 2122 | Loading Equipment | - | - | - | -
2 | 1 | 2 | 3 | 2123 | Hauling Equipment | - | - | - | -
2 | 1 | 2 | 4 | 2124 | Support Equipment | - | - | - | -
2 | 1 | 2 | 5 | 2125 | Mine Maintenance Equipment | - | - | - | -
2 | 1 | 2 | 6 | 2126 | Underground Communication | - | - | - | -
2 | 1 | 2 | 7 | 2127 | Reinforcements | - | - | - | -
2 | 1 | 2 | 8 | 2128 | Control and Instrumentation | - | - | - | -
2 | 1 | 3 | 0 | 2130 | Underground Mine Infrastructure | - | - | - | -
2 | 1 | 3 | 1 | 2131 | Mine Roads | - | - | - | -
2 | 1 | 3 | 2 | 2132 | Development | - | - | - | -
2 | 1 | 3 | 3 | 2133 | Dewatering | - | - | - | -
2 | 1 | 3 | 4 | 2134 | Truck Shop | - | - | - | -
2 | 1 | 3 | 5 | 2135 | Explosive Magazine | - | - | - | -
2 | 1 | 3 | 6 | 2136 | Mine Stockpiling Platforms | - | - | - | -
2 | 1 | 3 | 7 | 2137 | Timber Preparation Facilities | - | - | - | -
2 | 1 | 3 | 8 | 2138 | Mine Facilities and Services | - | - | - | -
2 | 1 | 3 | 9 | 2139 | Planning and Exploration | - | - | - | -
2 | 1 | 4 | 0 | 2140 | Underground Mine Shaft | - | - | - | -
2 | 1 | 4 | 1 | 2141 | Shaft Development | - | - | - | -
2 | 1 | 4 | 2 | 2142 | Head Frame | - | - | - | -
2 | 1 | 4 | 3 | 2143 | Hoisting | - | - | - | -
2 | 1 | 5 | 0 | 2150 | Ventilation and Services | - | - | - | -
2 | 1 | 5 | 1 | 2151 | Ventilation Shafts | - | - | - | -
2 | 1 | 5 | 2 | 2152 | Ventilation Fans and Equipment | - | - | - | -
2 | 1 | 5 | 3 | 2153 | Refrigeration | - | - | - | -
2 | 1 | 5 | 4 | 2154 | Compressed Air Plant | - | - | - | -
2 | 1 | 6 | 0 | 2160 | Underground Material Handling | - | - | - | -
2 | 1 | 6 | 1 | 2161 | Ore and Waste Passes | - | - | - | -
2 | 1 | 6 | 2 | 2162 | Underground Crushing | - | - | - | -
2 | 1 | 6 | 3 | 2163 | Underground Conveying | - | - | - | -
3 | 0 | 0 | 0 | 3000 | Dry Plant | Fluor | Fluor | Fluor | Fluor
3 | 1 | 0 | 0 | 3100 | Primary Crushing | Fluor | Fluor | Fluor | Fluor
3 | 1 | 1 | 0 | 3110 | Crushers | Fluor | Fluor | Fluor | Fluor
3 | 1 | 1 | 1 | 3111 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 1 | 2 | 3112 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 2 | 0 | 3120 | Truck Dump Pad | Fluor | Fluor | Fluor | Fluor
3 | 1 | 2 | 1 | 3121 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 2 | 2 | 3122 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 3 | 0 | 3130 | Chamber | Fluor | Fluor | Fluor | Fluor
3 | 1 | 3 | 1 | 3131 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 3 | 2 | 3132 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 4 | 0 | 3140 | Tunnel | Fluor | Fluor | Fluor | Fluor
3 | 1 | 4 | 1 | 3141 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 4 | 2 | 3142 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 5 | 0 | 3150 | Crusher Discharge Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 1 | 5 | 1 | 3151 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 5 | 2 | 3152 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 6 | 0 | 3160 | Transfer Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 1 | 6 | 2 | 3162 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 1 | 9 | 0 | 3190 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 1 | 9 | 7 | 3197 | Dust Control | Fluor | Fluor | Fluor | Fluor
3 | 1 | 9 | 8 | 3198 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 1 | 9 | 9 | 3199 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 2 | 0 | 0 | 3200 | Coarse Ore Transport | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 0 | 3210 | Stockpile Feed | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 1 | 3211 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 2 | 3212 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 3 | 3213 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 4 | 3214 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 2 | 1 | 5 | 3215 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 2 | 9 | 0 | 3290 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 2 | 9 | 7 | 3297 | Dust Control | Fluor | Fluor | Fluor | Fluor
3 | 2 | 9 | 8 | 3298 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 2 | 9 | 9 | 3299 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 3 | 0 | 0 | 3300 | Coarse Ore Storage & Reclaim | Fluor | Fluor | Fluor | Fluor
3 | 3 | 1 | 0 | 3310 | Base Pad | Fluor | Fluor | Fluor | Fluor
3 | 3 | 2 | 0 | 3320 | Chamber | Fluor | Fluor | Fluor | Fluor
3 | 3 | 3 | 0 | 3330 | Tunnel | Fluor | Fluor | Fluor | Fluor
3 | 3 | 3 | 1 | 3331 | Reclaim | Fluor | Fluor | Fluor | Fluor
3 | 3 | 3 | 2 | 3332 | Escape | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 0 | 3340 | Coarse Ore Reclaim | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 1 | 3341 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 2 | 3342 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 3 | 3343 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 4 | 3344 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 3 | 4 | 5 | 3345 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 3 | 9 | 0 | 3390 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 3 | 9 | 7 | 3397 | Dust Control | Fluor | Fluor | Fluor | Fluor
3 | 3 | 9 | 8 | 3398 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 3 | 9 | 9 | 3399 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 4 | 0 | 0 | 3400 | Coarse Ore Screening and Transport | Fluor | Fluor | Fluor | Fluor
3 | 4 | 1 | 0 | 3410 | Screening | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 0 | 3420 | Coarse Ore Screen Oversize | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 1 | 3421 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 2 | 3422 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 3 | 3423 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 4 | 3424 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 4 | 2 | 5 | 3425 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 0 | 3430 | Coarse Ore Screen Undersize | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 1 | 3431 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 2 | 3432 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 3 | 3433 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 4 | 3434 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 4 | 3 | 5 | 3435 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 0 | 3440 | HPGR Feed | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 1 | 3441 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 2 | 3442 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 3 | 3443 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 4 | 3444 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 4 | 4 | 5 | 3445 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 4 | 9 | 0 | 3490 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 4 | 9 | 7 | 3497 | Dust Control | Fluor | Fluor | Fluor | Fluor
3 | 4 | 9 | 8 | 3498 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 4 | 9 | 9 | 3499 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 5 | 0 | 0 | 3500 | Secondary Crushing | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 0 | 3520 | Secondary Crushing | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 1 | 3521 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 2 | 3522 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 3 | 3523 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 4 | 3524 | Train 4 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 2 | 5 | 3525 | Train 5 | Fluor | Fluor | Fluor | Fluor
3 | 5 | 9 | 0 | 3590 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 5 | 9 | 7 | 3597 | Dust collection | Fluor | Fluor | Fluor | Fluor
3 | 5 | 9 | 8 | 3598 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 5 | 9 | 9 | 3599 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 6 | 0 | 0 | 3600 | Tertiary Crushing | Fluor | Fluor | Fluor | Fluor
3 | 6 | 1 | 0 | 3610 | High Pressure Grinding | Fluor | Fluor | Fluor | Fluor
3 | 6 | 1 | 1 | 3611 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 6 | 1 | 2 | 3612 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 6 | 1 | 3 | 3613 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 0 | 3620 | Fine Ore Storage Feed | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 1 | 3621 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 2 | 3622 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 3 | 3623 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 4 | 3624 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 6 | 2 | 5 | 3625 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 6 | 9 | 0 | 3690 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 6 | 9 | 7 | 3697 | Dust Collection | Fluor | Fluor | Fluor | Fluor
3 | 6 | 9 | 8 | 3698 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 6 | 9 | 9 | 3699 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 7 | 0 | 0 | 3700 | Fine Ore | Fluor | Fluor | Fluor | Fluor
3 | 7 | 1 | 0 | 3710 | Storage Bins | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 0 | 3720 | Reclaim Feeders | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 1 | 3721 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 2 | 3722 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 3 | 3723 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 4 | 3724 | Train 4 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 5 | 3725 | Train 5 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 2 | 6 | 3726 | Train 6 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 0 | 3730 | Screen Conveyors | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 1 | 3731 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 2 | 3732 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 3 | 3733 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 4 | 3734 | Train 4 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 5 | 3735 | Train 5 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 3 | 6 | 3736 | Train 6 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 0 | 3740 | Screens | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 1 | 3741 | Train 1 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 2 | 3742 | Train 2 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 3 | 3743 | Train 3 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 4 | 3744 | Train 4 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 5 | 3745 | Train 5 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 4 | 6 | 3746 | Train 6 | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 0 | 3750 | Screen Oversize | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 1 | 3751 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 2 | 3752 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 3 | 3753 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 4 | 3754 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 7 | 5 | 5 | 3755 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 7 | 9 | 0 | 3790 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 7 | 9 | 7 | 3797 | Dust Collection | Fluor | Fluor | Fluor | Fluor
3 | 7 | 9 | 8 | 3798 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 7 | 9 | 9 | 3799 | Electrical | Fluor | Fluor | Fluor | Fluor
3 | 8 | 0 | 0 | 3800 | HPGR Oversize | Fluor | Fluor | Fluor | Fluor
3 | 8 | 1 | 0 | 3810 | Surge Bin | Fluor | Fluor | Fluor | Fluor
3 | 8 | 2 | 0 | 3820 | Reclaim Feeder | Fluor | Fluor | Fluor | Fluor
3 | 8 | 3 | 0 | 3830 | Reclaim Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 0 | 3840 | Surge Bin Overflow | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 1 | 3841 | Conveyor | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 2 | 3842 | Tail End | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 3 | 3843 | Drive Station | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 4 | 3844 | Take-up | Fluor | Fluor | Fluor | Fluor
3 | 8 | 4 | 5 | 3845 | Head End | Fluor | Fluor | Fluor | Fluor
3 | 8 | 5 | 0 | 3850 | Dead Stockpile | Fluor | Fluor | Fluor | Fluor
3 | 8 | 9 | 0 | 3890 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
3 | 8 | 9 | 8 | 3898 | Building or Structure | Fluor | Fluor | Fluor | Fluor
3 | 8 | 9 | 9 | 3899 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 0 | 0 | 0 | 4000 | Wet Plant | Fluor | Fluor | Fluor | Fluor
4 | 1 | 0 | 0 | 4100 | Grinding and Classification | Fluor | Fluor | Fluor | Fluor
4 | 1 | 1 | 0 | 4110 | Grinding | Fluor | Fluor | Fluor | Fluor
4 | 1 | 1 | 1 | 4111 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 1 | 2 | 4112 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 1 | 3 | 4113 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 3 | 0 | 4130 | Classification | Fluor | Fluor | Fluor | Fluor
4 | 1 | 3 | 1 | 4131 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 3 | 2 | 4132 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 3 | 3 | 4133 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 1 | 4 | 0 | 4140 | Flash Flotation (future) | Future | Future | Future | Future
4 | 1 | 5 | 0 | 4150 | Gravity Gold Recovery (future) | Future | Future | Future | Future
4 | 1 | 6 | 0 | 4160 | Gold Room (future) | Future | Future | Future | Future
4 | 1 | 7 | 0 | 4170 | Reagent Distribution | Fluor | Fluor | Fluor | Fluor
4 | 1 | 8 | 0 | 4180 | Media Handling | Fluor | Fluor | Fluor | Fluor
4 | 1 | 8 | 1 | 4181 | Ball Unloading | Fluor | Fluor | Fluor | Fluor
4 | 1 | 8 | 2 | 4182 | Ball Storage | Fluor | Fluor | Fluor | Fluor
4 | 1 | 8 | 3 | 4183 | Ball Conveying | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 0 | 4190 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 1 | 4191 | Grinding Train 1 Cooling Water | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 2 | 4192 | Grinding Train 2 Cooling Water | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 3 | 4193 | Grinding Train 3 Cooling Water | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 8 | 4198 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 1 | 9 | 9 | 4199 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 2 | 0 | 0 | 4200 | Copper Rougher Processing | Fluor | Fluor | Fluor | Fluor
4 | 2 | 1 | 0 | 4210 | Surge and Conditioning | Fluor | Fluor | Fluor | Fluor
4 | 2 | 1 | 1 | 4211 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 1 | 2 | 4212 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 1 | 3 | 4213 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 3 | 0 | 4230 | Flotation | Fluor | Fluor | Fluor | Fluor
4 | 2 | 3 | 1 | 4231 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 3 | 2 | 4232 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 3 | 3 | 4233 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 0 | 4240 | Concentrate Regrinding | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 1 | 4241 | Stage 1 Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 2 | 4242 | Stage 1 Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 3 | 4243 | Stage 1 Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 4 | 4244 | Stage 1 Train 4 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 5 | 4245 | Stage 2 Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 6 | 4246 | Stage 2 Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 7 | 4247 | Stage 2 Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 4 | 8 | 4248 | Stage 2 Train 4 | Fluor | Fluor | Fluor | Fluor
4 | 2 | 5 | 0 | 4250 | Concentrate Regrind Media Handling | Fluor | Fluor | Fluor | Fluor
4 | 2 | 5 | 5 | 4255 | Stage 2 Header | Fluor | Fluor | Fluor | Fluor
4 | 2 | 5 | 6 | 4256 | Stage 2 Dewatering | Fluor | Fluor | Fluor | Fluor
4 | 2 | 5 | 7 | 4257 | Stage 2 Recirculation | Fluor | Fluor | Fluor | Fluor
4 | 2 | 6 | 0 | 4260 | Tailings Collection | Fluor | Fluor | Fluor | Fluor
4 | 2 | 6 | 1 | 4261 | Tank | Fluor | Fluor | Fluor | Fluor
4 | 2 | 6 | 2 | 4262 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 2 | 7 | 0 | 4270 | Reagent Distribution (not used) | Fluor | Fluor | Fluor | Fluor
4 | 2 | 8 | 0 | 4280 | Sampling and Analysis | Fluor | Fluor | Fluor | Fluor
4 | 2 | 8 | 1 | 4281 | On-Stream Analyser 1 | - | - | - | -
4 | 2 | 8 | 2 | 4282 | On-Stream Analyser 2 | - | - | - | -
4 | 2 | 8 | 3 | 4283 | Stage 1 Train 1/2 Mill Product | - | - | - | -
4 | 2 | 8 | 4 | 4284 | Stage 1 Train 3/4 Mill Product | - | - | - | -
4 | 2 | 8 | 5 | 4285 | Stage 2 Train 1/2 Cyclone Overflow | - | - | - | -
4 | 2 | 8 | 6 | 4286 | Stage 2 train 1/2 Cyclone Overflow | - | - | - | -
4 | 2 | 8 | 7 | 4287 | Stage 2 Train 1/2 Mill Product | - | - | - | -
4 | 2 | 8 | 8 | 4288 | Stage 2 Train 3/4 Mill Product | - | - | - | -
4 | 2 | 9 | 0 | 4290 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 2 | 9 | 8 | 4298 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 2 | 9 | 9 | 4299 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 3 | 0 | 0 | 4300 | Copper Cleaner Processing | Fluor | Fluor | Fluor | Fluor
4 | 3 | 2 | 0 | 4320 | Aeration | Fluor | Fluor | Fluor | Fluor
4 | 3 | 2 | 1 | 4321 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 2 | 2 | 4322 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 2 | 3 | 4323 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 3 | 0 | 4330 | Conditioning | Fluor | Fluor | Fluor | Fluor
4 | 3 | 3 | 1 | 4331 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 3 | 2 | 4332 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 3 | 3 | 4333 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 4 | 0 | 4340 | First Cleaner Flotation - Scalper Flotation | Fluor | Fluor | Fluor | Fluor
4 | 3 | 4 | 1 | 4341 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 4 | 2 | 4342 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 4 | 3 | 4343 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 5 | 0 | 4350 | Second Cleaner Flotation - Scavenger Conditioning and Flotation | Fluor | Fluor | Fluor | Fluor
4 | 3 | 5 | 1 | 4351 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 5 | 2 | 4352 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 5 | 3 | 4353 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 6 | 0 | 4360 | Third Cleaner Flotation - Recleaner Conditioning and Flotation | Fluor | Fluor | Fluor | Fluor
4 | 3 | 6 | 1 | 4361 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 6 | 2 | 4362 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 6 | 3 | 4363 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 8 | 0 | 4380 | Sampling and Analysis | Fluor | Fluor | Fluor | Fluor
4 | 3 | 8 | 1 | 4381 | On-Stream Analyser 1 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 8 | 2 | 4382 | On-Stream Analyser 2 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 8 | 3 | 4383 | On-Stream Analyser 3 | Fluor | Fluor | Fluor | Fluor
4 | 3 | 9 | 0 | 4390 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 3 | 9 | 8 | 4398 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 3 | 9 | 9 | 4399 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 4 | 0 | 0 | 4400 | Coarse Particle Processing (future) | Future | Future | Future | Future
4 | 4 | 1 | 0 | 4410 | Feed Classification (future) | Future | Future | Future | Future
4 | 4 | 1 | 1 | 4411 | Train 1 (future) | Future | Future | Future | Future
4 | 4 | 1 | 2 | 4412 | Train 2 (future) | Future | Future | Future | Future
4 | 4 | 1 | 3 | 4413 | Train 3 (future) | Future | Future | Future | Future
4 | 4 | 2 | 0 | 4420 | Conditioning (future) | Future | Future | Future | Future
4 | 4 | 2 | 1 | 4421 | Train 1 (future) | Future | Future | Future | Future
4 | 4 | 2 | 2 | 4422 | Train 2 (future) | Future | Future | Future | Future
4 | 4 | 2 | 3 | 4423 | Train 3 (future) | Future | Future | Future | Future
4 | 4 | 3 | 0 | 4430 | Flotation (future) | Future | Future | Future | Future
4 | 4 | 3 | 1 | 4431 | Train 1 (future) | Future | Future | Future | Future
4 | 4 | 3 | 2 | 4432 | Train 2 (future) | Future | Future | Future | Future
4 | 4 | 3 | 3 | 4433 | Train 3 (future) | Future | Future | Future | Future
4 | 4 | 4 | 0 | 4440 | Concentrate Regrind (future) | Future | Future | Future | Future
4 | 4 | 4 | 1 | 4441 | Train 1 (future) | Future | Future | Future | Future
4 | 4 | 4 | 2 | 4442 | Train 2 (future) | Future | Future | Future | Future
4 | 4 | 4 | 3 | 4443 | Train 3 (future) | Future | Future | Future | Future
4 | 4 | 5 | 0 | 4450 | Regrind Media Handling (future) | Future | Future | Future | Future
4 | 4 | 8 | 0 | 4480 | Sampling and Analysis (future) | Future | Future | Future | Future
4 | 4 | 9 | 0 | 4490 | Facilities and Services (future) | Future | Future | Future | Future
4 | 4 | 9 | 8 | 4498 | Building or Structure (future) | Future | Future | Future | Future
4 | 4 | 9 | 9 | 4499 | Electrical (future) | Future | Future | Future | Future
4 | 5 | 0 | 0 | 4500 | Molybdenum Processing (future) | Future | Future | Future | Future
4 | 5 | 1 | 0 | 4510 | Bulk Concentrate Thickening (future) | Future | Future | Future | Future
4 | 5 | 2 | 0 | 4520 | Rougher Conditioning (future) | Future | Future | Future | Future
4 | 5 | 3 | 0 | 4530 | Rougher Flotation (future) | Future | Future | Future | Future
4 | 5 | 4 | 0 | 4540 | Cleaner Flotation (future) | Future | Future | Future | Future
4 | 5 | 8 | 0 | 4580 | Sampling and Analysis (future) | Future | Future | Future | Future
4 | 5 | 9 | 0 | 4590 | Common Facilities and Services (future) | Future | Future | Future | Future
4 | 6 | 0 | 0 | 4600 | Concentrate Handling | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 0 | 4610 | Copper Concentrate Thickening | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 1 | 4611 | Feed | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 2 | 4612 | Thickener | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 3 | 4613 | Overflow | Fluor | Fluor | Fluor | Fluor
4 | 6 | 1 | 4 | 4614 | Underflow | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 0 | 4620 | Copper Concentrate Filtration and Storage | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 1 | 4621 | Train 1 (filter 1) | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 2 | 4622 | Train 2 (filter 2) | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 3 | 4623 | Train 3 (filter 3) | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 4 | 4624 | Train 4 (filter 4) | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 5 | 4625 | Filtrate Transfer Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 6 | 4626 | Storage Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 2 | 7 | 4627 | Sampler Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 0 | 4630 | Copper Concentrate Reclaim and Loadout | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 1 | 4631 | Reclaim | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 2 | 4632 | Loadout Storage Reclaim Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 4 | 4634 | Product Sampler Conveyor | Fluor | Fluor | Fluor | Fluor
4 | 6 | 3 | 6 | 4636 | Loadout Conveyor | - | - | - | -
4 | 6 | 5 | 0 | 4650 | Molybdenum Concentrate Thickening (future) | Future | Future | Future | Future
4 | 6 | 6 | 0 | 4660 | Molybdenum Concentrate Filtration and Storage (future) | Future | Future | Future | Future
4 | 6 | 7 | 0 | 4670 | Molybdenum Concentrate Bagging (future) | Future | Future | Future | Future
4 | 6 | 9 | 0 | 4690 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 6 | 9 | 7 | 4697 | Truck Wash | Fluor | Fluor | Fluor | Fluor
4 | 6 | 9 | 8 | 4698 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 6 | 9 | 9 | 4699 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 7 | 0 | 0 | 4700 | Tailings Handling | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 0 | 4710 | Rougher Thickening | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 1 | 4711 | Feed Distribution | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 2 | 4712 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 3 | 4713 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 4 | 4714 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 5 | 4715 | Overflow | Fluor | Fluor | Fluor | Fluor
4 | 7 | 1 | 6 | 4716 | Underflow | Fluor | Fluor | Fluor | Fluor
4 | 7 | 2 | 0 | 4720 | Rougher Disposal Pumping | Fluor | Fluor | Fluor | Fluor
4 | 7 | 2 | 1 | 4721 | Line 1 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 2 | 2 | 4722 | Line 2 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 2 | 3 | 4723 | Line 3 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 3 | 0 | 4730 | Filtration (future) | Future | Future | Future | Future
4 | 7 | 4 | 0 | 4740 | CPF Sands De-Watering (future) | Future | Future | Future | Future
4 | 7 | 4 | 1 | 4741 | Train 1 (future) | Future | Future | Future | Future
4 | 7 | 4 | 2 | 4742 | Train 2 (future) | Future | Future | Future | Future
4 | 7 | 4 | 3 | 4743 | Train 3 (future) | Future | Future | Future | Future
4 | 7 | 5 | 0 | 4750 | Cleaner Thickening | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 1 | 4751 | Feed Distribution | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 2 | 4752 | Train 1 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 6 | 4756 | Train 2 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 4 | 4754 | Train 3 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 5 | 4755 | Overflow | Fluor | Fluor | Fluor | Fluor
4 | 7 | 5 | 6 | 4756 | Underflow | Fluor | Fluor | Fluor | Fluor
4 | 7 | 6 | 0 | 4760 | Cleaner Disposal Pumping | Fluor | Fluor | Fluor | Fluor
4 | 7 | 6 | 1 | 4761 | Line 1 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 6 | 2 | 4762 | Line 2 | Fluor | Fluor | Fluor | Fluor
4 | 7 | 7 | 0 | 4770 | Tailings Overland Conveying (future) | Future | Future | Future | Future
4 | 7 | 9 | 0 | 4790 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 7 | 9 | 8 | 4798 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 7 | 9 | 9 | 4799 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 8 | 0 | 0 | 4800 | Reagents | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 0 | 4810 | General | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 1 | 4811 | Exterior Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 2 | 4812 | Interior Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 3 | 4813 | Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 4 | 4814 | Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 1 | 5 | 4815 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 2 | 0 | 4820 | Collector | Fluor | Fluor | Fluor | Fluor
4 | 8 | 2 | 1 | 4821 | Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 2 | 2 | 4822 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 0 | 4830 | Promoter | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 1 | 4831 | Promoter 1 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 2 | 4832 | Promoter 1 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 3 | 4833 | Promoter 2 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 4 | 4834 | Promoter 2 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 5 | 4835 | Promoter 3 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 3 | 6 | 4836 | Promoter 3 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 0 | 4840 | Frother | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 1 | 4841 | Frother 1 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 2 | 4842 | Frother 1 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 3 | 4843 | Frother 2 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 4 | 4 | 4844 | Frother 2 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 0 | 4850 | SMBS | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 1 | 4851 | SMBS 1 Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 2 | 4852 | SMBS 1 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 3 | 4853 | SMBS 1 Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 4 | 4854 | SMBS 1 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 5 | 4855 | SMBS 2 Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 6 | 4856 | SMBS 2 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 7 | 4857 | SMBS 2 Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 5 | 8 | 4858 | SMBS 2 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 0 | 4860 | Flocculant | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 1 | 4861 | Flocculant 1 Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 2 | 4862 | Flocculant 1 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 3 | 4863 | Flocculant 1 Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 4 | 4864 | Flocculant 1 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 5 | 4865 | Flocculant 2 Handling | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 6 | 4866 | Flocculant 2 Preparation | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 7 | 4867 | Flocculant 2 Storage | Fluor | Fluor | Fluor | Fluor
4 | 8 | 6 | 8 | 4868 | Flocculant 2 Distribution | Fluor | Fluor | Fluor | Fluor
4 | 8 | 7 | 0 | 4870 | Spare Reagent Systems | Fluor | Fluor | Fluor | Fluor
4 | 8 | 7 | 1 | 4871 | Spare Reagent 1 | Fluor | Fluor | Fluor | Fluor
4 | 8 | 7 | 2 | 4872 | Spare Reagent 2 | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 0 | 4880 | Dosing | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 1 | 4881 | General | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 2 | 4882 | Collector | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 3 | 4883 | Promoter | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 4 | 4884 | Frother | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 5 | 4885 | SMBS | Fluor | Fluor | Fluor | Fluor
4 | 8 | 8 | 6 | 4886 | Flocculant | Fluor | Fluor | Fluor | Fluor
4 | 8 | 9 | 0 | 4890 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
4 | 8 | 9 | 8 | 4898 | Building or Structure | Fluor | Fluor | Fluor | Fluor
4 | 8 | 9 | 9 | 4899 | Electrical | Fluor | Fluor | Fluor | Fluor
4 | 9 | 0 | 0 | 4900 | Plant Services | Fluor | Fluor | Fluor | Fluor
4 | 9 | 1 | 0 | 4910 | Raw Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 1 | 1 | 4911 | Storage | Fluor | Fluor | Fluor | Fluor
4 | 9 | 1 | 2 | 4912 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 1 | 3 | 4913 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 2 | 0 | 4920 | Process Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 2 | 2 | 4922 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 2 | 3 | 4923 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 3 | 0 | 4930 | Gland Seal Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 3 | 1 | 4931 | Storage | Fluor | Fluor | Fluor | Fluor
4 | 9 | 3 | 2 | 4932 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 3 | 3 | 4933 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 4 | 0 | 4940 | Cooling Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 4 | 1 | 4941 | Storage | Fluor | Fluor | Fluor | Fluor
4 | 9 | 4 | 2 | 4942 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 4 | 3 | 4943 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 0 | 4950 | Treated Water | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 1 | 4951 | Plant | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 2 | 4952 | Storage | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 3 | 4953 | Pumping | Fluor | Fluor | Fluor | Fluor
4 | 9 | 5 | 4 | 4954 | Distribution | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 0 | 4960 | Plant Air | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 1 | 4961 | Processing Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 2 | 4962 | CPF Hydrofloat Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 3 | 4963 | CPF Tailings Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 4 | 4964 | Concentrate Filtration Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 6 | 5 | 4965 | Concentrate Drying Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 0 | 4970 | Instrument Air | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 1 | 4971 | Processing Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 2 | 4972 | CPF Hydrofloat Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 3 | 4973 | CPF Tailings Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 4 | 4974 | Concentrate Filtration Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 7 | 5 | 4975 | Concentrate Drying Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 0 | 4980 | Flotation Blower Air | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 1 | 4981 | Rougher Flotation | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 2 | 4982 | Cleaner Aeration Area | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 3 | 4983 | Cleaner Flotation | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 4 | 4984 | Cleaner Scavenger Flotation | Fluor | Fluor | Fluor | Fluor
4 | 9 | 8 | 5 | 4985 | SMBS Neutralisation | Fluor | Fluor | Fluor | Fluor
4 | 9 | 9 | 0 | 4990 | Nitrogen (future) | Future | Future | Future | Future
5 | 0 | 0 | 0 | 5000 | Tailings and Water Management | Fluor/KP | IPMT | IPMT/Fluor | IPMT/Fluor/RDMC
5 | 1 | 0 | 0 | 5100 | Tailings Management | KP/Fluor | IPMT | IPMT/Fluor | IMPT/Fluor
5 | 1 | 1 | 0 | 5110 | Rougher Dams | KP | IPMT | IPMT | RDMC/IPMT
5 | 1 | 1 | 1 | 5111 | Compartment 1 | KP | IPMT | IPMT | RDMC
5 | 1 | 1 | 2 | 5112 | Compartment 2 | KP | IPMT | IPMT | IPMT
5 | 1 | 1 | 3 | 5113 | Compartment 3 | KP | IPMT | IPMT | IPMT
5 | 1 | 1 | 5 | 5115 | Monitoring Wells | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 0 | 5120 | Cleaner Dams | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 1 | 5121 | Compartment 1 | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 2 | 5122 | Compartment 2 | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 3 | 5123 | Compartment 3 | KP | IPMT | IPMT | IPMT
5 | 1 | 2 | 5 | 5125 | Monitoring Wells | KP | IPMT | IPMT | IPMT
5 | 1 | 3 | 0 | 5130 | Seepage System and Return | Fluor | Fluor | Fluor | Fluor
5 | 1 | 3 | 1 | 5131 | Rougher Collection | Fluor | Fluor | Fluor | Fluor
5 | 1 | 3 | 2 | 5132 | Rougher Return | Fluor | Fluor | Fluor | Fluor
5 | 1 | 3 | 5 | 5135 | Cleaner Collection | Fluor | Fluor | Fluor | Fluor
5 | 1 | 3 | 6 | 5136 | Cleaner Return | Fluor | Fluor | Fluor | Fluor
5 | 1 | 4 | 0 | 5140 | Sand Deposition (future) | Future | Future | Future | Future
5 | 1 | 5 | 0 | 5150 | Transport and Deposition | Fluor/KP | Fluor/IPMT | Fluor/IPMT | Fluor/IPMT
5 | 1 | 5 | 1 | 5151 | Rougher Pipeline 1 | Fluor | Fluor | Fluor | Fluor
5 | 1 | 5 | 2 | 5152 | Rougher Pipeline 2 | Fluor | Fluor | Fluor | Fluor
5 | 1 | 5 | 3 | 5153 | Rougher Pipeline 3 | Fluor | Fluor | Fluor | Fluor
5 | 1 | 5 | 4 | 5154 | Rougher Deposition | KP | IMPT | IMPT | IPMT
5 | 1 | 5 | 5 | 5155 | Cleaner Transport | Fluor | Fluor | Fluor | Fluor
5 | 1 | 5 | 6 | 5156 | Cleaner Deposition | KP | IMPT | IMPT | IPMT
5 | 1 | 9 | 0 | 5190 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
5 | 1 | 9 | 8 | 5198 | Building or Structure | Fluor | Fluor | Fluor | Fluor
5 | 1 | 9 | 9 | 5199 | Electrical | Fluor | Fluor | Fluor | Fluor
5 | 2 | 0 | 0 | 5200 | Reclaim Water | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 0 | 5210 | Rougher TSF | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 1 | 5211 | Pontoons | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 2 | 5212 | Return Pumping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 3 | 5213 | Return Piping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 4 | 5214 | Transfer Pumping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 5 | 5215 | Transfer Piping | - | - | - | -
5 | 2 | 2 | 0 | 5220 | Cleaner TSF | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 1 | 5211 | Pontoons | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 2 | 5212 | Return Pumping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 3 | 5213 | Return Piping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 4 | 5214 | Transfer Pumping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 1 | 5 | 5215 | Transfer Piping | Fluor | Fluor | Fluor | Fluor
5 | 2 | 9 | 0 | 5290 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
5 | 2 | 9 | 8 | 5298 | Building or Structure | Fluor | Fluor | Fluor | Fluor
5 | 2 | 9 | 9 | 5299 | Electrical | Fluor | Fluor | Fluor | Fluor
5 | 3 | 0 | 0 | 5300 | Water Management | Fluor/KP | Fluor/IPMT/RDMC | Fluor/IPMT/RDMC | Fluor/IPMT/RDMC
5 | 3 | 1 | 0 | 5310 | Surface Water Diversion | Fluor/KP | Fluor/IPMT | RDMC/Fluor/IPMT | RDMC/Fluor/IPMT
5 | 3 | 1 | 1 | 5311 | Mining | KP | IPMT | RDMC | RDMC
5 | 3 | 1 | 2 | 5312 | Dry Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 1 | 3 | 5313 | Wet Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 1 | 4 | 5314 | TSF | KP | IPMT | IPMT | IPMT
5 | 3 | 1 | 5 | 5315 | Infrastructure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 2 | 0 | 5320 | Surface Water Collection and Storage | Fluor/KP | Fluor/IPMT | Fluor/IMPT/ RDMC | Fluor/IPMT/RDMC
5 | 3 | 2 | 1 | 5321 | Mining | KP | IPMT | RDMC | RDMC
5 | 3 | 2 | 2 | 5322 | Dry Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 2 | 3 | 5323 | Wet Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 2 | 4 | 5324 | TSF | KP | IPMT | IPMT | IPMT
5 | 3 | 2 | 5 | 5325 | Infrastructure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 3 | 0 | 5330 | Surface Water Pumping and Distribution | Fluor | Fluor | Fluor | Fluor
5 | 3 | 3 | 1 | 5331 | Mining | KP | IPMT | RDMC | RDMC
5 | 3 | 3 | 2 | 5332 | Dry Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 3 | 3 | 5333 | Wet Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 3 | 4 | 5334 | TSF | KP | IPMT | IPMT | IPMT
5 | 3 | 3 | 5 | 5335 | Infrastructure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 4 | 0 | 5340 | Surface Water Sediment and Erosion Control | Fluor | Fluor | Fluor | Fluor
5 | 3 | 4 | 1 | 5341 | Mining | KP | IPMT | RDMC | RDMC
5 | 3 | 4 | 2 | 5342 | Dry Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 4 | 3 | 5343 | Wet Plant | Fluor | Fluor | Fluor | Fluor
5 | 3 | 4 | 4 | 5344 | TSF | KP | IPMT | IPMT | IPMT
5 | 3 | 4 | 5 | 5345 | Infrastructure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 5 | 0 | 5350 | Process Water Dams | KP | IPMT | IPMT | IPMT
5 | 3 | 6 | 0 | 5360 | Raw Water Dams | KP | IPMT | IPMT | IPMT
5 | 3 | 7 | 0 | 5370 | Turkey Nests | RDMC | RDMC | RDMC | RDMC
5 | 3 | 8 | 0 | 5380 | Rejects Pond | KP | IPMT | IPMT | IPMT
5 | 3 | 8 | 1 | 5381 | Earthworks | KP | IPMT | IPMT | IPMT
5 | 3 | 8 | 2 | 5382 | Transfer Pumping | KP | IPMT | IPMT | IPMT
5 | 3 | 8 | 3 | 5383 | Transfer Piping | KP | IPMT | IPMT | IPMT
5 | 3 | 8 | 4 | 5384 | Sprayfield | KP | IPMT | IPMT | IPMT
5 | 3 | 9 | 0 | 5390 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
5 | 3 | 9 | 8 | 5398 | Building or Structure | Fluor | Fluor | Fluor | Fluor
5 | 3 | 9 | 9 | 5399 | Electrical | Fluor | Fluor | Fluor | Fluor
5 | 4 | 0 | 0 | 5400 | Acid Rock Drainage Treatment | - | - | - | -
5 | 4 | 1 | 0 | 5410 | Dams | - | - | - | -
5 | 4 | 2 | 0 | 5420 | Pumps and Pipelines | - | - | - | -
5 | 4 | 3 | 0 | 5430 | Seepage Control | - | - | - | -
5 | 4 | 9 | 0 | 5490 | Common Facilities and Services | - | - | - | -
5 | 5 | 0 | 0 | 5500 | Effluent Treatment | Fluor | Fluor | Fluor | Fluor
5 | 5 | 1 | 0 | 5510 | Industrial | - | - | - | -
5 | 5 | 2 | 0 | 5520 | Plant Sewage | Fluor | Fluor | Fluor | Fluor
5 | 5 | 2 | 1 | 5521 | Collection | Fluor | Fluor | Fluor | Fluor
5 | 5 | 2 | 2 | 5522 | Pumping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 2 | 3 | 5523 | Piping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 0 | 5530 | Village Sewage | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 1 | 5531 | Collection | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 2 | 5532 | Pumping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 3 | 5533 | Plant 1 | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 4 | 5534 | Plant 2 | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 5 | 5535 | Treated Effluent Storage | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 6 | 5536 | Treated Effluent Pumping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 3 | 7 | 5537 | Treated Effluent Piping | Fluor | Fluor | Fluor | Fluor
5 | 5 | 4 | 0 | 5540 | Agricultural | - | - | - | -
5 | 5 | 9 | 0 | 5590 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
5 | 5 | 9 | 8 | 5598 | Building or Structure | Fluor | Fluor | Fluor | Fluor
5 | 5 | 9 | 9 | 5599 | Electrical | Fluor | Fluor | Fluor | Fluor
5 | 6 | 0 | 0 | 5600 | Water Services | Fluor | Fluor | Fluor | Fluor
5 | 6 | 1 | 0 | 5610 | Firewater Storage | Fluor | Fluor | Fluor | Fluor
5 | 6 | 2 | 0 | 5620 | Firewater Pumping and Distribution | Fluor | Fluor | Fluor | Fluor
5 | 6 | 3 | 0 | 5630 | Potable Water Treatment | Fluor | Fluor | Fluor | Fluor
5 | 6 | 3 | 2 | 5632 | Plant 1 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 3 | 3 | 5633 | Plant 2 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 0 | 5640 | Potable Water Storage | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 1 | 5641 | Common | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 2 | 5642 | System 1 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 3 | 5643 | System 2 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 4 | 4 | 5644 | Plant | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 0 | 5650 | Potable Water Pumping and Distribution | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 1 | 5651 | Common | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 2 | 5652 | System 1 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 3 | 5653 | System 2 | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 4 | 5654 | Plant | Fluor | Fluor | Fluor | Fluor
5 | 6 | 5 | 5 | 5655 | Safety Shower | Fluor | Fluor | Fluor | Fluor
6 | 0 | 0 | 0 | 6000 | Internal Infrastructure | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 0 | 0 | 6100 | On-Site Infrastructure | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 1 | 0 | 6110 | Site Preparation, Earthworks and Fencing | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 1 | 3 | 6113 | Site Security Fencing | RDMC | RDMC | RDMC | RDMC
6 | 1 | 1 | 4 | 6114 | Bulk Earthworks | Fluor | Fluor | Fluor | Fluor
6 | 1 | 1 | 5 | 6115 | Detailed Earthworks | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 0 | 6120 | Roads and Platforms | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 2 | 1 | 6121 | Processing Plant Roads | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 2 | 6122 | Crushing Plant Roads | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 3 | 6123 | Exploration Roads | RDMC | RDMC | RDMC | RDMC
6 | 1 | 2 | 4 | 6124 | Parking Areas and Hardstand Areas | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 5 | 6125 | Exploration Platforms | RDMC | RDMC | RDMC | RDMC
6 | 1 | 2 | 6 | 6126 | On-Site Helipad and Airstrip | RDMC | RDMC | RDMC | RDMC
6 | 1 | 2 | 8 | 6128 | Permanent Village Road | Fluor | Fluor | Fluor | Fluor
6 | 1 | 2 | 9 | 6129 | Mine Site Access Road | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 0 | 6130 | Non-Process Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 1 | 6131 | Fire, Ambulance, and Emergency Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 2 | 6132 | Security and Medical Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 3 | 6133 | Main Administration Building | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 4 | 6134 | Laboratories | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 5 | 6135 | Plant Warehouse and Maintenance Shop | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 6 | 6136 | Change House and Dry Building | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 7 | 6137 | Training Building and Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 8 | 6138 | Stores and Warehouse | Fluor | Fluor | Fluor | Fluor
6 | 1 | 3 | 9 | 6139 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 4 | 0 | 6140 | Mobile Equipment | RDMC | RDMC | RDMC | RDMC
6 | 1 | 4 | 1 | 6141 | Maintenance | RDMC | RDMC | RDMC | RDMC
6 | 1 | 4 | 2 | 6142 | General and Administration | RDMC | RDMC | RDMC | RDMC
6 | 1 | 5 | 0 | 6150 | Bulk Storage (NB Storage of Utilities) | Fluor/PPE | Fluor/PPE | Fluor/PPE | Fluor/PPE
6 | 1 | 5 | 5 | 6155 | Diesel | Fluor | Fluor | Fluor | Fluor
6 | 1 | 5 | 7 | 6157 | Reagents Receival and Storage | Fluor | Fluor | Fluor | Fluor
6 | 1 | 5 | 8 | 6158 | Container Receival and Storage | Fluor | Fluor | Fluor | Fluor
6 | 1 | 5 | 9 | 6159 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 6 | 0 | 6160 | Services and Utilities (NB Distribution of Utilities) | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor | RDMC/Fluor
6 | 1 | 6 | 5 | 6165 | Environmental Monitoring | RDMC | RDMC | RDMC | RDMC
6 | 1 | 6 | 6 | 6166 | Compressed Air | Fluor | Fluor | Fluor | Fluor
6 | 1 | 6 | 8 | 6168 | Diesel Fuel Distribution and Refuelling | Fluor | Fluor | Fluor | Fluor
6 | 1 | 6 | 9 | 6169 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 7 | 0 | 6170 | Communications | Fluor | Fluor | Fluor | Fluor
6 | 1 | 7 | 1 | 6171 | Distributed Control System | Fluor | Fluor | Fluor | Fluor
6 | 1 | 7 | 2 | 6172 | Communications and Networks | Fluor | Fluor | Fluor | Fluor
6 | 1 | 7 | 9 | 6179 | Common Facilities and Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 0 | 6180 | Village | Fluor/PPE | Fluor/PPE | Fluor/PPE | Fluor/PPE
6 | 1 | 8 | 1 | 6181 | Accommodation | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 2 | 6182 | Mess Hall and Food Storage | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 3 | 6183 | Leisure Amenities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 4 | 6184 | Laundry Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 5 | 6185 | Potable Water | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 6 | 6186 | Firewater | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 7 | 6187 | Support Facilities | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 8 | 6188 | Underground Services | Fluor | Fluor | Fluor | Fluor
6 | 1 | 8 | 9 | 6189 | Common Facilities and Services | Fluor/PPE | Fluor/PPE | Fluor/PPE | Fluor/PPE
6 | 1 | 9 | 0 | 6190 | Rail | Vec | Vec | Vec | Vec
6 | 2 | 0 | 0 | 6200 | On-Site Power Supply and Transmission | PPE/WAR | PPE/WAR | PPE/WAR | PPE/WAR
6 | 2 | 1 | 0 | 6210 | Power Stations | WAR | WAR | WAR | WAR
6 | 2 | 1 | 1 | 6211 | Administration and General Buildings | WAR | WAR | WAR | WAR
6 | 2 | 1 | 2 | 6212 | Power Station 1 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 3 | 6213 | HFO Storage Power Station 1 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 4 | 6214 | Truck Unloading and Pumping Power Station 1 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 5 | 6215 | Power Station 2 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 6 | 6216 | HFO Storage Power Station 2 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 7 | 6217 | Truck Unloading and Pumping Power Station 2 | WAR | WAR | WAR | WAR
6 | 2 | 1 | 8 | 6218 | Rail Unloading | WAR | WAR | WAR | WAR
6 | 2 | 1 | 9 | 6219 | Common Facilities and Services | WAR | WAR | WAR | WAR
6 | 2 | 3 | 0 | 6230 | High Voltage (220 kV) Transmission Lines | PPE | PPE | PPE | PPE
6 | 2 | 3 | 1 | 6231 | Solar PV Substation to Power Station Substation | PPE | PPE | PPE | PPE
6 | 2 | 3 | 2 | 6232 | Power Station Substation to Plant Main Substation | PPE | PPE | PPE | PPE
6 | 2 | 3 | 3 | 6233 | NDTC (Pakistan Grid Operator) Power Supply (future) | PPE | PPE | PPE | PPE
6 | 2 | 4 | 0 | 6240 | High Voltage Substations | PPE | PPE | PPE | PPE
6 | 2 | 4 | 1 | 6241 | 33/220 kV Solar PV Substation | PPE | PPE | PPE | PPE
6 | 2 | 4 | 2 | 6242 | 33/220 kV Power Station Substation | PPE | PPE | PPE | PPE
6 | 2 | 4 | 3 | 6243 | 220/33 kV Plant Main Substation | PPE | PPE | PPE | PPE
6 | 2 | 5 | 0 | 6250 | Power Conditioning Equipment | PPE | PPE | PPE | PPE
6 | 2 | 5 | 1 | 6251 | Load Bank | PPE | PPE | PPE | PPE
6 | 2 | 5 | 2 | 6252 | Harmonic Filters 1 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 3 | 6253 | Synchronous Condenser 1 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 4 | 6254 | Battery Energy Storage System 1 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 5 | 6255 | Harmonic Filters 2 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 6 | 6256 | Synchronous Condenser 2 | PPE | PPE | PPE | PPE
6 | 2 | 5 | 7 | 6257 | Battery Energy Storage System 2 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 0 | 6260 | Emergency Power Generation | PPE | PPE | PPE | PPE
6 | 2 | 6 | 1 | 6261 | Administration and General Buildings | PPE | PPE | PPE | PPE
6 | 2 | 6 | 2 | 6262 | Emergency Power Substation 1 and Control Room 1 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 3 | 6263 | 36 MVA Power Station 1 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 4 | 6264 | Bulk Diesel Storage 1 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 5 | 6265 | Truck Diesel Unloading and Power Station 1 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 6 | 6266 | Emergency Power Substation 2 and Control Room 2 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 7 | 6267 | 36 MVA Power Station 2 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 8 | 6268 | Bulk Diesel Storage 2 | PPE | PPE | PPE | PPE
6 | 2 | 6 | 9 | 6269 | Truck Diesel Unloading and Power Station 2 | PPE | PPE | PPE | PPE
6 | 2 | 8 | 0 | 6280 | Medium Voltage (33 kV) Overhead Powerlines | PPE | PPE | PPE | PPE
6 | 2 | 8 | 1 | 6281 | Booster Pump Station | PPE | PPE | PPE | PPE
6 | 2 | 8 | 2 | 6282 | Borefields | PPE | PPE | PPE | PPE
6 | 2 | 8 | 3 | 6283 | Potable Water Treatment Plant | PPE | PPE | PPE | PPE
6 | 2 | 8 | 4 | 6284 | Sewage Treatment Plant | PPE | PPE | PPE | PPE
6 | 2 | 8 | 5 | 6285 | Village | PPE | PPE | PPE | PPE
6 | 2 | 8 | 6 | 6286 | Mining Open Pit | PPE | PPE | PPE | PPE
6 | 2 | 8 | 7 | 6287 | Primary Crushing | PPE | PPE | PPE | PPE
6 | 2 | 8 | 8 | 6288 | Tailings Storage Facility | PPE | PPE | PPE | PPE
6 | 2 | 8 | 9 | 6289 | Rail Offloading Facility | PPE | PPE | PPE | PPE
6 | 2 | 9 | 0 | 6290 | Renewable Energy | PPE | PPE | PPE | PPE
6 | 2 | 9 | 1 | 6291 | Administration and General Buildings | PPE | PPE | PPE | PPE
6 | 2 | 9 | 2 | 6292 | 11/33 kV Solar PV Substation 1 and Control Room 1 | PPE | PPE | PPE | PPE
6 | 2 | 9 | 3 | 6293 | Power Station 1 Photovoltaic Array, Inverters, and Transformers | PPE | PPE | PPE | PPE
6 | 2 | 9 | 4 | 6294 | 11/33 kV Solar PV Substation 2 and Control Room 2 (future) | Future | Future | Future | Future
6 | 2 | 9 | 5 | 6295 | Power Station 2 Photovoltaic Array, Inverters, and Transformers (future) | Future | Future | Future | Future
6 | 3 | 0 | 0 | 6300 | On-Site Rail | - | - | - | -
6 | 3 | 1 | 0 | 6310 | Site Preparation | - | - | - | -
6 | 3 | 1 | 1 | 6311 | Embankment & Cuttings | - | - | - | -
6 | 3 | 1 | 2 | 6312 | Drainage & Culverts | - | - | - | -
6 | 3 | 1 | 3 | 6313 | Site Security Fencing | - | - | - | -
6 | 3 | 1 | 4 | 6314 | Bulk Site Earthworks | - | - | - | -
6 | 3 | 1 | 5 | 6315 | Detailed Site Earthworks | - | - | - | -
6 | 3 | 1 | 6 | 6316 | Roads | - | - | - | -
6 | 3 | 1 | 7 | 6317 | Signaling | - | - | - | -
6 | 3 | 2 | 0 | 6320 | Site Utilities and Services | - | - | - | -
6 | 3 | 2 | 2 | 6322 | Fire Water Storage | - | - | - | -
6 | 3 | 2 | 3 | 6323 | Fire Water Pump House & Reticulation | - | - | - | -
6 | 3 | 2 | 4 | 6324 | Fuel Storage | - | - | - | -
6 | 3 | 2 | 5 | 6325 | Potable Water System | - | - | - | -
6 | 3 | 2 | 6 | 6326 | Sewage Collection & Distribution | - | - | - | -
6 | 3 | 2 | 7 | 6327 | Waste Sorting Facility | - | - | - | -
6 | 3 | 4 | 0 | 6340 | Rail Facilities | - | - | - | -
6 | 3 | 4 | 1 | 6341 | Incoming Train Covered Inspection Shed | - | - | - | -
6 | 3 | 4 | 2 | 6342 | Operation Staff Building | - | - | - | -
6 | 3 | 4 | 3 | 6343 | CuCon Filling Point | - | - | - | -
6 | 3 | 4 | 4 | 6344 | In-Motion Weighing Bridge + Office | - | - | - | -
6 | 3 | 4 | 5 | 6345 | Washing Station | - | - | - | -
6 | 3 | 4 | 6 | 6346 | Wagons and Locomotives Running Shed and Refueling Station | - | - | - | -
6 | 3 | 4 | 7 | 6347 | Rotainers and Containers Handling and Repairing Platform | - | - | - | -
6 | 3 | 6 | 0 | 6360 | Comms, IT and Controls | - | - | - | -
6 | 3 | 6 | 1 | 6361 | Telecommunications | - | - | - | -
6 | 3 | 6 | 2 | 6362 | CCTV System | - | - | - | -
6 | 3 | 6 | 3 | 6363 | IT and Systems | - | - | - | -
6 | 3 | 6 | 4 | 6364 | Control System | - | - | - | -
6 | 3 | 9 | 0 | 6390 | Rail Electrical | - | - | - | -
6 | 3 | 9 | 1 | 6391 | Sub-Station | - | - | - | -
6 | 3 | 9 | 2 | 6392 | Site Wide Area Lighting | - | - | - | -
7 | 0 | 0 | 0 | 7000 | External Infrastructure | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW
7 | 1 | 0 | 0 | 7100 | Off-Site Infrastructure | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW | RDMC/Fluor/Vec/PRDW
7 | 1 | 1 | 0 | 7110 | Off-Site Roads / Water Diversions | Fluor | Fluor | Fluor | Fluor
7 | 1 | 1 | 1 | 7111 | Site Access Road (45km) | Fluor | Fluor | Fluor | Fluor
7 | 1 | 2 | 0 | 7120 | Off-Site Facilities | RDMC/Fluor/Vec | RDMC/Fluor/Vec | RDMC/Fluor/Vec | RDMC/Fluor/Vec
7 | 1 | 2 | 1 | 7121 | Off-Site Permanent Buildings (Not Accomodation) | - | - | - | -
7 | 1 | 2 | 2 | 7122 | Off-Site Railways | - | - | - | -
7 | 1 | 2 | 3 | 7123 | Off-Site Accommodation | RDMC | RDMC | RDMC | RDMC
7 | 1 | 2 | 4 | 7124 | Off-Site Solid Waste Storage | Fluor | Fluor | Fluor | Fluor
7 | 1 | 2 | 5 | 7125 | Off-Site Hazardous Waste Storage | Fluor | Fluor | Fluor | Fluor
7 | 1 | 2 | 6 | 7126 | Site Bulk Road & Bulk Rail Loading | Vec | Vec | Vec | Vec
7 | 1 | 2 | 7 | 7127 | Port Qasim Bulk Road & Bulk Rail Unloading | - | - | - | -
7 | 1 | 3 | 0 | 7130 | Off-Site Mobile Maintenance Equipment | RDMC | RDMC | RDMC | RDMC
7 | 1 | 4 | 0 | 7140 | Off-Site Utilities Pipelines & Bulk Storage (exclude water) | Vecturis/PRDW | Vecturis/PRDW | Vecturis/PRDW | Vecturis/PRDW
7 | 1 | 4 | 2 | 7142 | Off-Site Fuel Pipeline | - | - | - | -
7 | 1 | 4 | 3 | 7143 | Off-Site Concentrate Pipeline | Future | Future | Future | Future
7 | 1 | 4 | 5 | 7145 | Off-Site Fuel Bulk Storage | Vecturis/PR DW | Vecturis/PR DW | Vecturis/PR DW | Vecturis/PR DW
7 | 1 | 4 | 6 | 7146 | Off-Site Concentrate Bulk Storage | PRDW | PRDW | PRDW | PRDW
7 | 1 | 4 | 7 | 7147 | Off-Site Effluent Utilities | Vecturis/PR DW | Vecturis/PR DW | Vecturis/PR DW | Vecturis/PR DW
7 | 1 | 4 | 9 | 7149 | Natural Gas Pipeline & Associated Equipment (K&T) | - | - | - | -
7 | 1 | 6 | 0 | 7160 | Off-Site Airport Facilities | - | - | - | -
7 | 1 | 6 | 1 | 7161 | Airport Runways | - | - | - | -
7 | 1 | 6 | 2 | 7162 | Airport Taxiways | - | - | - | -
7 | 1 | 6 | 3 | 7163 | Airport Aprons | - | - | - | -
7 | 1 | 6 | 4 | 7164 | Airport Passenger Terminal Buildings | - | - | - | -
7 | 1 | 6 | 5 | 7165 | Airport Freight Handling Facilities | - | - | - | -
7 | 1 | 6 | 9 | 7169 | Airport Facilities & Services | - | - | - | -
7 | 1 | 7 | 0 | 7170 | Off-Site Water Pipelines & Bulk Storage | Fluor | Fluor | Fluor | Fluor
7 | 1 | 7 | 1 | 7171 | Off-Site Desalinated Water Pipeline | Future | Future | Future | Future
7 | 1 | 7 | 4 | 7174 | Off-Site Water Bulk Storage
7 | 1 | 7 | 5 | 7175 | Off-Site Hamun-i-Mashkel (HIM) Bore Field | Future | Future | Future | Future
7 | 1 | 7 | 6 | 7176 | Off-Site Borehole Fieldwater Pipeline - Hamun-i-Mashkel (HIM) | Future | Future | Future | Future
7 | 1 | 7 | 7 | 7177 | Off-Site Fan Sediments Bore Field | Fluor | Fluor | Fluor | Fluor
7 | 1 | 7 | 8 | 7178 | Off-Site Borehole Fieldwater Pipeline - Fan Sediments Main Line | Fluor | Fluor | Fluor | Fluor
7 | 1 | 7 | 9 | 7179 | Off-Site Borehole Fieldwater Pipeline - Fan Sediments Construction Line | RDMC | RDMC | Fluor | Fluor
7 | 1 | 8 | 0 | 7180 | Off-Site Services/Utilities | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 1 | 7181 | Off-Site Fresh Water Distribution | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 2 | 7182 | Off-Site Potable Water Distribution | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 3 | 7183 | Off-Site Acid Rock Drainage (ARD) Water Distribution
7 | 1 | 8 | 4 | 7184 | Off-Site Fire Water Distribution | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 5 | 7185 | Off-Site Environmental Monitoring | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 6 | 7186 | Off-Site Communications | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 7 | 7187 | Off-Site Effluent Utilities | RDMC | RDMC | RDMC | RDMC
7 | 1 | 8 | 8 | 7188 | Off-Site Other Utilities (Compressed Air & Propane, etc.) | RDMC | RDMC | RDMC | RDMC
7 | 1 | 9 | 0 | 7190 | Off-Site Power Supply & Transmission
7 | 1 | 9 | 1 | 7191 | Switchyard
7 | 1 | 9 | 2 | 7192 | Off-Site Transmission
7 | 1 | 9 | 3 | 7193 | Main Substation
7 | 1 | 9 | 4 | 7194 | Power Generation
7 | 1 | 9 | 9 | 7199 | Off-Site Power Facilities & Services
7 | 2 | 0 | 0 | 7200 | Off-Site Port (Qasim & Gwadar) - (Not in Scope) | - | - | - | -
7 | 2 | 1 | 0 | 7210 | Port Concentrate Handling | - | - | - | -
7 | 2 | 1 | 1 | 7211 | Port Copper Concentrate Thickening | - | - | - | -
7 | 2 | 1 | 2 | 7212 | Port Concentrate Filtration | - | - | - | -
7 | 2 | 1 | 3 | 7213 | Port Concentrate Conveyor & Handling | - | - | - | -
7 | 2 | 1 | 4 | 7214 | Port Concentrate Stacking Conveyor | - | - | - | -
7 | 2 | 1 | 5 | 7215 | Port Concentrate Storage | - | - | - | -
7 | 2 | 1 | 6 | 7216 | Port Concentrate Emergencg Dump Pond | - | - | - | -
7 | 2 | 1 | 7 | 7217 | Process Water Treatment | - | - | - | -
7 | 2 | 1 | 8 | 7218 | Sampling Plant | - | - | - | -
7 | 2 | 1 | 9 | 7219 | Utilities & Services | - | - | - | -
7 | 2 | 2 | 0 | 7220 | Port Site Utilities & Services | - | - | - | -
7 | 2 | 2 | 1 | 7221 | Reagents Handling Facility | - | - | - | -
7 | 2 | 2 | 2 | 7222 | Utilities Services For Port Conveying Onshore | - | - | - | -
7 | 2 | 2 | 3 | 7223 | Fuel offloading & Refuelling | - | - | - | -
7 | 2 | 2 | 4 | 7224 | Fuel Storage & Dispensing | - | - | - | -
7 | 2 | 2 | 5 | 7225 | Fuel Pipeline | - | - | - | -
7 | 2 | 2 | 6 | 7226 | Potable Water System | - | - | - | -
7 | 2 | 2 | 7 | 7227 | Sewage Collection & Treatment | - | - | - | -
7 | 2 | 2 | 8 | 7228 | Waste Sorting Facility | - | - | - | -
7 | 2 | 2 | 9 | 7229 | Fresh & Fire Water System | - | - | - | -
7 | 2 | 3 | 0 | 7230 | Port Facilities | - | - | - | -
7 | 2 | 3 | 1 | 7231 | Port Gwadar Gatehouse | - | - | - | -
7 | 2 | 3 | 2 | 7232 | Port Gwadar Maintenance Shop | - | - | - | -
7 | 2 | 3 | 3 | 7233 | Port Gwadar Security Building | - | - | - | -
7 | 2 | 3 | 4 | 7234 | Port Gwadar Electrical Switchrooms | - | - | - | -
7 | 2 | 3 | 5 | 7235 | Guardhouse & Security Gate | - | - | - | -
7 | 2 | 3 | 6 | 7236 | Mobile Equipment | - | - | - | -
7 | 2 | 3 | 9 | 7239 | Utilities & Services | - | - | - | -
7 | 2 | 4 | 0 | 7240 | Port Earthworks & Drainage | - | - | - | -
7 | 2 | 4 | 1 | 7241 | Bulk Site Earthworks | - | - | - | -
7 | 2 | 4 | 2 | 7242 | Detailed Site Earthworks | - | - | - | -
7 | 2 | 4 | 3 | 7243 | Site Drainage & Culverts | - | - | - | -
7 | 2 | 4 | 4 | 7244 | In-Plant Roads | - | - | - | -
7 | 2 | 4 | 5 | 7245 | Carparks & Hardstand Areas | - | - | - | -
7 | 2 | 4 | 6 | 7246 | Site Improvements | - | - | - | -
7 | 2 | 4 | 7 | 7247 | Site Security Fencing | - | - | - | -
7 | 2 | 4 | 8 | 7248 | Underground Services | - | - | - | -
7 | 2 | 4 | 9 | 7249 | Utilities & Services | - | - | - | -
7 | 2 | 5 | 0 | 7250 | Concentrate Port offshore | - | - | - | -
7 | 2 | 5 | 1 | 7251 | Navigation & Dredging | - | - | - | -
7 | 2 | 5 | 2 | 7252 | Berth Structure | - | - | - | -
7 | 2 | 5 | 3 | 7253 | Shiploading | - | - | - | -
7 | 2 | 5 | 4 | 7254 | Marine Services | - | - | - | -
7 | 2 | 5 | 5 | 7255 | Coastal Structures | - | - | - | -
7 | 2 | 5 | 6 | 7256 | Navigation Aids | - | - | - | -
7 | 2 | 5 | 7 | 7257 | Mooring Systems | - | - | - | -
7 | 2 | 5 | 9 | 7259 | Utilities & Services | - | - | - | -
7 | 2 | 6 | 0 | 7260 | LNG Import Terminal | - | - | - | -
7 | 2 | 6 | 1 | 7261 | Navigation & Dredging | - | - | - | -
7 | 2 | 6 | 2 | 7262 | Berth Structure | - | - | - | -
7 | 2 | 6 | 3 | 7263 | Unloading System | - | - | - | -
7 | 2 | 6 | 4 | 7264 | Marine Services | - | - | - | -
7 | 2 | 6 | 5 | 7265 | Coastal Structures | - | - | - | -
7 | 2 | 6 | 6 | 7266 | Navigation Aids | - | - | - | -
7 | 2 | 6 | 7 | 7267 | Mooring Systems | - | - | - | -
7 | 2 | 6 | 9 | 7269 | Utilities & Services | - | - | - | -
7 | 2 | 8 | 0 | 7280 | SWRO Plant | - | - | - | -
7 | 2 | 8 | 1 | 7281 | Intake System | - | - | - | -
7 | 2 | 8 | 2 | 7282 | Ro Plant | - | - | - | -
7 | 2 | 8 | 3 | 7283 | Brine Discharge System | - | - | - | -
7 | 2 | 8 | 4 | 7284 | Coastal Structures | - | - | - | -
7 | 2 | 8 | 5 | 7285 | Bulk Earthworks | - | - | - | -
7 | 2 | 8 | 6 | 7286 | Roads & Paving | - | - | - | -
7 | 2 | 8 | 9 | 7289 | Utilities & Services | - | - | - | -
7 | 3 | 0 | 0 | 7300 | Off-Site Port Qasim - PIBT | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 0 | 7310 | Port Earthworks & Drainage | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 1 | 7311 | Bulk Site Earthworks | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 3 | 7313 | Site Drainage & Culverts | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 4 | 7314 | In-Plant Roads | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 5 | 7315 | Carparks & Hardstand Areas | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 6 | 7316 | Site and Soil Improvements | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 7 | 7317 | Site Security Fencing | PRDW | PRDW | PRDW | PRDW
7 | 3 | 1 | 8 | 7318 | Underground Services | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 0 | 7320 | Port Site Utilities & Services | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 1 | 7321 | Stormwater Piping | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 2 | 7322 | Fire Water Storage | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 3 | 7323 | Fire Water Pump House & Reticulation | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 4 | 7324 | Fuel Storage & Dispensing | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 6 | 7326 | Potable Water System | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 7 | 7327 | Sewage Collection & Treatment | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 8 | 7328 | Waste Sorting Facility | PRDW | PRDW | PRDW | PRDW
7 | 3 | 2 | 9 | 7329 | Services Building | - | - | - | -
7 | 3 | 3 | 0 | 7330 | Port Facilities | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 1 | 7331 | Port Qasim PIBT Gatehouse | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 2 | 7332 | Port Qasim PIBT Workshop & Engineering Offices | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 3 | 7333 | Port Qasim PIBT Security Building | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 4 | 7334 | Port Qasim PIBT Weighbridge | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 5 | 7335 | Port Qasim PIBT Security & Weighbridge Office | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 6 | 7336 | Port Qasim PIBT Administration Building | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 7 | 7337 | Port Qasim PIBT Control Room | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 8 | 7338 | Port Qasim PIBT Sampling & Laboratory | PRDW | PRDW | PRDW | PRDW
7 | 3 | 3 | 9 | 7339 | Port Qasim PIBT Washdown Facility | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 0 | 7340 | Port Concentrate Handling | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 1 | 7341 | Truck Discharge Station | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 2 | 7342 | Port Concentrate Conveyor CV-101 & TR-101 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 3 | 7343 | Port Concentrate Conveyor CV-102 & TR-102 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 4 | 7344 | Port Concentrate Port Storage Shed | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 5 | 7345 | Port Concentrate Conveyor CV-103 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 6 | 7346 | Port Concentrate Conveyor CV-104 & TR-103 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 7 | 7347 | Port Concentrate Conveyor CV-105 & TR-104 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 8 | 7348 | PIBT Port Handling Upgrade | PRDW | PRDW | PRDW | PRDW
7 | 3 | 4 | 9 | 7349 | Conveyor Galleries & Structures | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 0 | 7350 | Port Concentrate Offshore | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 1 | 7351 | Navigation & Dredging | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 2 | 7352 | Berth Structure | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 3 | 7353 | Shiploading | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 4 | 7354 | Marine Services | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 5 | 7355 | Coastal Structures | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 6 | 7356 | Navigation Aids | PRDW | PRDW | PRDW | PRDW
7 | 3 | 5 | 7 | 7357 | Mooring Systems | PRDW | PRDW | PRDW | PRDW
7 | 3 | 6 | 0 | 7360 | Port Comms, IT and Controls | PRDW | PRDW | PRDW | PRDW
7 | 3 | 6 | 1 | 7361 | CCTV and Security System | PRDW | PRDW | PRDW | PRDW
7 | 3 | 6 | 2 | 7362 | Port Handling Control System | PRDW | PRDW | PRDW | PRDW
7 | 3 | 6 | 3 | 7363 | IT | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 0 | 7390 | Port Electrical | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 1 | 7391 | Sub Station 1 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 2 | 7392 | Sub Station 2 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 3 | 7393 | Sub Station 3 | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 4 | 7394 | PIBT Karachi Electric Substation | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 5 | 7395 | Site Wide Area Lighting | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 6 | 7396 | HV Reticulation | PRDW | PRDW | PRDW | PRDW
7 | 3 | 9 | 7 | 7397 | PIBT Port Generator | - | - | - | -
7 | 4 | 0 | 0 | 7400 | Off-Site Rail Facilities
7 | 4 | 1 | 0 | 7410 | Earthworks & Drainage
7 | 4 | 1 | 1 | 7411 | Bulk Site Earthworks
7 | 4 | 1 | 3 | 7413 | Site Drainage & Culverts
7 | 4 | 1 | 4 | 7414 | In-Plant Roads
7 | 4 | 1 | 5 | 7415 | Carparks & Hardstand Areas
7 | 4 | 1 | 6 | 7416 | Site and Soil Improvements
7 | 4 | 1 | 7 | 7417 | Site Security Fencing
7 | 4 | 1 | 8 | 7418 | Underground Services
7 | 4 | 2 | 0 | 7420 | Site Utilities and Services
7 | 4 | 2 | 1 | 7421 | Stormwater Piping
7 | 4 | 2 | 2 | 7422 | Fire Water Storage
7 | 4 | 2 | 3 | 7423 | Fire Water Pump House & Reticulation
7 | 4 | 2 | 4 | 7424 | Fuel Storage & Dispensing
7 | 4 | 2 | 5 | 7425 | Potable Water System
7 | 4 | 2 | 6 | 7426 | Sewage Collection & Treatment
7 | 4 | 2 | 7 | 7427 | Waste Sorting Facility
7 | 4 | 2 | 8 | 7428 | Telecommunications
7 | 4 | 2 | 9 | 7429 | Signaling
7 | 4 | 3 | 0 | 7430 | Infrastructure and Systems
7 | 4 | 3 | 1 | 7431 | Maintenance Yard Sidings
7 | 4 | 3 | 2 | 7432 | Operation Sidings
7 | 4 | 3 | 3 | 7433 | Telecommunications
7 | 4 | 3 | 4 | 7434 | CCTV System
7 | 4 | 3 | 5 | 7435 | IT and Systems
7 | 4 | 3 | 6 | 7436 | Control System
7 | 4 | 3 | 7 | 7437 | ML-3 Upgrade Works
7 | 4 | 3 | 8 | 7438 | Rolling Stock Maintenance Facility
7 | 4 | 3 | 9 | 7439 | Rolling Stock Refueling Station
7 | 4 | 4 | 0 | 7440 | Operational Facilities Port
7 | 4 | 4 | 1 | 7441 | Incoming Train Covered Inspection Shed
7 | 4 | 4 | 2 | 7442 | Operation Staff Building
7 | 4 | 4 | 3 | 7443 | In-Motion Weighing Bridge + Weight Bridge Office
7 | 4 | 4 | 4 | 7444 | Reagents FIBC Management Platform
7 | 4 | 4 | 5 | 7445 | Rotainers Management Platform
7 | 4 | 4 | 6 | 7446 | Tank Containers, Containers and IBC Management Platform
7 | 4 | 4 | 7 | 7447 | Canteen, Drivers’ Dorm and Training Rooms Building
7 | 4 | 4 | 8 | 7448 | CuCon Security + Weight Bridge Office
7 | 4 | 4 | 9 | 7449 | Truck Access Gate + Truck Weight Bridge
7 | 4 | 5 | 0 | 7450 | Maintenance Facilities Port
7 | 4 | 5 | 1 | 7451 | Shunting Locomotives Parking Garage
7 | 4 | 5 | 2 | 7452 | Locomotives & Wagons Wash Station
7 | 4 | 5 | 3 | 7453 | Wagons And Locomotives Paint Booth
7 | 4 | 5 | 4 | 7454 | Underfloor Wheel Lathe
7 | 4 | 5 | 5 | 7455 | Fuel Storage
7 | 4 | 5 | 6 | 7456 | Pre-inpection and Refuelling shed
7 | 4 | 5 | 7 | 7457 | Major Assemblies and Spare Parts Store
7 | 4 | 5 | 8 | 7458 | Main Maintenance Workshop
7 | 4 | 6 | 0 | 7460 | Spur Line & Main line
7 | 4 | 6 | 1 | 7461 | Permanent Way
7 | 4 | 6 | 2 | 7462 | Koh-i-Dalil Station
7 | 4 | 6 | 3 | 7463 | Reko Diq Terminal Station
7 | 4 | 6 | 4 | 7464 | Engineering Structures
7 | 4 | 6 | 5 | 7465 | Level Crossings
7 | 4 | 6 | 6 | 7466 | Electrical and Power
7 | 4 | 6 | 7 | 7467 | Signaling
7 | 4 | 6 | 8 | 7468 | Telecommunications
7 | 4 | 7 | 0 | 7470 | Temporary Loading Facility
7 | 4 | 7 | 1 | 7471 | Incoming Train Covered Inspection Shed
7 | 4 | 7 | 2 | 7472 | Operation Staff Building
7 | 4 | 7 | 3 | 7473 | In-motion Weighing Bridge + Office
7 | 4 | 7 | 4 | 7474 | Washing Station
7 | 4 | 7 | 5 | 7475 | Wagons and Locomotives Running Shed + Refueling Station
7 | 4 | 7 | 6 | 7476 | Rotainers and Containers Handling and Repairing Platform
7 | 4 | 7 | 7 | 7477 | Fencing and Gates
7 | 4 | 7 | 8 | 7478 | CCTV System
7 | 4 | 7 | 9 | 7479 | Power Supply and Distribution
7 | 4 | 8 | 0 | 7480 | Rolling Stock
7 | 4 | 8 | 1 | 7481 | Main Line ocomotives
7 | 4 | 8 | 2 | 7482 | Shunting Locomotives
7 | 4 | 8 | 3 | 7483 | Wagons
7 | 4 | 8 | 4 | 7484 | Rotainers
7 | 4 | 8 | 5 | 7485 | Tanktainers
7 | 4 | 8 | 6 | 7486 | Shipping Containers
7 | 4 | 8 | 7 | 7487 | Mobile Equipment
7 | 4 | 9 | 0 | 7490 | Electrical Port
7 | 4 | 9 | 1 | 7491 | Sub-station
7 | 4 | 9 | 2 | 7492 | Site Wide Area Lighting
8 | 0 | 0 | 0 | 8000 | Indirect Costs (Owner)
8 | 1 | 0 | 0 | 8100 | Owner's Costs (Common Construction Facilities and Services)
8 | 1 | 0 | 0 | 8100 | Project Costs
8 | 1 | 1 | 1 | 8111 | Project Management | - | - | - | -
8 | 1 | 1 | 2 | 8112 | Project Controls
8 | 1 | 1 | 3 | 8113 | Engineering and Procurement
8 | 1 | 1 | 4 | 8114 | Construction Management
8 | 1 | 1 | 5 | 8115 | Legal and Permitting
8 | 1 | 1 | 6 | 8116 | Public Relations
8 | 1 | 1 | 8 | 8118 | Community Engagement
8 | 1 | 1 | 9 | 8119 | General and Administration
8 | 1 | 2 | 0 | 8120 | Spares and Inventory | RDMC | RDMC | RDMC | RDMC
8 | 1 | 2 | 1 | 8121 | Spares
8 | 1 | 2 | 2 | 8122 | First Fills
8 | 1 | 3 | 0 | 8130 | Pre-Production Operations
8 | 1 | 3 | 1 | 8131 | Recruitment and Training of Operation and Maintenance Staff
8 | 1 | 3 | 2 | 8132 | Mobile Fleet Supporting Operations
8 | 1 | 3 | 3 | 8133 | Wet Commissioning
8 | 1 | 3 | 4 | 8134 | Post-Commissioning Modifications
8 | 1 | 3 | 5 | 8135 | Ramp-Up
8 | 1 | 3 | 6 | 8136 | Working Capital
8 | 1 | 4 | 0 | 8140 | Studies
8 | 1 | 5 | 0 | 8150 | Closure and Rehabilitation
8 | 1 | 6 | 0 | 8160 | Health Security and Safety
8 | 1 | 6 | 1 | 8161 | Clinic
8 | 1 | 6 | 2 | 8162 | Emergency Response
8 | 1 | 6 | 3 | 8163 | Security
8 | 1 | 6 | 4 | 8164 | Safety
8 | 1 | 7 | 0 | 8170 | Operational Readiness | - | - | - | -
8 | 1 | 8 | 0 | 8180 | Owner’s Management
8 | 1 | 8 | 1 | 8181 | Team
8 | 1 | 8 | 2 | 8182 | Nonmanual Labour Expenses
8 | 1 | 8 | 3 | 8183 | Home Office Expenses
8 | 1 | 8 | 4 | 8184 | Project Office Expenses
8 | 1 | 8 | 5 | 8185 | Site Office Expenses
8 | 8 | 1 | 0 | 8810 | Allowance (Early Works)
8 | 9 | 0 | 0 | 8900 | Contingency and Reserve
8 | 9 | 1 | 0 | 8910 | Cost Contingency
8 | 9 | 2 | 0 | 8920 | Schedule Contingency
8 | 9 | 3 | 0 | 8930 | Owner Cost Reserve
9 | 0 | 0 | 0 | 9000 | Indirect Costs (Other Parties)
9 | 1 | 0 | 0 | 9100 | Indirect Costs (Implementation Contractors, EPCM)
9 | 1 | 1 | 0 | 9110 | EPCM Cost | - | - | - | -
9 | 1 | 1 | 1 | 9111 | EP Cost | - | - | - | -
9 | 1 | 1 | 2 | 9112 | CM Cost | - | - | - | -
9 | 1 | 1 | 6 | 9116 | Vendor Field Representatives | - | - | - | -
9 | 1 | 1 | 9 | 9119 | Miscellaneous Engineering, Construction Management Services Costs | - | - | - | -
9 | 1 | 2 | 0 | 9120 | Temporary Facilities
9 | 1 | 2 | 1 | 9121 | Offices and Support Buildings
9 | 1 | 2 | 2 | 9122 | Warehouse and Yards
9 | 1 | 2 | 3 | 9123 | Shelters
9 | 1 | 2 | 4 | 9124 | Power Generation
9 | 1 | 2 | 5 | 9125 | Aggregate and Concrete
9 | 1 | 2 | 6 | 9126 | Water System
9 | 1 | 2 | 7 | 9127 | Fuel Stations
9 | 1 | 3 | 0 | 9130 | Temporary Services
9 | 1 | 3 | 1 | 9131 | Power
9 | 1 | 3 | 2 | 9132 | Maintenance and Cleanup
9 | 1 | 3 | 3 | 9133 | Personnel Transportation
9 | 1 | 3 | 4 | 9134 | Survey, Inspection, and Quality Control
9 | 1 | 3 | 5 | 9135 | Medical and Security
9 | 1 | 3 | 6 | 9136 | Heating
9 | 1 | 3 | 7 | 9137 | Fuel Supply
9 | 1 | 3 | 8 | 9138 | Water, Sewage, and Waste Disposal
9 | 1 | 3 | 9 | 9139 | Other Functions
9 | 1 | 4 | 0 | 9140 | Construction Equipment
9 | 1 | 4 | 1 | 9141 | Cranes
9 | 1 | 4 | 2 | 9142 | Vehicles
9 | 1 | 4 | 3 | 9143 | Mobile Equipment
9 | 1 | 4 | 4 | 9144 | Specialty Equipment
9 | 1 | 5 | 0 | 9150 | Environmental, Safety, and Health
9 | 1 | 5 | 1 | 9151 | Environmental
9 | 1 | 5 | 2 | 9152 | Safety
9 | 1 | 5 | 3 | 9153 | Health
9 | 1 | 6 | 0 | 9160 | Temporary Camp and Catering
9 | 1 | 6 | 1 | 9161 | Facilities
9 | 1 | 6 | 2 | 9162 | Catering
9 | 1 | 7 | 0 | 9170 | Freight / Traffic Warehouse Services and Logistics
9 | 1 | 7 | 1 | 9171 | Offshore Inland Freight
9 | 1 | 7 | 2 | 9172 | Marine Transportation
9 | 1 | 7 | 3 | 9173 | Onshore Inland Freight
9 | 1 | 7 | 4 | 9174 | Air Freight
9 | 1 | 7 | 5 | 9175 | Brokerage and Agent Fees
9 | 1 | 7 | 6 | 9176 | Import Duties
9 | 1 | 7 | 7 | 9177 | Warehousing Service
9 | 1 | 8 | 0 | 9180 | Commissioning
9 | 1 | 8 | 1 | 9181 | Owners Team
9 | 1 | 8 | 2 | 9182 | EPCM
9 | 1 | 8 | 3 | 9183 | Contractor Support

## Discipline Codes
DISCIPLINE CODES |  | REVIEW OUTCOMES
Code | Discipline/Function Identifier | Codes
• Reviewed
A | Architectural | • A1 – Data Complete, No Comments, Do Not Resubmit
B | Project Controls | • B1 – Data Complete, With Comments, Proceed – Resubmit
C | Civil/Concrete | • B2 – Data Incomplete – Proceed – Resubmit
D | Supply Chain | • C1 – Data Incomplete – Hold Work – Resubmit
E | Electrical | • D1 – For Information Only – Do Not Resubmit
F | Process | • V1 – Cancelled
G | General | • S1 – Superseded
H | Health & Safety / Security | • Q1 – Quality Below Standard – Revise and Resubmit
I | Instrumentation
J | Environmental / Social Impact
L | Human Resources
M | Mechanical
N | Mining
P | Piping
Q | Quality & Control / HAZOP / HAZID / Risk
S | Structural
T | Geotechnical
U | Pipeline
W | Earthworks / Drainage / Fencing / Roads / Water

## Document and Drawing Type
Document and Drawing Types
Code | Document Type identifier | Description
GENERAL
AUT | Authority | - Permitting - Authority Implementation Plan - Authority Approval Packages - Regulatory Compliance - Environmental Permitting Compliance Requirements | AUT
BLT | Battery Limit | - Battery Limit Table | BLT
BOE | Basis of Estimate |  | BOE
BOS | Basis of Schedule |  | BOS
BOM | Bill of Material |  | BOM
CAL | Calculation |  | CAL
CHR | Chart | Organization Chart, Department Chart | CHR
CON | Contract | Any contract documentation | CON
DBD | Design Basis and Criteria | Design Criteria of the Project | DBD
DBK | Project Data Book | - Manufacturer Data Records | DBK
DDR | Document and Data Register | Master Data and Document Register for Supplier, Sub-Contractors | DDR
DEM | Demolition | Demolition Documents | DEM
DST | Datasheet |  | DST
DTA | Data (Digital Record) | Any data e.g. Survey Data | DTA
EQL | Equipment List | Specific list for equipments | EQL
EST | Estimates |  | EST
EXE | Execution | Can be used for Supplier Data - if not specify on the list | EXE
FRM | Forms |  | FRM
GDL | Guideline | - Guideline - Protocols | GDL
HAC | Hazard Classification | HAZOP, Hazard Analysis, Hazard identification | HAC
HMB | Heat Material Balance |  | HMB
IDX | Index | Technical and Non-technical | IDX
INS | Instructions | e.g. operation instructions, installation instructions | INS
IOM | Installation Operation and Maintenance Manual |  | IOM
ITP | Inspection Test Plan |  | ITP
IWP | Installation Work Package |  | IWP
LST | List/Matrix | Technical List: Valve List, Motor List, Instrument List, Spare Part List Non-Technical List: Distribution Matrix, Communication Matrix | LST
LTR | Letter |  | LTR
MAN | Manual |  | MAN
MDL | Models | - 3Models | MDL
MDR | Master Document Register | Document Register for Engineering - Documentation System Description - Document Filing Index - Transmittal Log - Gate Review Completed | MDR
MEM | Memorandum |  | MEM
MOM | Minutes of Meeting |  | MOM
MTO | Material Take Off |  | MTO
NAR | Narrative | - Process Control Narrative - Safeguarding Narrative | NAR
NCR | Non-Conformance Report |  | NCR
PCN | Project Change Notice |  | PCN
PDR | Procedure Deviation Request |  | PDR
PHL | Philosophy |  | PHL
DOCUMENTS |  |  | PLN
PCK | Pack | Pack consisting out of Cover Page, Index, GA, SCH and Parts List.
PLN | Plan | Used for non-technical plan i.e. Engineering Plan, Risk Plan, HSE Plan, Contract & Procurement Plan, HR plan, Project Execution Plan, Study Plan. etc. | PLC
PLC | Policy |  | PRC
PRC | Procedure | Document represents the procedure as prescribed by the various departments. The practices generally relate to the way in which work is to be done within or for the department and also the approved way in which the Company deals with Contractors, and other organizations | PRO
PRO | Procurement | Any procurement documentation | QAD
QAD | Quality Assurance Documents | Any quality assurance documents. Except Quality Management Plan can use PLN | QRA
QRA | Quantitive Risk Assessment | Structured approach to measuring and analyzing risk using numerical data | REQ
REQ | Request | - Travel request - Any requests | RFA
RFA | Recommendation for Award |  | RFI
RFI | Request for Information |  | RPT
RPT | Report | Technical Report: Geotechnical Investigation Report, , etc. Non-technical Report: Safety Monthly report | SCH
SCH | Schedule |  | SMP
SMP | Sample | - Interior Design and Furniture Sample - Finish Boards | SOP
SOP | Standard Operating Procedure |  | SOW
SOW | Scope of Work | Document outlines the extent of work to be performed by others. The SOW may include functional specifications when a functional specification is not written which typically occurs when the contents of a functional specification is minimal (2 pages). | SPC
SPC | Specification | Document represents the design and performance requirements for materials, parts, plant and equipment | SPL
SPL | Piping Specialty Item List |  | STD
STD | Standards | For any standards, codes, and regulation documents, are generally controlled | STR
STR | Strategy |  | SUM
SUM | Summary |  | TDM
TDM | Technical Decision Memorandum |  | TDN
TDN | Trends | Project Controls Trends | TMP
TMP | Templates |  | TOR
TOR | Terms of Reference |  | TRP
TRP | Test Report | #NAME? | TVR
TVR | Turnover Dossier |  | VIS
VIS | Visualisation | - Drone Video | WLD
WLD | Welding | Any welding documents | BLT
DRAWINGS |  |  | CAE
BLT | Battery Limit | - Battery Limit Drawings | CRV
CAE | Cause and Effect Drawing | - Cause and Effect Drawing, etc. | DEM
CRV | Curves |  | DIA
DEM | Demolition | Demolition Drawings | DID
DIA | Diagram | - Traffic Diagram - Schematic Diagram - Block Diagram | DTL
DID | Ducting and Instrument Diagram | HVAC Utility Piping Ducting and Instrumentation Diagram | EHT
DTL | Details | Any drawings details | ELE
EHT | Electrical Heat Tracing Isometric |  | FND
ELE | Elevation | Any drawings elevation | GAD
FND | Foundation Drawings | Any foundation drawings | ITD
GAD | General Arrangement | Any general arrangements drawings | ISO
ITD | Instrumentation Drawing |  | LAY
ISO | Isometrics | Drawing provides a three-dimensional layout of the equipment and piping. | MSD
LAY | Layout | Any drawings layout | PFD
MSD | Material Selection Diagram |  | PID
PFD | Process Flow Diagram |  | PLN
PID | Piping and Instrumentation Diagram |  | PPL
PLN | Plan | Any drawings plan | PSP
PPL | Plot Plan | Site Plot Plan | SEC
PSP | Piping Support | Drawing piping support. | SHP
SEC | Section | Any drawings section | SKT
SHP | Shop Drawings | Supplier Shop Drawings - Fabrication Drawings - Fabrication Steel Drawings - Erection Drawings - Plate Schedule - Spool Drawings - etc. | SLD
SKT | Sketch | Any drawings sketch | SSD
SLD | Single Line Diagram | Drawing provides a representation of an electrical system. | STD
SSD | Structural Steel Drawings | Engineering (Design) | TIE
STD | Standard Drawings | Drawing shows the materials, set out standard construction details and provide general design data.
TIE | Tie-In